## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP 013C - Aeronautical Ground Lighting (AGL) – Installation of Luminaires | itp |  |  |  | Yes | ITP 013C - Aeronautical Ground Lighting (AGL) | 076bcee2-39c5-4fa0-956f-faae347432d0
checkpoint-group |  |  | section | ITP 013C - Aeronautical Ground Lighting (AGL) – Installation of Luminaires
checkpoint-status |  |  | checkpoint | 1.1 Check for correct documentation
label | b33ddb7f-5985-451a-8282-247da8d41987 |  | note | FREQUENCY: Prior to commencing any activity
label | e19db15a-d2cd-4f9f-9e3c-10b9896b963f |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the latest and complete set of drawings
label | 88502ef9-c8a2-42bf-bed6-3d7ea7385252 |  | note | REFERENCE DOCUMENTS: IFC Drawings
label | 032cb3fd-54db-4538-9814-f9b86bb1922d |  | note | INSPECTION/TEST METHOD: Verify
label | 6db58cf7-c2ea-451f-a3bf-4bfb11d2ccd9 |  | note | RECORD OF CONFORMITY: Drawings
label | c390aeb6-31a8-4efe-ad0d-870301588d03 |  | note | IP
label | c71e551b-623a-4ea2-9a67-b2a469d12f22 |  | note | RESPONSIBILITY: Project Engineer
text | 6f15e581-53fe-4596-bd6f-073c76a9cb2e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 Implementation of all measures and controls
label | 0eec9dc3-ae9f-4c01-b642-0663eaa97c53 |  | note | FREQUENCY: Prior to commencing any activities
label | 96380c51-7cde-416b-b71c-6fc7ee87cbaf |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is PSP, EMP, TMP, SWMS & WP.
label | 3a8a70d5-1c8b-48d0-aed9-769b8996ba09 |  | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | 7e325c92-ee81-4d43-929d-bafb9a399354 |  | note | INSPECTION/TEST METHOD: Verify
label | b305583c-7559-4f50-9ec3-5d19ab21a913 |  | note | RECORD OF CONFORMITY: Site and Office Inspection
label | 5c5c59d1-3784-4896-9fd7-81ceb767deb2 |  | note | HP*
label | 6775a202-42f7-48fd-beab-17c6a423d5d1 |  | note | RESPONSIBILITY: Project Engineer / Site Supervisor
text | c3eb3c65-a550-454d-997f-749594f70cab |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 Material/Equipment Approvals
label | c2f258fa-2afd-4b42-8024-1e1bda18af34 |  | note | FREQUENCY: Prior to Start
label | eb8d80f6-9ee5-4c0b-aa19-5c7015304fb8 |  | note | ACCEPTANCE CRITERIA: All materials shall be proven to meet contractual requirements prior to acceptance
label | 2d836f9b-e27b-4195-824a-dbc220766786 |  | note | - Mags shall be from ATG Airfield guidance signs range
label | ace1d7bb-7582-425a-b127-59b46045df25 |  | note | - Taxiway centre lights shall be from the ADB Safegate Safeled IQ inset light range only
label | ea180541-44bd-4e77-8d26-7c8898c5c9df |  | note | - Runway guard lights shall be from the ADB Safegate SL-RGL-E Range only.
label | 0704c847-6edc-47b8-a6e6-98e0bcf52fe7 |  | note | - Intermediate hold position lights shall be from the ADB Safegate Safeled IQ inset light range only
label | 942144e2-793c-4eb5-9f87-1480dfda6d40 |  | note | - Stop Bar Lights shall be from the ADB Safegate. Inset fittings shall be from SafeLED IQ inset light range while elevated fittings shall be from the LEAP range
label | 1f44830f-7463-4e2f-bf9e-0361403f09bf |  | note | - Runway edge lights shall be from ADB Safegate SafeLED HSL Light Range
label | 59b03275-3056-4765-ad8a-00d25a8e1b72 |  | note | - Hold Short Lights shall be from the ADB Safegate SafeLED HSL Light Range
label | 3d7f58ed-53d5-4893-a4fc-96d524d68737 |  | note | - Microwave Barrier detectors shall be from the ADB Safegate Range only
label | 5e24dc2c-622a-4a84-b711-3a1f7fc0915e |  | note | - Bedding mortar shall be approved.
label | 62bd3f10-beca-4073-ac48-c6f9adb628cb |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002 Chapter 10.3 AGL Elements
label | 283ae426-17eb-48b0-953e-6eddcea104e9 |  | note | INSPECTION/TEST METHOD: Verify
label | f17c3545-22fe-4cd3-9c27-e515e0e948fa |  | note | RECORD OF CONFORMITY: Datasheet
label | bf400e9d-d772-4123-a6ca-35ca8b024f5b |  | note | HP*
label | d3ac45d3-70e6-4a8a-bb93-21e228253f72 |  | note | RESPONSIBILITY: Project Engineer
text | 7dcd9c65-d74a-4871-8459-2d11dffbe697 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.4 AGL Trial Installation
label | c9fbb695-2038-41f4-90e0-e25ce245944f |  | note | FREQUENCY: Prior to commencing any activity
label | e5efc238-8599-430e-89fc-438080a43b8f |  | note | ACCEPTANCE CRITERIA: Prior to commencing AGL Works, the contractor shall carry out a trial installation at an agreed location to demonstrate that AGL’s have been installed correctly.
label | 77c75eea-b427-4c8e-9af1-5f9a5c45a18e |  | note | - This shall involve over coring the installation and cutting the core in half vertically to demonstrate the depth of the bedding mortar up the sides of the units are compliant.
label | 34cf8e8d-3947-461d-860e-d90b064f6ab9 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002 CL10.2.7
label | 360044f5-7115-4653-b42e-aeb1c5c02132 |  | note | INSPECTION/TEST METHOD: Verify
label | 0231875f-71e8-4e04-b3f8-50bd27d9208c |  | note | RECORD OF CONFORMITY: This Signed ITP
label | c7eba2e0-64d6-4357-8551-f4147e0be0a0 |  | note | AP
label | 724a4024-becf-4379-a0c6-62cdd3c5af03 |  | note | RESPONSIBILITY: Project Engineer / Superintendent
text | f701faac-507c-4aa3-8188-aac85bc651b9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 MAG Sign Base
label | 59efeaec-7a12-410d-b23a-9820a6f1cdfc |  | note | FREQUENCY: Each Lot
label | 65e094a4-37f5-4359-8c63-307be91d1e91 |  | note | ACCEPTANCE CRITERIA: Position of rectangular base to be as per set out coordinated listed in Mag sign schedules.
label | 46447e60-39d7-418e-b0ef-47183e7de679 |  | note | - 150mm thick class 2 crushed rock base layer compacted to 98% SDD on prepared subgrade
label | 413a2110-ce90-419b-8d27-a75fc0607882 |  | note | - 200mm lean mix concrete foundation with dimensions as per drawings.
label | b7703db7-db3b-4f3b-844c-c7a8a5e357f8 |  | note | - SL81 Top and Bottom reinforcing bars with minimum 50mm cover from edge of concrete.
label | 09645447-6ecb-4829-b4e5-fbd83251404b |  | note | - Sign mounting brackets and connections as per manufacturers guidelines
label | 1d773302-b734-455c-b333-4445c30e05a2 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-DI-0585
label | e9b05912-5c97-41ac-8402-32338434f002 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 7c01182b-7686-44c8-81c2-b7c4f032109c |  | note | RECORD OF CONFORMITY: This ITP Signed – ADBSG Installation of MAG bases Checklist
label | 6b5afa47-4b9a-4381-89d5-dd21761d501d |  | note | IP
label | 2089890f-d9b0-4b7c-9a7b-838846d5e448 |  | note | RESPONSIBILITY: Project Engineer
text | 3da91c3b-f2e6-41e9-9500-0200f5321b23 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Shallow Seating Pot / Inset Luminaire Base
label | 0fb1a03a-3099-4a09-a825-7b4b91069932 |  | note | FREQUENCY: Each Lot
label | 490eb894-a50d-4a4b-962a-6f51a9399922 |  | note | ACCEPTANCE CRITERIA: Installed and Backfilled in accordance to drawings.
label | 30fcfbbb-d119-4819-8898-e7287d20306b |  | note | In Concrete Pavement
label | eab5e451-b531-4e31-9147-f33e54c9581b |  | note | - 230mm or 330mm diameter core into PCC concrete as required to seat the shallow can.
label | b966a77d-a08d-4d4d-a3be-4f7ece7e1085 |  | note | In Flexible Pavement
label | 9044f959-f3e5-4cf2-aa20-a61e7217758f |  | note | - After completion of CMCR base.
label | fc3617b3-3815-41d4-9d31-56a65d1e3b66 |  | note | - Core 500mm or 600mm diameter hole 500mm deep and backfill with 5MPa lean mix concrete to match surrounding CMCR.
label | 26b9aa23-b24a-4fbb-8655-b8f1905a8f87 |  | note | - Shallow can located centrally to concrete block.
label | fdd3caa6-bc87-4535-a997-63ac1a411ebf |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-CI-0685
label | 7d94279a-8973-41cc-9a3c-7b1c5588623e |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 9514c54d-0a19-4848-8737-76f44649d786 |  | note | RECORD OF CONFORMITY: This ITP Signed – ADBSG Shallow Base Installation Checklist
label | eb048303-dfe5-49d1-98b9-03ee1a8e3e35 |  | note | IP
label | f6e5d87a-f325-4341-abc7-b3a558d9597c |  | note | RESPONSIBILITY: Project Engineer
text | 7a8ec537-510a-4dc2-b95b-129af3c6cb76 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Elevated Luminaire Base
label | cbd31c1e-edd7-4595-abee-65788bf06112 |  | note | FREQUENCY: Each Lot
label | 2a5ce9e2-afb4-4236-99ff-1070641e6377 |  | note | ACCEPTANCE CRITERIA: 600mm Diameter hole cored 500mm deep, 300mm diameter Can located centrally.
label | b6f010ae-1eb5-4484-9d9a-0af8ae17083a |  | note | - 150mm thick 20MPa concrete base under can
label | 60e1ec3b-195e-4410-9a1b-2444cbe212a1 |  | note | - Seating pot/can to contain 20mm diameter PVC drain pipe to drain to subgrade below
label | 0588ecea-3cb1-41be-a6e9-36b73626eaa7 |  | note | - SL81 Mesh Reinforcement located centrally between can and outer core wall.
label | 7d49b765-683c-4859-8447-8880b1586b04 |  | note | - Core backfilled with 20MPa concrete around can.
label | 6096d4e1-4239-4bbe-8051-769159ae4b73 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-CI-0681
label | d6058ff0-92ab-4686-a860-f0ec8ffe4142 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | cbc5c533-c694-4103-a525-b4e59787ad87 |  | note | RECORD OF CONFORMITY: This ITP Signed – ADBSG Elevated Light Installation Checklist
label | b2387504-a98d-4e30-8a6e-46aa63a6895f |  | note | IP
label | a125bd28-ce23-40ce-a517-c179b0680bd6 |  | note | RESPONSIBILITY: Project Engineer / Site Supervisor
text | 08090cf8-7368-4d49-88c3-a82453605b72 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Mortar Bedding & Surround
label | f450ed9e-042c-42e0-98a9-57411081fca1 |  | note | FREQUENCY: Each Lot
label | b489f950-6e06-4582-b210-27e02e5fb558 |  | note | ACCEPTANCE CRITERIA: Each Airfield luminaire to be provided with appropriate concrete base or shallow seating pot as shown in IFC drawings.
label | ddeda24f-9524-453c-8fff-c538f3d50858 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002 Chapter 10.3 AGL Elements & cl.10.2.7
label | 8ccde698-6800-46a7-8b6f-b5c257a11cf7 |  | note | INSPECTION/TEST METHOD: Verify
label | 0f1f605d-c3b1-450e-8edf-3b12b105ed1f |  | note | RECORD OF CONFORMITY: This Signed ITP – ADBSG Shallow Base Installation Checklist
label | ee34055e-bc3d-432e-8889-0e964019ef06 |  | note | IP
label | c8cc1da7-d91c-4309-a4f9-177df41027db |  | note | RESPONSIBILITY: Project Engineer
text | c1608982-09be-4342-bf4e-78a0f72d94fa |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.1 Setting out for Airfield Luminaires
label | 3fafcf16-b209-4529-b55d-38a5caede142 |  | note | FREQUENCY: Each Lot
label | b8512106-2443-4f15-b3f0-1a41cd6d5f75 |  | note | ACCEPTANCE CRITERIA: Conformance with Jacobs Issued For construction drawings (CAD File) and Taxiway lighting schedules. Alignment of luminaire positions, shallow seating pots, junction cans or MAGS to be checked.
label | 6406a4ad-b341-4b3b-b60e-a21149524334 |  | note | Maximum tolerances:
label | d8e9422c-0fa7-4ca8-9d61-f1b33e505a40 |  | note | - 0.5 degrees tolerance in level in any direction
label | a642e3ca-6465-439c-b819-b2b246e604e3 |  | note | - 0.5 degrees tolerance in azimuth
label | 22c79d59-83a6-4305-836f-a64743301477 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002 cl. 10.2.7
label | 8ae0fecf-15bf-4ec3-988c-d8a84a6959d0 |  | note | INSPECTION/TEST METHOD: Verify
label | f43b4b09-e8b8-46d6-ab07-17534acfea6b |  | note | RECORD OF CONFORMITY: SCP
label | c6a4c35b-d989-4850-83b9-8ffa08c3e694 |  | note | IP
label | e90d4375-220e-400d-ac42-2c058d2d7396 |  | note | RESPONSIBILITY: Project Engineer / Surveyor
text | 0898bab5-2897-421c-976a-501159334173 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Frangible Couplings
label | 7cea7bdc-ad31-4585-b937-d25b5a20ae26 |  | note | FREQUENCY: Each Lot
label | b47df11d-bccf-49ef-bfa9-a985b516b50e |  | note | ACCEPTANCE CRITERIA: Each Airfield luminaire or shallow seating pot shall be provided with frangible couplings.
label | 5a2c56b6-fb49-46ca-bcd5-4c9bf2828779 |  | note | - Couplings shall be designed and tested in accordance with FAA Document 150/5345-46D
label | 54a0eb80-5543-439a-9272-f3342d7e643a |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002 cl.10.2.3
label | 7dae0e7b-db53-4352-9972-374d234d0754 |  | note | INSPECTION/TEST METHOD: Verify
label | 406fe05f-1010-4de2-a979-951e44c6a5c2 |  | note | RECORD OF CONFORMITY: This ITP Signed
label | 1d8683cd-7014-4481-b4d3-b5beeaf6faa4 |  | note | IP
label | 9475e239-973a-4796-b8f1-e03c68886dfe |  | note | RESPONSIBILITY: Project Engineer
text | 911c9627-a1b2-46b7-ab9f-5560af8e0646 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Earthing Cable
label | 6c8dee53-4ce5-40b7-bec7-d92e3ab00ea9 |  | note | FREQUENCY: Each Lot
label | 8411ab5c-8bc7-4222-b01c-2ec28e659588 |  | note | ACCEPTANCE CRITERIA: Each fitting shall have earthing cable provided
label | 30da3d0d-f8d1-4cb1-8d1b-39b0fae87266 |  | note | - Earthing to be 6mm2 single core green/yellow PVC cable.
label | 2ad7e827-10b1-4341-8de3-eb9efc398eb0 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002 Chapter 10.3 AGL Elements
label | dfaed9e9-4298-49fd-8e2e-8523904092f5 |  | note | INSPECTION/TEST METHOD: Verify
label | 0221fbb8-88b0-4371-bcef-68b74485c6ee |  | note | RECORD OF CONFORMITY: This Signed ITP - ADBSG Light Fitting Installation Checklist
label | 4d529f95-dbe0-48b4-8289-e7971e456e7d |  | note | IP
label | cce78836-aa64-4d28-acc6-8faaba23e1c3 |  | note | RESPONSIBILITY: Project Engineer
text | 94aa1f64-5f21-4186-892c-a43329c6e658 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 Series Isolation transformer
label | efb6435b-7116-4a4a-9382-d439e823c3ef |  | note | FREQUENCY: Each lot
label | f14c0dde-5977-433c-b5b2-20402330743c |  | note | ACCEPTANCE CRITERIA: Each luminaire / fitting shall be connected to a series isolation transformer in closest SIT duct pit/ junction can.
label | 0ce6a75a-6363-4e11-98f9-172a44cf3fbd |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002 Chapter 10.3 AGL Elements
label | 48fb0f45-1adb-4995-a24e-4a109604c41a |  | note | INSPECTION/TEST METHOD: Verify
label | f2829ddc-423d-43b5-9f52-0aab5973be59 |  | note | RECORD OF CONFORMITY: This Signed ITP - ADBSG Light Fitting Installation Checklist
label | 79ed76ad-e718-4081-ba7b-6c138a63ce55 |  | note | IP
label | 42cbf1de-dcae-45b3-aae7-66110649d1d5 |  | note | RESPONSIBILITY: Project Engineer
text | 06090c2e-e1c7-487a-b82b-d9d684720299 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.5 Luminaire Circuit
label | 4c486861-4c6d-49ee-a89e-1e32c283afff |  | note | FREQUENCY: Each Lot
label | 7f1062a8-6074-4797-9d2a-39489a1cfce4 |  | note | ACCEPTANCE CRITERIA: Each luminaire fitting shall be installed on the appropriate circuit as specified in the construction drawings.
label | c5d98502-b343-4ea2-b8fe-6bb5804d7be4 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002 Chapter 10.3 AGL Elements
label | cf6054dd-1bd2-41aa-b5a1-bacddbd78f12 |  | note | INSPECTION/TEST METHOD: Verify
label | d1e34780-e5c8-4226-ba3c-337452447219 |  | note | RECORD OF CONFORMITY: This Signed ITP / As-Built Documentation - ADBSG Light Fitting Installation Checklist
label | 556b4451-5493-4760-8e6c-89745c194342 |  | note | IP
label | b183a5a7-0045-4532-91af-2c530f7a3f81 |  | note | RESPONSIBILITY: Project Engineer
text | 49d87f6c-60d1-43af-80ae-9ee678e92795 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.6 Blanking Plate
label | 4d9028c9-ea0d-401c-a136-accc6bb945b9 |  | note | FREQUENCY: Each Lot
label | 53718d24-6d43-45f4-a5da-2f93056c5709 |  | note | ACCEPTANCE CRITERIA: All luminaire fittings safeguarded for future use to be provided with an ADB Safegate Blanking plate, which shall be installed onto the seating pot instead of the associated fitting.
label | 5c3a7e19-ebfb-4d85-8463-522652641a0f |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002 Chapter 10.3 AGL Elements
label | bb3c8647-8db9-45dd-8eb8-bcea557df275 |  | note | INSPECTION/TEST METHOD: Verify
label | 5dd73dd2-5440-472e-8610-7711970891d9 |  | note | RECORD OF CONFORMITY: This Signed ITP - ADBSG Light Fitting Installation Checklist
label | 4d02c15a-9a90-4ca4-9036-1e014edcfba6 |  | note | IP
label | e193be6f-a1bf-4026-8d42-c2d0105b8db4 |  | note | RESPONSIBILITY: Project Engineer
text | 1ccb3391-15ce-40c6-80b9-8d0bb54c7c67 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.7 MAG Sign Face
label | c89b68da-c088-498c-a22c-99ee907343d9 |  | note | FREQUENCY: Each Lot
label | 937c717a-ca81-4d58-8f40-5f9b341a9af8 |  | note | ACCEPTANCE CRITERIA: All MAG sign facia shall be as per IFC drawings
label | ea6777a8-dcab-47ff-8df9-630f36fc3b2c |  | note | Sign to be located centrally on rectangular concrete foundation.
label | 894e0b15-d9bf-47f3-a9da-c8d0dfd74710 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-CI-0520 to 0524
label | 953de2bd-3d72-4a7d-9e98-615bcc501af0 |  | note | INSPECTION/TEST METHOD: Verify
label | 836e384d-8ac9-440f-814f-52553e02469d |  | note | RECORD OF CONFORMITY: This ITP Signed – ADBSG Installation of MAG bases Checklist
label | d0bb8642-14cb-424c-8361-1eb30f8c3606 |  | note | IP
label | 8dc8d406-71c0-4276-b406-5b9a6ffe3379 |  | note | RESPONSIBILITY: Project Engineer
text | eceae734-bf27-44c2-987c-3dd813f9a585 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.8 Abandoned AGL Luminaire
label | 42881d55-0ee5-420e-a75a-014b30f0e48b |  | note | FREQUENCY: Each Lot
label | a35cf21a-4a29-4918-8197-7bebb297ba76 |  | note | ACCEPTANCE CRITERIA: All existing AGL bases shall be raised, abandoned, removed or replaced as indicated in the IFC drawings
label | 1d11a837-d729-4823-acc3-942073791fff |  | note | REFERENCE DOCUMENTS: CP140308-AIR-DET-PM-SP-0002 cl. 10.2.8
label | 6e7327dc-86de-4eed-8351-696158bf2830 |  | note | INSPECTION/TEST METHOD: Verify
label | c62126ee-9b68-4969-a536-601041bc3673 |  | note | RECORD OF CONFORMITY: This ITP Signed – ADBSG Light Fitting Removal Checklist
label | 3a7d534d-147f-4420-b410-0d3c77b6f36d |  | note | IP
label | 9f1a461e-7f3f-4feb-8d96-d7bfb91cfff7 |  | note | RESPONSIBILITY: Project Engineer
text | 68156338-41db-459a-ac52-f44940805c8e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.1 As-Built
label | 630d29ed-a877-4c18-830d-7dd58479dc8a |  | note | FREQUENCY: Each Lot
label | e5838901-0502-4380-912a-7b7125efa286 |  | note | ACCEPTANCE CRITERIA: Submission of surveyed luminaire position to superintendent prior to practical completion
label | d186483e-387a-410d-a8a7-677b582141d3 |  | note | REFERENCE DOCUMENTS: WP013
label | c356650b-ae25-462a-9e77-1899448a5152 |  | note | INSPECTION/TEST METHOD: Verify
label | ce879b6d-59b6-46e8-90d5-41de31e477a3 |  | note | RECORD OF CONFORMITY: SCP
label | b47ca749-0e16-46e9-b699-99c0f54280f7 |  | note | IP
label | 5142b8d2-ff19-46d5-9019-fc91bd263272 |  | note | RESPONSIBILITY: Project Engineer
text | f532dc5b-3fc2-41ff-82e1-90c465b5a7e8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 0d6782da-f98a-405c-a34e-1c1c9b38e939 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | a52284c7-c6d0-45e0-be40-c50a45df74f8 |  | textbox | Print Name:
text | 52d3f388-3c48-4ec1-bd84-b58e91d5b1db |  | textbox | Position:
text | 95e351b5-9f33-48a0-9353-1a7291b242e1 |  | textbox | Date:
checklist-sectioned |  |  | checklist | ITP037 - BIDIM A19 Installation | itp |  |  |  | Yes | ITP 037 - BIDIM A19 Installation | 11a2fe77-db70-4815-b1d7-6a5da5fc239c
checkpoint-group |  |  | section | ITP037 - BIDIM A19 Installation
checkpoint-status |  |  | checkpoint | 1.1 Check for correct documentation
label | 9ae8f23e-4319-430f-a0c2-dad30568029c |  | note | FREQUENCY: Prior to commencing any activity
label | 6e78abf4-0b70-43f6-8654-e83e825f5586 |  | note | ACCEPTANCE CRITERIA: Current revision drawing is being used including the subcontractors copy. Current Revision to be obtained via Aconex
label | 08de212a-6611-4d98-89c8-7b1a986f2bf9 |  | note | REFERENCE DOCUMENTS: Drawings and Aconex
label | 88f88bac-e31a-4d47-a5cd-94f9b74b4dec |  | note | INSPECTION/TEST METHOD: Visual inspection
label | cceafd01-a1ab-4d8d-a6e2-e5f8dbbd338b |  | note | RECORD OF CONFORMITY: This Signed ITP
label | 10030d33-3264-4ea0-b83a-bfd24faaf939 |  | note | HP*
label | 58f8d836-e829-481e-baeb-a4a3e12e7b96 |  | note | RESPONSIBILITY: Project Engineer
text | 5f2585a5-4d0e-4b01-8021-1a9873ec1f63 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 Implementation of all measures and controls
label | 7ed06c7b-bdb7-45a4-8dcd-f05ed8a423e2 |  | note | FREQUENCY: Prior to commencing any activity
label | b957dc84-8ac3-4f8f-b6e6-75afd740e67d |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | 89d95ac1-f848-4a99-81fc-5ee3ec7ae814 |  | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, SWMS, WP
label | 8ca0e5c1-35b4-495c-82df-f0c4c653ab91 |  | note | INSPECTION/TEST METHOD: Inspect
label | 4e2040db-c89e-44c6-a9ca-d8bfa19b015d |  | note | RECORD OF CONFORMITY: This Signed ITP
label | 91b44f66-4eb9-42f0-938c-f134669167f4 |  | note | HP*
label | d1f1dc8f-50d4-46a0-914f-19b99e3dad43 |  | note | RESPONSIBILITY: Project Engineer
text | a55fff8c-c75d-402b-a0b6-33e44701316c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 Material Approval
label | 0b15d800-02d3-4416-baa9-4e78f7bf4147 |  | note | FREQUENCY: Before procurement
label | 3962be64-4698-4f7e-abfd-b49712788b98 |  | note | ACCEPTANCE CRITERIA: BIDIM Geosynthetic with minimum Grade A19
label | e0d47de3-490f-44ef-b4e8-8967505ec849 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-CI-5041
label | 52ceb265-9367-49eb-a8ed-b13696f44ca9 |  | note | INSPECTION/TEST METHOD: Verify
label | 0a829a3f-63f5-49d7-a482-b956f1a0a304 |  | note | RECORD OF CONFORMITY: ACONEX / This signed ITP
label | 2ea18364-2ba5-499b-8bc4-8c5e8fb2d011 |  | note | HP*
label | 076f7fc2-2507-4d24-961d-2b1f3cb86138 |  | note | RESPONSIBILITY: Project Engineer
text | 39d572b8-6131-4868-a0ee-33d9f32300e0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 Material Storage
label | 24851aee-7d32-4180-b36a-c58fb6332b6a |  | note | FREQUENCY: During Installation
label | 5b30dcda-e258-46d3-8e22-13868046e97e |  | note | ACCEPTANCE CRITERIA: BIDIM Geosynthetic products must be delivered to site in rolls wrapped in plastic and must be placed on pallets and covered with a tarpaulin if stored outside.
label | 9ffc8380-f54a-4372-9332-2252dc11c6f8 |  | note | REFERENCE DOCUMENTS: BIDIM storage and installation guide
label | 63cad765-d19f-41d0-beb8-44d9919494d4 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 1c949e70-528b-4fbb-96bc-f6be6acafb92 |  | note | RECORD OF CONFORMITY: This signed ITP
label | 3de5892b-50d0-4bd7-ab24-3a6573c8dfcc |  | note | IP
label | d002e8d1-0610-42db-9485-eb1baa4a38de |  | note | RESPONSIBILITY: Project Engineer
text | 0e7db119-542b-4502-838a-fb95abe905ec |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Material Handling
label | a05320b1-e55a-4e36-ad76-5a3c59a03ef4 |  | note | FREQUENCY: During Installation
label | 8f583b65-7097-4b77-b308-79e13faca42d |  | note | ACCEPTANCE CRITERIA: Rolls will be handled using a fork lift or spreader bar with tele handler when being loaded and unloaded from the truck.
label | c514b35b-e717-40c5-87a3-84c60c321e99 |  | note | REFERENCE DOCUMENTS: BIDIM storage and installation guide
label | 0fe774ae-0ff1-48bc-96f9-36420f40ca0f |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | eb10039b-8e4a-4e99-8ee9-4cdf79eca9f5 |  | note | RECORD OF CONFORMITY: This signed ITP
label | 5a88ae4b-a012-4b11-a247-d859c45b0ef4 |  | note | IP
label | 1694cb01-9dd2-41e9-bc62-5d00d1259fe2 |  | note | RESPONSIBILITY: Project Engineer
text | edb8b90b-0e28-4058-80c7-33d74e62da95 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.1 CRWP Preparation
label | a621d546-6de2-494d-a426-3a913314c456 |  | note | FREQUENCY: Each Lot
label | 7d135d6f-57e8-4b43-a2d8-4ccbff38bddc |  | note | ACCEPTANCE CRITERIA: Inspection of underlying layer and ensuring the underlying associated CRWP Lot has been closed out.
label | 01396951-9057-4840-9b1c-624cd07a68c7 |  | note | REFERENCE DOCUMENTS: FH-ZULU-PM-ITP007
label | a51a9328-df8d-4dee-8964-225f0fdd4664 |  | note | INSPECTION/TEST METHOD: Verify
label | cb3c87bc-4bf9-40ba-a58e-ebafe33375ca |  | note | RECORD OF CONFORMITY: This signed ITP
label | d1d2f9e3-2ba4-49bc-9ef9-5fb884a40d84 |  | note | HP*
label | 62e8518b-397b-45ca-8a45-98a995b607a8 |  | note | RESPONSIBILITY: Project Engineer
text | 33c876ee-5f65-4252-b9cd-fd3163c6bb85 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Deployment
label | 7e9f1a92-9415-47b3-a70d-d1b8b480b0e0 |  | note | FREQUENCY: During Installation
label | 74b7195d-ab63-46f0-8c2c-c60e0e95a792 |  | note | ACCEPTANCE CRITERIA: During deployment material overlaps will be deployed as per the manufacturer’s guidelines. Minimum overlay of 300mm – 450mm as per BIDIM Storage and Installation Guide – 3.1 Overlapping.
label | 0196cbe2-79ea-4b4f-af2a-387457a227ff |  | note | REFERENCE DOCUMENTS: BIDIM storage and installation guide
label | 69e81650-0f78-43de-bacb-91162e10f8fa |  | note | INSPECTION/TEST METHOD: Verify
label | 0b6d6124-f090-41c3-914f-33ac199b5322 |  | note | RECORD OF CONFORMITY: This signed ITP
label | 9f13a72c-7654-41b0-8a23-1f1b583c0e95 |  | note | IP
label | 78ad5f14-e6ac-46ef-837d-bddc59dd7a0d |  | note | RESPONSIBILITY: Project Engineer
text | 4065d4cf-0983-4ff6-8dfa-9616b789bd76 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Defects and repairs
label | c65c919d-eddb-442c-b48c-804e03ee2af9 |  | note | FREQUENCY: During Installation
label | 64211973-f3dd-4110-bfae-ef81ef584a1e |  | note | ACCEPTANCE CRITERIA: Geotextile repair for damaged or disturbed geotextile sections to be patched with a minimum 300mm overlay and stapled to subgrade with 150mm U Shaped retaining pins. Repairs to be signed off by the Principals Representative.
label | c309fd89-16aa-41c8-9e68-ffe1318f4d37 |  | note | REFERENCE DOCUMENTS: BIDIM storage and installation guide
label | c713affd-41b2-412d-ae49-8715ea468f2b |  | note | INSPECTION/TEST METHOD: Verify
label | 46164c5e-0a64-4b22-b26f-db2ec52c6c9e |  | note | RECORD OF CONFORMITY: This signed ITP
label | 113457f4-9a27-4b0f-8f7a-fd5171e5be10 |  | note | HP*
label | 935ee350-6c60-4544-bb70-7e7ace9f396c |  | note | RESPONSIBILITY: Project Engineer, Principals Representative
text | 0ceadf91-4b83-484f-b938-9143b3622945 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 Fill placement
label | dd91639a-8a74-41ef-8413-d7ba4b5a5b67 |  | note | FREQUENCY: During Installation
label | 596b5ab0-9800-46ae-923a-39ecd241326d |  | note | ACCEPTANCE CRITERIA: Fill to be placed in 200mm. Fill placement over joints to be placed from the higher overlap side of the joint to ensure joint integrity during placement. No construction equipment to drive directly over the geotextile.
label | dbb413b7-09a6-48f5-b5b6-69c9a7ac628c |  | note | REFERENCE DOCUMENTS: BIDIM storage and installation guide, Vic roads section 204
label | 000aeba6-8a52-4a2d-8805-e8f5c927e554 |  | note | INSPECTION/TEST METHOD: Verify
label | 185d6755-36b0-42ef-9e55-4c1d75eaff58 |  | note | RECORD OF CONFORMITY: This signed ITP
label | 312d6fad-bd57-4a1a-8809-5b7e04bdf4d6 |  | note | IP
label | 87aca524-18ca-4ca9-94bb-7cec59b26f81 |  | note | RESPONSIBILITY: Project Engineer
text | 1b63dc96-fe93-4e90-92a5-c83457d29bc6 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | e010e011-6a4e-4e5b-b17e-95d5f38a2642 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 0db6eee1-d111-4821-89b2-5855b8227f92 |  | textbox | Print Name:
text | 7ed19d32-b568-439c-a57d-821f8f98b90f |  | textbox | Position:
text | 9ba6b194-af91-4f5e-8c0f-b2ec56b9e916 |  | textbox | Date:
checklist-sectioned |  |  | checklist | ITP 033 - Hot Mix Asphalt Production – Airfield Asphalt | itp |  |  |  | Yes | ITP 033 - Hot Mix Asphalt Production – Airfield Asphalt | 134003a1-bbbf-4597-b206-a136d324aee2
checkpoint-group |  |  | section | ITP 033 - Hot Mix Asphalt Production – Airfield Asphalt
checkpoint-status |  |  | checkpoint | 1.1 Mixing Plant Calibration Charts
label | 61a38469-3416-4723-b12e-24d3745b1073 |  | note | FREQUENCY: Prior to works
label | d68ddfb5-f3f0-4114-a65e-9dde0d1110e2 |  | note | ACCEPTANCE CRITERIA: Acceptable mixing plant calibration charts are provided to the Principal’s Representative prior to production trial
label | 889d2362-b5c0-484c-90d0-2fc27f84096a |  | note | REFERENCE DOCUMENTS: 7.7.2
label | 8f35ae0b-c84d-4cac-a2b3-c70ca7076ed5 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 25bf5bac-e456-46e0-9395-917734894dfd |  | note | HP
label | 612fb91c-58c7-4c71-85dc-2baf330bd527 |  | note | RESPONSIBILITY: Plant Supervisor
text | c7341f3b-d3a5-4a2c-ac93-7c0cc10f1f31 |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 2.1 Asphalt mix temperature
label | 54cf543f-dc47-4278-8919-4ee4b4db450f |  | note | FREQUENCY: Once per 250 tonnes asphalt produced
label | c474ceea-1704-4c67-b4a9-cfda7995c572 |  | note | ACCEPTANCE CRITERIA: Probe immersion thermometer inserted at least 150mm below the surface of asphalt in loaded truck to be not more than 175oC.
label | fa8f770f-f60e-4cea-9534-aef3b489606f |  | note | REFERENCE DOCUMENTS: 7.8.1
label | cdf7c556-1f32-4e3b-9a2b-43f551a77006 |  | note | INSPECTION/TEST METHOD: Inspection
label | 2282cfb4-ccb0-48fb-99be-79642929758c |  | note | IP
label | 9a64ffe0-7ecd-4586-bc37-489392eb1421 |  | note | RESPONSIBILITY: Laboratory Technician / Plant Operator
text | cae24235-14d0-4478-bff7-7cdd242c9283 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Mixing efficiency
label | fe914890-91b8-40a0-9481-945b6c1f3a00 |  | note | FREQUENCY: Every truck
label | 4c956021-001c-4274-9bac-a7cc1b86de07 |  | note | ACCEPTANCE CRITERIA: All coarse aggregate must be fully coated with bitumen; mix to have no visible segregation and no obvious presence of excess moisture.
label | 191b771c-be19-484e-adcf-a09fa7fe886e |  | note | REFERENCE DOCUMENTS: 7.8.1
label | ba563275-856e-42a7-a760-7977ae3db6d7 |  | note | INSPECTION/TEST METHOD: Inspection
label | 031d1e28-0ccd-45a5-9af5-286dc8818d1e |  | note | HP
label | cfd23d7d-0b84-4eb2-959d-5e95a4a9e81b |  | note | RESPONSIBILITY: Laboratory Technician / Plant Operator
text | 40377e07-15a2-4c89-bf5f-f30b57fc6c57 |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 3.1 Particle Density Coarse
label | c5633702-2bb2-4725-8e38-a1a9b6e12297 |  | note | FREQUENCY: 1 per 1000 tonnes aggregate
label | 334b6e7e-620a-4931-a0e5-92152713a1f8 |  | note | ACCEPTANCE CRITERIA: Not less than 2300 kg/m3
label | c065ab44-ca10-42ee-bdca-bb459ed0579e |  | note | REFERENCE DOCUMENTS: 7.3.2.2 & Table 7-4
label | da352684-1699-4200-be09-77da2522e8a3 |  | note | INSPECTION/TEST METHOD: AS 1141.6.1 /6.2
label | a551927f-8698-48e7-8e94-8317460589c2 |  | note | TP
label | 7e23c825-353c-4819-9add-3c1361f8d83f |  | note | RESPONSIBILITY: Laboratory Technician
text | c5c8955a-3857-481f-a218-2aa014f2a411 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Water Absorption
label | 6651dc41-fc1c-4881-a4ce-ce1f56f440c0 |  | note | FREQUENCY: 1 per 1000 tonnes aggregate
label | b12a2bb2-0081-4d3d-8fe3-02b6b7df8e27 |  | note | ACCEPTANCE CRITERIA: Not more than 2.0% (Asphalt mix designed to meet performance criteria with current aggregate source rock producing water absorption >2.0% - approved by Jacobs)
label | 24295f5f-e9eb-4278-b9ea-a14af4cf2830 |  | note | REFERENCE DOCUMENTS: 7.3.2.2 & Table 7-4
label | 591606d6-4e0e-452c-8b38-5e6de1641c41 |  | note | INSPECTION/TEST METHOD: AS 1141.6.1 /6.2
label | 41d2a6d2-6d41-4f37-a75f-f1ac7e54b596 |  | note | TP
label | 58bbc37d-1671-411e-8648-79edf1a6e895 |  | note | RESPONSIBILITY: Laboratory Technician
text | 3ddc0f3f-4b9a-4601-b289-602bba8a2343 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Particle Size Distribution
label | 43d9c054-9c37-476b-b47e-209f7efc3d32 |  | note | FREQUENCY: 1 per 500 tonnes aggregate
label | 96c7a69f-d02d-4733-9777-bb74cd753958 |  | note | ACCEPTANCE CRITERIA: PSD to FH Internal Limits
label | a46284fc-a6c2-4e6d-af82-f5ae43585f86 |  | note | REFERENCE DOCUMENTS: 7.3.2.2 & Table 7-4
label | 09558136-e15e-4c94-9115-959ea55da012 |  | note | INSPECTION/TEST METHOD: AS1141.11. 1 (washed)
label | 6a4ded86-a18e-4579-b4a9-3a238a6ac1b8 |  | note | TP
label | d93497d3-c989-498f-bfdf-af9a27e8b1d4 |  | note | RESPONSIBILITY: Laboratory Technician
text | 85f672bd-1fec-42af-801b-e1c80a4410f8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 Material Finer than 0.075mm in Aggregates (by washing)
label | a7be4802-3fd2-4127-9bae-0797048812d0 |  | note | FREQUENCY: 1 per 500 tonnes aggregate
label | 2869af68-5f04-4de1-b2c2-d62a439483d0 |  | note | ACCEPTANCE CRITERIA: Not more than 2.0%
label | 759e18b0-9b0d-47c2-a12f-10c676805d4d |  | note | REFERENCE DOCUMENTS: 7.3.2.2 & Table 7-4
label | 4c540a89-ab16-4238-9772-73c3e583d784 |  | note | INSPECTION/TEST METHOD: AS1141.11. 1 (washed)
label | 09452559-6987-491b-8905-9311b2408381 |  | note | TP
label | ff35e700-e859-4e6d-a0d1-c7608c6018f7 |  | note | RESPONSIBILITY: Laboratory Technician
text | 29a42d53-c998-41f9-acb2-02ad7e3bcc73 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.5 Flakiness Index (nominal 10 mm and larger aggregate)
label | 6fac1b29-0c84-4533-a80d-2c269dfe124f |  | note | FREQUENCY: 1 per 1000 tonnes aggregate
label | c9b472a6-91e0-4a3f-a5b7-e1a860e18976 |  | note | ACCEPTANCE CRITERIA: Not more than 25% (Flakiness Index used in place of particle shape test – approved by Jacobs)
label | 2946d659-eec0-4e9d-aa6a-2bdd8e6a4383 |  | note | REFERENCE DOCUMENTS: 7.3.2.2 & Table 7-4
label | 5c43203d-3a05-4b54-a794-93257726d472 |  | note | INSPECTION/TEST METHOD: AS 1141.15
label | d10292de-a6ed-459d-9192-277af33a24e6 |  | note | TP
label | d7c62891-b8e9-4828-a48b-e0e89660e007 |  | note | RESPONSIBILITY: Laboratory Technician
text | af535d86-3e83-4fd8-a665-79dd4ea6e855 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.6 Weak particles
label | 051c5c76-117d-4e24-900a-e19c42fa89a3 |  | note | FREQUENCY: 1 per 500 tonnes aggregate
label | fd7bc761-7c43-446e-bcea-d5d648bc7ce5 |  | note | ACCEPTANCE CRITERIA: Not more than 0.2%
label | cf3af95d-3c59-4d20-a92d-fb6f4f6ceeb0 |  | note | REFERENCE DOCUMENTS: 7.3.2.2 & Table 7-4
label | e9aab050-7106-45fe-b8a9-b1f94e3a341c |  | note | INSPECTION/TEST METHOD: AS 1141.32
label | 4b8bc1b1-0662-4ad1-ab02-6d1d41da8a0f |  | note | TP
label | ef2a57b2-e0aa-44ee-b4b0-ee757fe5c4f6 |  | note | RESPONSIBILITY: Laboratory Technician
text | 1ae1b3db-43fd-4dd7-9729-a29785290532 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.7 Freshly Fractured Faces
label | a1645dce-1e38-4fee-b05e-ba813d2f4c20 |  | note | FREQUENCY: N/A
label | 1cde933f-5645-43cc-b1ae-3d5308cbbb3c |  | note | ACCEPTANCE CRITERIA: Test not applicable for 100% crushed basaltic source rock
label | d45cd5c2-35a2-4c3d-ad7d-c3a4a313c668 |  | note | REFERENCE DOCUMENTS: 7.3.2.2 & Table 7-4
label | 4336ad5e-9de7-42bf-96fd-050df44ffe82 |  | note | INSPECTION/TEST METHOD: RMS T239
label | 8d18a08b-e5ff-47d6-a116-1acd20c07d84 |  | note | TP
label | 387db2db-4aa3-4e5e-8e78-4a323d5f1c30 |  | note | RESPONSIBILITY: Laboratory Technician
text | 19b1590f-6e8a-45ae-a9b5-498cce4688a0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.8 Soundness (using Sodium Sulphate)
label | 2c170441-586f-4bc6-ba03-a21aeaafc667 |  | note | FREQUENCY: Initial
label | 6d54677e-0792-4062-a5c0-e945e55e5003 |  | note | ACCEPTANCE CRITERIA: Not more than 3% weighted loss
label | be47a498-e5eb-4c48-94af-7e68b7fa1e54 |  | note | REFERENCE DOCUMENTS: 7.3.2.2 & Table 7-4
label | 68061f88-dc72-4a60-8daa-9b58613f2ae4 |  | note | INSPECTION/TEST METHOD: AS 1141.24
label | a74e3903-c726-44c5-a036-4e4d1578e32d |  | note | TP
label | 5e0b205d-d61d-4e34-8020-5720d701e17a |  | note | RESPONSIBILITY: Laboratory Technician
text | 803f8064-5fc4-41c7-ab40-ce2b554a86d6 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.9 Wet Strength
label | a345126e-7c72-4654-a387-0e560ed081cd |  | note | FREQUENCY: Initial
label | 219475aa-c0f9-4333-bd33-439bfce48386 |  | note | ACCEPTANCE CRITERIA: Not less than 150kN
label | 83b7a75e-4f78-4b94-a079-f12eda555cec |  | note | REFERENCE DOCUMENTS: 7.3.2.2 & Table 7-4
label | 8b2a2389-3d79-4c32-b319-9b01ade8bc70 |  | note | INSPECTION/TEST METHOD: AS 1141.22
label | e88bf747-3927-41bc-8312-cdb532e35e85 |  | note | TP
label | df39bb54-d3bf-48dd-b607-dbc9cf88262c |  | note | RESPONSIBILITY: Laboratory Technician
text | 90915f06-ab79-44ac-84f9-c2e08f9c9ec5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.1 Wet / Dry Strength Variation
label | 85afe67c-417c-4e45-a91c-5ea04a50f456 |  | note | FREQUENCY: Initial
label | b9e53a75-e413-42fc-a3e0-ab993430393c |  | note | ACCEPTANCE CRITERIA: Not more than 30%
label | 48e45771-95c0-40fc-8a29-190764fe6463 |  | note | REFERENCE DOCUMENTS: 7.3.2.2 & Table 7-4
label | 36ecfd03-25eb-4474-94ee-3e4a75c322fd |  | note | INSPECTION/TEST METHOD: AS 1141.22
label | 0a7e877f-b9d1-4d9d-94f6-0cfa567cf908 |  | note | TP
label | e7502ca9-2a8c-45d8-9fc4-823db204a1d6 |  | note | RESPONSIBILITY: Laboratory Technician
text | d956912c-884f-46b3-9574-4f667f1f7da4 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.11 Los Angeles Value
label | 581d3d22-fe16-4c82-a7ea-ce303cbc29cb |  | note | FREQUENCY: Initial
label | 25a74fb3-0863-43ad-83cf-4b69de63749d |  | note | ACCEPTANCE CRITERIA: Not more than 25% loss, B or K Grading
label | 4cd31f66-d317-43e8-a954-b018be07b27d |  | note | REFERENCE DOCUMENTS: 7.3.2.2 & Table 7-4
label | 953675df-82c6-4382-994b-50d68b0dbc9b |  | note | INSPECTION/TEST METHOD: AS 1141.23
label | 88fb6619-459a-42a1-ad71-946a1851c2b2 |  | note | TP
label | 2e51284d-cba8-458d-81be-802da5b1d469 |  | note | RESPONSIBILITY: Laboratory Technician
text | e7a39439-3287-4420-b029-eca9610f9f89 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.12 Secondary Mineral Content
label | d80f3b6b-2634-46e8-95b4-c1cb37116a97 |  | note | FREQUENCY: Initial
label | c9f60aab-25c7-4fb2-b6ee-3665bb2d0861 |  | note | ACCEPTANCE CRITERIA: Not more than 20% (Basic rock types only)
label | 1baa9368-e15c-4438-8e7f-05843cd31031 |  | note | REFERENCE DOCUMENTS: 7.3.2.2 & Table 7-4
label | d4349d6c-a85a-4c43-adef-7454e49563ca |  | note | INSPECTION/TEST METHOD: Petrographic Analysis
label | 79d2df53-868b-44ae-a163-e8d2c50369c4 |  | note | TP
label | 38ff4d7a-4ab2-4ac5-9fe3-b5445fac7199 |  | note | RESPONSIBILITY: Laboratory Technician
text | 2babecd8-b519-4ae0-9db4-dd3464da7ca3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.1 Particle Size Distribution
label | 354e4bc3-09d9-4037-9776-f054a2adf6f7 |  | note | FREQUENCY: 1 per 500 tonnes aggregate
label | 6ef633e1-0cc0-4db3-b2b1-1afb5b77341a |  | note | ACCEPTANCE CRITERIA: PSD to FH Internal Limits
label | b836f81c-4794-42a1-93df-901e629b970a |  | note | REFERENCE DOCUMENTS: 7.3.2.3 & Table 7-5
label | e61b6107-c1a4-4fc5-be79-f9773bbeeec7 |  | note | INSPECTION/TEST METHOD: AS1141.11. 1
label | 5347b1f9-71e8-470a-bbf2-997217f25196 |  | note | TP
label | 584ec30b-8084-4202-a886-c357c01de892 |  | note | RESPONSIBILITY: Laboratory Technician
text | fad60fa7-3110-4ae8-a5de-6996da998614 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Particle Density Fine
label | c70efb7e-2ee4-4b84-867b-444878bf25bd |  | note | FREQUENCY: 1 per 1000 tonnes aggregate
label | c6766de3-e5ab-4388-bed5-5722bc35ed16 |  | note | ACCEPTANCE CRITERIA: Not less than 2300kg/m3
label | ad8f544e-fc4e-457d-8437-07bb540ea3f7 |  | note | REFERENCE DOCUMENTS: 7.3.2.3 & Table 7-5
label | b3e8d65b-7f86-4c2a-8283-713465d7ed0b |  | note | INSPECTION/TEST METHOD: AS 1141.5
label | 05ee0a37-777d-4a76-a64f-164bb8ce924d |  | note | TP
label | 7da96832-80c7-4788-ad0c-98e08b37d899 |  | note | RESPONSIBILITY: Laboratory Technician
text | 1ced7b84-6308-4fc6-afe0-73f37a283ecf |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Water absorption – crushed aggregate
label | b74ee304-77ec-462b-b6af-ce473039a54e |  | note | FREQUENCY: 1 per 1000 tonnes aggregate
label | 5fbaba44-523f-4d83-833f-ee34c7d7cda9 |  | note | ACCEPTANCE CRITERIA: Not more than 2.5%
label | 314160c5-cf1d-4105-9cc9-e1b09b761159 |  | note | REFERENCE DOCUMENTS: 7.3.2.3 & Table 7-5
label | 865b7690-7a3c-4767-91d6-b4319dd62f4b |  | note | INSPECTION/TEST METHOD: AS 1141.5
label | c3a2dc5a-658f-41b0-8e50-ff49fdc6b773 |  | note | TP
label | b9b24d49-62b4-4a1a-a74f-86fce893752b |  | note | RESPONSIBILITY: Laboratory Technician
text | 5c128bbe-23b3-4b6a-a6a6-e31acab85e85 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 Water absorption – uncrushed aggregate
label | ed5f3d0d-aa38-4921-827e-f2d6fe12fa80 |  | note | FREQUENCY: 1 per 1000 tonnes aggregate
label | 7fecd06c-b280-4ab9-a421-b3089c9c89df |  | note | ACCEPTANCE CRITERIA: Not more than 2.0%
label | 743a825d-a97d-4f23-9d58-b0274ae6c64d |  | note | REFERENCE DOCUMENTS: 7.3.2.3 & Table 7-5
label | 42617284-2bce-465a-b332-837ea44a7818 |  | note | INSPECTION/TEST METHOD: AS 1141.5
label | c827d16c-4a08-46e4-8403-2e87cbdcad0b |  | note | TP
label | b54346d0-f66a-412c-b3e6-efa31cb46977 |  | note | RESPONSIBILITY: Laboratory Technician
text | 607f1e0a-b321-4ec0-bdaf-e32f4bb4a3ee |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 Plasticity Index
label | af3b5749-be42-4aa4-a76b-8030397398e8 |  | note | FREQUENCY: 1 per 500 tonnes aggregate
label | 8758228a-7c6d-4311-91c3-3c9e43770192 |  | note | ACCEPTANCE CRITERIA: Non Plastic
label | fabeb6b3-13bd-4e8a-aaa0-bcfda5547681 |  | note | REFERENCE DOCUMENTS: 7.3.2.3 & Table 7-5
label | 3d136bcd-8c7d-4eef-b783-7036e88478da |  | note | INSPECTION/TEST METHOD: AS 1289.3.3.1
label | a5050b83-105a-4b88-9d44-272a677ff761 |  | note | TP
label | 88be9074-9f4a-46c2-a2f0-eda5a6415a30 |  | note | RESPONSIBILITY: Laboratory Technician
text | 8e64ba8f-9127-49cb-a8a2-f7028a13268c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.6 Linear Shrinkage
label | f1ccd444-7be1-4113-aa4e-b4b0a8761822 |  | note | FREQUENCY: 1 per 500 tonnes aggregate
label | a55df2ab-153d-44da-9a3f-5f669f82d72b |  | note | ACCEPTANCE CRITERIA: Not more than 1%
label | 682903db-2df4-47b3-b40e-2570badc5a99 |  | note | REFERENCE DOCUMENTS: 7.3.2.3 & Table 7-5
label | 2e16181e-5163-4e45-9b52-4a313822ad2e |  | note | INSPECTION/TEST METHOD: AS 1289.3.4.1
label | 30f9461b-4d0e-4290-92c2-f296c1b1dea8 |  | note | TP
label | 9142c04e-92a8-4d0c-91a1-8461509fbaa3 |  | note | RESPONSIBILITY: Laboratory Technician
text | 2d2231f6-77de-4a60-b342-5341807b2fb9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.7 Soundness (using Sodium Sulphate)
label | bdc27549-87f2-4ea0-9710-4fafa6be822e |  | note | FREQUENCY: Initial
label | 5f54c0c7-5548-4ed5-b139-983df0fa1c97 |  | note | ACCEPTANCE CRITERIA: Not more than 3% weighted loss
label | ccc3eb9d-ea0c-4fe1-bdc0-cc2ace817be2 |  | note | REFERENCE DOCUMENTS: 7.3.2.3 & Table 7-5
label | d0b514c2-d69b-469e-b557-129eb5085b63 |  | note | INSPECTION/TEST METHOD: AS 1141.24
label | 11161fb0-4ad0-4b5b-b02e-963554cb4644 |  | note | TP
label | f766cf0f-0a82-45ed-929f-0aa27b428c29 |  | note | RESPONSIBILITY: Laboratory Technician
text | f98b3a13-5771-4857-9d18-e22d33976c56 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.1 Binder Sampling
label | 48ce9e93-c650-4a49-b430-4533e40447f9 |  | note | FREQUENCY: Prior to Placing
label | bfe7abb3-501a-4b8b-b0ab-e42df5fdfe67 |  | note | ACCEPTANCE CRITERIA: Samples of bitumen are to be obtained in accordance with AS 2008 ( Appendix B); A minimum of three samples each not less than 1.0L;
label | 27c1502e-ba33-4c85-a045-fb779b9df91c |  | note | REFERENCE DOCUMENTS: 7.10.2.4
label | 986c01f1-35c8-42d3-8d3c-7d60c452db60 |  | note | INSPECTION/TEST METHOD: AS 2008
label | cbd96d97-f2ec-4c69-b6d5-a0f5691b023e |  | note | WP
label | b1f6e10c-04e8-4f4a-817c-0df8d431b873 |  | note | RESPONSIBILITY: Laboratory Technician
text | 98813e50-f36d-43c9-bbc3-6dd89d8004a5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Binder Testing
label | b8b9c761-f0e6-4fa8-ad4c-d79ac2207b73 |  | note | FREQUENCY: Prior to works
label | 46fe3732-2aba-4cbb-9538-79496a2fd023 |  | note | ACCEPTANCE CRITERIA: Bitumen is to be tested at the point of delivery. The sample is to be tested for the following:
label | 526b2973-7bb8-4e51-8ca6-3155c23ca5a0 |  | note | - Viscosity at 165°C according to AG:PT/T1 11.
label | f3ea0258-2885-433e-9409-424875fd49f2 |  | note | - Torsional recovery at 25°C, 30 s according to AG:PT/T1 22
label | 8b1a40b7-e59e-4a2e-98ed-ee4efb1c43bb |  | note | - Softening Point according to AG:PT/T1 31
label | a6397373-000c-4d38-af40-56d30ffcca83 |  | note | REFERENCE DOCUMENTS: 7.10.2.4
label | 06b34f8c-e2cb-4373-9b55-c1d9d08837ec |  | note | INSPECTION/TEST METHOD: AG:PT/T1 11 AG:PT/T1 22
label | 2e7ebe0d-ea31-4e6e-a722-7062620cb23c |  | note | HP
label | 09c3e051-709b-4161-bfb6-0c9373f92a43 |  | note | RESPONSIBILITY: Laboratory Technician
text | ff77879a-433a-4ab5-a6a5-dc6accd0ed36 |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 6.1 Sampling
label | 4f20180e-aa51-47ce-839f-a98fca1a3437 |  | note | FREQUENCY: Once per 250t asphalt produced (Revised frequency approved by Jacobs)
label | 2536909d-4054-4a9c-bfbc-4b950b1b0641 |  | note | ACCEPTANCE CRITERIA: Mix to be sampled from asphalt delivery trucks.
label | 268f031f-ea1f-4190-a499-5a0900a87c39 |  | note | REFERENCE DOCUMENTS: 7.10.3
label | 6e9784de-95f7-4a11-b03b-802008abdbf6 |  | note | INSPECTION/TEST METHOD: AS 2891.1.1
label | 92289939-f16a-4595-8f53-c2338f4c06fb |  | note | TP
label | 66b0adf2-6a80-43fc-a917-c3bcb4f02f81 |  | note | RESPONSIBILITY: Laboratory Technician
text | 15bcecc5-8221-4eae-9db2-26cf61a9a0e7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Moisture content
label | de797d5a-413b-43ee-9135-95b2d2dde371 |  | note | FREQUENCY: Once per sample obtained as per Item 6.1 of this document
label | daf69695-e65e-4ad1-88f1-b8f13b4ed514 |  | note | ACCEPTANCE CRITERIA: Moisture content of asphalt to be <0.5%.
label | b982d248-36e7-4763-b7d0-6bcdd3466a93 |  | note | REFERENCE DOCUMENTS: FH Internal
label | 708dcb48-c61c-4a99-ab45-08fdc7d70438 |  | note | INSPECTION/TEST METHOD: RC 211.011
label | f16ddf68-7dba-4f2d-8054-35acc0e6dc47 |  | note | TP
label | 41f66146-4365-4245-a13d-a7afbd653e53 |  | note | RESPONSIBILITY: Laboratory Technician
text | 1c83184c-0ca1-4d13-b3b0-e50afa605099 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Combined aggregate grading
label | 9d721737-2b28-43af-969d-45df236ea1b2 |  | note | FREQUENCY: Once per sample obtained as per Item 6.1 of this document
label | e851d27a-ef5c-4ff2-9e32-a1b483dc64d9 |  | note | ACCEPTANCE CRITERIA: Grading to be within the following tolerances of the “job mix” target grading:
label | ec74cbc1-5f02-44ab-bd90-7fecbbb0adf8 |  | note | FH NCR Procedure to be adopted when grading falls outside tolerances.
label | 2ebc642d-cebc-40e4-9225-b6e56d37dbeb |  | note | REFERENCE DOCUMENTS: 7.8.2 & Table 7-9
label | da8a5e17-6204-4cad-ad31-62ec4e04d767 |  | note | INSPECTION/TEST METHOD: AS 2891.3.3
label | 91e74adc-49c3-4bcb-9d0f-a762d435c836 |  | note | TP
label | 70a79bb3-0cdf-4fb4-842c-b4a4afdda821 |  | note | RESPONSIBILITY: Laboratory Technician
text | d3a7d462-554d-4abf-9865-952faaa267d4 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 Binder content
label | efb0806c-5408-4c60-949a-5cba0542f5ae |  | note | FREQUENCY: Once per sample obtained as per Item 6.1 of this document
label | ea88bb4b-43af-48e8-83c4-8c95cf829e58 |  | note | ACCEPTANCE CRITERIA: Bitumen content to be within -0.3% and +0.3% of the “job bitumencontent”target. FHNCRProceduretobeadopted when bitumen content falls outside tolerance.
label | 8f5e9ffe-fae1-41c8-b2d8-ed17b1078a7c |  | note | REFERENCE DOCUMENTS: 7.8.2 & Table 7-9
label | 0e961de3-0403-4988-9866-0d688c54bc65 |  | note | INSPECTION/TEST METHOD: AS 2891.3.3
label | 9133d57c-b524-4067-ac55-5c0e6bb628bd |  | note | TP
label | 098e3bb6-44d6-4e3d-a48c-62d6b50579de |  | note | RESPONSIBILITY: Laboratory Technician
text | bf508ced-cc2d-4bea-9500-f6cbf7839f38 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.5 Maximum density
label | f1bbbdda-707b-433e-aac0-791ac076b70a |  | note | FREQUENCY: Once per sample obtained as per Item 6.1 of this document
label | 7b7cd4fb-5325-4066-84e2-522435be0cbb |  | note | ACCEPTANCE CRITERIA: Average maximum density for each production shift to be reported.
label | 329125f3-4a43-4345-adf8-7af7cad807e2 |  | note | REFERENCE DOCUMENTS: 7.8.2 & Table 7-8
label | cf61805a-a3d7-4cac-8b4d-082e9e7d7f0c |  | note | INSPECTION/TEST METHOD: AS 2891.7.1
label | 927e6733-1d55-42d6-a5ac-c64df462b87a |  | note | TP
label | 4b487414-d6a3-4f1e-980f-378c6a7f5310 |  | note | RESPONSIBILITY: Laboratory Technician
text | d9010859-3aec-49d0-92c7-449111f73ff9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.6 Bulk density
label | 305076f3-ff01-409d-8c8b-48c7016dbcd9 |  | note | FREQUENCY: Once per sample obtained as per Item 6.1 of this document
label | 79a99d76-9049-4653-a036-a28cf0ea9cb7 |  | note | ACCEPTANCE CRITERIA: Two Marshall blocks to be produced using automatic hammers (75 blow compaction) and the results averaged. Compaction temperature is to be within the range of 165oC to 175oC. Result to be reported.
label | 32c92870-2fff-428a-8935-26a07dfcc212 |  | note | REFERENCE DOCUMENTS: 7.8.2 & Table 7-8
label | ec392b48-cfb3-4a44-ac3d-174e88a5e855 |  | note | INSPECTION/TEST METHOD: AAA MT 001-2007
label | 8e5fcebd-33a1-45f7-8033-5fb9decf191f |  | note | TP
label | f4dbe37b-12f9-4498-9534-c482650467a0 |  | note | RESPONSIBILITY: Laboratory Technician
text | 68c7e56b-319b-412b-b062-ed1b9a60c154 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.7 Voids in mineral filler (VMA)
label | 7f12afaa-cb10-4e45-8b04-576d33a855fc |  | note | FREQUENCY: Once per sample obtained as per Item 6.1 of this document
label | 9e46a407-0535-4701-b532-af6aa75e6fca |  | note | ACCEPTANCE CRITERIA: 15% minimum
label | c1033996-a20e-4702-aca1-8746184879c0 |  | note | REFERENCE DOCUMENTS: 7.8.2 & Table 7-8
label | e7952b63-aa99-4469-b89a-2bbb2a0c9253 |  | note | INSPECTION/TEST METHOD: AAA MT 001-2007
label | 90811934-deb0-44fc-b8ff-bb399223bb85 |  | note | TP
label | 79e6d75b-49c6-4223-bb65-46ead96a534f |  | note | RESPONSIBILITY: Laboratory Technician
text | 72bdb9b7-bd87-4698-a4c5-b323b20ba90b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.8 Voids filled with binder (VFB)
label | 8b87e6f6-09b6-483d-b664-1109d451d3ab |  | note | FREQUENCY: Once per sample obtained as per Item 6.1 of this document
label | 653307fc-c62b-4fe7-8521-85edbf02711f |  | note | ACCEPTANCE CRITERIA: 70% minimum to 80% maximum
label | 0fe5c6a2-0901-4b58-a3d5-09a75067d1fb |  | note | REFERENCE DOCUMENTS: 7.8.2 & Table 7-8
label | fe10d7bf-6641-4f93-a61b-484470f2b8f1 |  | note | INSPECTION/TEST METHOD: AAA MT 001-2007
label | 2f1f17f1-506f-46d7-a977-d446d7138e8a |  | note | TP
label | e2fb596a-8d3e-4ec7-8619-49a5572e8d9a |  | note | RESPONSIBILITY: Laboratory Technician
text | 1a0786e2-03d9-4edc-8b20-67e51c848e08 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.9 Air voids
label | bb490640-7a90-4cd3-b965-68caf4fea999 |  | note | FREQUENCY: Once per sample obtained as per Item 6.1 of this document
label | 2ceb862b-5db3-402b-88a7-b4838dc74a82 |  | note | ACCEPTANCE CRITERIA: Two Marshall blocks to be produced using automatic hammers (75 blow compaction) and the results averaged. Compaction temperature is to be within the range of 165oC to 175oC. Air voids to be within ±1.5 of design – approved by Jacobs
label | be0c8c14-7b74-4151-8cfe-b7c2857b090a |  | note | REFERENCE DOCUMENTS: 7.8.2 & Table 7-8
label | 2a0c88d3-def9-4a0d-882e-aa8072e78c37 |  | note | INSPECTION/TEST METHOD: AAA MT 001-2007
label | dae47fca-431a-4776-b7db-9714685e90fd |  | note | TP
label | 66a9882a-1aaa-4e52-8d51-7c273f07d232 |  | note | RESPONSIBILITY: Laboratory Technician
text | d6ef2cf5-c10c-4489-b4b3-f6d4f8e21dea |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.10 Marshall stability
label | bb50dec5-c19a-471d-94c5-eb9cb0f7d67c |  | note | FREQUENCY: Once per sample obtained as per Item 6.1 of this document
label | a8fdb642-feb1-4de6-923b-13317f450e6e |  | note | ACCEPTANCE CRITERIA: Two Marshall blocks to be produced using automatic hammers (75 blow compaction) and the results averaged. Compaction temperature is to be within the range of 165oC to 175oC. Minimum Marshall stability to be 12kN.
label | 1946a08c-1254-4a61-aafa-16708a4e1de8 |  | note | REFERENCE DOCUMENTS: 7.8.2 & Table 7-8
label | 642d4414-6b8d-4d3b-aef0-215d09ab9df9 |  | note | INSPECTION/TEST METHOD: AAA MT 001-2007
label | 451ab086-c42d-4ff2-a7b6-5d6cc84f48ca |  | note | TP
label | 13e5251e-86cd-4fb3-b308-65d8be2d20f6 |  | note | RESPONSIBILITY: Laboratory Technician
text | 0020273d-2d87-467f-952e-a91d0f88e80f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.11 Marshall flow
label | c535309b-75a3-4063-8de3-1b6b72da6066 |  | note | FREQUENCY: Once per sample obtained as per Item 6.1 of this document
label | 52bd86b6-12f7-4422-afec-87015d5faa63 |  | note | ACCEPTANCE CRITERIA: Two Marshall blocks to be produced using automatic hammers (75 blow compaction) and the results averaged. Compaction temperature is to be within the range of 165oC to 175oC. Report flow result. Report stability vs flow chart.
label | f7760694-b310-4e9e-99b1-b46bb8302ad0 |  | note | REFERENCE DOCUMENTS: 7.8.2 & Table 7-8
label | 2fe22a42-36a8-44dd-b7e0-9bf364846c89 |  | note | INSPECTION/TEST METHOD: AAA MT 001-2007
label | 4b69f8c5-42ac-4103-998e-262153e484e6 |  | note | TP
label | 0a097eae-a824-4aff-ad20-2566cc9835b5 |  | note | RESPONSIBILITY: Laboratory Technician
text | 8a592669-c083-4ea0-8f07-870f429892c1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | f1247002-2c28-4eff-ad67-20505306d5ab |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | b042f776-44e8-4a15-8b0a-79f8948f56df |  | textbox | Print Name:
text | 3a2e2fea-6278-4691-9eed-2ff096f42750 |  | textbox | Position:
text | 7b8a1d74-bf13-43c8-9647-495318ed01e1 |  | textbox | Date:
checklist-sectioned |  |  | checklist | ITP 016 - Linemarking | itp |  |  |  | Yes | ITP 016 - Linemarking | 13cbba8f-c148-49e5-940c-8f900f340e10
checkpoint-group |  |  | section | ITP 016 - Linemarking
checkpoint-status |  |  | checkpoint | 1.1 Check for correct documentation
label | 2c7e6b53-1268-42d8-b004-b1a22ca2a85e |  | note | FREQUENCY: Prior to commencing any activity
label | 7618fd9a-8c28-42e7-a70d-ed48b25763e8 |  | note | ACCEPTANCE CRITERIA: Current revision drawing is being used including the subcontractors copy. Current Revision to be obtained via Aconex.
label | f7ec96bc-4258-472c-9ddf-3b64d5af15cf |  | note | REFERENCE DOCUMENTS: Drawings and Aconex
label | d163afe2-1083-4eb5-9e61-56754339de33 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | c1ef5770-5355-4b7b-a048-8de674ee164f |  | note | RECORD OF CONFORMITY: This Signed ITP
label | 7a1ea477-d73f-4f4d-8b1e-2d1a0d623ad5 |  | note | HP*
label | 1448e844-faf8-4568-8512-0c664cb07db3 |  | note | RESPONSIBILITY: Project Engineer
text | 02a7af8e-7862-4f88-af04-b7975bcc2624 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 Material acceptance
label | 7e31646f-ae56-45ee-a842-68e437954177 |  | note | FREQUENCY: One month prior to commencing works
label | a029724b-dcb5-4afa-b066-e679d41faf47 |  | note | ACCEPTANCE CRITERIA: Submission of the proposed paint manufacturer details and material properties to be submitted to Superintendent via Aconex
label | 64bd07c8-c52f-4802-9514-c1966d05d33f |  | note | REFERENCE DOCUMENTS: Cl11.3.2, AS4049, MAS-CVL-003: Section 6
label | c795a0c1-696b-4e22-b944-acb5583a9a1a |  | note | INSPECTION/TEST METHOD: Verify
label | fab6a6f0-b5ee-4db3-9073-f7cd36bfa2ea |  | note | RECORD OF CONFORMITY: Aconex Notification
label | 5e06577d-45a6-4a3b-bfc4-31e400ddbaaa |  | note | HP
label | 82ce80f2-f6d4-46fc-8792-ea5479ecff6a |  | note | RESPONSIBILITY: Project Engineer, Principal’s Representative
text | 2099750c-3d8e-41b7-ae13-19f8c5a04af7 |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 1.3 Implementation of all measures and controls
label | 04f09f0d-02c9-41cb-8b40-204c566a737c |  | note | FREQUENCY: Prior to commencing any activity
label | eddf41ef-9000-458f-bdfb-07f27ea730a0 |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | c04bf428-c316-4d5f-9d8d-ef908c757bbc |  | note | REFERENCE DOCUMENTS: PSP,EMP, TMP, WP SWMS
label | 57da7af7-dc16-4408-b09e-58a95158c573 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | c63c5054-72b7-47bc-8220-6402d7633aed |  | note | RECORD OF CONFORMITY: Site and Office Inspection
label | ed904e6f-717b-4ade-88c8-4cfc643ec037 |  | note | HP*
label | cfd28729-21de-4019-b32a-fc139ae353ef |  | note | RESPONSIBILITY: Project Engineer Site Supervisor
text | e045c150-e944-46ba-a66e-20addfd303b9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.4 Plant and Equipment
label | 30ea32d9-2d54-4311-980d-9aef33fcf6d0 |  | note | FREQUENCY: Prior to placing works
label | 175ebcbc-048f-40c6-836b-1efca221e9b8 |  | note | ACCEPTANCE CRITERIA: Plant and equipment used in the Works are appropriate to achieve specification requirements
label | 638b8066-8041-48a2-b077-024324bf99a0 |  | note | REFERENCE DOCUMENTS: Cl11.5.2
label | 5f4f7924-f2e1-4851-b741-7949adcf4533 |  | note | INSPECTION/TEST METHOD: Verify
label | 6ac00776-1d33-4438-be00-4b18b96ea6c9 |  | note | RECORD OF CONFORMITY: This Signed ITP
label | f15ec562-bdd3-4d90-bd2d-9705c2400e4c |  | note | HP*
label | 5b5fe72d-b411-4752-b7cd-1a3635902883 |  | note | RESPONSIBILITY: Project Engineer
text | 043d2b8d-acac-4843-bcff-b63e2a72b002 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.5 Setting out
label | e4d1f82a-ed81-4661-8d8c-03b6e2c44a9b |  | note | FREQUENCY: Prior to commencing works
label | 1d349bc1-ad4b-4afa-a5eb-3b8404989f8c |  | note | ACCEPTANCE CRITERIA: The contractor shall carry out the setting out of the pavement Markings as shown on the drawings. Accuracy of survey setout to be confirmed to be within +/- 25mm.
label | 1549a2c6-fc7d-4061-a0d4-b24ffe93692f |  | note | REFERENCE DOCUMENTS: Cl11.4
label | ce9f974f-1874-4dbf-9668-63a350d5c0b4 |  | note | INSPECTION/TEST METHOD: Verify
label | 3aace9dd-b36a-4780-9e97-e6f18c49382a |  | note | RECORD OF CONFORMITY: This Signed ITP
label | 60223ec0-a426-4a8c-b333-ee204917a37c |  | note | HP
label | 3baef000-0cf4-48a6-8136-7560e0cc1ee1 |  | note | RESPONSIBILITY: Project Engineer, Principal’s Representative
text | 2365d9ac-94db-4d0b-92ff-6296f70eeaa8 |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 1.6 Test Strip
label | ae957dc4-8d10-42bb-b319-590d08515e3d |  | note | FREQUENCY: Prior to commencing works
label | c5097661-d5fa-4ed0-a233-7a5d4a3d70ba |  | note | ACCEPTANCE CRITERIA: Prior to the full application of airport markings, a test strip shall be produced in the presence of the Superintendent.
label | b98336d6-2b8d-46d7-9f19-254fe596d35d |  | note | REFERENCE DOCUMENTS: Cl11.5.7
label | 0950098f-f705-4637-bc4c-3dfa6499ce31 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | c4dfb77b-26b7-4ac4-975f-6689cf1371bc |  | note | RECORD OF CONFORMITY: This Signed ITP
label | d5b09f90-610c-46e0-a090-cac323128926 |  | note | WP
label | c5e3dd0f-e45f-4481-81fb-bd5af2a19562 |  | note | RESPONSIBILITY: Project Engineer, Principal’s Representative
text | 65b414e3-8723-4e97-8b9c-2b7391587e66 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 Removal of Existing Line Marking
label | 3d86e19b-9cc1-4bec-91cd-2926b3a20a69 |  | note | FREQUENCY: Each Lot
label | 4e63e64f-1aea-4cd0-a2a1-0f270c073583 |  | note | ACCEPTANCE CRITERIA: Existing and temporary paint markings shall be removed prior to application of permanent markings, where indicated on drawings or no longer needed, by the use of high-pressure water blasting.
label | e99ee8ce-f6e8-40e6-9f28-bfeb5a45f6c5 |  | note | REFERENCE DOCUMENTS: Cl11.6, MAS-CVL-003: Section 8
label | 1b9130b0-b77d-455f-8bf9-ac19170a5050 |  | note | INSPECTION/TEST METHOD: Verify
label | b2965db6-8d41-4de1-9217-a9f1477b6f40 |  | note | RECORD OF CONFORMITY: This Signed ITP
label | ada3d6d0-b45c-4851-b04c-d26f04ff4a26 |  | note | IP
label | c9dded4d-e73f-4256-923b-cb7faeb90b7c |  | note | RESPONSIBILITY: Project Engineer
text | 9d2b5e75-fdef-48e6-a017-610cd2b7d090 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Surface preparation
label | 8ef6f07e-ed65-4ca2-8672-cff2588fdf54 |  | note | FREQUENCY: Each Lot
label | f6ccdd5f-43f4-4e65-8f3f-97f3e025184a |  | note | ACCEPTANCE CRITERIA: Immediately before application of paint, surfaces are to be dry and free from curing compound, dirt, grease, oil, laitance, or other foreign material that would reduce the bond between the paint and the pavement. The contractor shall verify in writing that the surface has been prepared in accordance to the manufacturers requirements. This shall be approved by the Principal’s Representative.
label | 1cbfc9fc-2a79-49c5-b1fd-192ea0845057 |  | note | REFERENCE DOCUMENTS: Cl11.5.3, MAS-CVL-003: Section 11
label | ff2a2102-9263-4e8d-8113-766818eae71a |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 0c4ad279-fa4c-4d3d-ae74-d18bcbb75a57 |  | note | RECORD OF CONFORMITY: This Signed ITP
label | 331a925a-e2e2-49a8-a9c7-aae8878e066b |  | note | HP
label | 5ecb84f6-d16b-4860-9db0-22c38a2678dc |  | note | RESPONSIBILITY: Project Engineer, Principal’s Representative
text | 0a02ca23-d555-46dd-98e1-e20f2c589aca |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 2.3 Weather Conditions
label | a9632719-865f-4807-b009-553a8c5148cf |  | note | FREQUENCY: Each Lot
label | 07b89273-a0bf-4e35-820a-79fe5c803821 |  | note | ACCEPTANCE CRITERIA: Painting shall be performed only when the surface is dry, the surface temperature is at least 7C and rising or meets manufacturer’s recommendations. Markings shall not proceed if temperatures reach 55C or winds exceed 16kph, unless windscreens are put in place.
label | 0272c076-4de1-4c11-b112-790d3a0f52e8 |  | note | REFERENCE DOCUMENTS: Cl11.5.1
label | a99eec53-a69a-4aa0-a369-bd1635f1dca7 |  | note | INSPECTION/TEST METHOD: Verify & Visual Inspection
label | 092a9a21-b044-401e-a13e-4d948297af98 |  | note | RECORD OF CONFORMITY: This Signed ITP
label | 8b18d08c-cb19-4718-8969-e75e4187c306 |  | note | IP
label | bb02d38e-72e9-4d26-8b39-b43dea3b690e |  | note | RESPONSIBILITY: Project Engineer
text | d0770095-d9f6-465e-b6c3-dfca731b91e2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Application
label | 7e523363-dfdb-46f6-9a33-da24838db725 |  | note | FREQUENCY: Each Lot
label | dd886b88-9c72-4d67-a958-90ab74522c5c |  | note | ACCEPTANCE CRITERIA: Paint shall not be applied until layout and condition of the surface has been approved by the Principal’s Representative. The paint shall be applied in two even coats to give a minimum total dry film thickness of 120 microns. The paint shall be applied to produce a crisp even line without side splatter.
label | 70530a4b-9eda-4021-b552-25477181c354 |  | note | REFERENCE DOCUMENTS: Cl11.5.4
label | 6411fe8c-3b03-4b18-b6fd-b9eda318664e |  | note | INSPECTION/TEST METHOD: Approval and Visual Inspection
label | c349bd5a-e537-45d6-b423-7ef7d9bf08e5 |  | note | RECORD OF CONFORMITY: This Signed ITP
label | 2ff3e3df-8d32-4e1a-8c1b-6153e5a91ed5 |  | note | AP
label | 461daeb8-cc7c-4d6c-b5bc-cb0f15cd234b |  | note | RESPONSIBILITY: Project Engineer, Principal’s Representative
text | 459bc721-bc55-47ab-a424-f76310a41fcc |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 Application Rate and Conformity of Application
label | d6b06be3-c6ef-4604-877b-e540e3bf684f |  | note | FREQUENCY: Each Lot
label | 08690404-78ca-4a1e-8152-28d410eb883c |  | note | ACCEPTANCE CRITERIA: Daily records of paint usage and area covered shall be maintained to ensure that the specified coverage is being obtained consistently. Contractor to retain all empty paint containers for inspection by the Principal’s Representative
label | cc81b03b-4ac1-4d96-9035-44b58fe3ef27 |  | note | REFERENCE DOCUMENTS: Cl11.5.9
label | f0f8ea04-7197-475c-bc0d-5eaea1fd555b |  | note | INSPECTION/TEST METHOD: Daily Records
label | 592972e9-cf5d-4495-bfa8-3a37600f1fa5 |  | note | RECORD OF CONFORMITY: This Signed ITP
label | de1f7197-2ca1-4a5f-aa20-56c16e752574 |  | note | IP
label | fd8f4cca-0ee6-45ac-babe-8a688fe9cf99 |  | note | RESPONSIBILITY: Project Engineer
text | d1e026f2-8194-4d4f-85cb-6d8fddcea788 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | e49c8be3-1332-4c37-9760-5d29d584521d |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 905a91c0-a24e-4e3a-be6c-0febb76484e0 |  | textbox | Print Name:
text | 09b98cea-b2b5-4f40-8af0-ce851a98fbc6 |  | textbox | Position:
text | 1fc465d4-e6b2-4d85-85da-ef9c808746af |  | textbox | Date:
checklist-sectioned |  |  | checklist | CL009A Pre Pour - | itp |  |  |  | Yes | CL009A Pre Pour Checklist | 18e5799b-b03b-497e-a10b-7751ce213fea
checkpoint-group |  |  | section | CL009A Pre Pour
checkpoint-status |  |  | checkpoint | Confirm current drawings being used
checkpoint-status |  |  | checkpoint | Surveyor set out slab area and locations of cast in items surveyed etc. Pre-pour survey conformance completed and provided to Fulton Hogan.
checkpoint-status |  |  | checkpoint | Existing slab faces checked
label | f57d8399-a020-48fc-9992-fba7c923f303 |  | note | Must be cleaned of any lose material
label | 30a285b2-49cc-436a-ae6a-6f2c6c873a38 |  | note | If required, patched & smooth
checkpoint-status |  |  | checkpoint | Check formwork secured & constructed correctly
checkpoint-status |  |  | checkpoint | Check no debris/rubbish in shutters. All cleaned.
checkpoint-status |  |  | checkpoint | No movement in forms. Top end of form does not vary 3mm in 3m.
checkpoint-status |  |  | checkpoint | Check reinforcement placed as shown on the drawings
checkpoint-status |  |  | checkpoint | Check bar spacing
checkpoint-status |  |  | checkpoint | Check cover Top & Sides (125mm +/-10mm)
checkpoint-status |  |  | checkpoint | Check no debris/dirt on reinforcement or in pour area. All cleaned.
checkpoint-status |  |  | checkpoint | Lap lengths as per specifications.
checkpoint-status |  |  | checkpoint | Check Block Outs are installed (if required)
checkpoint-status |  |  | checkpoint | Cast in items
checkpoint-status |  |  | checkpoint | Dowels installed as per drawings. Dowels epoxied into existing slabs and coated with bituminous emulsion.
checkpoint-status |  |  | checkpoint | Conduits and other cast in items such as electrical cans in place.
checkpoint-status |  |  | checkpoint | Joints (if applicable)
checkpoint-status |  |  | checkpoint | Expansion joints in correct position, 15mm compressible material in place.
checkpoint-status |  |  | checkpoint | Dowel Cradles set out and secured.
checkpoint-status |  |  | checkpoint | Check Pour Area
checkpoint-status |  |  | checkpoint | Scratch template test undertaken and areas have been rectified.
checkpoint-status |  |  | checkpoint | Check base of bond breaking layer is not damaged, any areas missing to be. Check area is clean from debris.
checkpoint-status |  |  | checkpoint | Checklist completed (Fulton Hogan)
text | 9e829a54-c5f5-4ad7-b8e1-12508c70dd25 |  | textbox | Checked By:
text | 4c8d3de6-c139-4326-b882-b6544934fcfb |  | textbox | Sign off Date
checklist-sectioned |  |  | checklist | ITP 009 - Portland Cement Concrete (PCC) Pavements | itp |  |  |  | Yes | ITP 009 - Portland Cement Concrete (PCC) Pavements | 1ad674a9-34e3-49d2-94d2-c5f143920b93
checkpoint-group |  |  | section | ITP 009 - Portland Cement Concrete (PCC) Pavements
checkpoint-status |  |  | checkpoint | 1.1 Approval of Mix Design & Submission
label | cfa1ddf7-a53b-56c7-a7a6-83d24f74c09f |  | note | FREQUENCY: At least 28 days prior to trials
label | c7c06acd-3f8b-5a43-bcc7-449b1a00f6f6 |  | note | ACCEPTANCE CRITERIA: All submission through Aconex and approved by Principles Representative
label | 751c5edf-611a-54fe-8e57-7f2eef4ffc91 |  | note | Mix formulas submitted and approved
label | 89d3ec41-5b2e-5c9a-9db5-4c1c86754b07 |  | note | Reference samples provided to Principal's Representative
label | 8032d3f5-e277-56e8-a2c9-5a3a6b751e2f |  | note | Material certificates provided
label | c67d1d79-239c-54a4-a239-a48e1b9c5137 |  | note | Batch plant inspection
label | 4f95a502-b243-5fe8-aed1-87200fae89a0 |  | note | Mixer uniformity tests and submissions
label | b8aad4b8-2d21-5d49-8631-ca8cfdefeb28 |  | note | All WP and ITPs submitted and approved
label | b2b198f6-b409-57e6-bf4f-5a854bd24982 |  | note | REFERENCE DOCUMENTS: Clause 6.3.2/6.5.2/6.5.4
label | d6ec7af4-91fd-5f96-b386-54f7f2041a9a |  | note | INSPECTION/TEST METHOD: Verify
label | 485ff0ab-3a27-50ce-bc7d-c0d2a58bfc31 |  | note | RECORD OF CONFORMITY: Aconex
label | 5ba012dd-d05a-5b21-b66c-59c4915035c0 |  | note | WP/HP
label | 68f4ec65-8acd-5a6d-9be2-5fee22a007d0 |  | note | RESPONSIBILITY: Engineer/Principal's Representative
text | f3fae19c-f349-5639-9f56-fa11f5fc606a |  | textbox | Date Completed:
label | 58eadc88-790d-5fe6-bf70-4df7e4835e74 |  | note | Please refer to Aconex for hold point sign off
label | 77931f93-42b5-582b-b832-6158d4712328 |  | note | Aconex Ref: FHPL-TRANSMIT-000045, FHPL-TRANSMIT000057, DCWC MgtPMA-000339, DCWC Mgt-PMA-000435, FHPL-GCOR-000489
checkpoint-status |  |  | checkpoint | 1.2 Joint Sampling
label | 30800367-d16d-55da-b9b0-cf2e524fa5c1 |  | note | FREQUENCY: 7 Days from acceptance of Job Mix Formula
label | 9b6c50a0-0498-50f7-adfb-c1367871f80f |  | note | ACCEPTANCE CRITERIA: Witness Point
label | f443a87a-19b7-50e8-92b5-8d3b1f7d01ba |  | note | Within 7 days of acceptance of the Job Mix Formula a 80kg sample of aggregate and 10kg sample of cement will be taken. Half will be kept by the contractor and half by the Principles Representative.
label | 897b0661-b802-5ff3-ad81-2be3c4ae3688 |  | note | REFERENCE DOCUMENTS: Clause 6.6.5
label | 447b8130-827d-59f2-94af-a93479040063 |  | note | INSPECTION/TEST METHOD: Verify
label | dde8d115-1df5-5ebf-8b24-adaf0e0f7406 |  | note | RECORD OF CONFORMITY: Aconex
label | fbb55072-167d-5474-96e8-5f6253eae319 |  | note | WP
label | 2faf4230-5b5c-564b-8c7d-e3cbec6f81fc |  | note | RESPONSIBILITY: Engineer/Principal's Representative
text | 354bed41-c003-546e-be33-f0dd33d8b165 |  | textbox | Date Completed:
label | 10388cae-4101-5c17-a9fa-559de57cdb79 |  | note | Please refer to Aconex for hold point sign off
label | a783f4b0-96bb-50e4-b080-7a132851b175 |  | note | Aconex Ref: DCWC Mgt-PMA-000534
checkpoint-status |  |  | checkpoint | 1.3. Airfield Construction Procedure
label | c265f561-d533-5176-9502-b325bc3f808a |  | note | FREQUENCY: At least 28 days prior to trials
label | beb9683d-c8e1-51be-ab8a-45aaeabcae90 |  | note | ACCEPTANCE CRITERIA: Holdpoint
label | c919433a-5d0e-5d3a-b9eb-254c3209d405 |  | note | Airfield Construction Procedure sent through Aconex and approved by the Principal's Representative
label | aea72f94-8c0a-5fd5-b745-85140c294211 |  | note | REFERENCE DOCUMENTS: Clause 6.4
label | 9cbccf7a-e5d5-5b33-a681-10259bb244e0 |  | note | INSPECTION/TEST METHOD: Verify
label | d655a920-a6dd-5dbb-b4f2-470c90aeed5d |  | note | RECORD OF CONFORMITY: Aconex
label | 3310dc0b-28b2-53e0-883e-7d28130c8593 |  | note | HP
label | e338c6c9-995a-5199-90eb-2150a66f9ae4 |  | note | RESPONSIBILITY: Engineer/Principal's Representative
text | 38aea62a-06a3-5e9f-ba6e-c8deabd729ab |  | textbox | Date Completed:
label | 76c6b70e-b1bc-5a0c-a419-e92ca4dcfa18 |  | note | Please refer to Aconex for hold point sign off
label | 689d3ddd-977a-5b10-8227-6fa30d9dba14 |  | note | Aconex Ref: DCWC Mgt-PMA-000435
checkpoint-status |  |  | checkpoint | 1.4 Production Trial
label | c6dc23f6-6e13-51c1-89fe-d56ce76660a9 |  | note | FREQUENCY: At least 48 days prior to Concrete pour
label | 1c5c660a-acd7-5b9b-86bb-7e8d488aeafa |  | note | ACCEPTANCE CRITERIA: Witness Point
label | 52367b0b-22b7-543b-bfd4-3c9d104ae3c5 |  | note | Attendance at Production Trial given at least 14 days calender notice to Principles Representative
label | ac420753-7de0-5f00-b1e9-65ed4997de75 |  | note | REFERENCE DOCUMENTS: Clause 6.6.1
label | 59c1729d-9af1-5005-b82e-337199518990 |  | note | INSPECTION/TEST METHOD: Verify
label | b7f17bfe-83f7-5620-a094-ce25b3d967fb |  | note | RECORD OF CONFORMITY: Aconex
label | d48ba402-fc38-5117-9146-cbd3d3b44d2e |  | note | WP
label | 3b2a1c7f-bd1e-55f5-a622-24e1a63a1d71 |  | note | RESPONSIBILITY: Engineer/Principal's Representative
label | 7a3d35a1-b940-5f30-85c1-fdd094f447eb |  | note | Aconex Ref: FHPL-GCOR-001118
label | 339e05fa-45cf-531a-8e73-d7323d97e893 |  | note | 0/10/2019
checkpoint-status |  |  | checkpoint | 1.5 Construction Trial
label | e01cf969-dade-584a-931a-061f0266a692 |  | note | FREQUENCY: Prior to Concrete Pour
label | c6382cf5-65ff-5c0e-99cd-55bd7ea32c67 |  | note | ACCEPTANCE CRITERIA: Witness Point
label | c9f411d8-a9fe-5c08-bdd2-1ae55b24214b |  | note | Attendance at Construction Trial given at least 14 days calender notice to Principles Representative
label | e0195c7e-51ec-5368-ab28-182f21f06edf |  | note | REFERENCE DOCUMENTS: Clause 6.6.1
label | 6df05d75-d039-5358-b4e6-e7286e40fc7a |  | note | INSPECTION/TEST METHOD: Verify
label | 8baa637c-ea31-5c45-8300-33d926658953 |  | note | RECORD OF CONFORMITY: Aconex
label | f7992a1f-2f1b-562d-83f0-65db82f3f38d |  | note | WP
label | 2bf53e57-ad25-5bbb-927b-f072cdba08e3 |  | note | RESPONSIBILITY: Engineer/Principal's Representative
label | 7ba148fb-8517-5251-8de2-82c0d7c22414 |  | note | Aconex Ref: FHPL-GCOR-001118
label | ec113651-b248-55a2-853f-2cc0ae6b15e5 |  | note | 10/10/2019
checkpoint-status |  |  | checkpoint | 1.6 Test Panel Inspection
label | ae70a0d2-a62f-50bd-8936-b18c4c89377f |  | note | FREQUENCY: Prior to Concrete Pour
label | 75f6c125-b090-54db-a5d3-fd4b85f0e3ea |  | note | ACCEPTANCE CRITERIA: Witness Point
label | 55872251-a077-53c6-b923-4662bc75e395 |  | note | 5 no. of 1x1m Test Panels are to be broomed to different depths and the depths to be used confirmed by the Principal's Representative on Aconex
label | aeba64b5-4b97-55a4-981a-99f64af6276f |  | note | REFERENCE DOCUMENTS: Clause 6.6.2
label | 7f368e89-964a-5ac2-8b33-01fce380aba2 |  | note | INSPECTION/TEST METHOD: Verify
label | 6823bf20-7379-52c1-b803-fa048e1162d8 |  | note | RECORD OF CONFORMITY: Aconex
label | 3720fb1d-d497-5e89-88bf-c33fc1d0135a |  | note | WP
label | afa945a2-237e-57ca-b834-7988765964bc |  | note | RESPONSIBILITY: Engineer/Principal's Representative
text | 50cc2031-a44d-5983-8185-52c15246dc94 |  | textbox | Date Completed:
label | 68b190ca-7b11-5963-85a3-3a52d7711339 |  | note | Please refer to Aconex for hold point sign off
label | a3243f59-59c7-5877-bf51-78a9f0d0ef6d |  | note | Aconex Ref: DCWC Mgt-PMA-000873
checkpoint-status |  |  | checkpoint | 1.7 Production Trial Report
label | b372f6ba-230b-54ec-968a-bebe87b4bdf5 |  | note | FREQUENCY: Prior to Concrete Pour
label | baa3bec4-2b7a-5e90-8ee5-b389a2990228 |  | note | ACCEPTANCE CRITERIA: Production Trail undertaken at concrete plant and tests as per specification undertaken
label | 10ac8919-a9a6-5cd4-9727-7a2b6929eeb0 |  | note | REFERENCE DOCUMENTS: Clause 6.6.4/6.6.3.3
label | 79e9b0dd-7051-5af8-9938-d53b68442e64 |  | note | INSPECTION/TEST METHOD: Principal's Representative Approval via Aconex
label | e2131c1d-f398-51d8-8b61-a0d159ca059f |  | note | RECORD OF CONFORMITY: Aconex
label | 3d6b8c11-3b20-5317-8870-cbc83dae389b |  | note | HP
label | 33f25d61-9a4c-5f0c-bf30-834f3c23f0ed |  | note | RESPONSIBILITY: Engineer/Principal's Representative
label | a53260b2-d505-5bab-9459-38efb9140dd0 |  | note | Aconex Ref: DCWC Mgt-PMA-001717
label | 70853f02-c4df-5e2f-a731-232c28e109b0 |  | note | 4/02/2020
checkpoint-status |  |  | checkpoint | 1.8 Construction Trial Report
label | dfea00d8-a64f-58d4-a112-ea7a3effd819 |  | note | FREQUENCY: Prior to concrete Pour
label | 2a6de53a-73f9-567e-86f3-8939f1fb5987 |  | note | ACCEPTANCE CRITERIA: Hold Point
label | 505a577b-454d-5db8-86db-72248c72e63c |  | note | Construction Trial undertaken and results provided to Principal's Representative
label | 1e95f720-3256-55b3-b09d-209554255bca |  | note | REFERENCE DOCUMENTS: Clause 6.6.4/6.6.3.3
label | 7447e332-8a09-5c01-9d11-b9494a921f22 |  | note | INSPECTION/TEST METHOD: Principal's Representative Approval via Aconex
label | c1959b7c-9b6d-5300-bafd-1d406b8c05f9 |  | note | RECORD OF CONFORMITY: Aconex
label | fcb43b51-cf27-5db7-a5cd-68ebcbb0e241 |  | note | HP
label | e6ab8fae-10bc-5671-8ebe-e6bcbd7629e3 |  | note | RESPONSIBILITY: Engineer/Principal's Representative
label | 9db30c62-a3b3-5a93-a309-3dc5638d07c6 |  | note | Aconex Ref: DCWC Mgt-PMA-001717
label | 4a93644e-3c9d-575e-8bfe-9e2479fa858c |  | note | 4/02/2020
checkpoint-status |  |  | checkpoint | 2.1 Project Documentation/Drawings
label | 94de8789-57c4-592a-ba89-00e65b31f4bd |  | note | FREQUENCY: Prior to concrete pour
label | 8c5baf73-6379-55e0-85d6-fc89dd59ce8e |  | note | ACCEPTANCE CRITERIA: The latest revision of the project documentation/drawings sent to the subcontractors and reo supplier.
label | d4d6e7a0-acf5-5ed0-8e45-313aaf1be406 |  | note | The latest revision of the project documentation/drawings is being used on site (check the drawings register)
label | a94d7129-700a-5ff1-a173-57fae70864d7 |  | note | TMP and EMP in place for pour
label | f35dd14d-09a1-5fc7-80ec-d4c75db23e35 |  | note | REFERENCE DOCUMENTS: Drawing and drawing registers
label | 010cd77f-06a8-5e82-a85c-29b2804f8055 |  | note | INSPECTION/TEST METHOD: Verify
label | c6cca89b-bb52-5abd-bb77-227af571e78d |  | note | RECORD OF CONFORMITY: Up to date drawing sets and this ITP signed
label | e6b7dd6d-f293-5749-b989-2386e21f030e |  | note | HP*
label | 744274a2-505d-5e5f-b07f-eb1b42e263d0 |  | note | RESPONSIBILITY: Engineer
text | 9c5ba26c-fab4-57f6-8b7d-afaad10b1553 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Implementation of all measures and controls
label | c9a5374d-4827-58f5-acdb-074b0f93b7ed |  | note | FREQUENCY: Prior to concrete pour
label | 1cfe9447-3765-5b92-ab8d-e843145427ca |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP , EMP , TMP , JSEA , SWMS & WP
label | 87ecc0c0-4b4f-5d04-bb49-ddef37a67a71 |  | note | REFERENCE DOCUMENTS: PSP/EMP/TMP/JSEA/SWMS/ WP
label | f264ac75-035b-5db5-a6b2-53777bb597f2 |  | note | INSPECTION/TEST METHOD: Verify
label | 7c40df40-3f7b-5053-8b25-6931035ff5e9 |  | note | RECORD OF CONFORMITY: Site and Office Inspection
label | 5d5974a0-aa87-58bb-867e-143b0ccd88ef |  | note | HP*
label | d1f8b476-a719-57f3-8470-b1d38fd5f429 |  | note | RESPONSIBILITY: Engineer/Site Supervisor
text | f7450ab0-485d-5200-91b7-80d68e44c0d3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Definition of the work area (survey)
label | ac37b00b-28e1-5a9b-beb2-6cda996a04ae |  | note | FREQUENCY: Prior to concrete pour
label | db03b01f-e2cb-5054-869a-5ce15cea2fd8 |  | note | ACCEPTANCE CRITERIA: Work area has been cleared and surveyed (marked on site)
label | 11c5486e-85ea-52d0-94e8-b464779a6bd2 |  | note | REFERENCE DOCUMENTS: Drawings
label | 12807a72-630d-5a9e-99e8-1bb480d4bc83 |  | note | INSPECTION/TEST METHOD: Verify
label | 3b1d7ac4-c408-5d0a-8d2a-0de802817fee |  | note | RECORD OF CONFORMITY: Site Inspection
label | 866ed0ab-34dd-537c-ada0-623b0f920d83 |  | note | HP*
label | 884fab1b-0c38-59b3-8b3c-46e732886020 |  | note | RESPONSIBILITY: Site Supervisor/Surveyor
text | 70cc75cb-8d85-5ac6-8d09-a42a4ea7f333 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Placement Plan
label | 2cec2cae-03d3-519e-ac51-47a677e58b73 |  | note | FREQUENCY: 7 Days prior to Concrete pour
label | 2f80cef4-1730-598a-992b-04f20f4212b2 |  | note | ACCEPTANCE CRITERIA: Hold Point
label | 0e5f2757-f111-5a58-bc56-c40783019df7 |  | note | 7 Days prior to concrete pour a plan with the proposed pour lanes is to be submitted
label | f49b10bc-09b0-573e-b071-5b41f9ef80c7 |  | note | REFERENCE DOCUMENTS: Clause 6.7.2.8.
label | e473e2c2-69da-57d4-a26e-4c9b70db1ef9 |  | note | INSPECTION/TEST METHOD: Verify
label | fc97f51f-e989-5338-a7b2-f370720badd2 |  | note | RECORD OF CONFORMITY: Aconex
label | 3b68a616-9c43-5d90-b323-614810d194e3 |  | note | HP
label | 2bf04e3b-8783-51aa-ac40-0dc04289b80e |  | note | RESPONSIBILITY: Engineer/Principal's Representative
text | 1525b4c2-ddc4-53af-b49d-9835c0b58d5b |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 2.5 Placement of concrete against existing concrete slabs
label | e413c6e9-bd2d-497c-80eb-e36fee30de9d |  | note | FREQUENCY: Prior to coring/drilling existing concrete slab
label | af977270-e54b-4d70-9b3f-854d1fef098a |  | note | ACCEPTANCE CRITERIA: The Principal’s Representative shall be notified of the Contractors intention to core or drill dowels into existing concrete face
label | b4f5e162-61ee-428d-8986-e6158cf191af |  | note | REFERENCE DOCUMENTS: Clause 6.7.2.1
label | 047fab8b-8920-4816-afa6-6330541f6ac1 |  | note | INSPECTION/TEST METHOD: Inspect
label | a36c6059-0392-4b5c-bfac-0a3223b8beae |  | note | RECORD OF CONFORMITY: Site Inspection
label | 58e5dab6-ce9b-453c-8204-1dc96d786e5a |  | note | WP
label | 8cae2957-6835-4f5f-9e89-543eddff8cc6 |  | note | RESPONSIBILITY: Engineer / Principal’s Representative
text | ea582674-ce78-47ab-a477-cbcba761faef |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 3.1 CMCR Inspection
label | 81815374-ed44-5611-b333-c9cfa4d49dd6 |  | note | FREQUENCY: 1 day prior to pour
label | 1ea6c542-ddf6-530c-9241-e1bddae14183 |  | note | ACCEPTANCE CRITERIA: Ensure that the finished surface if the CMCR has been surveyed and is to level. ITP008 has been completed.
label | 62cb6012-b536-5a21-a986-228285d1426e |  | note | REFERENCE DOCUMENTS: Clause 6.7.2.2.
label | 19d64ebe-584d-5eaa-b6f0-8dedd9dc4b67 |  | note | INSPECTION/TEST METHOD: Verify
label | 86730d31-5503-5a00-abcf-e60f0eab70c8 |  | note | RECORD OF CONFORMITY: Site Inspection/ITP008
label | b32226ef-384f-5e3d-9a99-ab38698d2768 |  | note | IP
label | 8fcddcc0-593a-52d7-9eef-c25f592668e7 |  | note | RESPONSIBILITY: Engineer
text | b7ef974b-6ea5-58a5-abf7-9cbe4f8ff84a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Formwork Installation
label | d1010e1e-e483-5b3a-a3b9-f042c52a3adb |  | note | FREQUENCY: 4 hours prior to pour
label | cf143046-3a81-5ed5-9b6f-a0b33827b458 |  | note | ACCEPTANCE CRITERIA: Rigid, watertight , braced and tied together as to maintain shape during all construction activities
label | 14ba19ab-8804-5671-b0e4-b0c2fcdc720e |  | note | Forms must be free from warps, bends and kinks and the top edge of the form not vary from a straight edge by more than +/- 3mm in 3m
label | 99c77d81-f2c1-589a-aab2-db45357952bd |  | note | Formwork has been surveyed and is to the required level
label | 152b306b-fc13-539b-95e4-9ec79b8ac61b |  | note | REFERENCE DOCUMENTS: Clause 6.7.2.9 / 6.7.5.1
label | eb45995b-b61f-5569-97d9-05666177e594 |  | note | INSPECTION/TEST METHOD: Inspect
label | 60526c6d-2543-5cbb-a43c-8f696df81442 |  | note | RECORD OF CONFORMITY: Site Inspection
label | 998b3124-939b-5cd7-a1e3-a82efe6fb531 |  | note | HP
label | ef5e0ea9-ae89-5175-b1b8-89345d01be03 |  | note | RESPONSIBILITY: Engineer/Principal's Representative
text | e49bc4ef-f634-5fab-9762-917112d42b3a |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 3.3 Pre- Pour survey
label | ef5edc96-db14-5411-8aa8-4b7340aa9625 |  | note | FREQUENCY: Prior to concrete Pour
label | 9833cd7d-4243-531d-b434-b166de0a8d18 |  | note | ACCEPTANCE CRITERIA: A pre-pour survey of the formwork carried out by a surveyor. Surveyor set out and checked forms. Alignment and grade elevation shall be checked
label | 4abeedae-1ffe-57e2-85e0-4fd9843be31c |  | note | Erected formwork within the tolerance
label | 19835b57-12e2-51f4-9eab-4087e7188fa5 |  | note | REFERENCE DOCUMENTS: WP 009
label | 3d8317a1-f3d0-536a-a358-03c7bc0d9358 |  | note | INSPECTION/TEST METHOD: Inspect
label | 3ea9f804-dd03-5e11-8ca4-61c85da8c785 |  | note | RECORD OF CONFORMITY: Site Inspection & Survey Reports
label | 711a7140-8ade-53ad-9b00-ee56ebd8840c |  | note | SCP
label | 3834fbf4-17fb-5601-a719-f7f6bf4078d3 |  | note | RESPONSIBILITY: Surveyor
text | 2cb7ae53-6283-5f58-8400-3ba771969718 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.1 Reinforcement Inspection
label | ebb1a5bf-0824-5c6f-bf30-be0a4d576a2d |  | note | FREQUENCY: Prior to concrete pour
label | 0077fc2a-5e77-5358-97e6-63f52f96bb98 |  | note | ACCEPTANCE CRITERIA: Pre-pour Checklist Completed
label | 29fe99a0-b897-543a-8d79-b3e868c08588 |  | note | Position and spacing check and recorded
label | ba936b9f-9aa5-58b1-83f6-60153ca32d9e |  | note | Cover checked and recorded (60mm +/- 10mm)
label | 83cd5ecd-9be0-5510-b637-4e2ca11a793d |  | note | Reinforcing supports checked and recorded (TOP 125mm +/- 10mm, edge 75mm +/- 10mm)
label | d1a1fbb6-36e9-547c-ba95-f448725601df |  | note | Reinforcement overlapping by 300mm or securely fastened to prevent separation
label | 5a763792-424b-502c-be34-5151d60e5071 |  | note | Reinforcement shall be free from mud, oil and other organic matters
label | 86bd77a7-201e-552e-b4d5-4a206380ad7d |  | note | REFERENCE DOCUMENTS: Drawings
label | 934f6404-90f4-55c9-ad39-c325aa75c92e |  | note | REFERENCE DOCUMENTS: Clause 6.7.2.10
label | f9d2956e-56b9-5f88-9810-ce12ef0d15fb |  | note | INSPECTION/TEST METHOD: Inspect
label | 64c61fb2-e246-5c00-a908-9061acf509e8 |  | note | RECORD OF CONFORMITY: Site Inspection & CL009A
label | 5367ec74-5838-5ba8-9ff0-f342e57a0111 |  | note | HP*
label | f2274f34-84b7-5e3d-a03d-5c0455986a20 |  | note | RESPONSIBILITY: Engineer
text | fa78df69-2e6b-5699-a2d4-020e626a80e7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Scratch Template
label | db1f9d20-a525-5b5d-bc40-d756f2d724fe |  | note | FREQUENCY: Prior to concrete pour
label | 70e1be50-fdac-567e-bddb-9a9ec5d20a96 |  | note | ACCEPTANCE CRITERIA: Hold Point
label | 812eab0c-abe4-56ba-a8f8-7390ce331915 |  | note | The base of the pour shall be tested with approved template to investigate correct depths & shall be corrected as necessary
label | a269afb8-b132-586f-9c90-e90b3ded5911 |  | note | REFERENCE DOCUMENTS: Clause 6.7.2.1
label | d010a5f3-2b87-5b32-ac69-b38b235ad1ab |  | note | INSPECTION/TEST METHOD: Verify
label | 5de3ed46-c0ce-5f71-bc16-ad86b1552279 |  | note | RECORD OF CONFORMITY: Site inspection and this ITP Signed
label | bbcfb686-41a7-57cc-b5c3-c0476175009c |  | note | HP
label | cff612a8-b136-5950-a954-8a30d5d92554 |  | note | RESPONSIBILITY: Engineer/Principal's Representative
text | 789de314-77d2-5aba-a30b-a8fc0111afc7 |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 4.3 Pre-pour inspection
label | a5320e98-848b-58f9-ba29-26a0a49a65d3 |  | note | FREQUENCY: Prior to concrete pour
label | a93c1393-ed49-5e11-bbd0-b73d74a2f052 |  | note | ACCEPTANCE CRITERIA: The Principal's Representative shall be notified of the Contractors intention to place concrete within a lot
label | e6070d32-3473-5c14-ac40-51e150288f7b |  | note | REFERENCE DOCUMENTS: Clause 6.7.2.1
label | f771f850-9f68-5dcf-b8b1-359577d85f6a |  | note | INSPECTION/TEST METHOD: Inspect
label | a1b54f35-59d4-5389-b522-ce93d3dca5f9 |  | note | RECORD OF CONFORMITY: Notification and this ITP Signed
label | 68dbc7db-60e1-59f7-88e1-a98b36a41d5d |  | note | WP
label | 653b5fe7-1f8b-5fd9-9d02-e0e4b67e17d7 |  | note | RESPONSIBILITY: Engineer/Principal's Representative
text | f0e41b67-01c7-5a58-80a0-e7c09e18f565 |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 4.4 Check the weather forecast
label | 62857b01-01a3-5007-84e9-f8855a756f82 |  | note | FREQUENCY: Prior to pour
label | 9ed98c85-fefe-5944-b57e-cfda8f322c98 |  | note | ACCEPTANCE CRITERIA: Check weather forecast for unfavourable conditions- rain, cold or hot weather. To be checked the day before and immediately prior to confirmation of batching concrete
label | 5a9b7254-57c9-54c0-a7d2-c88fb8d0605c |  | note | REFERENCE DOCUMENTS: Clause 6.7.2.4
label | 23a9ecb9-fada-5726-8daf-d3a840f2791c |  | note | INSPECTION/TEST METHOD: Inspect
label | b06edb81-3a0a-51ff-8e8e-e85c95002613 |  | note | RECORD OF CONFORMITY: This ITP Signed
label | 4a138ea7-d499-55cf-8428-1d9d45048242 |  | note | IP
label | 4f9c4b64-237b-572f-b821-98416426a79e |  | note | RESPONSIBILITY: Engineer
text | 05626646-62fc-5bd6-a50e-4c0a6c082fb5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.1 Sampling concrete
label | 31c9a994-8831-58c8-8ddb-9b578c366138 |  | note | FREQUENCY: Each concrete pour
label | 0a640894-5507-5b24-9771-3fad3f74e8b7 |  | note | ACCEPTANCE CRITERIA: Sampling in accordance with Zulu Specification
label | 621e3003-0542-5c6d-8853-aaf6511965ef |  | note | BEAMS – First 5 Lots
label | 5d1ebff1-1123-5ee4-bc65-b3d19f9dac23 |  | note | 7 Days – 2 beams per 75m3 or part thereof
label | 301ce06c-0b8d-55e2-bc07-2bae41866e65 |  | note | 28 Days – 2 beams per 75m3 or part thereof
label | ef8c089a-67a3-5eaf-9675-d186014b6153 |  | note | BEAMS – After 5 Lots
label | 6f239215-55f1-56a5-95ca-c3ebad27c481 |  | note | 7 Days – 2 beams every second 75m3 or part thereof
label | 53c59603-867a-5861-af51-85fa52b1eae4 |  | note | 28 Days – 2 beams per 75m3 or part thereof
label | 0a8ebb87-2fba-578f-b189-a6c4c73d0772 |  | note | SLUMP
label | 1a1c29ea-a042-5b7c-9460-a91ccfcbd453 |  | note | Slump to be performed on every truck (50mm for hand placed concrete +/- 10mm) testing reduced to every 2nd truck after 5 days of purs if tests are consistent and within tolerance. (Approval to be provided by Principal's Representative prior to reduction)
label | 74421ac3-2882-5767-88e1-5b0815f5c6c4 |  | note | AIR, MASS PER UNIT AND WASH GRADING
label | 2704561e-eead-5775-8c0b-eedb6197f899 |  | note | Air Content test (3% - 5%) mass per unit volume and a wash grading test is to be performed once per lot
label | 00b7e175-f83b-5b63-9091-4c1c46d8ef7a |  | note | All tests taken to be recorded in CL 009B - Concrete Pour Record Sheet
label | dbf4b8d4-0d7f-5dc5-977a-b8e5b0ffef65 |  | note | Check number of tests taken during the shift/lots conforms to the testing criteria. (Beams cast, stored and secure)
label | f3005779-2197-5e9a-b264-4cb28d8c9409 |  | note | REFERENCE DOCUMENTS: Clause 6.8.9/6.8.10/CL009B
label | c85c61c8-f13b-50e0-a756-19af2bdf8930 |  | note | INSPECTION/TEST METHOD: Test and Verify
label | cc2910f0-bab8-5baa-8832-8f467aef3d53 |  | note | RECORD OF CONFORMITY: This ITP signed & CL009B
label | 69323873-9ccf-51fe-8bcd-811e3242563d |  | note | IP
label | 438a46d7-6d00-5f2e-ac91-0d8cbfbf82a2 |  | note | RESPONSIBILITY: Engineer
text | a8b7600e-b3b4-5731-86fb-ccc3aff3d8f0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Place Concrete
label | 32beede5-3b18-5d2a-bdce-1f6cdfda7d06 |  | note | FREQUENCY: Each concrete pour
label | cba1b492-741e-5b3a-aef9-8d1ffd0cfa5a |  | note | ACCEPTANCE CRITERIA: Discharge time must be < 90 minutes from batch time
label | a543229c-e7c4-5195-979c-4630d58e186d |  | note | Concrete must be poured at a rate greater than 10 lineal meters per hour
label | 781a9756-e741-59f5-9fb4-62c5f919dc74 |  | note | Concrete must not be dropped from higher than 1m
label | 775ef2d1-2a82-574a-ad4a-9f49187616f7 |  | note | Ensure there are no breaks greater than 30min between concrete placement
label | 7a5844ae-eac9-5e59-b946-11fefe51f966 |  | note | All delivery times to be recorded in CL 009B - Concrete Pour Record Sheet
label | 9e8b16bd-946b-56d1-ae67-d4f9e83ac741 |  | note | REFERENCE DOCUMENTS: Clause 6.7.2.4 / CL009B
label | 602fcbab-9759-511e-97d5-bcd78e883228 |  | note | INSPECTION/TEST METHOD: Verify
label | d4b2aba2-807f-571c-98e0-2edb5d9ad953 |  | note | RECORD OF CONFORMITY: This ITP Signed
label | b71fe93e-0045-5150-b59a-d1d04cf1afc4 |  | note | IP
label | 691fbfb5-3762-5de1-ad64-b73535bb636b |  | note | RESPONSIBILITY: Engineer
text | 9b69e226-cba6-5628-a73c-fbb447f252c3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Hot Weather Requirements Met
label | 3d35e2f7-1cb3-5891-acb4-439772d6bbaa |  | note | FREQUENCY: Each concrete pour
label | 15f43de6-2dfa-58af-bb64-fe4c0a841e8e |  | note | ACCEPTANCE CRITERIA: No concrete can be poured if air or concrete temperature exceeds 30°C without Principal's Representatives approval
label | 793db2df-d956-5dbf-b50c-bb7901a26012 |  | note | REFERENCE DOCUMENTS: Clause 6.7.2.6
label | 4eb3f9aa-d033-5878-a736-d78fa00be8f6 |  | note | INSPECTION/TEST METHOD: Verify
label | 4ed439d4-30fb-5a15-8352-f6c2f93ccd47 |  | note | RECORD OF CONFORMITY: This ITP Signed & CL009E
label | eac1d0e4-f906-541b-aa96-b2c24b6d8f77 |  | note | IP
label | e493d4dd-fac0-54ae-81a9-d78298b9d918 |  | note | RESPONSIBILITY: Engineer
text | 9fb463cb-b385-5017-90c3-92143a90923f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 - Cold Weather Concreting
label | bec01f89-4656-5431-ad49-6fe66baef01b |  | note | FREQUENCY: Each concrete pour
label | 7643da34-6ea5-507e-9de9-216d8549b6c9 |  | note | ACCEPTANCE CRITERIA: Concrete shall not be placed when the ground temperature is below 5°C
label | 06ac7c0f-8ca5-53cf-b6aa-735917b421ba |  | note | Concrete shall not be placed when the temperature of the concrete mix is below 10°C
label | 678170df-0308-50cf-9c87-b9905629932f |  | note | FH to confirm temperature on site prior to pouring.
label | cf8e956b-5440-5c01-93db-9b4ac1a1a668 |  | note | In the event that PCC pavements are poured when the air temperature, aggregates or water is below 10oC or the completed pavement is expected to be exposed to freezing conditions the pavements must be protected with insulation coverings (plastic/ bubble wrap) during the first 72 hours of curing to maintain a minimum temperature of 10°C.
label | ead666e1-5f85-529a-9b10-9e33d73ff092 |  | note | REFERENCE DOCUMENTS: Clause 6.7.2.7
label | 14d28c7c-8611-5d35-b61a-8a75a187fd60 |  | note | INSPECTION/TEST METHOD: Verify
label | 50b799cb-1b3c-5c1b-b2ca-8e2d428400b3 |  | note | RECORD OF CONFORMITY: This ITP signed & CL009E
label | d6ed8a6f-68b6-5c59-8f63-e9bc38010c29 |  | note | IP
label | fa0b1a4a-2e53-5e9e-88e5-106cba18af6f |  | note | RESPONSIBILITY: Engineer
text | 373ec404-18fe-52e3-9556-d5b132c95f11 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Recording Pour Location
label | 0856eb21-4c5e-544e-a0b8-663cb0a07463 |  | note | FREQUENCY: Each concrete pour
label | 736d0237-c80c-516e-9ed0-5a8e561d85d9 |  | note | ACCEPTANCE CRITERIA: Pour location recorded on plan at the completion of pouring each lot – CL 009C. Include progress with times.
label | bfce67fc-9dd5-558a-8516-e36feb1a1719 |  | note | REFERENCE DOCUMENTS: CL009C
label | 3b7c8bcf-6b46-5495-9edc-4034f814db71 |  | note | INSPECTION/TEST METHOD: Verify
label | 364e069f-de40-5310-aa89-e1f5aa13fae4 |  | note | RECORD OF CONFORMITY: This ITP signed & CL009C
label | 91c758c0-39e5-5801-91f5-a0d14e148044 |  | note | IP
label | dafcc051-a3af-5f13-83d6-8ad6e9843cf7 |  | note | RESPONSIBILITY: Engineer
text | 6fd34990-3a0f-50a5-91a5-deae704c051f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Evaporation Rate
label | a49ba55d-6309-5cb6-9bda-14c991dd98c8 |  | note | FREQUENCY: Each Concrete Pour
label | 734f0ae0-0274-5369-a5d8-9227fb2a3a13 |  | note | ACCEPTANCE CRITERIA: Evaporation rate recorded every hour 0- 0.8kg/m2/hr or every 15min int 0.8-0.9kg/m2/hr. If evaporation rate is >= 1kg/m2/h works must cease and a transverse construction joint installed
label | 82b73bc9-c8e8-548e-8f5b-309abc82ae22 |  | note | REFERENCE DOCUMENTS: Clause 6.7.2.4/CL009E
label | 42a0b8e7-c870-5a04-a9d6-2a9ff612c10e |  | note | INSPECTION/TEST METHOD: Verify
label | 1f8f52bf-7fa8-5afd-a5fe-15d75a96cb3e |  | note | RECORD OF CONFORMITY: This ITP signed & CL009E
label | 02b2edee-8c3c-5784-8874-95b72901f053 |  | note | IP
label | 0f74ed82-8ca1-543c-9e34-f9b637d53092 |  | note | RESPONSIBILITY: FH Engineer
text | e917ec4d-e7fc-58f2-bd42-2a84fe491a76 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Surface finish
label | f90015cd-1eea-5f0c-bf42-ab67e5c513ff |  | note | FREQUENCY: Each Concrete Pour
label | 4430eeb4-d5b6-5481-897d-d04d683e9b4f |  | note | ACCEPTANCE CRITERIA: Concrete shall comprise of traverse finishing, longitudinal straight-edge finishing, floating and then broom finishing, in that order.Brooming shall be in a direction at right angles to the direction of the placing of the concrete.
label | 8cae8f0b-e04a-5106-98d2-255b04aaaec9 |  | note | REFERENCE DOCUMENTS: Clause 6.7.3.3/6.7.3.4
label | 34d5af25-cd3e-504f-9b4c-5facd0bec11d |  | note | INSPECTION/TEST METHOD: Verify
label | d94c9502-a8ee-56cd-b9c0-8cff0a7bd586 |  | note | RECORD OF CONFORMITY: Site Inspection
label | f76df9d2-2a9f-56a2-8cd0-2924e97b71e6 |  | note | IP
label | 762074c5-2224-500f-a71d-bef5435adf1a |  | note | RESPONSIBILITY: Foreman
text | 5159bb6b-2c6e-54de-bdc2-d072b95457d4 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.1 Curing
label | c30ebac7-a47b-51b3-9d6e-9bc24e87cfad |  | note | FREQUENCY: Each concrete pour
label | 33ab6150-895a-5afe-ba8f-e78316b79280 |  | note | ACCEPTANCE CRITERIA: Concrete to be wet cured for a minimum of 7 days. Initial Curing shall commence immediately after finishing operations have been completed. Moist curing to commence as soon as possible after finishing. This will be wetted hessian mats covering the pour. The mats shall overlap to ensure sufficient coverage. Mats shall be kept saturated for not less than 7 days. Curing methods and details shown on post pour checklist CL009D.
label | d34d19cb-2c2f-5af1-a450-ffc8be32e7cd |  | note | Details to be recorded in CL 009D
label | 30e7c487-bb3e-5c2e-bff5-929eef5c575e |  | note | REFERENCE DOCUMENTS: Clause 6.7.4/ CL009D
label | 0cf19949-fffc-5879-9a73-510477111e97 |  | note | INSPECTION/TEST METHOD: Verify
label | 786fdaf8-e47b-5df5-a2f8-b0457ad9c801 |  | note | RECORD OF CONFORMITY: Site inspection & CL009D
label | 9a385ed4-abf0-5ebe-b978-f9de7def7d65 |  | note | IP
label | 66941e8c-59bc-536c-b087-c864803e6c97 |  | note | RESPONSIBILITY: Engineer
text | 7635bafa-511d-592b-9e26-016d4f85050d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Cold Weather/Wind Concrete Protection
label | 222efff4-c080-5e50-8f9c-8d836ec93e13 |  | note | FREQUENCY: Each concrete pour
label | 78022799-3abf-53f0-9053-f7502a849d4b |  | note | ACCEPTANCE CRITERIA: In the event that PCC pavements are poured when the air temperature is below 10oC or the completed pavement is expected to be exposed to freezing conditions the pavements must be protected with insulation coverings (plastic/ bubble wrap) during the first 72 hours of curing to maintain a minimum temperature of 10°C. Details recorded on checklist CL 009H.
label | 7ccb897c-b806-5883-8af9-ec84be453833 |  | note | REFERENCE DOCUMENTS: Clause 6.7.2.7
label | 62f5c644-2e2a-58e9-a05e-881960063641 |  | note | INSPECTION/TEST METHOD: Verify
label | 99d49bc1-82f4-53c0-9865-405d6151ff42 |  | note | RECORD OF CONFORMITY: Site Inspection & CL009H
label | 068ab17c-bd0e-5830-adc0-f8e9cf16d2e9 |  | note | IP
label | b858b7a1-aa0e-5d75-ab57-d34f9064b532 |  | note | RESPONSIBILITY: Foreman or Engineer
text | 8715f9bb-9229-549f-b08f-9e1225a3888f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Inducement Saw Cutting
label | ab49f120-ba45-55ed-b081-78329a2f96e8 |  | note | FREQUENCY: Each concrete pour
label | 66337bdc-81e6-5d89-b7b4-9748cd1303c1 |  | note | ACCEPTANCE CRITERIA: Initial 3mm wide x 150mm deep saw cuts to be carried out as soon as possible. Details recorded on post pour checklist CL 009D.
label | 58a3e4df-6f9a-5380-8da4-a12d953ddc5a |  | note | REFERENCE DOCUMENTS: Clause 6.7.5.2 /CL009D/ Drawings
label | 6e8048e2-eff7-5ba0-b8d5-8fbbea9e66b6 |  | note | INSPECTION/TEST METHOD: Verify
label | 8b0eb2e4-39a6-5d5d-92b9-81a44691aa2d |  | note | RECORD OF CONFORMITY: Site inspection & CL009D
label | 06294519-fc36-5814-8424-85008a135ec4 |  | note | IP
label | 345f95d8-a967-5628-8488-c7667c02960a |  | note | RESPONSIBILITY: Foreman or Engineer
text | 058dc217-de50-5bf9-a4ee-bbd95cc429e8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 Formwork Removal
label | c84bd095-d395-547d-866f-fcac227d5faf |  | note | FREQUENCY: Each concrete pour
label | 4f6f2b7b-f6e7-51e4-8cf8-bf605b07fe44 |  | note | ACCEPTANCE CRITERIA: Formwork may only be removed after a minimum of 12 hours after concrete placement. Details to be recorded in CL 009D
label | b4656417-cd0e-5bf3-9a2e-e965a1977366 |  | note | REFERENCE DOCUMENTS: Clause 6.9.9
label | bac1a143-030e-510a-8b9a-ab647810654b |  | note | INSPECTION/TEST METHOD: Verify
label | 21a7a088-1d61-53f1-8732-2b7936582273 |  | note | RECORD OF CONFORMITY: Site inspection & CL009D
label | cdbf6c5e-4080-5db7-bacd-05fe78d2c963 |  | note | IP
label | efcc4643-6fbb-534e-9a3d-c7d2fdea2e58 |  | note | RESPONSIBILITY: Foreman
text | b2794e48-b2fb-5ca5-91f3-070c70272c8f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.5 Positional Tolerance and dimensions of concrete (finished surface levels)
label | 3a4735d0-d18a-5e6b-8f09-38f1655614ee |  | note | FREQUENCY: Each lot
label | 7e5bd096-8b39-5c5a-8dd1-98c814d535fb |  | note | ACCEPTANCE CRITERIA: Survey done and report prepared: +5mm, -5mm tolerance from design required. Dimensions within the tolerances – details recorded within CL009D.
label | 97671095-48c2-5b2f-be9d-0c363f2d794f |  | note | REFERENCE DOCUMENTS: Clause 6.7.2.9/CL009D
label | 1cc8d214-7173-5b11-bc36-1223d28b3a0d |  | note | INSPECTION/TEST METHOD: Inspect
label | d175366f-f2c3-588a-8802-f3c98f94c05d |  | note | RECORD OF CONFORMITY: Survey & CL009D
label | a46f17a1-8bbc-5540-a6d1-d665d724c7bd |  | note | SCP
label | 7d8479b2-f491-5b8b-bbe9-d0c170366c99 |  | note | RESPONSIBILITY: Engineer/Survey
text | fa8df019-c82f-502e-a5c6-43c4deff3d21 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.6 Pavement Density
label | 5c7fbd5b-8fd4-5442-9a64-71807beebb65 |  | note | FREQUENCY: Each Lot
label | 001ada47-70cd-59fd-933a-be9784b78a6a |  | note | ACCEPTANCE CRITERIA: DENSITY
label | 7b37a104-5444-545c-a99d-85bd6e9059b5 |  | note | Core (120mm dia x full pavement depth) to be cut and tested for density.
label | 1e56b111-6d55-5409-bc99-61a1b3c267f9 |  | note | FREQUENCY
label | 4a4e427c-c40f-51ca-8d26-c7fdc654d0cc |  | note | Minimum of 2 cores per lot (<=150m3)
label | 12367b87-83d7-5983-9d82-bd406794bbd4 |  | note | 1 additional core per 75m3 or part thereof
label | 8f520020-6c24-5dd6-a76d-bd24d309a606 |  | note | Maximum of 4 cores per lot
label | 2fe4e2a0-c403-5bc4-882c-2b927e9f9fa6 |  | note | REFERENCE DOCUMENTS: Clause 6.9.6
label | dc701525-2d82-5e08-a2ae-9d48d0f47d33 |  | note | INSPECTION/TEST METHOD: Test and Verify
label | ef244ff8-a271-5deb-88e2-a8d31556c7d8 |  | note | RECORD OF CONFORMITY: Test Report
label | d3202ea2-0565-5cb8-900a-fa5758e91fed |  | note | IP
label | 933bf243-ce03-5944-8ed1-4bf7cbcae7cd |  | note | RESPONSIBILITY: Engineer
text | 67cf4e54-4aeb-51da-8acf-cce39b5fb9cf |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.7 Surface Smoothness Testing
label | de229a84-4f71-5698-8800-9fd2f615f074 |  | note | FREQUENCY: Each lot
label | fcc87380-a843-5084-98eb-744fb1716e8c |  | note | ACCEPTANCE CRITERIA: The surface smoothness of the finished surface shall be checked using a straight mobile edge, and the minimum of the finished surface is that it shall not deviate from the testing edge of a 3.5 m straight edge by more than 5 mm.
label | 76a96f57-6d81-5708-98d4-184e166965ad |  | note | REFERENCE DOCUMENTS: Clause 6.9.10/ CL009F
label | 8cb9f707-5c36-57cd-904b-02c96e4db18b |  | note | INSPECTION/TEST METHOD: Inspect
label | 79887c8b-cc79-5628-a03a-9e3cb237828b |  | note | RECORD OF CONFORMITY: Site inspection & CL009F
label | 594ea303-7c5c-5d19-b09a-f6f0c96e08ba |  | note | WP
label | 9c4e5c8c-32e0-556f-afe2-e67e3a71a871 |  | note | RESPONSIBILITY: Engineer/Principal’s Representative
text | d5822796-db74-53c8-8e54-8bcfd65a40a4 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.8 Defects in the concrete
label | a5dee442-b957-5e9a-a4ac-d36cc61e5c86 |  | note | FREQUENCY: Stripping of Forms
label | df4bf424-22ea-520e-88b7-a586ff21af2e |  | note | ACCEPTANCE CRITERIA: Check for any non conforming or defects (cracks) in the concrete slabs. Any locations identified to be recorded in the post pour checklist - CL 009D.
label | b46a5f81-2a88-5d7e-b45b-11a56c6be36b |  | note | REFERENCE DOCUMENTS: Clause 6.9.8
label | 35b4819e-fdc5-5ce7-a5d9-d624dfedb7c9 |  | note | INSPECTION/TEST METHOD: Inspect and Verify
label | da38a060-c612-510d-9d8d-348300776464 |  | note | RECORD OF CONFORMITY: Site inspection & CL009D
label | b15679b3-56cd-5e20-ae5e-78777baf8d9d |  | note | IP
label | 901eff59-c6c8-515a-8832-32c3401ca0fc |  | note | RESPONSIBILITY: Engineer
text | aac0a4c8-2c1c-5e4f-bf0e-35952019cff7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.9 Spalling or honeycombing
label | 7efbf22d-80ab-500a-aa8c-cebf26bee86d |  | note | FREQUENCY: Stripping of Forms
label | e20689ed-1a76-5d13-bae4-e38e7932eb35 |  | note | ACCEPTANCE CRITERIA: Check for spalling or honeycombing during and after curing of the concrete slabs. (Must be less than 5% of surface area). Any locations identified to be recorded in the post pour checklist - CL 009D.
label | f4f8e4fe-4f50-5e33-a301-32093561e535 |  | note | REFERENCE DOCUMENTS: Clause 6.9.7
label | edb6dd7c-0145-565c-813b-8be5c25bb9fe |  | note | INSPECTION/TEST METHOD: Inspect and Verify
label | 74de37a3-df09-59b1-b8f7-4ef35c274460 |  | note | RECORD OF CONFORMITY: Site inspection & CL009D
label | 9df613ec-c866-54ab-a170-4a87ba8bdf76 |  | note | IP
label | 45365b8c-6061-510e-a46f-75b87a44d936 |  | note | RESPONSIBILITY: Engineer
text | 95248136-d5fe-5846-81f7-747d4f46b276 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.10 Protection of Concrete Pavement
label | 76318efc-d435-5d41-ad1f-ac5277c1fa40 |  | note | FREQUENCY: Each Lot
label | 101cf457-8030-51b3-8b78-2839c1ca39cf |  | note | ACCEPTANCE CRITERIA: Concrete pavement not to be trafficked until 7 days old or early strength results are obtained (3.2MPa min)
label | 5758aa21-b802-5411-a31b-6f25c2a7f192 |  | note | Steel tracked or wheeled equipment is not to be used
label | 7a031d8f-8023-58b4-b4e4-1206adecbbbf |  | note | REFERENCE DOCUMENTS: Clause 6.7.6
label | 0dfd14de-01b8-5e35-bde2-ecc65af932e5 |  | note | INSPECTION/TEST METHOD: Verify
label | 9054de2d-c617-58de-976e-cd2f00ceb21c |  | note | RECORD OF CONFORMITY: Test Report
label | 58cd2f51-6d56-5318-84b1-b9651b354874 |  | note | IP
label | 66a03ad8-89e6-5d0e-96a4-8aa26d18d891 |  | note | RESPONSIBILITY: Engineer
text | 39a017e1-3078-5fda-ac22-34c0b6a28d58 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.11 Concrete Test Results
label | f8b27c57-bbfa-5e01-9df4-a937bb2e893d |  | note | FREQUENCY: Each concrete Pour
label | 4bdff466-9ce9-5c7d-b86c-5fc52ed85bef |  | note | ACCEPTANCE CRITERIA: All concrete test results obtained and attached to ITP
label | 07ea3163-5aaf-5bd0-ad08-0d99af642c4f |  | note | All concrete test results submitted on Aconex. Check results of concrete tests are compliant as per specifications (eg graphical plots, Analysis of Flex. Strengths)
label | 3bd2d747-1239-57f6-8fe3-087d0d1835a7 |  | note | REFERENCE DOCUMENTS: Clause 6.9.4
label | 15ccc215-ca60-5424-afb4-5822a4bd5cd6 |  | note | INSPECTION/TEST METHOD: Verify
label | 662acd00-4d36-5c9f-af9f-42dbb193948c |  | note | RECORD OF CONFORMITY: Test Report
label | b4cabdb0-f5f0-5e68-b18d-333570419281 |  | note | IP
label | c9c90559-a75d-5cbc-b805-8195cfef99a2 |  | note | RESPONSIBILITY: Engineer
text | 17e8be37-9e36-5296-8a4d-4397bacac57a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.12 Post-Pour Checklist
label | 169e6f97-7973-5b7f-bef4-193ac9049ac0 |  | note | FREQUENCY: Each concrete pour
label | 850307b8-ddb0-5748-a3d5-d7c7ff9ff0da |  | note | ACCEPTANCE CRITERIA: CL 009D – Post-pour Checklist completed and signed.
label | e636a090-f754-5984-8950-654ce8c6cc08 |  | note | REFERENCE DOCUMENTS: CL 009D
label | 211b4b0b-5633-5ed2-b47b-f88ddc575b3f |  | note | INSPECTION/TEST METHOD: Verify
label | 664d58cc-e25c-534b-aef6-95d58daea08e |  | note | RECORD OF CONFORMITY: CL009D
label | 1f029a1a-e03a-5176-9ab5-ee321c91dadd |  | note | HP*
label | 93d7a368-ff18-5e91-909d-38fcbedd57d8 |  | note | RESPONSIBILITY: Engineer
text | 33cba3a3-ce32-5757-b2cd-082e271aecfb |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.13 Surface Texture
label | b3e3ff11-6908-53d3-be6d-9246ac25f83b |  | note | FREQUENCY: Each Lot
label | 4fe25c17-9f99-5e68-a55f-b836a5e4d3d2 |  | note | ACCEPTANCE CRITERIA: Surface texture measured 1 test per 500m2
label | c68f308f-d0cf-5474-b221-f5e06f81d524 |  | note | REFERENCE DOCUMENTS: Clause 6.9.11 / CL 009D
label | c28f3f93-86dc-5c52-b00c-8914d91d6156 |  | note | INSPECTION/TEST METHOD: Verify
label | afadbaca-e1eb-5430-b5bc-f6dac2222837 |  | note | RECORD OF CONFORMITY:Test Report
label | cd55ab55-7059-5678-805a-bc3e48474df2 |  | note | IP
label | 953d976a-c07c-5f76-9f1f-c64257f33bfb |  | note | RESPONSIBILITY: Engineer
text | 3964e089-dc6f-5c30-aaed-ed2eeec77868 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 649bf7c2-dcdb-519c-9746-6710ba863978 |  | textbox | Name:
text | 01302b1f-5a40-560c-853c-0dead90b5c76 |  | textbox | Position:
checklist-sectioned |  |  | checklist | ITP 029 - Native Grass Inspection | itp |  |  |  | Yes | ITP 029 - Native Grass Inspection | 1c2a3ab9-6a0f-4c5a-a041-6f9ea3b69f9b
checkpoint-group |  |  | section | ITP 029 - Native Grass Inspection
checkpoint-status |  |  | checkpoint | 1.1 Check for correct documentation
label | 9ff0ca19-3508-4596-b2e9-e2fcf41611e4 |  | note | FREQUENCY: Prior to site establishment
label | d89f45e5-aeca-4b9b-bdf2-4fc430905368 |  | note | ACCEPTANCE CRITERIA: Review whether a preliminary report has been completed for the project which will outline where the Significant native grasses are and what protection has been specified. (Example: Biosis report for the EPBC referral for a Part13 permit to remove native grasses)
label | 315eaf8a-ec8a-4f90-9936-7d4e0537661c |  | note | REFERENCE DOCUMENTS: Consultant reports
label | 13c7480f-90a5-4d2a-bba8-c802329640e5 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 978c5dee-f97b-4a17-812c-a075acc09cb3 |  | note | RECORD OF CONFORMITY: This signed ITP
label | 634a55dc-6453-4b21-aa35-139f6204ae46 |  | note | HP*
label | 9b1cb466-b132-4dcd-bb00-3482cee28be0 |  | note | RESPONSIBILITY: Project Engineer
text | b87b09bf-db23-4170-994e-113170c2a01e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 Check the Biosis Google Earth Mapping
label | c31d5785-363d-44a8-8983-5e03c7d4731f |  | note | FREQUENCY: Prior to site establishment
label | c6a95c6e-c13e-4014-933a-0a2519884249 |  | note | ACCEPTANCE CRITERIA: Review the Biosis Google mapping which outlines the boundary of the native grasses at the time they were mapped. (Note: that mapping only occurs approximately every 5 years, so the exact boundary will need to be defined)
label | 178b45fc-b2d0-4fca-90d9-5efa5088bf8c |  | note | REFERENCE DOCUMENTS: Biosis Google Earth Mapping
label | ebe24d71-8126-4938-8695-f724dc17347e |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 8da22b49-3b07-439c-af65-382aa7f15bde |  | note | RECORD OF CONFORMITY: This signed ITP
label | 3a1121b7-da73-42f7-a652-f9894a671e45 |  | note | HP*
label | f7573d89-2f70-4fa9-bc4b-e8dfa54575d0 |  | note | RESPONSIBILITY: Project Engineer
text | 4b067e10-394a-46ad-84f5-17d7cfe5015c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 Biosis Inspection
label | 2f685352-0307-4f2f-aa7b-9287c778c2c1 |  | note | FREQUENCY: During site establishment
label | ac4d9441-4b25-4423-9294-f0b310348d36 |  | note | ACCEPTANCE CRITERIA: On approval from APAM, arrange for Biosis to conduct an inspection of the site to confirm the boundary of the Significant native grasses which need to be protected. The surveyor can then mark out these areas with Biosis to ensure the boundary is being protected. Place bollards along the boundary area.
label | 07f02edc-89a9-4ef4-98c8-71035e3ecdd1 |  | note | REFERENCE DOCUMENTS: Biosis Google Earth Mapping
label | e7aab10c-7dc1-4b60-b3b3-dc387a0b1607 |  | note | INSPECTION/TEST METHOD: Visual inspection compared against the Google earth mapping
label | ddc4696c-1b2e-4268-a284-4a36773cb2fb |  | note | RECORD OF CONFORMITY: This signed ITP
label | 3bf15133-6d6b-420f-ba0c-714aec83f26e |  | note | HP
label | cccad86b-2f20-4634-80ff-ff8836e4fea3 |  | note | RESPONSIBILITY: Environmental Manager / Biosis Botanist Surveyor
text | 9b3bb2a5-19b6-4112-9849-b11505ce8377 |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 3.1 Mark out the exact significant Native Grass Boundary Area
label | e448fb16-3431-44f9-bbe9-50694b11b0a6 |  | note | FREQUENCY: Prior to commencing any activity
label | 6d1e57c6-0a0c-4258-8302-0dad68cf0348 |  | note | ACCEPTANCE CRITERIA: Work with the surveyor to mark out the Significant Native grass boundary. Signage will be placed onto the bollards stating ‘Native Grass Boundary Area.’ NTGVVP Nationally Significant Grasses to protect within this area.
label | 324eb3f1-db46-4ec3-a155-4a1b56c4bd99 |  | note | REFERENCE DOCUMENTS: EMP
label | cf37dcf7-8395-4de4-97fb-9daa49cf9663 |  | note | INSPECTION/TEST METHOD: Inspect
label | 0321e614-4bcc-4f72-973c-91d9f7b05809 |  | note | RECORD OF CONFORMITY: This signed ITP
label | 5b4de2fb-b560-4da1-ac33-760c550668c3 |  | note | HP*
label | d2292aa1-33ae-4ef9-aab0-36f88d9da242 |  | note | RESPONSIBILITY: FH Environmental Manager Surveyor FH Project Engineer
text | 4fce0baa-8eec-4cf8-9227-6beec6858ab6 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Use temporary fencing and signage to block access to the Significant native grasses where we are working in close proximity.
label | dbe4d6ec-d3d5-4847-87e3-11676e731ed5 |  | note | FREQUENCY: Prior to commencing any activity
label | 2e9084e4-5fd6-4154-a412-5d6d436bc0d7 |  | note | ACCEPTANCE CRITERIA: The Botanist (Biosis) report may define what type of protection is required for the Native grasses. For works in close proximity to the native grasses, use temporary fencing to block access with signage stating “Vegetation Protection – No Go Zone.” This fencing will be installed at a distance away from the actual native grass boundary to act as a ‘buffer zone’ but still allows works to progress.
label | 5f4e01f3-76e5-4a35-bfda-dee723b3fe7d |  | note | REFERENCE DOCUMENTS: Biosis report, EMP
label | 56a5e068-c9a0-4d80-9d81-46a4b898302f |  | note | INSPECTION/TEST METHOD: Inspect
label | 26885913-c4b6-410d-90ad-7ff96e551eda |  | note | RECORD OF CONFORMITY: This signed ITP
label | 00ad9bb5-da9e-4af1-99c6-db68e8690b0a |  | note | HP*
label | 58be0a7c-acfe-4bb8-94cb-3d8b3cb67c17 |  | note | RESPONSIBILITY: FH Project Engineer Surveyor
text | 675cba41-fc51-4b90-8420-3c13d0db2c7b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Implementation of control measures required to protect the significant native grasses around our project area
label | 2a26a362-7a66-416c-ab6f-295304c81c9d |  | note | FREQUENCY: Prior to commencing any activity
label | 51d14ca2-acc3-4de1-8a53-df6fe53aa9d7 |  | note | ACCEPTANCE CRITERIA: An exclusion zone will be set up with bollards and signage stating “Vegetation Protection – No Go Zone” between our works area and the native grass boundary area to act as a ‘buffer zone.’ Allow a minimum 2.5m buffer zone.
label | 675665df-2d56-48fe-aed8-76ac74452767 |  | note | REFERENCE DOCUMENTS: Biosis Zulu report, EMP
label | e17218ec-a34c-4300-b9ea-c58cc451bdcd |  | note | INSPECTION/TEST METHOD: Inspect
label | f34e4575-0670-472a-8c1c-70219da6eca1 |  | note | RECORD OF CONFORMITY: This signed ITP
label | 4ce2257a-749a-4723-9361-29ae27ef7035 |  | note | HP
label | addd0273-68b2-41ba-9e8b-c270a44645de |  | note | RESPONSIBILITY: FH Project Engineer
text | 7ca79623-f535-4554-83f2-2ed0ecd62565 |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 4.1 Release of Hold Point for Native grass Protection
label | cdd48f95-3a81-4406-8742-f2ac73a97139 |  | note | FREQUENCY: Prior to commencing construction
label | d0c94ab9-a99a-4888-9e4b-2e18e4f49e4b |  | note | ACCEPTANCE CRITERIA: Arrange a joint inspection with APAM and the botanist (Biosis) to conduct a visual inspection to confirm that the native grasses are protected with the required temporary fencing or bollards and correct signage where required. All parties are to sign off on the separate Hold Point Release document
label | d6e8c2cd-e32b-417b-bd33-4b483b5ae3ff |  | note | REFERENCE DOCUMENTS: EMP Botanist report
label | c0250484-9d5e-4efe-b16a-8290a26eeb1f |  | note | INSPECTION/TEST METHOD: Visual
label | 635e5518-d0fc-4ccf-91e9-32b9ffda3621 |  | note | RECORD OF CONFORMITY: This signed ITP
label | da45fb2c-d192-4c73-9755-ccc302d55b4d |  | note | HP
label | 84a4dcac-0143-43c5-8d85-a52af6f1a2b5 |  | note | RESPONSIBILITY: Biosis APAM Fulton Hogan Environmental Manager or Project Manager
text | 70762e44-2511-45f3-a9f8-b90b4d766130 |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | FULTON HOGAN FINAL INSPECTION - "On behalf of Fulton Hogan, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract".
text | 3cf86eff-03e7-4247-b3ff-3b637d752afd |  | textbox | Name:
text | be0dd2e7-22f4-4332-b105-6dfb11e70444 |  | textbox | Position:
checklist-sectioned |  |  | checklist | ITP 008 - Cement Modified Crushed Rock | itp |  |  |  | Yes | ITP 008 - Cement Modified Crushed Rock | 207d517f-3645-4dce-85d0-5f0fd2532860
checkpoint-group |  |  | section | ITP 008 - Cement Modified Crushed Rock
checkpoint-status |  |  | checkpoint | 1.1 - The current revision drawings are being used including subcontractors copy.
label | 641add48-d0af-4f00-a561-74c9da7e3ded |  | note | FREQUENCY: Prior to commencing works
label | 750a348d-3583-4068-ad57-f2d2fae2eb4e |  | note | ACCEPTANCE CRITERIA: Current revision drawing is being used including the subcontractors copy. Current Revision to be obtained via Aconex
label | 5c1d5e84-e547-41e3-9789-614fc05320b0 |  | note | REFERENCE DOCUMENTS: Aconex
label | ce7e786c-1823-4b65-a971-70723ea6a354 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | d3136c67-ed8b-4a4a-b68e-cc6b4c216c6c |  | note | RECORD OF CONFORMITY: This signed ITP
label | 665a80c3-e091-4e1f-8e77-36dd0aa97e93 |  | note | HP*
label | 8e5fa659-5375-4a57-8639-bb2048e6081f |  | note | RESPONSIBILITY: FH
text | b2a135e6-27d4-44ec-a2ac-294b86281765 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 ITP and Construction Procedure Documentation
label | b68b3194-0a47-49f3-a33d-659bd1f78b1a |  | note | FREQUENCY: 28 days prior to work
label | 13de5f8a-8e81-401f-a83a-9cb524c5007c |  | note | ACCEPTANCE CRITERIA: ITP and Construction procedure for CMCR placement to be provided to the Principal’s Representative for review.
label | 51effd13-8fe2-4735-a9c7-77892eb33787 |  | note | REFERENCE DOCUMENTS: Spec cl. 5.2.1 and 5.4
label | af70e2a7-2eda-431a-a6f2-10e3633a2c4c |  | note | INSPECTION/TEST METHOD: Verify
label | a334529b-5a20-46b7-81fe-c1cc9139a5cc |  | note | RECORD OF CONFORMITY: Approved Work Procedure Report
label | a7878314-0d7d-44a8-be1e-ce5a8f18566c |  | note | HP
label | da9aef68-d21c-47f0-b443-a110d0e9238c |  | note | RESPONSIBILITY: FH Jacobs
text | 29fa636e-4fad-45e5-aaa7-cbf64ffdfead |  | textbox | Date Completed:
label | 2f55f0da-fa57-4aa8-ba85-6c7da466e796 |  | note | Hold point sign off reference: ACONEX: FHPL-TRANSMIT-000078
label | a28330fc-3115-4650-9439-fc20e903984f |  | note | Date: 14/06/2019
checkpoint-status |  |  | checkpoint | 1.3 Submission of mix design report
label | 9b0124fd-b03d-4592-bc69-87723c08847c |  | note | FREQUENCY: Prior to works
label | 84d6bb79-3ea7-41b0-9b07-ccc7fdbaa6a0 |  | note | ACCEPTANCE CRITERIA: Material and test results to be submitted to the Principal’s Representative for review.
label | 6933f458-dfc9-4e1a-aba1-7628227cf3f5 |  | note | REFERENCE DOCUMENTS: Spec cl. 5.5.3
label | 072bd8f9-f678-44b9-b1b5-53b6591dbf86 |  | note | INSPECTION/TEST METHOD: Verify
label | 163ac0bf-46fc-433e-9908-2916056be7b8 |  | note | RECORD OF CONFORMITY: Approved mix design report
label | b726249c-91b0-4817-bb27-0bf208ddab59 |  | note | HP
label | 9f97fbc9-6d80-4e79-8741-03fd2be1f7ac |  | note | RESPONSIBILITY: FH Jacobs
text | df2a76a4-5880-439a-8813-0468c18291c9 |  | textbox | Date Completed:
label | f9e2af7a-cc29-4cfb-abd6-7131ef38b285 |  | note | Hold point sign off reference: ACONEX: FHPL-TRANSMIT-000162
label | 27a5bb20-a5c1-4064-aa2a-7a6136fe9eb2 |  | note | 4/8/2019
checkpoint-status |  |  | checkpoint | 1.4 Construction Trial Report
label | bc03c49f-c86f-4dc1-8d38-561d403af4e8 |  | note | FREQUENCY: Prior to works
label | bf6bab81-c69e-458c-9c14-7fb7c8576c91 |  | note | ACCEPTANCE CRITERIA: Trials will form part of permanent works, as agreed to as part of Schedule 6 of departures. Construction Trial report submitted and reviewed by the Principal’s Representative. Trial report to be written based on first day of placement. Construction procedure to be reviewed and updated if there are any non-conformances associated with the initial trial. The trial requirements are per Clause 5.8 and detailed in the Construction Work Procedure.
label | c2fb356f-f04c-4e49-8f3d-a02927973c1e |  | note | REFERENCE DOCUMENTS: Spec cl 5.8, FH-ZULU-PM-WP008, & FHPL-TRANSMIT-000420
label | 8ef03813-0d22-440f-a5a0-e4cbf4060d42 |  | note | INSPECTION/TEST METHOD: Verify
label | 0b0df4c4-264d-42d2-86d4-e129381542b1 |  | note | RECORD OF CONFORMITY: Approved Construction Trial Report
label | d1118285-d551-43f2-a312-a586b737cdc0 |  | note | HP
label | d74773e3-ffda-4442-ae8a-5fa7214cefc2 |  | note | RESPONSIBILITY: FH Jacobs
text | 87e1c10a-ebff-4ab9-ad45-04238aa14bf6 |  | textbox | Date Completed:
label | 16073e92-a4d0-4b61-8bec-6b52c328cf3e |  | note | Hold point sign off reference: ACONEX: FHPL-TRANSMIT-000420
label | 39872691-7c5e-4c22-b1b3-34b34d675c7d |  | note | 19/12/2019
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 1.5 Implementation of all measures & controls
label | 181d2d6a-4c25-4276-91e9-a703e4d7b24f |  | note | FREQUENCY: Prior to works
label | bdf2477c-bb17-45a4-812c-e64bb227211b |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | e1aa2a94-1e86-4994-9ed0-dd330d4c9083 |  | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, WP SWMS
label | 2de686bf-85ee-4b66-8ada-c2ba026142fe |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 61531c27-df6f-4bfb-ae61-aff5758d0689 |  | note | RECORD OF CONFORMITY: Site inspection
label | 264ecec3-1fc0-4055-9c97-ed29199cae93 |  | note | HP*
label | 13e798b0-08a9-410b-a40c-6beb8fd3a0e7 |  | note | RESPONSIBILITY: FH
text | 94afabc1-d4db-4585-8156-02ca4ac74611 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.6 Inspection of prepared underlaying layer
label | 29ffa013-b7d4-4b01-b72d-1f8cf4df9b72 |  | note | FREQUENCY: Prior to works
label | 515fc7e5-064d-450c-b20e-b2fd5b8ac9b2 |  | note | ACCEPTANCE CRITERIA: Prior to CMCR placement, the construction of the underlying layer must be completed.
label | 218dbe06-f9f7-492b-9cd7-d066233a193c |  | note | REFERENCE DOCUMENTS: Spec cl 5.9.1
label | 82583bad-7bf6-4504-8707-7da07bf069b1 |  | note | INSPECTION/TEST METHOD: Verify
label | ed06f599-516f-4664-96f0-f31ef8281a90 |  | note | RECORD OF CONFORMITY: This ITP signed
label | f949cb2a-fa6c-4e21-89a3-df038de22ed8 |  | note | HP
label | 609e5c6d-0022-4fa5-8ecb-fd52c6c59b33 |  | note | RESPONSIBILITY: FH Jacobs
text | 041c897a-aee0-4cc6-a8b9-450601899786 |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 2.1 Mixing of Materials
label | a4802374-b989-4866-8b39-d111d568fec6 |  | note | FREQUENCY: Each lot
label | f2a161d8-6f73-49c8-bfd1-854de0f8708d |  | note | ACCEPTANCE CRITERIA: At the end of each 200T production, verification of the amount of binder is to be checked against the measurement made by the mixing plant. A copy of this is to be submitted to the Principal’s Representative within twenty-four hours.
label | e1458d3e-c63d-4611-a8ac-766dec824ee5 |  | note | REFERENCE DOCUMENTS: Spec cl. 5.9.2
label | caa6fa70-2e12-43e3-a88e-2455860b0e18 |  | note | INSPECTION/TEST METHOD: Builder verification
label | 0b1d8c19-fff9-4fad-b86f-bf0172f4a420 |  | note | RECORD OF CONFORMITY: Calculations spreadsheet and this ITP signed
label | 3ec22c95-7ae0-4d9b-815a-006295a5517a |  | note | HP*
label | ce2e5bf7-1a11-429e-aa2c-0b0d2b4f10ee |  | note | RESPONSIBILITY: FH
text | 34c64c15-4ec8-456c-a53c-7c5aa99bc76d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Placing CMCR
label | cce1b1ad-10dc-4832-9da8-30a25f70a51f |  | note | FREQUENCY: Each lot
label | ef725b95-7fac-48a0-9df3-dc7a5d5efacd |  | note | ACCEPTANCE CRITERIA: The underlying layer must be watered thoroughly prior to the spreading of the CMCR.Grader to enable automatic control of thickness or levels as required to meet the placing requirements of the specifications. (GPS enabled)All CMCR joints to be cut back to near vertical. Material at the joint to be kept close to OMC by watering the edge of the CMCR. Any segregated material shall be removed and the joint must be fully compacted. Per results of CMCR trial, field moisture content to target 1% below lab OMC. Acceptance criteria based on density result. A bobcat and excavator with smudger attachments to be utilised for placement in areas where a grader is not feasible.
label | a9f253c7-1078-4b1f-a4f5-da62e458b45b |  | note | REFERENCE DOCUMENTS: Spec cl. 5.9.2 & FHPL-TRANSMIT-000420
label | 44f7e742-d55b-4416-871b-502cf9c75a7d |  | note | INSPECTION/TEST METHOD: Visual inspection
label | d7e91120-8b57-4d63-8923-893559b01581 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 897c9aac-7cb0-4472-abf9-da956a44adb3 |  | note | HP*
label | fd2b5a08-860b-4428-b568-e3a429dd11fc |  | note | RESPONSIBILITY: FH
text | 0d9121e3-4e8f-486c-8e8b-db8225e537ae |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Compaction and Compaction Testing
label | 6828482b-d69d-4f61-9f69-8436c2a1901c |  | note | FREQUENCY: Each lot
label | 022c3247-74f4-4ce4-b3b4-3a7d2ae399c0 |  | note | ACCEPTANCE CRITERIA: The density ratio shall be determined for compliance purposes using the nuclear density gauge (NDG) to a frequency of 1 test per 200 m2. The NDG shall be calibrated as part of the Construction Trials and this calibration will be checked during construction.
label | 374184bc-95db-4970-bb71-25ae15f93a60 |  | note | Sand replacement tests shall be carried out every 5 lots for the purpose of verifying the calibration of the NDG, and shall incorporate a minimum of 5 tests. Cores cut in the CMCR for the purpose of sand replacement tests must be filled with CMCR and thoroughly compacted in thin layers at between OMC-1% and OMC+1% using a mechanical hammer within the Allowable Working Time.
label | a516b822-fa86-4819-bde4-67b3fb9a4a50 |  | note | Each lot of compacted and proof rolled CMCR shall achieve a minimum characteristic density ratio of 98%, comprising density testing results for intermediate and final layer of CMCR.
label | 6b898842-35d9-4145-83de-96e3dc773165 |  | note | Minimum eight coverages of the heavy vibrating roller and twelve coverages with a 38T Pnuematic Tyred Roller on CMCR under concrete pavement, and on first two layers of CMCR when used as part of a flexible composite pavement. Marco Roller used in lieu of 38T Pneumatic Wheel Roller on final layer of CMCR in a flexible composite pavement, including GPS Mapping data
label | c9b8e215-7bf0-4d2a-a10b-b6cca7580def |  | note | REFERENCE DOCUMENTS: Specs cl 5.9.3 & 5.10.7 & FHPL-GCOR-001023
label | fbc489f3-728c-4a9e-9f5e-3acbbc1e1e53 |  | note | INSPECTION/TEST METHOD: Testing
label | c8697677-b5e7-4b54-a824-f3ae981e619e |  | note | RECORD OF CONFORMITY: This signed ITP
label | 7b1a4d1b-6770-43bd-bb54-92704e5e49d2 |  | note | TP
label | 8fe91775-6ce0-42b7-bcd4-2d6f37a46bb3 |  | note | RESPONSIBILITY: FH
text | 5c824795-c29f-4e40-91a1-3cf0d8829a4a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Proof Rolling
label | 98b93755-9095-4d3b-a466-9fc57e1850ea |  | note | FREQUENCY: Each lot
label | 92e88078-c28a-46b4-b539-b72ad0679d06 |  | note | ACCEPTANCE CRITERIA: Following compaction of the CMCR layers, each layer shall be proof rolled (1 pass) with a 38T Pneumatic Tyred Roller. Marco Roller used in lieu of 38T Pneumatic Wheel Roller on final layer of CMCR in a flexible composite pavement.
label | 7fe28d6e-df58-4d48-be08-264329b79a43 |  | note | The pneumatic tyre roller shall be equipped with an integrated on board GPS based mapping system that can be utilised to demonstrate that the specified roller coverages have been achieved.
label | 021aba3d-01bd-4623-ba81-792464d864ea |  | note | WP verified from results of the GPS Mapping System Data, as confirmed in CMCR Trial Report.
label | 118b07ef-111e-40a4-8f4e-561003f42861 |  | note | REFERENCE DOCUMENTS: Spec cl 5.9.4, FHPL-GCOR-001023 & FHPL-TRANSMIT-000420
label | 8a8a8383-1268-4d66-9c46-4e5328091aee |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 97f41603-09e7-44ae-a4db-60b966b74ce7 |  | note | RECORD OF CONFORMITY: Visual inspection / GPS mapping data, & this ITP signed
label | 50f5963a-d393-4b11-9115-07adedf1cf96 |  | note | WP
label | 3abb92e7-54a6-46ae-8191-83138e5529bd |  | note | RESPONSIBILITY: FH Jacobs
text | a152a3fd-11ea-4a5d-b560-b915bd82cf7b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 Failure of Proof Rolling
label | 2d2a55f2-6412-4847-9a8d-4bbba7feff79 |  | note | FREQUENCY: Each lot
label | 9fedfa3f-ee59-4c18-bf0b-5cf2d890dd86 |  | note | ACCEPTANCE CRITERIA: Any areas of the CMCR layer that rut, yield or become unstable during compaction or proof rolling must be investigated in the presence of the Principal’s Representative.
label | f338d62f-85c4-418d-b4db-8b1ab5e4e957 |  | note | REFERENCE DOCUMENTS: Spec cl 5.9.4
label | 1c4fa9ac-b1eb-4019-8c07-75380da3bc45 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | db9494ab-889d-42b9-a606-b12514ec6ce6 |  | note | RECORD OF CONFORMITY: Site inspection & this ITP signed
label | d000d8e7-522a-4f0c-b7ec-5cc84f326f59 |  | note | HP
label | dc169cb8-091f-4884-94cc-743bce328e44 |  | note | RESPONSIBILITY: FH Jacobs
text | 7fcc05f1-c153-4ef8-93c4-2ffb91ea6e66 |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 2.6 Completed CMCR Inspection (surface smoothness test)
label | f8903401-5daa-4b40-9d08-6baf7202fd5d |  | note | FREQUENCY: Each lot
label | 7d5d485a-dea9-4627-a01b-8a496e47a5aa |  | note | ACCEPTANCE CRITERIA: Inspection of completed CMCR undertaken with Principal’s Representative, or with the Straight Edge/Surface Smoothness Report, subject to approval.. Surface smoothness shall be undertaken using a rolling 3.5 meter straight edge/hand held 3.5 meter straight edge.The straight edge shall be used at 1 test every 20 meters along each longitudinal joint and across every transverse joint. The surface of the CMCR shall not deviate from a 3.5m long straight edge, placed on the surface in any direction, by more than 7mm, except in directions where a change of grade occurs.
label | 20f6cd1b-d595-442e-a650-6c892cf518f4 |  | note | REFERENCE DOCUMENTS: Spec cl 5.10.4
label | 9553aaef-7f2b-415d-81b7-e4e6d9036800 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 76d799c2-3af5-4609-a553-fa7ed37fa634 |  | note | RECORD OF CONFORMITY: Site inspection / Straight Edge Report & this ITP signed
label | 73d5fe2b-c9aa-448f-a694-93f70077e197 |  | note | WP
label | 972879f7-c78f-43ba-8482-94a27f742b6c |  | note | RESPONSIBILITY: FH Jacobs
text | 000d07a9-fb7e-48d8-9945-0a8ab8601b4f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.7 Curing of CMCR
label | 26a1519a-0324-49fb-a666-2db62e62b002 |  | note | FREQUENCY: Each lot
label | d2e7aec4-b8e3-4f7d-b196-9423e20ba686 |  | note | ACCEPTANCE CRITERIA: CMCR to be water cured and protected until primerseal is placed. Primerseal to be placed within 72 hours after compaction.
label | 91e68fe5-68e3-46b9-8cf0-a7d839884c7c |  | note | REFERENCE DOCUMENTS: Specs cl. 5.3.4 & DCWC Mgt-TRANSMIT-000011 (Item #9)
label | aeefad3e-0e93-48b2-9b63-bf697c4ae6c5 |  | note | INSPECTION/TEST METHOD: Verify
label | 47f0a234-7b39-4f21-a5db-e2dd79801f05 |  | note | RECORD OF CONFORMITY: This signed ITP
label | 190dc854-a5f0-4e69-8d93-a37c141ebfca |  | note | HP*
label | 68aae23a-93d2-46b9-8573-7b003e504f03 |  | note | RESPONSIBILITY: FH
text | 8078a37b-d745-4b9a-af99-ed6d537b8553 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.1 Unconfined Compressive Strength
label | ca3edad2-c87a-48c1-ab00-cb620951260a |  | note | FREQUENCY: Each lot, divided into four approx. equal sub-lots
label | 2914e65b-24eb-45f1-87e5-0454ec1e7b5e |  | note | ACCEPTANCE CRITERIA: The UCS strength of each test at 28-days shall be between 3.5 and 8.0 MPa.
label | b6bc1b45-b362-4a9f-91e8-95f3e1e04c67 |  | note | REFERENCE DOCUMENTS: Spec cl 5.10 & FHPL-NCR-000021
label | 08d70c6c-a108-4d43-abd0-064804120c88 |  | note | INSPECTION/TEST METHOD: Testing
label | e968c3a0-61a8-4d37-825f-f16e0159d52f |  | note | RECORD OF CONFORMITY: This signed ITP & 28-Day Test Results
label | 0d067d53-a045-4825-9ba3-71f37fc05a62 |  | note | TP
label | c48e198d-76d5-4f7a-8a5a-20ba5e277ff2 |  | note | RESPONSIBILITY: FH
text | 3ca4b692-f5b3-485d-aaa6-faac282f39bd |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Survey As-Built Report
label | 651448ce-fc6d-40e0-975b-4662ddaee614 |  | note | FREQUENCY: Each Lot
label | 77610b5c-a7d8-45ab-aea0-1406c30751c5 |  | note | ACCEPTANCE CRITERIA: The surface level at the top of the final CMCR layer shall not deviate from design level at the specified points by +0mm or -10mm. The layer thickness report is not required where surface level conforms to specified limits. Where more than 1 layer of CMCR is being placed (PT5, PT10, Transition Pavement etc.), survey reports not required for intermediate layers of CMCR.
label | da1f8cb0-6207-4ea2-91f6-439c2a8057fb |  | note | REFERENCE DOCUMENTS: Spec cl 5.10 & FHPL-RFI-000431
label | a0b5d1b8-ba0f-47c4-93ac-28183729da63 |  | note | INSPECTION/TEST METHOD: Testing
label | 03869ea2-8324-48a4-b911-5471cef57d71 |  | note | RECORD OF CONFORMITY: This Signed ITP & Survey Report
label | 623d10dd-be91-4078-a414-9a39ae6bc16e |  | note | SCP
label | 5c382416-4043-4ea6-a678-453bbbf53ad7 |  | note | RESPONSIBILITY: FH
text | 3e8a959d-e84f-4da4-b6b7-2747bb479865 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Production Test Results
label | 904ca1d1-7e78-4d5f-ac35-15e55fd2d15f |  | note | FREQUENCY: Each lot
label | 2f8741bf-f4c2-4078-bb69-f135befef62b |  | note | ACCEPTANCE CRITERIA: Production Testing for grading and plasticity of Class 1 material to conform to VicRoads Section 304 & 812. Post-Compaction Atterberg and PSD Testing not required for bound material. Refer to Item 2.3 above for density testing of each CMCR lot.
label | f44e300d-e6bd-42cd-b80d-cb402db99058 |  | note | REFERENCE DOCUMENTS: Spec Cl 5.10 & VR Section 304 & 812
label | c52e2538-bc83-4882-8c4a-8c162c69a1da |  | note | INSPECTION/TEST METHOD: Testing
label | 7717c9f1-edaf-48da-9c17-6286cdaab40f |  | note | RECORD OF CONFORMITY: This Signed ITP & Test Results
label | cd1b0d34-9b0a-4883-86ec-c47228bfecc5 |  | note | TP
label | 6d003608-5623-4629-84bd-ab08c87f8e43 |  | note | RESPONSIBILITY: FH
text | aaa5e848-d328-4d4b-990b-f107f038c061 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 Failure to meet 7 day UCS
label | 5e2b25c1-70f1-4714-98c4-deebd2a3f868 |  | note | FREQUENCY: Each lot
label | f1c5fd33-d46a-4dcb-9ec5-901be289c4d6 |  | note | ACCEPTANCE CRITERIA: The 7 day (normal curing) strength is to be compared to the strengths determined during the mix designs. Where the strength is less than 2.5MPa, a hold point is to be installed. The Principal’s Representative is to be advised of the necessary steps to be taken to ensure that the 7 day strength criteria is meet.
label | 3b4e6007-5804-4402-9a38-7386e14387cb |  | note | REFERENCE DOCUMENTS: Spec cl 5.9.7 & FHPL-TRANSMIT-000709
label | 28cb8fd1-50ac-43b9-b111-f0d24c0b6f48 |  | note | INSPECTION/TEST METHOD: Testing
label | b9956448-75d4-4ec1-b1e1-f6e7a668c8e3 |  | note | RECORD OF CONFORMITY:Test result register
label | 3185f741-8797-4b8d-b239-6fd48c89148c |  | note | HP
label | 9721007a-ff23-4cc5-92d2-5e276ac74dfe |  | note | RESPONSIBILITY: FH Jacobs
text | 651cde44-a745-47ed-9103-1105ba5d6490 |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 3.5 Non-Conforming CMCR
label | a2b6e450-0c27-4b45-8bdb-d47d0c2ec30b |  | note | FREQUENCY: Each lot
label | 08db04b2-899b-4814-a05a-7318d18a4475 |  | note | ACCEPTANCE CRITERIA: All CMCR that does not meet all the specified requirements will be rejected. Materials to be removed full depth of the layer and reinstated, unless otherwise approved through the NCR process.
label | c37cdb83-d761-46df-8802-3c611e9523bb |  | note | REFERENCE DOCUMENTS: Spec cl. 5.11
label | 37b1e50b-081a-4e2f-a257-c6dac4c71386 |  | note | INSPECTION/TEST METHOD: Verify
label | ac511bd5-2266-4724-bf5e-343823b5d03c |  | note | RECORD OF CONFORMITY: This signed ITP
label | 1d9195c9-4415-4972-9416-e437c784db69 |  | note | HP*
label | 76483078-cce5-489a-a36e-86a8574b2fe3 |  | note | RESPONSIBILITY: FH
text | 4805c65b-40be-457d-a61a-05029e2caea0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | FULTON HOGAN FINAL INSPECTION - On behalf of Fulton Hogan, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract
text | edf9e197-0c8c-4796-ac6b-0be98c3a5da5 |  | textbox | Name:
text | 07afdf4b-ffeb-4ef4-9b4f-b699dc8606ab |  | textbox | Position:
checklist-sectioned |  |  | checklist | ITP 032 - Hot Mix Asphalt Production & Placement – Airfield Asphalt | itp |  |  |  | Yes | ITP 032 - Hot Mix Asphalt Production & Placement – Airfield Asphalt | 2299e710-45bc-4896-a73f-4be2c06cf287
checkpoint-group |  |  | section | ITP 032 - Hot Mix Asphalt Production & Placement – Airfield Asphalt
checkpoint-status |  |  | checkpoint | 1.1 Mixing Plant Calibration Charts
label | 57b24dc2-a014-40e7-8505-db71b89ed476 |  | note | FREQUENCY: Prior to works
label | 584c6343-8ba6-4014-8e68-7d1e431764b4 |  | note | ACCEPTANCE CRITERIA: The Contractor shall provide a report on the calibration of mixing plants as specified in at least five working days prior to the commencement of the work.
label | 5be437a4-3f78-4dc2-8e9b-57acdfbacdf1 |  | note | REFERENCE DOCUMENTS: 7.7.2
label | ca8cc407-4ce4-41fb-b0ff-ab115737fe58 |  | note | INSPECTION/TEST METHOD: Calibration Certificate
label | 38fd150a-ac41-4013-afa4-6e93c05a4b2a |  | note | HP
label | 81593be3-120d-4ccd-ba23-03c9f5cd482f |  | note | RESPONSIBILITY: Plant Supervisor
text | 51c00bb7-230d-4565-add8-4aa2e2ffc47f |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 2.1 Asphalt mix temperature
label | 0aae56de-1175-4039-8d4d-f9f53bd7395d |  | note | FREQUENCY: Once per sample obtained as per Item 3.2 of this document
label | a203c93f-7ee5-4a45-9f4c-087e9c97559d |  | note | ACCEPTANCE CRITERIA: Probe immersion thermometer inserted at least 150mm below the surface of asphalt in loaded truck to be not more than 175oC.
label | 92f997a6-a32f-40dc-8f45-f736ef93ce3c |  | note | REFERENCE DOCUMENTS: 7.7
label | ae2ad9ae-0b53-4118-9179-4e927cbad49b |  | note | INSPECTION/TEST METHOD: Inspection
label | 019cb077-060c-4e8c-b54b-16d20769f9af |  | note | IP
label | 9acad6ee-9641-470d-84fa-0709df4343fc |  | note | RESPONSIBILITY: Laboratory Technician / Plant Operator
text | 5177798e-58f1-4b60-a2a4-6c69ca0bd8f1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Mixing efficiency
label | 09981351-c5a5-489e-a684-8db8431e5437 |  | note | FREQUENCY: Every truck
label | cfee0446-c0ae-4eb5-9662-d8975531b9fe |  | note | ACCEPTANCE CRITERIA: All coarse aggregate must be fully coated with bitumen; mix to have no visible segregation and no obvious presence of excess moisture.
label | c0a03bc6-fcb0-4c3d-b83a-3802678ea0f9 |  | note | REFERENCE DOCUMENTS: 7.8.1
label | b73ca59c-ceab-4272-9c6d-69ea7251838b |  | note | INSPECTION/TEST METHOD: Inspection
label | 964c7ba8-9b05-4693-955a-f8a2e8af43f5 |  | note | HP
label | 46f48453-0042-4a16-8751-33f4641bc223 |  | note | RESPONSIBILITY: Laboratory Technician / Plant Operator
text | e418bf50-51c9-422b-8851-1ff76c2377ad |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 3.1 Commencement & Attendance of Production Mix Trial
label | 9df285f4-3601-4da2-9dca-ae3c584e4c8a |  | note | FREQUENCY: Prior to commencement
label | b00be134-96b1-44ad-84e0-e8cd8e8e61ac |  | note | ACCEPTANCE CRITERIA: Notification prior to commencement of production mix trial and Attendance of production trial
label | 73201f8b-70b4-4f1f-b712-15f145055a10 |  | note | REFERENCE DOCUMENTS: FH Internal & 7.7.1
label | 83382096-f46e-42c4-bf38-9fb56198f3ff |  | note | INSPECTION/TEST METHOD: Notification
label | a6755873-94f3-4144-9988-bf94e6f365c4 |  | note | WP
label | 9227d0c3-8aa3-4704-8b5d-ffd0400476e5 |  | note | RESPONSIBILITY: Production Manager / Engineer
text | 9a4d965d-45e5-429c-9934-4df2f19364a0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Sampling
label | 219f4d65-b32d-476d-89a1-edd3678e65b6 |  | note | FREQUENCY: 3 samples taken at approximately the quarter points in the asphalt production trial of not less than 100 tonnes
label | beddbe7f-72fd-4465-81b9-52d07a6b1fb4 |  | note | ACCEPTANCE CRITERIA: Mix to be sampled from asphalt delivery trucks.
label | 88c599e1-cc6d-416b-863d-ae9b455f77ba |  | note | REFERENCE DOCUMENTS: 7.7
label | 74a40697-cd08-41c2-91a8-2764d707d568 |  | note | INSPECTION/TEST METHOD: AS 2891.1.1
label | 197a8360-bc31-4256-9699-4e7a14d289d4 |  | note | TP
label | 9beee8d8-5485-4b2b-8e9d-6e22a9306970 |  | note | RESPONSIBILITY: Laboratory Technician
text | aacfb6a0-7376-4816-8b35-2c324ba56760 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Moisture content
label | 6522e147-c6c7-4343-98a5-43fe10999b02 |  | note | FREQUENCY: Once per sample obtained as per Item 3.2 of this document
label | 4316485a-af80-4491-8e65-0453fe6d9a18 |  | note | ACCEPTANCE CRITERIA: Moisture content of asphalt to be <0.5%.
label | 4e3aebf8-d447-4513-a338-427390a114fe |  | note | REFERENCE DOCUMENTS: FH Internal
label | 753ed247-ce7e-46e1-aea8-05e921d7d809 |  | note | INSPECTION/TEST METHOD: RC 211.01
label | 2080fbcb-c2bc-43b7-9573-375c8400b3ec |  | note | TP
label | 2e837095-13f7-4132-b345-77317714db56 |  | note | RESPONSIBILITY: Laboratory Technician
text | 1bd550a9-525b-4574-adc2-0a9bb07999db |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 Combined aggregate grading
label | 252a47fc-e5bb-4ff8-ab85-2fca1749e015 |  | note | FREQUENCY: Once per sample per Item 3.2 of this document
label | 18000959-6a74-4b08-b4bd-d24e6cf88b45 |  | note | ACCEPTANCE CRITERIA: Grading to be within the following tolerances of the mix design target:
label | d57946a5-b0e4-47d4-ba0f-8c8a20787ec2 |  | note | FH NCR Procedure to be adopted when grading falls outside tolerances.
label | 55c31a44-05b9-4af2-b3ba-7ac0079891de |  | note | REFERENCE DOCUMENTS: 7.8.2 & Table 7-9
label | 55427cbe-1b9a-44c2-a00a-f65709f2eb91 |  | note | INSPECTION/TEST METHOD: AS 2891.3.3
label | 55745e13-eb85-49ad-99d3-fb47b4963872 |  | note | TP
label | c3ff1a2e-021d-4fe1-898c-6c0eba6fd8f9 |  | note | RESPONSIBILITY: Laboratory Technician
text | 5e5451e4-1b9b-47a7-95ef-19f4e70434e0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.5 Binder content
label | 814d4940-0037-4be7-8166-c1f0aa56bbfe |  | note | FREQUENCY: Once per sample obtained as per Item 3.2 of this document
label | a973ed11-2e7e-4608-93d1-df88a925cacb |  | note | ACCEPTANCE CRITERIA: Bitumen content to be within -0.3% and +0.3% from asphalt mixdesignbindercontenttarget. FHNCRProceduretobe adopted when grading falls outside tolerances.
label | cbc7157b-1d42-4292-a706-c031e8374eb4 |  | note | REFERENCE DOCUMENTS: 7.8.2 & Table 7-9
label | 1baf61fe-3226-4f01-82e5-a84a88608bda |  | note | INSPECTION/TEST METHOD: AS 2891.3.3
label | 9efa476c-1c7c-429f-ac84-69261f38a692 |  | note | TP
label | b98a18fc-c0a8-48ab-87e0-26dc3081b0d8 |  | note | RESPONSIBILITY: Laboratory Technician
text | 5d31134b-2b91-4fe4-9637-ce032a03202c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.6 Maximum density
label | cc9889e9-3b2e-46c3-8830-1d1ff399fe3b |  | note | FREQUENCY: Once per sample obtained as per Item 3.2 of this document
label | 5a7ac7ab-fa7a-439e-846b-c74b8c62dc09 |  | note | ACCEPTANCE CRITERIA: Average maximum density for each production shift to be reported.
label | 1dd88bcb-b619-4a27-bd31-fcdf8f780a77 |  | note | REFERENCE DOCUMENTS: 7.8.2 & Table 7-8
label | 460e59e0-4b54-4f63-be42-a19a4a506ffc |  | note | INSPECTION/TEST METHOD: AS 2891.7.1
label | f562aa11-3ebd-4dd1-838f-306e3cdfc7dd |  | note | TP
label | 08e31638-a7cd-4242-b0ef-3f420c831f84 |  | note | RESPONSIBILITY: Laboratory Technician
text | dfa06a3c-ae19-4dea-8de3-fa27ef7110c0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.7 Bulk density
label | 8d342792-0cc4-4bf7-b4da-593fa30f36bc |  | note | FREQUENCY: Once per sample obtained as per Item 3.2 of this document
label | 893157a3-4181-48f7-8a2a-358c21dbd559 |  | note | ACCEPTANCE CRITERIA: Two Marshall blocks to be produced using automatic hammers (75 blow compaction) and the results averaged. Compaction temperature is to be within the range of 165oC to 175oC. Result to be reported.
label | 39287b1b-af4e-4c0d-9461-3a125bd8ad59 |  | note | REFERENCE DOCUMENTS: 7.8.2 & Table 7-8
label | 4bbdb52c-0f16-4c84-9605-1e471646abc2 |  | note | INSPECTION/TEST METHOD: AAA MT 001-2007
label | 0f117e80-6958-4a67-ba73-39691d4d3598 |  | note | TP
label | f75dde50-d9df-4efd-bf3f-ddfc9ad9aa41 |  | note | RESPONSIBILITY: Laboratory Technician
text | cb9e027e-5353-4124-b30f-f35590378457 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.8 Voids in mineral filler (VMA)
label | 3fe6cf31-791f-444e-a3cd-97ac26949c39 |  | note | FREQUENCY: Once per sample obtained as per Item 3.2 of this document
label | 952ed423-cbad-4af1-b466-7d65400e887d |  | note | ACCEPTANCE CRITERIA: 15% minimum
label | 9d79671a-a68a-47c1-9f1a-95fb380cc7ca |  | note | REFERENCE DOCUMENTS: 7.8.2 & Table 7-8
label | 1cfc7de6-0358-4835-b0ae-a16c1040907f |  | note | INSPECTION/TEST METHOD: AAA MT 001-2007
label | f2775f3f-f49c-4e1e-9b25-e6d24fc7a2fc |  | note | TP
label | a761a068-6afa-47f5-8df8-afc9aaf02909 |  | note | RESPONSIBILITY: Laboratory Technician
text | d06c747a-eca1-4985-9a02-f7e78c9ab7e3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.9 Voids filled with binder (VFB)
label | c8e598f5-53e8-4f66-825b-8e352de54bba |  | note | FREQUENCY: Once per sample obtained as per Item 3.2 of this document
label | 4063b934-126e-4a4c-b87c-c3b293d9c302 |  | note | ACCEPTANCE CRITERIA: 70% minimum to 80% maximum
label | 1adf9eed-6041-4222-959c-40ce263b2c95 |  | note | REFERENCE DOCUMENTS: 7.8.2 & Table 7-8
label | 06cd7db6-24c1-4acd-8294-05b4d5c92722 |  | note | INSPECTION/TEST METHOD: AAA MT 001-2007
label | 7c67ce67-a26d-40b8-bfa2-7630f9cc80b5 |  | note | TP
label | 23e19fb7-082a-4cef-bbbd-536b5cd232dd |  | note | RESPONSIBILITY: Laboratory Technician
text | 179049fa-5ede-40eb-80e0-886cfb7e5e15 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.10 Air voids
label | 56c2002e-39a8-493e-b4e3-68650a46d85f |  | note | FREQUENCY: Once per sample obtained as per Item 3.2 of this document
label | 21bd655e-f6df-4ff5-b7e0-5416fac251bf |  | note | ACCEPTANCE CRITERIA: Two Marshall blocks to be produced using automatic hammers (75 blow compaction) and the results averaged. Compaction temperature is to be within the range of 165oC to 175oC. Air voids to be within ±1.5 of design – approved by Jacobs
label | ecd20304-bc53-43ce-9738-18962b0aac71 |  | note | REFERENCE DOCUMENTS: 7.8.2 & Table 7-8
label | fcf78be3-9425-4030-a6a5-0ba8d9d4159e |  | note | INSPECTION/TEST METHOD: AAA MT 001-2007
label | 52d4bbea-c33e-45a7-8cda-478b3c83d0c0 |  | note | TP
label | f5544a25-d3d9-4a22-b38a-bbe6b15e3c35 |  | note | RESPONSIBILITY: Laboratory Technician
text | dee1d8c9-5607-4a6f-8247-c8263bcdb67c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.11 Marshall stability
label | 56fe1521-16bb-42d6-8f92-f946ef822adf |  | note | FREQUENCY: Once per sample obtained as per Item 3.2 of this document
label | 8871cd6e-14d6-44b3-a768-da1916b1d30b |  | note | ACCEPTANCE CRITERIA: Two Marshall blocks to be produced using automatic hammers (75 blow compaction) and the results averaged. Compaction temperature is to be within the range of 165oC to 175oC. Minimum Marshall stability to be 12kN.
label | 4da1d240-ac3e-4b84-b6a1-932d9ccf7efe |  | note | REFERENCE DOCUMENTS: 7.8.2 & Table 7-8
label | 4a4c9d7e-fb4a-4525-9a92-91d095b6b802 |  | note | INSPECTION/TEST METHOD: AAA MT 001-2007
label | 147c848b-87ed-45af-ad1f-5b3c7ac41cb7 |  | note | TP
label | 534c43b9-761c-4f2e-b10b-62facbe0cace |  | note | RESPONSIBILITY: Laboratory Technician
text | 4d81c15a-4188-4513-ba7f-943728e31745 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.12 Marshall flow
label | 17f00ed0-83dc-4086-a9e1-e0ab1096618e |  | note | FREQUENCY: Once per sample obtained as per Item 3.2 of this document
label | 5dedd404-9386-4351-a0a6-1fe163a2be40 |  | note | ACCEPTANCE CRITERIA: Two Marshall blocks to be produced using automatic hammers (75 blow compaction) and the results averaged. Compaction temperature is to be within the range of 165oC to 175oC. Report flow result. Report stability vs flow chart.
label | 77939c77-5320-4525-b754-609887532ab8 |  | note | REFERENCE DOCUMENTS: 7.8.2 & Table 7-8
label | ea485351-6534-496d-b5d5-07f00d864384 |  | note | INSPECTION/TEST METHOD: AAA MT 001-2007
label | 321c3edf-7592-4e78-a9ff-064709844245 |  | note | TP
label | c0bd64c7-32b1-4363-a265-59665c30fb76 |  | note | RESPONSIBILITY: Laboratory Technician
text | cb2fcd0c-35b8-4c3d-be6b-49f73636ac1c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.1 Construction Trial
label | 94f60404-8db9-4d23-9344-fec7061b3840 |  | note | FREQUENCY: Prior to Asphalt Paving
label | 127ba9cb-74f8-4ee7-98a9-2affaaa20215 |  | note | ACCEPTANCE CRITERIA: 14 days prior to asphalt paving is due to commence, all proposed mixing and paving plant and personnel details are to be subjected (i.e. available and used as part of the trial) to the principal
label | c23dc245-8cb7-474d-afbd-cf4df111bf1a |  | note | REFERENCE DOCUMENTS: 7.7.1
label | edbcda00-3527-4504-815b-609eef87c393 |  | note | INSPECTION/TEST METHOD: Verify
label | 779d13d6-bc75-4ad1-8b9c-c6c37aa3261a |  | note | WP
label | 1f8daf27-c66b-4429-a68e-e728bd259d55 |  | note | RESPONSIBILITY: Project Manager / Engineer
text | fcc440f0-c897-4ec1-b109-8fd75786dfe7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Trial Section
label | 8dca7b53-8a05-459f-8c26-0f4ca44cb229 |  | note | FREQUENCY: Once
label | ead2871d-9271-4b61-a2a2-9b9bdc25da99 |  | note | ACCEPTANCE CRITERIA: The construction trial shall comprise at least two adjacent lanes nominally 60 mm thick, each 3.75 m wide and at least 100 m long.
label | 4f76d0b9-7f7c-4e31-911b-292789b573a8 |  | note | REFERENCE DOCUMENTS: 7.7
label | 084fdad5-1319-48c8-b131-26b28877ddd8 |  | note | INSPECTION/TEST METHOD: Visual
label | 35ab200d-3ba8-409b-a619-e4ad998de75b |  | note | HP
label | 4ef5a497-e819-4d57-a93d-ce04c1178325 |  | note | RESPONSIBILITY: Project Manager / Engineer
text | 269371c7-c586-41d2-aef5-0adceb2d5dd5 |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 4.3 Nuclear density gauge calibration
label | e1813d67-1eb8-48d7-ac82-a6ad9620fe9f |  | note | FREQUENCY: Once during construction trial
label | 6e872640-18cd-4fbd-afe4-05b29ad9c47e |  | note | ACCEPTANCE CRITERIA: Nuclear density testing to be conducted at 12 locations away from paving joints and 4 locations on longitudinal joints, as agreed with the Principal’s Representative. The cores must be cut from the asphalt surface at the tested locations, and determine the core density in accordance with AS 2891.9.2 when not on a joint, and in accordance with AS 2891.9.1 when on a joint.
label | b66d8edf-6b12-4a18-a0a3-d4ba474d78c1 |  | note | REFERENCE DOCUMENTS: 7.7.3
label | 9a7978c7-47ae-4c96-8c33-2454c7d359a2 |  | note | INSPECTION/TEST METHOD: RC 316.10, AS 2891.9.1, 9.2, 14.2
label | 81fc13e3-92be-4849-b50d-720929f7f39e |  | note | TP
label | 568aa6b0-fa39-4837-ad9c-1dc260f0cc50 |  | note | RESPONSIBILITY: Laboratory Technician
text | 4514f46a-8cf6-408e-bef0-f00e91aee9f2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 Lot Characteristic Air Voids Assessment
label | ba479cfc-8a4b-4ab4-9e42-e637d01dd429 |  | note | FREQUENCY: Once during construction trial on cores taken in item 4.3
label | e15cd92f-3a64-4a2f-bd30-03f85f1d8f1e |  | note | ACCEPTANCE CRITERIA: Air voids to be calculated using maximum density determined construction trial on cores taken in item 4.3 in Item 3.6. Air voids to be within the following range:
label | 0107202c-a332-4a17-be8c-811dbda0f7fd |  | note | Upper characteristic value of in situ air voids not located on a joint - Maximum 7.0%
label | 63c35ce2-de88-4332-bbd9-e1804fcf1f5a |  | note | Lower characteristic value of in situ air voids not located on a joint - Minimum 3.0%
label | 8fc33e06-0854-4992-9d4b-cea4e1b86990 |  | note | Average value of in situ air voids located on joints - Maximum 7.0%
label | 536d9bfb-f1f9-4bdd-beb0-4f4baec18ddf |  | note | FH will follow specification tolerances on Air voids and if any results fall out of tolerance, FH raise NCR according to FH NCR procedure and principal to confirm the acceptance.
label | 5c4fd0d6-a29f-458b-8ac2-8da7ac247be9 |  | note | REFERENCE DOCUMENTS: 7.11.8.6
label | 4d7f9288-fb2a-488b-ba41-341466f68a42 |  | note | INSPECTION/TEST METHOD: AS 2891.14.5 &
label | 0cfc5d43-1cb8-4473-9cff-3bc61a0d1e63 |  | note | TP
label | a4f2e9fa-3e76-4835-acee-0d7f26dc25b7 |  | note | RESPONSIBILITY: Laboratory Technician
text | 1d53ae2b-a977-486a-bd32-2fafa009033b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 Reference Section
label | 929f3c83-4155-493e-85fe-c4fd24fedea5 |  | note | FREQUENCY: After Construction Trial
label | c28af0c3-170a-42db-8092-a9e3070458b6 |  | note | ACCEPTANCE CRITERIA: A reference section from the asphalt construction trial shall be selected that has a suitable surface finish such that any suspect surface finish produced during the Works can be referred back to this section to establish whether there is a non-conformance and the surface finish is defective.
label | 542dc751-35fb-4dae-af3b-ede1baf0164d |  | note | REFERENCE DOCUMENTS: 7.7.3
label | f451f88f-eada-4cb5-9689-a87ce5cc3f35 |  | note | INSPECTION/TEST METHOD: Visual
label | ba17ba3d-99d0-426d-88ac-2bab5fb61599 |  | note | HP
label | ac356865-2a24-4e95-850d-b5bdd830ada7 |  | note | RESPONSIBILITY: Engineer
text | e0610e32-73bc-4aea-96c1-a81c5e09a4fb |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 5.1 Production and Construction Trial Reports
label | 7767424f-39a9-435b-b91d-0b9bea004d97 |  | note | FREQUENCY: After construction Trial
label | b325c2fe-0b93-45bb-9845-4f7113652413 |  | note | ACCEPTANCE CRITERIA: Within seven days of the production and construction trials report is to be submitted to the principal’s representative
label | b21e4e29-01e4-4afe-ab78-f216842d8f8e |  | note | REFERENCE DOCUMENTS: 7.7.4
label | 7c8a8d4e-fe27-4872-ae54-efa2f76243fc |  | note | INSPECTION/TEST METHOD: Verify
label | 96259fb0-8001-4c17-9093-f5cfdebda4d8 |  | note | HP
label | eb1ad71b-2e45-4520-9a52-a168734e22b5 |  | note | RESPONSIBILITY: Project Manager / Engineer
text | 7a9e30b3-ef14-45c2-9eb5-87a15241a375 |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | Final Inspection
label | 1fad1910-5398-4224-9185-018d01ce5ec3 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 4c945303-4da4-446f-bbf6-576df80c1a1a |  | textbox | Print Name:
text | 81c91826-090f-4ce9-9422-da2f21a6fec0 |  | textbox | Position:
text | 34811486-fb2c-4514-a1a7-cca7dc9153ab |  | textbox | Date:
checklist-sectioned |  |  | checklist | ITP 018 - Watermain Works | itp |  |  |  | Yes | ITP 018 - Watermain Works | 2c178b14-7b54-48d4-9c90-8d2debe9ce93
checkpoint-group |  |  | section | ITP 018 - Watermain Works
checkpoint-status |  |  | checkpoint | 1.1 Checking Documentation and Permits
label | 167cccbc-cbd3-41b9-86bc-d8ade4465aec |  | note | FREQUENCY: Prior to commencing any activity
label | 35e625dd-9e82-417d-8101-c5cc09295c9d |  | note | ACCEPTANCE CRITERIA: Ensure all workers are using the correct set of drawings prior to starting works each day.
label | b16f6cec-b3cf-407d-87d7-de83a5e31fe4 |  | note | REFERENCE DOCUMENTS: IFC Drawings / Excavation permits
label | f01d97c9-153e-492f-b2e9-cbcd40ee095d |  | note | INSPECTION/TEST METHOD: Review
label | 9055a5e4-9835-422b-84fb-be2b841797cd |  | note | RECORD OF CONFORMITY: Up to date drawing sets & ITP
label | 6673ff40-dad7-4212-adf4-52c971f00369 |  | note | HP*
label | e405148e-e4fd-47c6-be6d-96c8ddccff23 |  | note | RESPONSIBILITY: Project Engineer
text | 1fdf2640-1bb1-43f6-9d31-a9fed5b1ff03 |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 1.2 Implementation of all measures and controls
label | 7abf6a1f-dbbc-41cb-9c36-90d60a74002e |  | note | FREQUENCY: Prior to commencing any activity
label | 4b855079-33cb-43ae-b270-b0884fa991ba |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented including EMP, TMP, SWMS & WP.
label | 39aaa53f-7abf-49fb-b8bd-53c9bcd3d034 |  | note | REFERENCE DOCUMENTS: EMP, TMP, SWMS & WP
label | 90604302-cade-4601-95ed-1091e1b2259a |  | note | INSPECTION/TEST METHOD: Review
label | 960242cc-a7cc-45aa-9d36-2f791c00ec19 |  | note | RECORD OF CONFORMITY: ITP
label | fbaa73b3-51ef-4742-a765-1120cfc4716c |  | note | HP*
label | dc3d5f7d-aed6-4f7b-883b-eff0e661ce1d |  | note | RESPONSIBILITY: Project Engineer/ Site Supervisor
text | d3c1172b-6674-4e57-b211-1671dfd747f3 |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 1.3 Definition of the work area (survey)
label | 4313853c-2ecb-4b6f-9b44-02b12b94aa66 |  | note | FREQUENCY: Prior to commencing any activity
label | a43a4dcc-6a22-4caa-8b67-430f560b66ac |  | note | ACCEPTANCE CRITERIA: Work area has been cleared and surveyed. Limits of excavation clearly marked.
label | ede7bf71-8ed3-45df-b8d7-ca5e069e89ff |  | note | REFERENCE DOCUMENTS: FC Drawings / Specification
label | c8727a51-8041-4813-b667-a089c4f90453 |  | note | INSPECTION/TEST METHOD: Verify
label | b3cecf9a-0950-46b8-a1b2-55d39d640fe9 |  | note | RECORD OF CONFORMITY: ITP
label | ce7294c8-8d2c-46c7-bc50-81ff2481a850 |  | note | HP*
label | a826e666-572e-4a5e-8e4d-a9df9414ad32 |  | note | RESPONSIBILITY: Surveyor/Site Supervisor
text | 6aa04f7f-ef0e-4b2a-a069-a4d932105c2d |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 1.4 Service Locations
label | ff60a420-9e8b-4250-a3d9-43b0035d468f |  | note | FREQUENCY: Prior to commencing any activity
label | c9bc2780-b71e-4e76-bd2c-8e0456fbced3 |  | note | ACCEPTANCE CRITERIA: Where works are in the vicinity of existing services, the services are to be located and exposed/ proved and additional care shall be taken when excavating.
label | e5d342ed-9614-46a8-8b7d-c7dd9e147195 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP0002¦1, cl9.1.1
label | 97159615-5448-4549-b866-a21893a04e91 |  | note | INSPECTION/TEST METHOD: Verify/ITP
label | 156211c0-f9c0-4e5e-b3f3-95cfadea3a4d |  | note | RECORD OF CONFORMITY: Survey report of service locations and depths
label | 73f36a9b-f5be-4373-ad55-683957e2496f |  | note | IP/SCP
label | f2cd914f-867c-45f5-aa6f-3bb066edb2b3 |  | note | RESPONSIBILITY:Project Engineer/ Surveyor/ Foreman
text | 63bf8fcf-7a22-4db1-a42e-1c860189a94c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.5 Confirmation of existing Watermain details
label | b97bbb3b-2252-4bc7-b858-65a574824cc6 |  | note | FREQUENCY: Prior to commencement
label | 1b7c3e3a-15ce-44a5-a01f-b76452a2e1bd |  | note | ACCEPTANCE CRITERIA: Confirmation of site of existing watermain details including pipe diameter, pipe material, pipe alignment, extent of the existing concrete sleeve and depth at connections. If there are any discrepancies report them to the Principal’s Representative for instruction.
label | c8e5321f-2e1b-44e0-bc07-3c52635cce0a |  | note | REFERENCE DOCUMENTS: IFC Drawings
label | 4dd6f2b8-8ee7-45f1-87a9-73f3ccb30dba |  | note | INSPECTION/TEST METHOD: Verify / ITP
label | 82c8f12e-e0ab-4700-87c5-c5bcfd69466e |  | note | RECORD OF CONFORMITY: ITP
label | 081419a5-7965-45d7-9262-fcc1da80a67b |  | note | IP
label | a4c4f99b-3632-49f6-9cd5-d96b139bdf5a |  | note | RESPONSIBILITY: Project Engineer
text | 50aeafa8-6dda-40de-b260-a588ef97abf6 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 Polyethylene (PE) pipes
label | ae9ae5fa-2790-4d55-a712-e4403d62993f |  | note | FREQUENCY: Prior to procurement
label | 2178cb1b-feb0-4fb7-9a8c-9a7569f2ded1 |  | note | ACCEPTANCE CRITERIA: Polyethylene (PE) Pipes for pressure applications shall be of the class PN16 SDR11 are to be manufactured and tested in accordance with AS 4130: 2009, ‘Polyethylene pipes for pressure appliances’. Fittings for PE pipes shall comply with AS 4129.
label | 570ecb22-9633-4e4f-87c2-3475812a0ef5 |  | note | ACCEPTANCE CRITERIA: PE pipes shall comply with WSA 207:2002, ‘Polyethylene Pipes for Pressure Application – Water Supply and Sewerage’ and the following requirements:
label | 257cd6e5-a0b9-4db6-a75b-a5bd828d86cd |  | note | ACCEPTANCE CRITERIA: a) PE pipe shall be PE 100 Series 1 complying with AS/NZ 4130:2009/Amdt 1:2009.
label | f1e0d512-e8ee-43ae-96fb-d87d489828c9 |  | note | ACCEPTANCE CRITERIA: b) Drinking water pipes shall be solid blue or sheathed blue or black with blue stripes.
label | e985d544-63c6-4a7c-b080-fa53755996db |  | note | ACCEPTANCE CRITERIA: c) Unless shown otherwise on the drawings, PE pipes for pressure applications shall have fully welded joints (No electrofusion couplers are permitted)
label | 7f7023db-0217-4e0b-ad52-b016e1502641 |  | note | REFERENCE DOCUMENTS: CP14038- AIR-DET-PM-SP0002¦1, cl. 9.2.1.1, AS4130, AS4129, WSA207, AS4087
label | bc080bf0-0da4-4f9e-bd0f-0b1e836ed006 |  | note | INSPECTION/TEST METHOD: Verify /manufacture’s certificate
label | 4e523498-516c-4928-ab58-a52b1add2788 |  | note | RECORD OF CONFORMITY: Conformance/Technical Data Sheet
label | c9d4585d-bd19-467f-a724-81136826a0f1 |  | note | IP
label | 1c9bb17d-04f5-4d7b-b8ea-27f6c1e66b49 |  | note | RESPONSIBILITY: Project Engineer
text | 70279eb6-e699-40e0-b1b4-db915f724469 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Ductile Iron Cement Lined (DICL) Material
label | e1ec9b46-6b81-442a-8ffd-4b24d0bb1ea6 |  | note | FREQUENCY: Prior to procurement
label | 9d2056c4-9ed6-4ca9-a39f-1d166cd85119 |  | note | ACCEPTANCE CRITERIA: All DICL pipes and fittings to be manufactured to AS2280 ‘Ductile Iron Pressure Pipes and Fittings’ Pressure class PN20.
label | 1cf11851-308f-4935-9dd2-2fbc1ea59065 |  | note | ACCEPTANCE CRITERIA: External protective coating for DICL pipes and fitting shall be thermal bonded polymeric coating in accordance with AS4158.
label | 1839db81-b933-40c9-af57-8d17fcf4ff52 |  | note | ACCEPTANCE CRITERIA: Joints for DICL pipes and fittings to be flanged joints to AS4087 PN16.
label | 30317c09-60a8-406c-b3e9-6a8882a81dd7 |  | note | ACCEPTANCE CRITERIA: Internal bore of pipes and fittings to be cement mortar lined and dimensions comply with AS2280. The cement mortar lining shall be sealed with pipe manufacturer approved seal coating for pipes.
label | e9063484-53c4-423d-b690-1d4c3534b002 |  | note | ACCEPTANCE CRITERIA: Submit test certificates including metal composition tests.
label | 97c1387b-388d-478e-96f0-8c12093e317a |  | note | REFERENCE DOCUMENTS: CP14038- AIR_DET-PM-SP0002¦1,cl.9.2.1.2 , AS2280 , AS4158 , AS4087
label | ca687f34-2337-431c-96e6-e588f25f87c0 |  | note | INSPECTION/TEST METHOD: Verify and manufacture’s certificate
label | 3a238fd8-6ca7-4edb-a567-75d5e0dcdfd8 |  | note | RECORD OF CONFORMITY: Manufacturer’s certificates and test results including metal composition tests
label | dedcbcda-a528-4f88-b6b5-6150b720057f |  | note | IP
label | 05c16b84-9826-41c5-a63a-5d5838fc72d8 |  | note | RESPONSIBILITY: Project Engineer
text | 12cf6105-4085-49f8-a062-9865e9aaabb8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Reinforced Concrete Pipes (Duct)
label | 6e7f9792-3d0e-4eff-8d24-591dd597a3c0 |  | note | FREQUENCY: Prior to procurement
label | 1b25c9e0-799e-490f-9a3e-19e9dfa0d2eb |  | note | ACCEPTANCE CRITERIA: Pipes supplied for sleeve pipe/ duct under taxiway shall be Class 4 RC pipes unless otherwise specified.
label | fbbdf0b6-a69b-493d-89ab-6daf6817f6bc |  | note | ACCEPTANCE CRITERIA: All concrete pipes to be spigot & socket with rubber rings joint (unless otherwise stated).
label | c8d9d200-fbfa-489b-bb51-b93d272160c5 |  | note | ACCEPTANCE CRITERIA: Deviation at the joints in pipes not to be exceeded the manufacturer’s specification.
label | 865a7322-afe6-401c-89f6-d4c48abe0a05 |  | note | ACCEPTANCE CRITERIA: RCP to comply with AS4058-1992/Amdt 1-1996, butt joined and installed in accordance with AS 3725-1989.
label | 101ee909-865d-4e04-95b5-2aad8e5f3e34 |  | note | REFERENCE DOCUMENTS: CP14038-AIR_DET-PM-SP0002¦1, cl.9.2.1.3, IFC drawings , AS4058, AS3725
label | d4c5d069-6c6f-4b82-82d6-586c4edf1dd7 |  | note | INSPECTION/TEST METHOD: Verify and Technical Data Sheet
label | 77502747-c9ce-4404-8b4f-46ffc2828edb |  | note | RECORD OF CONFORMITY: Technical Data Sheet
label | 748e08d3-bb5f-4892-836d-48eec5ad4edf |  | note | HP*
label | 5077715b-2fa9-4720-b0f3-8bb61e08d5dd |  | note | RESPONSIBILITY: Project Engineer
text | a4ad4445-ddd0-416b-b712-34fe3d55f7c3 |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 2.4 Valves and Fittings
label | 98c83ad4-e6cc-4c68-a171-1c692ba5a0c5 |  | note | FREQUENCY: Prior to construction of pits
label | d015af12-282a-4b34-9b1b-b878cfbb742f |  | note | ACCEPTANCE CRITERIA: All Valves to be anti-clockwise closing, with 316 stainless steel extension spindles with key caps and adequate support
label | af0c266f-6f08-439a-90a5-1f88f3a92e0f |  | note | ACCEPTANCE CRITERIA: Valves and fittings types and details to be in accordance with the details shown on the drawings.
label | 37359ca8-8116-4ef4-b73c-047369c1c69c |  | note | ACCEPTANCE CRITERIA: Sluice/Gate Valves shall be class PN16 comply with AS 2638, complete with flanged ends, dezincification resistant material and resilient sealing.
label | 1a1766df-6d02-4140-88d2-adcd9d3474cb |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP0002¦1, cl.9.2.2 ,IFC drawings , AS2638
label | 1f0eafc1-16a3-4eb8-b995-d09dd97dfb86 |  | note | INSPECTION/TEST METHOD: Verify
label | 57f9fcc1-5dd3-4bc5-9431-2d839fd46f41 |  | note | RECORD OF CONFORMITY: Technical Data sheets
label | 778362dc-aa38-4b6c-8ed8-556866672e86 |  | note | IP
label | 2333c48f-997d-4e28-935e-01b8e1e4f5a4 |  | note | RESPONSIBILITY: Project Engineer
text | 722e3407-12e9-4682-b0d5-18e384d602fb |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 Spring Hydrant
label | c5a4f46a-a16a-499a-8338-513aac60606f |  | note | FREQUENCY: Prior to construction
label | 08e5014c-021b-49b9-bf7b-9e8dacdb1257 |  | note | ACCEPTANCE CRITERIA: Spring hydrant shall be DN100 PN16 rating complying with AS3952 with flange configuration of AS4087 PN16
label | ea4a6ff7-4187-4a90-a4b3-bc5f017db2d5 |  | note | ACCEPTANCE CRITERIA: Spring hydrant shall be connected to DN100 hydrant isolation valve and placed inside pit as shown on drawings.
label | 9f866a43-9c40-430e-a0a2-c4d6b281fbbc |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP0002¦1, cl.9.2.2.2 , AS4087
label | c4d3d5a9-2c81-46b0-8d93-3302186e78a4 |  | note | INSPECTION/TEST METHOD: Verify
label | 6fd4430f-e351-4cc6-bd8a-7d57a5510742 |  | note | RECORD OF CONFORMITY: Technical Data sheet
label | 7363c20b-4749-486e-9b6a-e40792cba93a |  | note | IP
label | 5a64c3bc-ced7-44d1-a943-95729fc89499 |  | note | RESPONSIBILITY: Project Engineer
text | 524bc1c8-b229-42d7-8c91-6ca8503f4406 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.6 Bedding and surround material
label | bb8fd2f0-4255-46fd-8b64-46b54a903060 |  | note | FREQUENCY: Prior to procurement
label | cd70d8b1-41f3-4709-b363-bcd5ac44298a |  | note | ACCEPTANCE CRITERIA: Areas RCP ducts used shall be 5MPa Lean Mix Concrete.
label | 35bd84f7-7e89-472b-a7fa-750ba490f333 |  | note | ACCEPTANCE CRITERIA: Areas typical watermain pipe used shall be 5mm crushed rock.
label | 04c745c3-f707-426b-8962-9ede3cee3909 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP0002¦1,cl.9.2.3.3 , IFC drawings
label | 4c8ad781-5702-4108-8da6-6105618680d3 |  | note | INSPECTION/TEST METHOD: Verify
label | 25bfc9d4-dea9-4165-b195-2ae6754cb4ee |  | note | RECORD OF CONFORMITY: Delivery docket or ITP signed
label | 52613e11-0f94-491a-bb80-7ce55d01ac75 |  | note | IP
label | fbacf8dd-6d31-4add-bb43-0c9b2dba7f25 |  | note | RESPONSIBILITY: Project Engineer
text | c0955895-c429-4598-b4eb-82965bfe42fd |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.7 Backfill material
label | 9b6eb4e8-8a17-4b97-9e3d-8f0746a92851 |  | note | FREQUENCY: Prior to procurement
label | d88add32-d148-4a55-99cb-ae665b089209 |  | note | ACCEPTANCE CRITERIA: Material used under pavement shall be 6% Cement Stabilised sand to design subgrade level.
label | 21d05c1c-55a2-4ab0-a411-272d09f70ba5 |  | note | ACCEPTANCE CRITERIA: Material used for non-taxiway area shall be select fill free from perishable matter and lumps
label | 0a9e5534-f222-4fa7-861b-091fb1c49bdc |  | note | REFERENCE DOCUMENTS: CP14038- AIR-DET-PM-SP0002¦1,cl.9.2.3.3 IFC drawings
label | 349cff54-a01d-4808-b2c9-4dbb907c46ca |  | note | INSPECTION/TEST METHOD: Verify
label | a3e0864f-9b53-4be4-9cf4-57bd0e28b9fc |  | note | RECORD OF CONFORMITY: Delivery docket or ITP signed
label | 016fa9d8-6ea7-40bb-adca-824fdc869729 |  | note | IP
label | cd855758-bf76-4283-87c6-e912c0ae2f4f |  | note | RESPONSIBILITY: Project Engineer
text | 710fb803-d1b6-4382-a364-fae57b6738b0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.1 Survey set out
label | 6daa523b-fcef-4c65-ab15-6f7f46de2ff8 |  | note | FREQUENCY: Prior to construction of each lot
label | 82cee203-453e-4f79-9fc9-288aafc22322 |  | note | ACCEPTANCE CRITERIA: Set out location and levels of pipes and watermain structures and proved underground services
label | ce5bf89a-5793-4d20-97f7-1d6ed533a09d |  | note | REFERENCE DOCUMENTS: IFC Drawings
label | 27195baa-ab15-44bd-8b80-f6e82e1b15f6 |  | note | INSPECTION/TEST METHOD: Survey
label | 07d63ace-b965-47a6-a41d-bd97924ad88a |  | note | RECORD OF CONFORMITY: ITP
label | 99d69773-2282-4cb0-afe0-081891ba30cf |  | note | HP*
label | 041099cd-b324-41af-9ed9-e81fea47b6b5 |  | note | RESPONSIBILITY: Project Engineer/Surveyor/ Foreman
text | 2cb8b0c0-ac4f-455a-a462-87e159a5be55 |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 3.2 Excavation for pipe laying
label | 871aafc7-9c3a-4bdc-bd19-beeed519277d |  | note | FREQUENCY: Each lot
label | 070e5cb6-5a93-4bb2-bdd4-96e71c2a9b7d |  | note | ACCEPTANCE CRITERIA: In accordance with the drawings Excavation depth shall include depth required to achieve specific bedding depth
label | 72c96035-f265-4534-a0f2-2807f162f8c9 |  | note | ACCEPTANCE CRITERIA: Completion of trench excavation prior to placement of bedding materials shall be inspected by the Principal’s Representative.
label | f4bfbabd-90b6-4cae-b4fb-62945b96c111 |  | note | REFERENCE DOCUMENTS: IFC drawings
label | c1488b74-71cc-4b2b-a0fe-9b838267b1c8 |  | note | INSPECTION/TEST METHOD: Inspection
label | 1d7fe0fa-e4f2-4d91-bf9d-16642aedc00b |  | note | RECORD OF CONFORMITY: ITP WP
label | fe97c181-14d4-4e3f-b700-d228b7550fc8 |  | note | WP/IP
label | 1f06c680-915b-42ee-95d9-f20544915374 |  | note | RESPONSIBILITY: Principal’s Representative/Project Engineer
text | cd2ca330-01e8-4dd8-8371-2e05a05041da |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Pipe Laying
label | f11166a8-3f5c-4889-9bb0-0f1c9bec7e6e |  | note | FREQUENCY: Each Lot
label | a77e41aa-76c6-4b97-836e-2f836a3e2173 |  | note | ACCEPTANCE CRITERIA: Pipes to be handled and laid strictly in accordance with the manufacturers recommendations
label | 406c4162-70ae-4db8-9eee-371f59357272 |  | note | ACCEPTANCE CRITERIA: Pipes to be thoroughly cleaned before final connection ensuring no water or foreign material is present.
label | aaef2dff-691e-45a2-9ada-1ae3312f1008 |  | note | ACCEPTANCE CRITERIA: Ensure skids are placed as per the drawings and manufacturer requirements
label | 42d4a20a-ca79-46d1-8729-efbc9e5647ba |  | note | ACCEPTANCE CRITERIA: Completion of conduit laying prior to any backfilling shall be inspected by the Principal’s Representative.
label | c603a3fb-ac81-4411-a821-2fa6a3bee054 |  | note | REFERENCE DOCUMENTS: IFC Drawings
label | 9c7b3057-3b66-4cfb-bdb3-71109584399f |  | note | INSPECTION/TEST METHOD: Verify Inspection
label | 2b43af2b-0769-459d-9f23-fd6cc9f55a61 |  | note | RECORD OF CONFORMITY: ITP WP
label | ba6bcb6b-4acf-44a8-9d73-6e5e91031197 |  | note | IP/WP
label | 049a7c09-a6d1-4c0f-b787-80252049be47 |  | note | RESPONSIBILITY: Project Engineer/Principal’s Representative
text | 34e4cbc0-8a7a-485c-9432-ac5554a13993 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 Pipes and Ducts in Trench
label | abcbd134-8b1f-440a-8093-9bdac6a00f27 |  | note | FREQUENCY: Each Lot (Where applicable)
label | 4c2a997c-e3eb-4aa1-bce5-0f51536ba29f |  | note | ACCEPTANCE CRITERIA: Unless specified otherwise, pipe and duct laying in trenches shall be in accordance with the requirements of WSA03-2011-3.1 MRWA Version 2.0.
label | 6bd86b48-c50f-41a5-9fdc-a2e119cd10df |  | note | ACCEPTANCE CRITERIA: Trench foundation for pipes and ducts shall be finished to the approval of the representative prior to placing bedding material
label | 558c8d14-b1c5-4955-a13a-bbb8cca6d5a9 |  | note | REFERENCE DOCUMENTS: CP14038- AIR-DET-PM-SP0002¦ 1,cl.9.2.3.2 , WSA03-2011-3.1
label | 980d38bf-94fa-4cfa-82e7-c75a5758a6e6 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 88eb7fd0-5d35-46d4-9a9d-88343101e338 |  | note | RECORD OF CONFORMITY: ITP
label | db82b308-2dab-4d84-84cf-a0fb787a5fd7 |  | note | HP*/AP
label | 84d93b3f-803d-42ec-bede-ef7ed04079b0 |  | note | RESPONSIBILITY: Project Engineer/ Principal’s Representative
text | a66604ac-65f6-4d24-8c35-91982f403090 |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 3.5 Pipe cutting
label | 9a4263b7-03fb-4975-be0d-af6c3fbf7196 |  | note | FREQUENCY: Each lot (where required)
label | 921261b5-0b34-4793-b12c-1ebb65a5d487 |  | note | ACCEPTANCE CRITERIA: Cut pipes square to the barrel of the pipe with a total deviation of not more than 5mm and to be in accordance with manufacturer’s instructions. Remove jagged edges.
label | c0109ba9-d571-4a99-b86b-fad01dff7e34 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP0002¦1,cl.9.2.3.4
label | 817ad888-9c25-407d-bfdd-97cd928a95ef |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 119dced3-3c90-4ca3-b6fd-27ffe86e5524 |  | note | RECORD OF CONFORMITY: ITP Signed
label | 174d857b-1436-4ae8-a0d9-1bcf5ef4eb2b |  | note | HP*
label | 2c2d14cc-ba85-468e-b054-23c8fb109c00 |  | note | RESPONSIBILITY: Project Engineer/Foreman
text | 1095a441-4243-45c2-8abe-9748624eed13 |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 3.6 Joints
label | 4dd83e63-c759-41c8-8fb0-e949def3151f |  | note | FREQUENCY: Each Lot
label | 67e11f85-ded9-49d9-a796-2b07c964dcfa |  | note | ACCEPTANCE CRITERIA: Pipe joint and fittings to be in accordance with the manufacturer’s instructions and recommendations
label | 486e1ed7-77f9-46c5-9429-0f5488ab3504 |  | note | ACCEPTANCE CRITERIA: Pressure pipework to be tested in accordance with WSA03-2011-3.1 MRWA Vers2, work specification and IFC drawings.
label | 140a9390-a37a-45f2-945a-412256686b2e |  | note | ACCEPTANCE CRITERIA: Unless otherwise specified, PE pipes to be joined by full butt welding and install in accordance with AS 2033.
label | 536fa744-b75b-4820-a55e-7e39a0f72f4d |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP0002¦1,cl.9.2.1.1 , WSA03- 2011.3.1AS2033
label | 1814573f-6445-4054-8c37-f4c6a0c50dc4 |  | note | INSPECTION/TEST METHOD: Verify
label | 3cdaa58b-a2e0-414e-b63f-2dd524e90ec7 |  | note | RECORD OF CONFORMITY: ITP signed
label | f8564797-b317-4cd5-9690-1a90985f8a87 |  | note | IP
label | b2c421be-5c76-4785-8ae0-c0ab5f26eec6 |  | note | RESPONSIBILITY: Project Engineer
text | bcf8d912-25d2-41cf-886a-691caca13cef |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.7 Installation of Valves and Fittings
label | 8d9d4932-5f02-4515-9fbe-29e9967bc8ae |  | note | FREQUENCY: Each Lot
label | 91ff6135-c2f0-4260-9c24-c9eed23ec515 |  | note | ACCEPTANCE CRITERIA: Ensure valves and fittings are located in the correct positions as per the drawings with adequate support assuring valve operation does not deflect the connected pipes.
label | 3b6658c2-e02a-43e8-9e67-2495ec311e42 |  | note | ACCEPTANCE CRITERIA: Flanged valves may connect to PE main with PE stub flange matching the SDR rating of mating pipe
label | c312da2a-1c62-480f-8f2f-24fc1a45c112 |  | note | ACCEPTANCE CRITERIA: Backing flanges shall be drilled to AS4087 PN16 drilling pattern. Backing rings, bolts nuts and washer are to be grade 316 stainless steel.
label | 2b47895e-ed2c-4ff5-8fa1-b38345da4da2 |  | note | REFERENCE DOCUMENTS: IFC Drawings , AS4087
label | 37cdfa53-b19e-4b01-9d41-a5f8434ccdf2 |  | note | INSPECTION/TEST METHOD: Verify
label | 5f5cb40e-65ea-4b8d-b459-c3a2745f249c |  | note | RECORD OF CONFORMITY: ITP Signed
label | ae3d16bd-ffaa-4fd0-ae79-10a21b9a875e |  | note | IP
label | 6e3a4ec8-2383-410e-a351-d667c5d17e85 |  | note | RESPONSIBILITY: Project Engineer /Foreman
text | 210c0028-c32e-4a81-93de-edbdedaeaf1b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.8 Bedding and surround for pipes under taxiway and aprons
label | 2c329642-a532-4e19-b368-bdf3c880bd04 |  | note | FREQUENCY: Each Lot (Where applicable)
label | 76dc305f-3dda-4b25-b2d9-316d85888202 |  | note | ACCEPTANCE CRITERIA: Bedding and surround for pipes and ducts under taxiway and aprons to be 5MPa Lean Mix Concrete (LMC).
label | 04fe1fdb-79a1-4235-a462-9ed0b260c24c |  | note | ACCEPTANCE CRITERIA: LMC to be placed and compacted using immersion vibrators accompanied by hand methods (as appropriate).
label | 338db013-6d28-4f7b-82a9-f5d9f897ca0c |  | note | ACCEPTANCE CRITERIA: Ensure concrete is fully compacted and entrapped air removed.
label | 2372e536-c99a-4d95-b20d-bc1127b38964 |  | note | ACCEPTANCE CRITERIA: Do not allow vibrators to come into contact with pipe or duct to avoid any damages.
label | 3cd82cfc-b00d-4844-9a7c-dcf4d943891b |  | note | ACCEPTANCE CRITERIA: Stages of backfilling to be inspected by the Principal’s Representative.
label | d1b0b5c0-3d2d-456b-ae6c-70c7e0b14afb |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP0002¦01,cl.9.2.3.3
label | 7735822b-398f-4e3b-8e0a-934030306a9d |  | note | INSPECTION/TEST METHOD: Verify Visual inspection
label | d551d3fa-df1a-49a1-ba0d-313a86f90a64 |  | note | RECORD OF CONFORMITY: ITP Signed WP
label | b81bf4a7-7ce9-4412-a6a9-29256fbd4386 |  | note | IP/ WP
label | 1a7608e2-8431-4208-bf4b-52a6c53a34c7 |  | note | RESPONSIBILITY: Project Engineer/Principal’s Representative
text | bcca83ff-5656-405e-a95a-420aa2e0d6af |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.9 Bedding and surround under grasses/ nontrafficable area
label | 764069c8-f259-44ea-91ed-be023d720a88 |  | note | FREQUENCY: Each Lot (Where applicable)
label | 9488dd3e-9a2e-4226-bd0b-6f674177b718 |  | note | ACCEPTANCE CRITERIA: Pipes installed without pipe sleeve undergrassed/ non-trafficable area, the bedding and surround material to be 5mm crushed rock in accordance with WSAA
label | 13d382d1-920a-4e85-b684-abac1dffc3f0 |  | note | ACCEPTANCE CRITERIA: Production Specification WSA PS-361 and compacted to requirement as per the drawings
label | 5c28cec4-f1ee-43cd-b1c7-1d27b7addc98 |  | note | ACCEPTANCE CRITERIA: Stages of backfilling to be inspected by the Principal’s Representative.
label | 360de0e8-e689-4a6f-8659-800053f5e6ea |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP0002¦1,cl.9.2.3.3 , IFC drawing , WSA PS361
label | cd5ddf34-c02f-4d28-a5b8-36446ca9eb77 |  | note | INSPECTION/TEST METHOD: Verify Visual inspection
label | 4d6d1661-8294-4119-815a-46b19e8336cd |  | note | RECORD OF CONFORMITY: ITP Signed WP
label | e51760c4-657f-42d4-b408-f96c8bb98481 |  | note | IP/WP
label | 2fd75d60-0bec-4c23-bb57-8cf049b587b8 |  | note | RESPONSIBILITY: Project Engineer/Principal’s Representative
text | 7d34b911-b284-4a31-9af9-fa10ae548f54 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.10 Thrust and Anchor Blocks
label | d733216b-5b6b-4fb9-97f4-2b106aeab197 |  | note | FREQUENCY: Each Lot
label | 0688ff62-cdd2-4916-af9a-12ac359d6602 |  | note | ACCEPTANCE CRITERIA: Ensure thrust blocks are constructed to WSA 03-2011 v3.1 sec 7.9 and as per drawings
label | fd939927-4ec4-48c0-8ba4-c5ddf38b4d6b |  | note | ACCEPTANCE CRITERIA: Blocks positioned in the direction of thrust and over the specified bearing area.
label | caf76167-cb70-4307-ab77-a96cfe63477b |  | note | REFERENCE DOCUMENTS: IFC Drawings , WSA 03-2011
label | 95bf9887-f2b2-4c34-8236-084aac0805cb |  | note | INSPECTION/TEST METHOD: Verify
label | 7028b8a8-903d-4f4f-ab89-1ce1cf8f87a1 |  | note | RECORD OF CONFORMITY: ITP Signed
label | d9d38e9d-df98-4977-8c62-defc09c5010d |  | note | IP
label | cbe198ee-17ca-449f-88d1-9d87ea4a353b |  | note | RESPONSIBILITY: Project Engineer /Foreman
text | 5a5786e6-f950-4039-852d-74ac75dd13c5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.11 Jointing of pipes
label | 8d54c9e2-0ad3-4096-841e-0298bf096b9d |  | note | FREQUENCY: Each lot
label | f0f0c78a-92a1-4cac-aa38-cc630fd915ca |  | note | ACCEPTANCE CRITERIA: Pipe joint and fittings to be fitted by a competent welder and in accordance with the manufacturer’s instructions and recommendations.
label | ee1e195f-82a1-41f7-9f66-5458a1812b99 |  | note | ACCEPTANCE CRITERIA: Pressure pipework to be tested in accordance with WSA03-2011-3.1 MRWA Vers2, work specification and IFC drawings.
label | 03f9ce40-4d54-4b95-8de4-57fe818bb4ef |  | note | ACCEPTANCE CRITERIA: Unless otherwise specified, PE pipes to be joined by full butt welding and install in accordance with AS 2033.
label | 23a9ce04-fad6-4506-8e13-62732f071859 |  | note | REFERENCE DOCUMENTS: WSA03-2011-3.1, IFC drawings , AS2033
label | 988e953c-48d2-4250-a854-6d35123d352f |  | note | INSPECTION/TEST METHOD: Verify
label | 41af6863-5951-4b3e-8cb6-4e5129e1bcb4 |  | note | RECORD OF CONFORMITY: ITP Signed
label | f88e9b87-629f-4e11-acee-f73a9cbaf969 |  | note | HP*
label | 26ce2008-a118-4fec-9e49-3517430aa70e |  | note | RESPONSIBILITY: Project Engineer
text | de8ed0ce-1f5f-44cc-af89-8cc241941500 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.12 Detectable tracer tape and marker tape
label | 8aa2ef4e-0c58-4b24-900d-cee6470b02dd |  | note | FREQUENCY: Prior to placing select fill
label | 0b97d682-87d0-4791-8be4-76563e6cae82 |  | note | ACCEPTANCE CRITERIA: Detectable tracer tape and marker tape shall be placed on top of 5MPa lean mix concrete (where RCP duct used) or on compacted 5mm crushed rock (under non trafficable area) prior to placing select fill (non-taxiway area) or 6% cement stabilised sand (under pavement).
label | c496ad63-0562-4005-9b3d-31f50ca526e1 |  | note | REFERENCE DOCUMENTS: IFC drawings
label | b726ec7c-ba08-4dfb-b992-5e64e024f889 |  | note | INSPECTION/TEST METHOD: Verify
label | 4a132faa-b04b-4147-a0cf-65252439a340 |  | note | RECORD OF CONFORMITY: ITP Signed
label | f0bdc57c-bcaf-406b-b8c3-d40d8548a7c7 |  | note | IP
label | fecea7fc-b516-4443-9b05-052753c95867 |  | note | RESPONSIBILITY: Project Engineer / Foreman
text | 950e72b1-8d0a-47bf-85fe-fe9c66aee019 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.13 Backfilling trenches
label | 89e65e8f-537d-4d6d-8e06-ac712b0fcf50 |  | note | FREQUENCY: Each lot
label | fe6d3a6c-d738-4843-a289-05a2b6dc71e5 |  | note | ACCEPTANCE CRITERIA: Material used under pavement shall be 6% Cement Stabilised sand to design subgrade level.
label | 0c6217ed-5423-4e12-98a5-876bbca4d0cf |  | note | ACCEPTANCE CRITERIA: Material used for non-taxiway area shall be select fill free from perishable matter and lumps.
label | a30dbb57-70b9-48b5-ad37-d61eeec8b482 |  | note | REFERENCE DOCUMENTS: IFC drawings
label | 184ba726-17a0-4609-8400-c98440e76ca1 |  | note | INSPECTION/TEST METHOD: Inspect and Verify
label | ea239f07-ead1-40e3-ac81-43388b44b1fe |  | note | RECORD OF CONFORMITY: ITP Signed
label | 3588501a-e5f2-4002-9b3c-a4c53e2b1887 |  | note | IP
label | b914c963-326b-418d-8f9c-e8f710ff29ed |  | note | RESPONSIBILITY: Project Engineer/Foreman
text | d473fae7-56d4-4085-af3c-250e2a8f1e13 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.14 Compaction
label | c9b1dde6-7e78-482d-9dc9-8d91654df516 |  | note | FREQUENCY: Each Lot
label | 01d43add-d404-4512-bc6e-36567f4da451 |  | note | ACCEPTANCE CRITERIA: Backfill placed on both sides of pipe equally. Concrete backfill to be vibrated to fill all voids
label | 123f30dc-7adc-4244-8231-545e34d57ab6 |  | note | ACCEPTANCE CRITERIA: Where 5mm crushed rock is used, it is to be compacted to minimum index density ratio of 70%
label | b57700af-2f67-430f-80ff-7109ee08d65c |  | note | ACCEPTANCE CRITERIA: Select fill shall be placed in layers not exceeding 200mm and shall be compacted to minimum of 95% M.D.D.
label | ee0d377c-4bc0-4588-8edb-db422301ad04 |  | note | REFERENCE DOCUMENTS: IFC Drawings
label | c9f09d63-5be2-4cb9-bf3f-95b7666aca39 |  | note | INSPECTION/TEST METHOD: Inspect and Verify
label | 56524d41-1936-460e-93ef-d81d9e83c240 |  | note | RECORD OF CONFORMITY: ITP Signed
label | 7286e31b-9697-4925-968c-2c9e6ecc6e21 |  | note | IP
label | 6ebae3c3-9c22-48ca-95ec-3f16f8075545 |  | note | RESPONSIBILITY: Project Engineer / Foreman
text | f01cd56b-94a0-4304-b46e-cbd6b150b082 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.1 Pressure testing Mains
label | e7691f53-fd86-476f-9836-9981c20ccc1a |  | note | FREQUENCY: Each Lot
label | 450b9894-9387-4e56-9974-b07931a55393 |  | note | ACCEPTANCE CRITERIA: Hydrostatic pressure testing of the pipeline as per WSA03-2011-3.1 MRWA V2, Section 19.4
label | 4858bc23-3db5-491b-9b04-22f86e36c186 |  | note | ACCEPTANCE CRITERIA: Each pipeline may be tested in one length, or in sections provided that pipe section ends under test are adequately secured.
label | e8fb5dad-3dc6-453b-9fa3-b3c205cec54d |  | note | ACCEPTANCE CRITERIA: The pipeline test pressure for each pipeline or individual test section, shall be 1.25 x maximum design pressure of 600kPA at the lowest point of the test section
label | aa33a144-2996-4236-9f39-6fe8e039935a |  | note | ACCEPTANCE CRITERIA: Maximum pressure of the mains to be confirmed with Melbourne Airport.
label | 6a146b92-e9c3-47d8-be71-064996e8e3b2 |  | note | REFERENCE DOCUMENTS: CP14038- AIR-DET-PM-SP0002¦1,cl.9.2.4 , WSA03-2011
label | b1820d4d-28e0-4768-8fc1-2ae192c46371 |  | note | INSPECTION/TEST METHOD: Verify
label | bcdd6872-2dc5-49d7-ba1d-cd92ae9a02e6 |  | note | RECORD OF CONFORMITY: Test Report
label | 808b49ab-f564-4b74-b4fc-7c02a7e7f2b4 |  | note | TP
label | a6d37bb5-7479-4e60-a283-b7bdea1c3ebc |  | note | RESPONSIBILITY: Project Engineer
text | cc0d9e96-5f7b-43e9-bec6-4fea98de3ec1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Disinfecting Main
label | 061c565f-94bc-41d7-a186-78179a5303e4 |  | note | FREQUENCY: Following Pressure test
label | e157d581-e6b4-4998-a2d0-cb616c54f0ee |  | note | ACCEPTANCE CRITERIA: Clean & Disinfect the watermain prior to connection and use as per procedure and requirements set out in WSA03-2011-3.1 MRWA v2 Section 20- Disinfection.
label | d7906091-1027-4886-9b13-62fd6366aa90 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP0002¦1,cl.9.2.5 , WSA03- 2011-3.1
label | 98f64fd8-01dc-4d62-9707-32aff6f98dbc |  | note | INSPECTION/TEST METHOD: Verify
label | 2ee14856-fbe6-4e74-ab31-ba1149a14feb |  | note | RECORD OF CONFORMITY: Test Report
label | ba80c29e-3028-4785-985d-5f40fc3a4abe |  | note | TP
label | bad1ddd7-6911-4767-84d3-8a64e928d7d3 |  | note | RESPONSIBILITY: Project Engineer
text | 64218b2b-ff36-4fb5-849e-dcaa5ec17692 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Connecting to Existing Mains
label | 7b826136-4b2c-4a27-8b47-6cb4d5e9a590 |  | note | FREQUENCY: After Water Testing
label | a64ed76e-ff04-4aff-aab1-77e6f3b37c3d |  | note | ACCEPTANCE CRITERIA: New or re-connections must be made in accordance with Melbourne Airport procedures.
label | f9765cc8-8b9a-4148-9552-9027e5ce8f12 |  | note | ACCEPTANCE CRITERIA: Provide service authority at least 72 Hours’ notice prior to isolating mains
label | 92ddb854-682f-47ef-8175-8d31d322f84d |  | note | REFERENCE DOCUMENTS: Melbourne Airport Procedure
label | 939b4831-1452-4bae-a9fa-022acdb73f0e |  | note | INSPECTION/TEST METHOD: Verify
label | 55c460d8-10cb-4f7f-9eea-fbfa2da31eda |  | note | RECORD OF CONFORMITY: This ITP Signed
label | 0bb0d791-caed-4c6a-a8ba-dae5988bf1fa |  | note | IP
label | ea8691fc-ffd1-4039-95c1-b264eb66f6d9 |  | note | RESPONSIBILITY: Project Engineer
text | 66635dea-3cf8-4b82-a75d-ba5ea5a70500 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 As built survey
label | a2eb079b-ec0d-428f-a821-9e188ea741b1 |  | note | FREQUENCY: Each Lot
label | cbd629ae-911b-4fd5-8d51-cbf09413ee74 |  | note | ACCEPTANCE CRITERIA: Surveyor to pick up completed valves in pits to show final locations within the pits.
label | 5e9608a2-31f5-48b5-8c72-a9b08ec58b71 |  | note | INSPECTION/TEST METHOD: Review
label | a889db94-4619-4039-a975-45f0753f3934 |  | note | RECORD OF CONFORMITY: Survey Report
label | 2200e003-6507-4750-9ce0-872adfe5600a |  | note | SCP
label | 66c03655-44dc-4df4-8a5b-bf70d2f89d77 |  | note | RESPONSIBILITY: Project Engineer
text | d0643c43-5b1e-4ad0-8a61-19d34ca219c8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | FINAL INSPECTION FULTON HOGAN - On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 691f4a31-fd62-444e-b7ae-53aced24a250 |  | textbox | Print Name:
text | 46bbf235-0d0a-4724-9cbd-e76c71f1f918 |  | textbox | Position:
checklist-sectioned |  |  | checklist | ITP 036 - Placement of HaTelit BL Asphalt Reinforcement Geogrid |  |  |  |  | Yes | ITP 036 - Placement of HaTelit BL Asphalt Reinforcement Geogrid | 3a13ba83-eed1-498d-9cca-a9a8885c4b14
checkpoint-group |  |  | section | ITP 036 - Placement of HaTelit BL Asphalt Reinforcement Geogrid
checkpoint-status |  |  | checkpoint | 1.1 Equipment
label | 5ec84da4-525b-469a-8b34-667260ce0806 |  | note | FREQUENCY: Prior to Commencing
label | 17a75200-6955-4613-82e3-28bdabf3c0fb |  | note | ACCEPTANCE CRITERIA: Pre-Start checks completed by Operators. All plant equipment acceptable for use. Report any faults. Back up equipment in place where required.
label | 5f1c2847-00c5-4ed5-8ee2-143080a0bdfa |  | note | REFERENCE DOCUMENTS: PBAA Spec 7.1Jacobs 7.6.1 , Huesker HaTelit Installation Guide
label | 150cfdda-efd0-4c25-85ff-5ba2ce848da2 |  | note | INSPECTION/TEST METHOD: Site Inspection
label | d154968e-2c9b-48b6-9f51-fc14b57aa8c5 |  | note | RECORD OF CONFORMITY: This ITP
label | 034bd811-295c-4d21-bc9d-3152d33e4a9c |  | note | WP
label | 858bfbb2-5b08-4b62-9907-3d273b79acaa |  | note | RESPONSIBILITY: Fulton Hogan , Jacobs
text | a62056f1-1802-467e-9438-5adfe8cc38b0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 Transportation & Storage
label | 83e81dab-afa1-44e4-bf8d-bdcd2e53d2fd |  | note | FREQUENCY: Each Shift
label | ce69533a-b23f-4aae-aa4d-d5c454a84099 |  | note | ACCEPTANCE CRITERIA: The HaTelit BL rolls should be checked for damage caused in transit prior to use. Faulty should not be used
label | d6b13037-69e0-45a2-ae98-59d04ee3d0dd |  | note | REFERENCE DOCUMENTS: Huesker HaTelit Installation Guide
label | 05679e35-5f5b-4532-b902-af334dff7347 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 159f9625-1ae9-48f1-9f71-94c622e74fdf |  | note | RECORD OF CONFORMITY: ITP sign-off
label | 33e8ad83-b1a1-437c-a902-d676ee09ed36 |  | note | IP
label | 7be0e14b-b399-4a03-a5c4-26cbddf1f78b |  | note | RESPONSIBILITY: Supervisor
text | a63cbb17-2221-4248-882c-ebc6dd236b6b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Surface Preparation
label | fd8e8378-163e-4e04-b264-44869519d0d6 |  | note | FREQUENCY: Each Lot
label | 81797b0a-1b54-4325-90d6-29e6d97ab4a4 |  | note | ACCEPTANCE CRITERIA: Surface should be dry, clean and free from any loose material. Surface produced by milling shall not exhibit any grooves >10mm.
label | 009003cb-59d6-45f1-bdab-30d010b58919 |  | note | REFERENCE DOCUMENTS: Huesker HaTelit Installation Guide
label | 1212eeba-cb74-4864-992c-0ce091fa2d4d |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 17657245-fbe3-4eb2-ae38-519f77ec8688 |  | note | RECORD OF CONFORMITY: ITP sign-off
label | a5273ec3-37f3-4243-8e5f-41dc2b3d9c83 |  | note | HP
label | c35a79ac-d857-42f9-a6ba-8202b22a60eb |  | note | RESPONSIBILITY: Supervisor
text | e5089305-ca61-447a-bdbb-47bfd96e7eac |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 3.1 HaTelit BL installation
label | 2b4819bb-f57b-4589-be3f-8b5c5d6f60ac |  | note | FREQUENCY: Each Shift
label | 5538c38e-d061-490d-b0dc-0cddbda7c45d |  | note | ACCEPTANCE CRITERIA: HaTelit BL is only to be placed in dry weather on a dry surface. Placement of sheets shall butt up against each other without any overlap and pressed down
label | 1b3bb7c3-ea2e-4bac-b307-5189e9f074e5 |  | note | REFERENCE DOCUMENTS: Huesker HaTelit Installation Guide
label | fe6c121b-8ce3-4d53-8ae9-255f8639ed19 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 6f1097ad-cb18-4ebc-b4db-dfc113c20902 |  | note | RECORD OF CONFORMITY: ITP sign-off
label | 05af0885-7622-448b-9ece-a57890b3085a |  | note | WP
label | 3ea80de0-4390-4b17-888a-5b3a692ce004 |  | note | RESPONSIBILITY: Fulton Hogan , Jacobs
text | 5181d2e7-639d-401b-92ed-857a5742603d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Asphalt Placement over HaTelit BL
label | 792b01af-4d50-4fd5-bdc8-453313d1bbf6 |  | note | FREQUENCY: Each Shift
label | 53a60b6e-5146-42e5-bdd1-0db53e239154 |  | note | ACCEPTANCE CRITERIA: Where practical, avoid any sudden steering movements as well as acceleration or braking. Thickness of the first layer of asphalt shall be at least 40mm and comply with good practice for asphalt construction.
label | 163d4da9-8013-4436-acb7-eb6641334ce7 |  | note | REFERENCE DOCUMENTS: Huesker HaTelit Installation Guide
label | 9b35a2fd-6ae2-433f-bd87-bb9f4215bbf8 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 42712d76-7e2f-4e5b-9afa-ab2c8678abb1 |  | note | RECORD OF CONFORMITY: ITP sign-off
label | 18454c62-fcba-48cc-9d30-b5918df79bb7 |  | note | IP
label | b2e6c95c-03e4-4827-b2bf-6a77aad285fa |  | note | RESPONSIBILITY: Supervisor
text | 8730f423-b35f-4863-9e07-90f7deac2ed5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.1 HaTelit BL Supply Conformance
label | 93472045-b769-4d93-bc92-4f8a2f77173b |  | note | FREQUENCY: Prior to the commencement of application
label | f13d5146-276f-4efd-a86d-83d675b58211 |  | note | ACCEPTANCE CRITERIA: The Contractor is to supply the HaTelit BL source, name and address of manufacturer, manufacturer information.
label | f30b1735-a08d-41c8-8cef-00484cae8c74 |  | note | REFERENCE DOCUMENTS: Huesker HaTelit Installation Guide
label | e8a8dc44-59e0-49ec-ae9b-158a2655941b |  | note | INSPECTION/TEST METHOD: Record
label | a5cb4391-a998-45e5-ac8a-fe250bb03156 |  | note | RECORD OF CONFORMITY: ITP sign-off
label | 050424bb-4dd2-4fe7-a490-ce490259540f |  | note | WP
label | 741cd609-a07f-4d45-8761-583f1e285c4d |  | note | RESPONSIBILITY: Fulton Hogan , Jacobs
text | 292e79bb-28fd-49a3-8845-9051bd749cf5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Non-conforming HaTelit Lot areas
label | e60a9de1-3b9d-4d23-a383-082143ddce8a |  | note | FREQUENCY: Each Lot
label | 8955b2a8-8ac5-47fc-b6ff-2668e4caf673 |  | note | ACCEPTANCE CRITERIA: Any sections deemed non-conforming shall be removed and replaced according to Manufacturer’s Specifications
label | 893861a6-dae7-4873-918b-16d2caec5c2e |  | note | REFERENCE DOCUMENTS: Huesker HaTelit Installation Guide
label | 2684a985-475d-4424-928f-281bc0c2a74f |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | e1f99ae5-7a87-4ee8-8961-3f3464445c93 |  | note | RECORD OF CONFORMITY: Non-conformance Report
label | 2cea44b5-9c31-48e5-a9c0-47a22bd9e540 |  | note | -
label | b3de7009-8b82-4728-bf46-9c598ba2b3c0 |  | note | RESPONSIBILITY: Project Engineer
text | 13a42778-3b99-464a-8b38-5963ba334206 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | c1bf4652-b761-43a0-880c-a60df2f4ba81 |  | note | This is to verify that the final inspection has been carried out in accordance with the FH’s Quality Procedures and Project Quality Strategy and the product is hereby certified to conform with the contract specifications:
text | 959e93bb-6780-41a7-aaf3-8896b171e5cb |  | textbox | Print Name:
text | 4b525aed-62fb-4848-ae55-c59c34fe2f3a |  | textbox | Position:
text | 2fae76a3-e443-4937-ad2a-15a6b70aac9b |  | textbox | Date:
checklist-sectioned |  |  | checklist | ITP 035 - Placement of HaTelit C Asphalt Reinforcement Geogrid Rev 3 | itp |  |  |  | Yes | ITP 035 - Placement of HaTelit C Asphalt Reinforcement Geogrid Rev 3 | 453c82ff-8c1b-409f-8420-7d7f4a583a8c
checkpoint-group |  |  | section | ITP-035 - Placement of HaTelit C Asphalt Reinforcement Geogrid Rev 3
checkpoint-status |  |  | checkpoint | 1.1 Equipment
label | 2dceec15-f548-45cc-b620-a549ab5d7976 |  | note | FREQUENCY DURING HaTelit INSTALLATION: Prior to Commencing
label | 1aa49706-5560-4e67-b98e-2b3272774afd |  | note | ACCEPTANCE CRITERIA: Operators shall complete pre-Start checks on all plant and equipment prior to commencing on site. All plant and equipment shall be deemed acceptable for use. Report any faults. Back up equipment in place where required. A representative from Huesker shall be on site to verify the installation process.
label | 3d2fd89e-de7f-4e71-86d5-cd1f0fc3cd3d |  | note | REFERENCE DOCUMENTS: PBAA Spec 7.1Jacobs 7.6.1 , 1.3.3 (a) Huesker HaTelit Installation Guide & Dwg 283 Note 3
label | bdff7eaa-64bd-45d5-a12d-df1810c25063 |  | note | INSPECTION/TEST METHOD: Site Inspection
label | e7b2fd10-58f7-4496-b6e7-e575c8db2799 |  | note | CONFORMANCE RECORD: This ITP
label | 2a39b2c1-7591-4a61-b759-bd1f9f894b4a |  | note | HP*
label | 168a4255-9f3a-4f66-9523-9560d5f39037 |  | note | RESPONSIBILITY: Fulton Hogan
text | 2bb8ecc5-6473-4974-a1f4-a2064a4ed66d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 Surface Preparation
label | 65893137-bcec-45c0-be9b-780d691cdf8f |  | note | FREQUENCY DURING HaTelit INSTALLATION: Prior to placing
label | ba39b580-dd2e-48c7-8950-b557298d3eb4 |  | note | ACCEPTANCE CRITERIA: Prior notice that all of the treatments within the area to be tack coated are completed and ready for inspection.
label | fe9ff642-9c03-4bd8-ad9d-1db0a05ef9fe |  | note | REFERENCE DOCUMENTS: Huesker Asphalt Reinforcement Technical Specification – Part 1
label | 6c0abc42-f690-4a4d-8c4e-7d88be688c4e |  | note | INSPECTION/TEST METHOD: Site Inspection
label | c3c8ad3d-cea7-4e2c-a4d9-7afffe6fdbea |  | note | CONFORMANCE RECORD: This ITP
label | bfeee627-b4aa-426d-8394-2db47e5cb8da |  | note | HP*
label | 2e915e55-ea59-48c8-9b30-2d83ac828869 |  | note | RESPONSIBILITY: Fulton Hogan
text | 1045d6d1-37b2-4856-b94c-b4dc885794b9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 Surface Preparation
label | b613087c-5f54-44c4-94f9-956512e4fcfd |  | note | FREQUENCY DURING HaTelit INSTALLATION: Prior to placing
label | 4c9bf4b6-5eb4-47fc-989c-0ebc9e446acc |  | note | ACCEPTANCE CRITERIA: Prior notice that all of the treatments within the area to be tack coated are completed and ready for inspection.
label | 725f0d6b-719d-4d60-9928-37ad100e9c96 |  | note | REFERENCE DOCUMENTS: Huesker Asphalt Reinforcement Technical Specification – Part 1
label | 0e59a155-f8a7-4e6b-8bf2-5ae5c370840a |  | note | INSPECTION/TEST METHOD: Site Inspection
label | 3af5f81c-4d40-47bd-b542-292883b95bd1 |  | note | CONFORMANCE RECORD: This ITP
label | 810c396c-3fb2-4048-92b0-803b07f9e015 |  | note | HP*
label | dc98f2e8-ef52-4d26-910f-7386b4cbd7c0 |  | note | RESPONSIBILITY: Fulton Hogan
text | d9409353-74a2-4a72-a04e-4d15130f2dd8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Surface Preparation
label | e314076c-cf34-4a68-a421-a901f3cdf91a |  | note | FREQUENCY DURING HaTelit INSTALLATION: Each Lot
label | a7f2efd1-fa5b-450b-83ad-14c21893af26 |  | note | ACCEPTANCE CRITERIA: Surface should be dry, clean and free from any loose material. Prior notice that all of the treatments within the area to be tack coated are completed and ready for inspection. Surface produced by milling shall not exhibit any grooves >10mm.
label | 0114e2d2-a737-4075-aa7a-651467b3205d |  | note | REFERENCE DOCUMENTS: Huesker HaTelit Installation Guide
label | 4ffd94e1-60d9-4dcd-94a5-4174f82fb3b5 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | fdc2e35d-ec10-442d-85a4-e96f7ef2025f |  | note | CONFORMANCE RECORD: ITP sign-off
label | ca818889-e8c6-4fac-bc22-6bc9087b98b8 |  | note | HP
label | 4419bb5f-e59e-4c76-9af6-a7cd009f728c |  | note | RESPONSIBILITY: Supervisor
text | a9e70670-b3d0-4d66-ad09-96b0b9b067f6 |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 2.3 Spraying of Tack Coat
label | 63e9d443-f675-4115-b93d-32459f309f4c |  | note | FREQUENCY DURING HaTelit INSTALLATION: Each Shift
label | 006c692f-ad94-4a23-99ba-c4563ed00c99 |  | note | ACCEPTANCE CRITERIA: The tack coat shall be sprayed evenly at the required spray rate of 04-0.55 l/m2 to achieve target residual bitumen as per guide. For; a) Straight bitumen based tack the HaTelit C shall be placed immediately after each run.
label | 3000d0b2-1075-437d-bf2b-6ea295d515f7 |  | note | REFERENCE DOCUMENTS: Huesker HaTelit Installation Guide
label | 3487f06b-63b3-4353-928e-abc73bfc56a1 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | f0c55232-511e-466c-9dee-909d784d077e |  | note | CONFORMANCE RECORD: ITP sign-off
label | 17841202-5649-41e0-8a16-0f55f2300217 |  | note | IP
label | e05b2593-1cfd-4a19-b22d-d27f7f3f5030 |  | note | RESPONSIBILITY: Supervisor
text | ada24db0-ccf1-45fd-9d4d-0970108502d8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.1 Prior to placing HaTelit
label | 0f26330a-55f7-4803-a1e1-a60adc348609 |  | note | FREQUENCY DURING HaTelit INSTALLATION: Each Shift
label | ec337b5e-891a-4d03-8ca8-2a6b5e72940e |  | note | ACCEPTANCE CRITERIA: A minimum of 48 hours’ notice shall be given to the Client representative prior to the commencement of placing the HaTelit.
label | fa2291b8-c5e5-4720-8e49-bcce691391dc |  | note | REFERENCE DOCUMENTS: Huesker Asphalt Reinforcement Technical Specification – Part 1
label | 2a859802-d674-49e5-8852-80fa05ef2d6b |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 1dda7d59-558b-4c9f-a19c-7d89de21716c |  | note | CONFORMANCE RECORD: ITP sign-off
label | d3ea6c65-ee7d-43dd-b978-2072127cc990 |  | note | WP
label | 9b30f0b1-59c8-4c4f-8f2f-e5184825bb2f |  | note | RESPONSIBILITY: Project Engineer
text | 387dd89d-f510-4b43-a898-c5a2b4ecbbe5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 HaTelit installation
label | e0c4ef37-89e8-4565-ad3c-54269387e344 |  | note | FREQUENCY DURING HaTelit INSTALLATION: Each Shift
label | 6124489c-5d14-46a3-97bc-c086351b1584 |  | note | ACCEPTANCE CRITERIA: HaTelit to be installed to Manufacturers Specification. Rolls applied to tack coated surface without wrinkles, creases and folds. HaTelit to be rolled with 2 passes using pneumatic tyred rollers following application. Where placing multiple rolls, an overlap of 150mm transversely and 250mm longitudinally is required. The overlaps shall be treated with tack coat and rolled to bond to one another. For small areas, manual installation is acceptable provided a fully flat and cease free installation is achieved.
label | 06b90ae0-29f6-4661-bad3-5d25988cd1a8 |  | note | REFERENCE DOCUMENTS: Huesker HaTelit Installation Guide , 1.3.3 (a) & 1.7.2
label | 7c77bed0-7fa9-47ee-8177-870eb7b357a8 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 572fb327-841b-4b0e-803e-c2fec477a212 |  | note | CONFORMANCE RECORD: ITP sign-off
label | f5df4c71-3f19-4712-843b-5ce72733d413 |  | note | WP
label | 076842c0-8657-4aad-ada1-f8fc23bf6a6a |  | note | RESPONSIBILITY: Fulton Hogan , Jacobs
text | ba0c9753-1882-44aa-bc32-948bc7510fcc |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Surface Finish Inspection
label | b3388daa-82f0-4747-8f53-4ed62e06afe3 |  | note | FREQUENCY DURING HaTelit INSTALLATION: Each Shift
label | 78a48701-118f-4939-96d4-26fc9e4eb3bb |  | note | ACCEPTANCE CRITERIA: Installed HaTelit surface to be inspected and areas recorded where required for: a) Flatness – surface wrinkled, creased, folded or not meeting standard of reference area. b) Free from any loose or deleterious material.
label | 0a35fc51-2dd1-4b42-a933-e48cce593c38 |  | note | REFERENCE DOCUMENTS: Huesker HaTelit Installation Guide
label | 466e4c35-7401-4d43-95aa-ae9559d15cdc |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 9b6c4916-a232-4be4-89c8-80a2e3486092 |  | note | CONFORMANCE RECORD: ITP sign-off
label | fae5d10d-50ea-43da-b43c-8132c8712554 |  | note | WP
label | 74800283-ac12-4c6c-b8d0-8b8131b0683e |  | note | RESPONSIBILITY: Fulton Hogan , Jacobs
text | 550d4831-482f-4222-8913-060e315ff4b1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 Assessment of bond
label | eb07340a-dab8-4428-ba2e-cca3a7408fe0 |  | note | FREQUENCY: Each Shift
label | 69d19205-4d66-440d-a384-c3fc603bca9c |  | note | ACCEPTANCE CRITERIA: Spring Balance Adhesion testing is to take place. Frequency: 1 every 50 to 150m2
label | 48f88576-8720-4fb3-9702-c6b64fc3b92d |  | note | REFERENCE DOCUMENTS: Huesker Asphalt Reinforcement Technical Specification – Part 1
label | bef9ea42-86be-40c8-9c0f-a51646978e6a |  | note | INSPECTION/TEST METHOD: Test Point
label | c0107c1f-45fc-4edd-979e-89656769cdfa |  | note | RECORD OF CONFORMITY: ITP Sign off
label | f74cc970-27df-4603-84d9-96bd2d770116 |  | note | WP
label | 1e73e524-c499-451b-be7d-403a876c640e |  | note | RESPONSIBILITY: Fulton Hogan , Jacobs
text | 003bc487-73ac-4d06-9647-835a9d8b9f8f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.5 Asphalt paving over HaTelit
label | 857277a8-be60-4974-bcee-c18868f0981d |  | note | FREQUENCY: Each Shift
label | fb1b27ff-c47b-4d2f-aac3-ef33deb7d871 |  | note | ACCEPTANCE CRITERIA: Ensure that the surface of the installed HaTelit and the underlying asphalt layer is dry, clean, undamaged and free from loose material until the completion of paving over the installed HaTelit. A minimum asphalt layer of 40mm is required to overlay the HaTelit C.
label | 0ff3788c-b6d2-4a8e-8bcf-5090f213f8ad |  | note | REFERENCE DOCUMENTS: Huesker HaTelit Installation Guide
label | 74d24ae3-bc9d-4762-b80c-9a64a98bbfa5 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | cf138f2f-77fc-4164-a7d2-103a75d21192 |  | note | RECORD OF CONFORMITY: ITP sign-off
label | 128e1eea-4867-4878-8144-fa543a6ffb9f |  | note | IP
label | d0067841-938e-47dd-92a1-960ba78964b1 |  | note | RESPONSIBILITY: Supervisor
text | 8ca23f4f-405d-4c3b-89e6-98e6c99ce055 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.1 Bitumen Emulsion Conformance
label | 8a654ba4-9e86-4ca5-9bf2-8a4e7417c506 |  | note | FREQUENCY: Prior to the commencement
label | 89dec923-42d0-45b3-9de3-463d2d20d731 |  | note | ACCEPTANCE CRITERIA: For each type of bitumen emulsion proposed, the Sub Contractor is to supply the bitumen emulsion source, name and address of manufacturer, manufacturer information not less than 10 days prior to commencement of delivery of bitumen emulsion to site.
label | 96a3cc31-1249-4ed2-b3ab-0892c93b9166 |  | note | REFERENCE DOCUMENTS: Huesker HaTelit Installation Guide
label | b64427d1-da0d-44f5-b9b3-5afd48be0b86 |  | note | INSPECTION/TEST METHOD: Results
label | e008f48f-f7f9-40a6-9288-502e4b69d278 |  | note | RECORD OF CONFORMITY: ITP sign-off
label | 748cf68c-c77b-45bc-930d-8267461d8a82 |  | note | HP*
label | ca31005f-274c-4485-8f36-3647c16a2f89 |  | note | RESPONSIBILITY: Fulton Hogan , Jacobs
text | 452f71d5-ccc7-4b3b-aa72-e517ada7d4a7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 HaTelit Supply Conformance
label | 3f049f49-2832-471f-a742-469958783a8f |  | note | FREQUENCY: Prior to the commencement of application
label | 81e5ded3-0cbb-4f1a-a9d7-162e88ec929f |  | note | ACCEPTANCE CRITERIA: The Contractor is to supply the HaTelit source, name and address of manufacturer, manufacturer information not less than 20 working days prior to scheduled commencement.
label | de538eea-a31f-4053-8a9c-d4429da95968 |  | note | REFERENCE DOCUMENTS: Huesker Asphalt Reinforcement Technical Specification – Part 1
label | a734c44c-2794-4844-94f1-ccaf641ece63 |  | note | INSPECTION/TEST METHOD: Record
label | 98f877e8-6cbe-4fb3-87e7-44a9b7f1d12f |  | note | RECORD OF CONFORMITY: ITP sign-off
label | 8205ce22-8a85-42d9-aeb5-ac953d68a6f6 |  | note | WP
label | 2261329f-b8fb-490f-9a52-e86102f190fc |  | note | RESPONSIBILITY: Fulton Hogan , Jacobs
text | 03d4e1b4-74e2-4b83-bf00-4a18be50ecc7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 HaTelit C Surface Conformance
label | 43708088-7e55-4ba4-a18a-fa5dd878b8c9 |  | note | FREQUENCY: Each Lot
label | e4ea7df8-d4a2-424c-bec2-099f82bae507 |  | note | ACCEPTANCE CRITERIA: The Contractor shall assess the conformance of the surface flatness and saturation of the installed HaTelit C surface
label | 65e85e4a-d26d-4ef7-8733-ec653304f94b |  | note | REFERENCE DOCUMENTS: Huesker Asphalt Reinforcement Technical Specification – Part 1 , Section 1.12.1
label | bb14c2d8-8c85-41d1-be65-a7a25d8dbeb5 |  | note | INSPECTION/TEST METHOD: Survey Report & Visual Inspection
label | 1690ad7f-498b-4afa-bb35-3b1714c245a9 |  | note | RECORD OF CONFORMITY: ITP sign-off
label | fcdfaaea-9303-46a7-9d89-d4894ce2a3ae |  | note | HP
label | 7040e6dd-4c4a-4309-ac82-b9c9c2b254bb |  | note | RESPONSIBILITY: Fulton Hogan
text | 746405d7-7f2b-4680-a3c5-650ab74308e7 |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | Final Inspection
label | bf82313b-748a-4355-9b78-b601bad1f546 |  | note | This is to verify that the final inspection has been carried out in accordance with the FH’s Quality Procedures and Project Quality Strategy and the product is hereby certified to conform with the contract specifications:
text | 6836501b-46c0-46dd-abfd-ce11b4978776 |  | textbox | Print Name:
text | c3d209c6-4d03-4c23-98c7-5ef6982381fa |  | textbox | Position:
text | 397023f7-5a0b-4bbf-83e6-8f616894aa76 |  | textbox | Date:
checklist-sectioned |  |  | checklist | ITP 015 - Existing Underground Service Protection | itp |  |  |  | Yes | ITP 015 - Existing Underground Service Protection | 572caa3b-a803-4b9e-9e9b-27a8bdf69d1f
checkpoint-group |  |  | section | ITP 015 - Existing Underground Service Protection
checkpoint-status |  |  | checkpoint | 1.1 Check for Correct Documentation
label | 80a1ce71-4db8-4b78-bec4-edf19fad34ed |  | note | FREQUENCY: Prior to commencing activity
label | 2e155d3d-d902-4a17-81ee-141ede20c6fd |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | 3275d71e-d160-4ea3-873a-fb6251abcedc |  | note | Using the correct and complete set of drawings
label | e343eb4f-9802-491b-9fea-5516840d1df9 |  | note | All drawings are the latest revision
label | d9163ff6-7c20-46a4-bdf8-531c3f0403b1 |  | note | REFERENCE DOCUMENTS: Drawings /Aconex Register
label | 247465f3-88c8-4248-bda9-31fc5393f545 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | f83b48fd-6bee-464f-be1f-9f59edfbe4e0 |  | note | RECORD OF CONFORMITY: Drawings and drawing registers
label | 6d6e909f-cad0-4ddb-b75a-002c7f1197cf |  | note | HP*
label | 3af945d6-2630-4b33-95c5-ba68d4b145b5 |  | note | RESPONSIBILITY: Project Engineer
text | 2ee5c4a3-069c-4521-92f4-88dc4c463042 |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 1.2 Implementation of all measures and controls
label | cdd8d8ff-5fc3-4afd-bd61-7051a72ec8c5 |  | note | FREQUENCY: Prior to commencing activity
label | fd0eef70-0465-438a-8108-e11d78ca4669 |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls being implemented, that is PSP, EMP, TMP, SWMS & WP
label | 69eb9e68-0a25-44a7-9f8d-0b4d2980c34a |  | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | 3374b135-5f4a-488b-a3e1-6c2c3aa3dd0d |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 4cdb4394-4f13-42e3-8964-c6a9f1bdda89 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 80975bb2-520a-4c10-bc25-1b1647a3413d |  | note | HP*
label | faa08f4c-d2c4-4b8c-8359-7a525c238cf3 |  | note | RESPONSIBILITY: Project Engineer
text | 9725c18f-945f-4105-b275-fe2ba3431e04 |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 1.3 Concrete Material Compliance
label | c910587f-f64b-4304-b034-e9d4a8efb953 |  | note | FREQUENCY: Prior to commencing activity
label | 3e99ffad-b7ef-43d9-843e-d54b7987165f |  | note | ACCEPTANCE CRITERIA: Cement for use in concrete encasement shall be 20MPa Portland Cement Type GP complying with AS 3972
label | da4d1e87-c00e-4e57-9028-ad6a9907e716 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PMSP-0002 / cl. 12.3.4 / cl. 9.3.1.10
label | e9f57f14-2e81-4f21-9a66-9cb2bb810fa5 |  | note | INSPECTION/TEST METHOD: Verify
label | 0af36717-d847-49d9-ade2-c8c0f6b3d01e |  | note | RECORD OF CONFORMITY: Mix Design Approval
label | 3dd1bb47-14fe-4945-ae45-75437ddc5244 |  | note | HP
label | 640869d8-a901-4313-bc6d-933c6cb4f88d |  | note | RESPONSIBILITY: Project Engineer /Principal’s Representative
text | b74fff45-6081-45c9-86ae-5f7ffdbe903d |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 1.4 Steel Reinforcement Material Compliance
label | 54a2d49e-06e4-46a4-bf31-4c31c8eb85c1 |  | note | FREQUENCY: Prior to commencing activity
label | 2e9600e5-d5b6-45cc-a0ae-fb99694c2181 |  | note | ACCEPTANCE CRITERIA: Welded wire fabric shall be SL92 mesh as per drawings
label | e6816484-2bf9-46e2-b127-2ffdf56bc186 |  | note | REFERENCE DOCUMENTS: CP14038- AIR-DET-CI- 0387
label | 4790d5f2-cdd4-4e28-9b29-2202f382ab0d |  | note | INSPECTION/TEST METHOD: Verify
label | 71e623f8-aba9-4ace-ac14-4955c64e9484 |  | note | RECORD OF CONFORMITY: Material Conformance Certificate
label | 0dc2dd66-2abb-4868-84c2-7f3db5fc1fb9 |  | note | HP*
label | abaec05b-52d5-42c1-9966-17d7915dd6de |  | note | RESPONSIBILITY: Project Engineer
text | 2952570e-7c80-4886-b9bf-da9bbb1a98ae |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 1.5 Service Identification
label | 517f6ce7-d005-4715-99ca-19cb4ae6b205 |  | note | FREQUENCY: Prior to commencing activity
label | 0f7f7bde-4a54-47e2-a2db-06d8291bdc6a |  | note | ACCEPTANCE CRITERIA: All existing services’ locations must be confirmed prior to commencing work.
label | f860f559-d07f-4f05-b2c9-901a4bdd104c |  | note | Contractor to obtain excavation permit from APAM.
label | 17a94a5b-773f-4994-9b3e-c504b975ea2b |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PMSP-0002 / cl. 9.1.1
label | ecfe8e47-0de2-4570-8128-88c9235d816d |  | note | INSPECTION/TEST METHOD: Verify
label | ef2ac28b-4186-4568-b168-2c50783a2073 |  | note | RECORD OF CONFORMITY: APAM Excavation Permit
label | 762da8d3-dbd5-48b3-b30d-a23acc98586e |  | note | HP*
label | afa3115f-25fa-47b9-936e-9c912c64b9c6 |  | note | RESPONSIBILITY: Project Engineer
text | b348be21-1e2d-4f0f-9736-26e90880f693 |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 1.6 Method of Treatment
label | ff3d4e0a-aea8-42f2-a287-4fa46599a018 |  | note | FREQUENCY: Prior to commencing activity
label | 009144a5-3c8f-4303-b150-e59bcca2bd3f |  | note | ACCEPTANCE CRITERIA: The method of treatment for existing services to be protected shall be included in the demolition work plan submitted to the Principal’s Representative
label | 4e41302c-2202-4fc3-a0db-16ca3b17dcf8 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PMSP-0002/ cl. 2.2
label | a6be341e-efdc-43b7-927d-5c3136de0bf6 |  | note | INSPECTION/TEST METHOD: Verify
label | c6642c1d-681d-4c47-ab84-89d5020f0a8d |  | note | RECORD OF CONFORMITY: Demolition Work Plan
label | 5e87935e-2d17-41ab-b2df-66bd4c738e88 |  | note | HP
label | 3d48a83c-ca10-42d9-abe5-3bd03fcfc234 |  | note | RESPONSIBILITY: Project Engineer /Principal’s Representative
text | 9f1325da-f4ea-4572-9e35-a9a4e7b88651 |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 2.1 Excavation
label | 07ab5a2c-2d73-463d-88e4-553fb5c3646c |  | note | FREQUENCY: Each Lot
label | 6bd44278-57fc-4c3d-80a9-c37fb09bf288 |  | note | ACCEPTANCE CRITERIA: Only excavation methods approved by the Principal’s Representative (as per Demolition Work Plan) will be used.
label | 513eccd0-00d1-47b0-bcf4-c44ead3e28cf |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-CI0010
label | aff321f2-617d-4759-a1f0-72288c31c32c |  | note | INSPECTION/TEST METHOD: Verify
label | 7f75bb4d-d8ca-477c-a1bd-49195dff49d5 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 1b6c1e2f-7408-4061-b9b9-bf36cdbe1bf5 |  | note | IP
label | f2f9bf28-07e3-4c4b-b6f1-435367459b23 |  | note | RESPONSIBILITY: Project Engineer /Foreman
text | 689da524-a2a6-4143-9843-bd76c7c630d5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Survey Record
label | 7eea23d5-a48b-41d2-8a00-e8176bdc4a04 |  | note | FREQUENCY: Each Lot
label | d793e5fe-9f44-45b9-bc9b-86690226fec5 |  | note | ACCEPTANCE CRITERIA: Where existing services are to be retained, a surveyor shall record the position of proven service, including depth and cover to each surface.
label | c9d435ff-e7fb-496c-87b3-a383001c9899 |  | note | REFERENCE DOCUMENTS: FH QMP Section 6.3
label | 6bbe1bbd-849c-4b7c-8cf0-bad08e266370 |  | note | INSPECTION/TEST METHOD: Verify
label | 8f2fe6c1-8dc6-4eca-a861-293c8621c51f |  | note | RECORD OF CONFORMITY: Survey Record
label | 850774ce-f132-4020-a71a-ed0616500c40 |  | note | IP
label | f67d7294-7a3c-47c4-95ad-dc8e0835b5a1 |  | note | RESPONSIBILITY: Project Engineer /Foreman
text | 3fa15c6b-bcd2-4b32-ba64-217eac4d305d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Protection of existing services crossing trenches
label | 4bb17537-e4a4-489e-92b7-9eec03f6c9dd |  | note | FREQUENCY: Each Lot
label | 14b02348-8d17-4652-a947-ff60d4b915b3 |  | note | ACCEPTANCE CRITERIA: Where existing services are to be retained, careful actions must be taken to ensure that no damage is caused to the service
label | e6418505-7664-4b48-8b78-eb38c7291ef8 |  | note | Services are to be carefully exposed, supported and protected whilst excavation works and other activities under and around the service are being carried out.
label | e086437f-df9b-4f25-a611-610377d77c1d |  | note | Any backfilling that is required under the existing service must be properly compacted.
label | 68db724b-e5b1-4271-ba12-6cfdeb6e508c |  | note | REFERENCE DOCUMENTS: CP14038-AIDET-PM-SP002-C-Cl 9.3.1.7
label | 4320a143-5f3e-4a9e-8912-ae5d5a99e1f1 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 3d3f67f5-0a25-4aba-be94-0f8b0c78cc58 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 288f076e-2eea-49e5-a2bf-45c528f3b644 |  | note | IP
label | 200a29a4-bf34-40dc-91b3-7cc1f186788a |  | note | RESPONSIBILITY: Project Engineer
text | 38907e0b-3bc3-41e7-9dd1-c30f71956100 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Placement of Reinforcement
label | 4cfc1342-a5b3-4deb-9255-68237482c05c |  | note | FREQUENCY: Each Lot
label | b7871fd2-37bf-4c26-ba8f-ecff99dedd11 |  | note | ACCEPTANCE CRITERIA: SL92 mesh shall be placed all around the service to be protected as specified on the Drawings.
label | 8a89eb82-62fd-4d80-9bec-91b4a455dd18 |  | note | Steel reinforcement shall have a minimum cover of 60mm
label | 4586e058-4fba-4e76-b35e-05fa7be17f61 |  | note | Minimum lap length shall be 150mm.
label | a064d085-3e96-4ece-b94a-6b2f4a87335b |  | note | Spacers and supports shall be either proprietary or purpose-made using 20MPa concrete.
label | 25cc86bc-269f-4e49-a50c-23e1f7e4ca81 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-CI0387 / CP14038-AIR-DET-PMSP-0002 / cl. 12.3.7
label | 2e0cb908-1989-4401-8175-d9a971aa561a |  | note | INSPECTION/TEST METHOD: Verify
label | e7be031d-d566-4084-a903-e39d4daf4c77 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 347b930a-1536-43b3-ba51-496c749e6542 |  | note | IP
label | a69e8462-8563-4f5c-84f1-de15375970dd |  | note | RESPONSIBILITY: Project Engineer /Foreman
text | de1afbda-bb69-4408-9d89-03f9e5015142 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 Concrete Encasing
label | 12525d33-c6c7-466c-a930-20737ce7230b |  | note | FREQUENCY: Each Lot
label | fad7c232-ac2a-4650-bdfd-919ef489e9d9 |  | note | ACCEPTANCE CRITERIA: 20MPa concrete shall be used for the concrete encasement.
label | 52f98064-b916-4d66-a2a2-e6f509b57d5a |  | note | For existing services banks containing ducts up to 150mm in diameter, ensure minimum thickness of 100mm of concrete from surface of individual conduits.
label | bf7f0efa-ebcf-4b81-8377-bc2c56cd3989 |  | note | For existing pipes up to 675mm in diameter, ensure minimum thickness of 150mm of concrete from surface of pipe
label | 8500bf39-cd81-4b9e-83ea-965cf30a7589 |  | note | Concrete shall be placed within 90 minutes from batch time.
label | a7c97f8b-d66e-4b6a-a2eb-690bb47f041a |  | note | Temperature of concrete shall be not less than 10C and no more than 30C.
label | e4a7cfeb-f8d7-4184-860a-ddf43097406b |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PMSP-0002 / cl. 9.3.1.9 / CP14038-AIR-DET-CI0387
label | 2edbfc7f-f4ff-4e14-999c-e1bd04ff756d |  | note | INSPECTION/TEST METHOD: Verify
label | ab0a32be-0b8c-46b1-a614-3857d4664596 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 978f5872-dfc9-404c-a5b8-d7ecfb701e9e |  | note | IP
label | 957cd289-28f1-4c4e-91f8-ff13a1d7f5f2 |  | note | RESPONSIBILITY: Project Engineer /Foreman
text | 256e7190-c003-4b16-bf95-a4cc3fbbb15d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.6 Concrete Compaction
label | 8d2c75ff-01b1-448a-9a13-d15120732e51 |  | note | FREQUENCY: Each Lot
label | 5014c661-9e3d-40f2-9b43-fa8c51eebbbc |  | note | ACCEPTANCE CRITERIA: Concrete shall not be placed at a rate which will prevent adequate compaction and the layer shall not exceed 300mm thickness before vibration.
label | de9e634e-768c-49ad-bd0d-83047a5df4dc |  | note | Internal vibrators shall not impinge on the outer surface of conduits/pipes during vibration of concrete.
label | 380bdd53-b7f6-430c-9265-afeb61534270 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PMSP-0002 / cl. 12.4.8 & 12.4.9
label | 26cf8687-7b84-4a7d-876a-f8664dabfc8f |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | c3af1b0c-a183-41f4-8651-0687182f33d7 |  | note | RECORD OF CONFORMITY: This ITP signed
label | fb951ff0-570e-4f68-9917-88f2d1f10e42 |  | note | IP
label | 0b18772c-72e8-4345-abc1-3c131f94f5e6 |  | note | RESPONSIBILITY: Project Engineer /Foreman
text | 377e0887-123c-4c2f-8daf-a88f9898be3b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.7 Orange Detectable Warning Tape
label | 0c9bed9e-3e2a-4c48-92dd-9f23df3063ce |  | note | FREQUENCY: Each Lot
label | b66213dd-9b21-4ca5-b84b-4672ad535d23 |  | note | ACCEPTANCE CRITERIA: Orange detectable warning tape incorporating a magnetic strip shall be installed with at least 200mm cover to the top of concrete encasement.
label | 56a5c917-fc6a-4090-8dbb-aae18c7cbf71 |  | note | REFERENCE DOCUMENTS: CP14038- AIR-DET-CI- 0387
label | abc0d651-ec19-44af-9f09-b96643302416 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 489127d9-ab41-4d3a-b75e-c66d919d2ce5 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 475c6c85-6963-4c46-96b4-7553809ca74b |  | note | IP
label | 4d21dacc-497e-4fa2-82c5-31374b50e039 |  | note | RESPONSIBILITY: Project Engineer /Foreman
text | 2c7bfa58-359b-4c3b-924c-553c255c2071 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.8 Completion of Protection of Existing Services
label | 0835bfe6-5efd-40d9-9544-5c084858c13d |  | note | FREQUENCY: Each Lot
label | a84bdc11-cd10-4b73-8237-a42b7b998d70 |  | note | ACCEPTANCE CRITERIA: All existing electric cables which are to remain, where noted, shall be protected by split ducting and surrounded as described or directed by the Principal’s Representative.
label | e6c65594-246b-4ced-9c38-8e5ab12c3d1a |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002 cl. 10.2.9
label | e6ae927a-8c79-4ae7-91e5-fdc5063a0962 |  | note | INSPECTION/TEST METHOD: Verify
label | fc03509b-8c30-4241-8e9e-50224bcbb697 |  | note | RECORD OF CONFORMITY: This ITP signed
label | b353ce95-af7c-425f-bf24-df94e63a1f34 |  | note | IP
label | 0f849d71-7704-4f01-b1c7-a737b608845b |  | note | RESPONSIBILITY: Project Engineer
text | 4a5ce941-407e-481d-aa1f-a2362a6e534b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 7497bfaf-2df9-494e-9240-d5aa4fea5741 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
text | 82364b22-c81d-410b-a38b-b8da00ab711c |  | textbox | Print Name:
text | edf7020f-8e49-4530-b29b-ce44395f7dff |  | textbox | Position:
text | 71783f62-d804-4713-8270-accb0a23d278 |  | textbox | Date:
checklist-sectioned |  |  | checklist | ITP 001 - Demolition of Existing Concrete Pavement, Pits, Pipes, Duct Banks & Electrical Infrastructure Civil | itp |  |  |  | Yes | ITP 001 - Demolition of Existing Concrete Pavement, Pits, Pipes, Duct Banks & Electrical Infrastructure Civil | 60e18e58-522e-43e4-9480-248606b82826
checkpoint-group |  |  | section | ITP 001 - Demolition of Existing Concrete Pavement, Pits, Pipes, Duct Banks & Electrical Infrastructure Civil
checkpoint-status |  |  | checkpoint | 1.1 - The current revision drawings are being used including subcontractors copy.
label | 580376d9-80c3-474f-b52d-c3619779361e |  | note | FREQUENCY: Prior to commencing works
label | 1a879979-a170-443e-8ad7-71dfc834c105 |  | note | ACCEPTANCE CRITERIA: Current revision drawing is being used including the subcontractors copy. Current Revision to be obtained via Aconex
label | 814f9841-cc9c-4f8a-bec9-1ed2e613d756 |  | note | REFERENCE DOCUMENTS: Aconex
label | 4eca415b-3740-4578-9ddd-7bf106939270 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | b9ee3704-8046-42c9-9fac-18d01fe3c72a |  | note | RECORD OF CONFORMITY: This signed ITP
label | f135adc6-fbae-47f2-97f5-4d8c256eb69e |  | note | HP*
label | 2ca94bbb-5f8f-4235-8b1d-dfb3d5974857 |  | note | RESPONSIBILITY: Project Engineer
text | 49122473-ee6a-428b-afda-55417bd7891b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 - Demolition Work Plan
label | a27baf46-baca-45d9-93df-11a95bcd6c39 |  | note | FREQUENCY: Prior to commencing works
label | 4d0d5c08-42a1-4170-a005-566e7932ecc1 |  | note | ACCEPTANCE CRITERIA: Submit a Demolition Procedure to the Principal’s Representative not less than two weeks prior to commencing demolition work on site.
label | 97cfa170-02d8-4724-8d5f-c389e6579ee6 |  | note | REFERENCE DOCUMENTS: Jacobs – Zulu Spec. Cl2.2
label | db318314-6418-475b-8767-d6b3133d39d9 |  | note | INSPECTION/TEST METHOD: Verify
label | 2407617e-af88-49a0-bc77-743b52f01c02 |  | note | RECORD OF CONFORMITY: This ITP signed
label | ba89cc4a-baf0-49f3-a653-2769e88736e4 |  | note | HP
label | f7221d95-437d-41e4-bfe1-88a74871ef29 |  | note | RESPONSIBILITY: Project Engineer /Principal’s Representative
text | e8247eda-c78b-4706-a43f-f76912a8a6e8 |  | textbox | Date Completed:
label | fa8324de-45ee-4b82-886a-15db75ab8e6e |  | note | Hold point sign off reference: Aconex: FHPL-TRANSMIT-000109 Mail Number: DCWC Mgt-PMA-000330
label | 79820f32-d014-4176-8241-4e4d05b60907 |  | note | Date: 9/7/19
checkpoint-status |  |  | checkpoint | 1.3 - Dilapidation Report
label | f6b4a6c9-7a5d-4f84-805b-2ca89a626658 |  | note | FREQUENCY: Prior to commencing works
label | e0ba6515-ae6b-4f42-8110-6a9ce07203f4 |  | note | ACCEPTANCE CRITERIA: Dilapidation survey to be carried out around the perimeter of the section to be demolished with the Principal’s Representative, prior to commencement of demolition works.
label | 6191988e-cc64-463e-849e-9b4becf0b10d |  | note | Dilapidation report submitted to Principal’s Representative for approval not less than two weeks prior to demolition works commencing. Report to include photographic evidence.
label | 681b7c0d-fdfa-4ef4-a86c-840296d6317e |  | note | REFERENCE DOCUMENTS: Jacobs – Zulu Spec. Cl2.3
label | 3341ae5a-2ac6-4503-aa95-97bf7d56396b |  | note | INSPECTION/TEST METHOD: Verify
label | cd4a8913-ada3-43bd-b117-01b3402e22de |  | note | RECORD OF CONFORMITY: This ITP signed
label | c694c731-752b-4c20-b7c9-ce0f51f0c8cc |  | note | HP
label | aa9da607-2024-4cfd-a205-1559be2caaf1 |  | note | RESPONSIBILITY: Project Engineer /Principal’s Representative
text | bb723736-2239-4c1f-9999-64c99f0cbabe |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 1.4 - Implementation of all measures and controls
label | 89555b4e-e81d-4df4-a3ae-ce47fb001ec0 |  | note | FREQUENCY: Prior to commencing works
label | 2831ac2a-ee87-4714-bb18-02699b7f798b |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | b25f854f-a147-4323-8010-316e1bddc30d |  | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, SWMS, WP
label | dba9f570-6e26-41f7-b95a-5f38d34ee025 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 6a0f0a5d-cefb-4458-b80f-5850a1f98b83 |  | note | RECORD OF CONFORMITY: This signed ITP
label | f7aef7e9-c621-4ded-bc50-9b8864dda361 |  | note | HP*
label | c250c5ce-c765-40b0-a9ec-dd111c84758c |  | note | RESPONSIBILITY: Project Engineer/ Site Supervisor
text | 9537c5a7-9ea3-423c-9829-857242257da9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.5 - Current excavation and Isolation permit has been issued.
label | 41f748c6-7eb9-4f84-bfd4-fbaa5351733a |  | note | FREQUENCY: Prior to commencing works
label | 07db8eb6-f3f8-42f5-97b8-dc0f02c12dea |  | note | ACCEPTANCE CRITERIA: An Excavation Permit and an Isolation permit issued by Melbourne Airport.
label | db2e3562-040b-4b84-9e98-d07ef1e6f4be |  | note | Fulton Hogan Excavation permit issued to plant operators.
label | 3566ccaa-450e-42dc-9ec4-d0b5a0a846b5 |  | note | REFERENCE DOCUMENTS: Excavation Permit
label | 539347ca-8758-47fb-8a06-35ce6983cff9 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | ba0a0367-52d0-4577-9b62-73b7b243ab58 |  | note | RECORD OF CONFORMITY: Permits
label | 4a76b3ec-4087-4442-802d-3aef1a0fca7d |  | note | HP*
label | 0ed12758-0cbe-426f-89d4-7196c4ccfb6f |  | note | RESPONSIBILITY: Project Engineer / Foreman
text | f500262a-2480-483d-8f90-3d59e6ce3792 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 - Protection
label | ac0439dc-e9ca-452e-a0c0-75614958c612 |  | note | FREQUENCY: Each Lot
label | 979be36f-0cef-4226-a744-707bbd1dc6b4 |  | note | ACCEPTANCE CRITERIA: Equipment: All installed equipment to be protected against damage by dust, dirt, shock or other causes
label | 79418f4c-71d4-4c52-acd5-5b5c44b052d0 |  | note | Services: All existing services are to be known prior to commencing demolition works. Principal’s Representative to be immediately notified in the event of damage to any services.
label | 743f5b63-7763-4fa5-929a-b293849b4627 |  | note | Encroachment: If encroachments from adjacent structures or infrastructure are encountered and are not documented, the Contractor shall give notice to the Principal’s Representative and obtain instructions.
label | 4231adb9-e8a2-4442-aaa9-6bce70609292 |  | note | Weather: Temporary covers to be provided to prevent water penetration if surfaces of adjoining buildings are exposed following demolition work. Covers provided to protect existing plant, equipment and materials intended for re-use.
label | 2908ab07-23f0-493a-9b80-a661c8d49870 |  | note | REFERENCE DOCUMENTS: Jacobs – Zulu Spec. 2.4.3
label | 30cc94bb-2ece-4b00-8755-eb890308b5c7 |  | note | INSPECTION/TEST METHOD: Verify
label | c32290c1-e08d-47ac-aa48-471e4f9c92fb |  | note | RECORD OF CONFORMITY: This ITP signed
label | 1333b3ca-30e6-43fe-8828-129a667caaab |  | note | HP*
label | 454d6f85-b5ae-4e63-80f3-46b1f6246eac |  | note | RESPONSIBILITY: Project Engineer / Foreman
text | 78515ec1-ab6c-46cc-8a2b-59f2757a89eb |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 - Temporary Supports
label | 67d8bf25-1f3e-4af3-b385-153edfd03e6e |  | note | FREQUENCY: Each Lot
label | d33f19ab-32c3-4be2-861c-2e07e34863ee |  | note | ACCEPTANCE CRITERIA: Where temporary supports are required, certification for its design and installation must be obtained from a certified engineer
label | 6f8fbfb3-7c24-41e9-a5b7-c75bef65bf78 |  | note | REFERENCE DOCUMENTS: Jacobs – Zulu Spec. Cl2.4.4(a)
label | 7f5a02bc-4db1-4310-b82f-7eccc6b2ee43 |  | note | INSPECTION/TEST METHOD: Verify
label | 62234823-d41a-4930-aad0-c9e27f782b4c |  | note | RECORD OF CONFORMITY: This ITP signed
label | 6e66c215-74c7-4894-b77f-a07a2dda8e13 |  | note | HP
label | 615c105f-34d3-42cf-adb3-6fca423ce796 |  | note | RESPONSIBILITY:
text | eacafde6-23c3-4154-951a-6fe7af485960 |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 2.3 - Permanent Supports
label | 2e93081f-33e2-437c-91e0-f83c9a32a593 |  | note | FREQUENCY: Each Lot
label | 2dcb8254-fd4e-4822-bb2f-0b1d802ce33e |  | note | ACCEPTANCE CRITERIA: Where permanent supports are required and not documented, the Contractor must give immediate notice to the Principals representative and obtain instructions.
label | 3847efe6-ca93-4d42-a462-56a5b7c02435 |  | note | REFERENCE DOCUMENTS: Jacobs – Zulu Spec. Cl2.4.4(b)
label | 29f163be-b1a2-4224-8040-87163916c156 |  | note | INSPECTION/TEST METHOD: Verify
label | 3d802b52-2938-4002-9325-6a3f780acb85 |  | note | RECORD OF CONFORMITY: This ITP signed
label | d9b11b36-b07b-484e-8d37-e34f6a62facd |  | note | HP
label | 59934734-98d7-454e-8d1e-2481c156b8e4 |  | note | RESPONSIBILITY: Project Engineer /Principal’s Representative
text | 61cb9b15-70de-4cf1-94fc-9eaea9e3395d |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 2.4 - Definition of Works Area
label | f5ba366b-683b-4df1-982c-300515436d30 |  | note | FREQUENCY: Each Lot
label | dc45279b-1b8d-49ad-b8f4-4d6d3c0e1ccc |  | note | ACCEPTANCE CRITERIA: Work area has been cleared and limits of demolition zone are clearly marked.
label | b682c25e-2920-4cce-8ac5-4b06372eeb4d |  | note | REFERENCE DOCUMENTS: Design Drawings
label | 7a3f18a3-2f6e-450f-b2cd-a4168dbd75fe |  | note | INSPECTION/TEST METHOD: Verify
label | 60682f5f-4969-4c37-af63-f77782e21645 |  | note | RECORD OF CONFORMITY: This ITP signed
label | c5891d70-1cd1-4a26-87a0-db4e87624950 |  | note | HP*
label | e74ad5c2-6dbe-4ad8-97b9-65ca4b287336 |  | note | RESPONSIBILITY: Project Engineer /Foreman
text | 8f9a03c4-d4e9-4a91-93cc-9e490f8dbd80 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 - Isolation of Existing Services
label | 22c11c6b-16f3-45b2-af47-371e09d19676 |  | note | FREQUENCY: Each Lot
label | 153ab7e9-44d2-42c6-977c-9a2b2bfcef1f |  | note | ACCEPTANCE CRITERIA: If services have been indicated to be taken up and removed or relocated, the Contractor must ensure that they are disconnected prior to removal.
label | 32f471bb-51b2-4c39-8d01-72dd2b0c308f |  | note | The Airport Lighting Manager must be informed prior to isolation of services.
label | bb2d0fa8-fa5f-4fc5-a3b7-223581bc9196 |  | note | REFERENCE DOCUMENTS: Design Drawings
label | 26bfc33d-5db1-447c-ae46-bb3abe1d444a |  | note | INSPECTION/TEST METHOD: Verify
label | 43e32d78-31ef-49f1-838a-97039b4e08c5 |  | note | RECORD OF CONFORMITY: This ITP signed
label | c1f85606-5190-4abf-9c06-8dc564fe62f6 |  | note | HP*
label | bf404e3a-3a16-42ba-a772-af639965addc |  | note | RESPONSIBILITY: Project Engineer /Foreman
text | 0489b0ac-fb3b-43c2-a4cf-7a38d0b09fac |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.6 - Contaminated and hazardous materials
label | 9f1e898f-d8fb-4998-9f54-832a047af284 |  | note | FREQUENCY: Each Lot
label | f9eaefb0-51c6-4894-be50-1e995f97f740 |  | note | ACCEPTANCE CRITERIA: The Contractor must give immediate notice to the Principal’s Representative when contaminated or hazardous materials are found.
label | 811ac7af-ff7c-4e9d-ab05-5c2c91861a77 |  | note | REFERENCE DOCUMENTS: Jacobs – Zulu Spec. Cl2.4.5
label | f81a7aa0-d14e-46b2-bbf7-64b6ec5130fe |  | note | INSPECTION/TEST METHOD: Verify
label | b50c128b-5bdd-44de-931d-30b837d9d2b3 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 9f1c6342-1254-41d6-94c3-ec65ab2052ba |  | note | HP
label | 87e9ce4f-04c9-4db5-9ed4-a0ab51a5b6c0 |  | note | RESPONSIBILITY: Project Engineer /Principal’s Representative
text | 17b38944-42d8-4ee7-9013-cbacfe35864f |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 2.7 - Disposal of Material
label | 24f59588-86fb-45a9-bbe3-1af007a39135 |  | note | FREQUENCY: Each Lot
label | fe3365bf-0894-4137-a545-94f24da1c4fa |  | note | ACCEPTANCE CRITERIA: Surplus material, debris and demolished material will be sorted into:
label | aa378005-fdeb-40dd-82a5-c16cee484b17 |  | note | - Hazardous Materials
label | 5f630e38-0e7e-447f-87fe-e1feee44cca4 |  | note | - Non-Hazardous Materials;
label | 3feafac6-b0ad-4024-9d48-9a64599cc045 |  | note | - Clean fill;
label | 218724c3-5873-45ef-ac94-38440e940b87 |  | note | - Crushed Clean Fill;
label | d29c052c-a225-473a-a7fc-2b8594445b07 |  | note | - Salvageable Materials.
label | e5983dfa-1d5f-4357-960d-47514a9c7012 |  | note | REFERENCE DOCUMENTS: Jacobs – Zulu Spec. Cl2.5.1
label | f26dc104-3362-44f9-ba8a-626c8bed0180 |  | note | INSPECTION/TEST METHOD: Verify
label | eda4b230-8fd0-4397-a7d7-6123d922f999 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 3787253b-19b0-450e-907f-dd892d623622 |  | note | HP*
label | 59e42ada-0222-462b-b446-3fa19ee00417 |  | note | RESPONSIBILITY: Project Engineer/ Foreman
text | 776ebdb9-fb8e-418d-a762-a33947b69f49 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.8 - Containment of Demolished Materials
label | 81e0cf8a-79d5-4a35-af81-7b12bdac21c6 |  | note | FREQUENCY: Each Lot
label | 6d4cffeb-a767-48af-b994-6d840f216a78 |  | note | ACCEPTANCE CRITERIA: If materials are to be removed from site upon completion of work, the stockpile areas are to be cleaned up to their original condition.
label | 7df5110c-ef4d-4905-8fc9-06bac6388ed1 |  | note | REFERENCE DOCUMENTS: Jacobs – Zulu Spec. Cl2.5.2
label | b6bbf836-e025-4f46-a405-aeeeffab9d5b |  | note | INSPECTION/TEST METHOD: Verify
label | 8aa8ba41-ef86-49c7-b20b-0d524761876a |  | note | RECORD OF CONFORMITY: This ITP signed
label | e41b6d1c-4312-4256-82ce-3881b4ac627c |  | note | WP
label | fd9640f7-0b24-4641-be51-7489e012365e |  | note | RESPONSIBILITY: Project Engineer/ Foreman
text | 19a770aa-090b-4c01-add1-f6c6c08b2fd1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.9 - Completion
label | 8c0a8af2-171a-44e5-b746-b595b637f2e4 |  | note | FREQUENCY: Each Lot
label | 24a7cc66-a58d-4574-9a62-629c145ae512 |  | note | ACCEPTANCE CRITERIA: The Contractor must give at least one working days’ notice of completion of demolition.
label | 2929d513-4c47-402e-ba69-fcbab0a9065c |  | note | REFERENCE DOCUMENTS: Jacobs – Zulu Spec. Cl2.7.1
label | fe81ed52-0c48-4054-ab15-ada4c25cc7fb |  | note | INSPECTION/TEST METHOD: Verify
label | e66e31ef-cd24-47e7-824d-5d832fe7b6d1 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 0b053fb2-7593-4a53-8a09-8385f55fce7f |  | note | HP
label | 38f5cce7-6be3-428e-8924-5e30282a08e7 |  | note | RESPONSIBILITY: Project Engineer /Principal’s Representative
text | c0583892-c300-49ac-a5dd-4fa154cce992 |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | FULTON HOGAN FINAL INSPECTION - "On behalf of Fulton Hogan, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract".
text | 338116f3-101f-42df-a8cd-418b7b528ecd |  | textbox | Name:
text | 8c5c46f1-6015-4f9b-90a6-eff376768e70 |  | textbox | Position:
checklist-sectioned |  |  | checklist | ITP 027 - Grouting Frame & Lid for In-Situ Pits | itp |  |  |  | Yes | ITP 027 - Grouting Frame & Lid for In-Situ Pits | 6ac1cada-79dd-46de-9806-1be3d2bfc050
checkpoint-group |  |  | section | ITP 027 - Grouting Frame & Lid for In-Situ Pits
checkpoint-status |  |  | checkpoint | 1.1 Materials & source Approval
label | d9860d8f-e085-4ce5-a6f5-8f83afbacd4f |  | note | FREQUENCY: Pre- commencement
label | fc24f731-e23e-4ca4-8545-5f316c545f8d |  | note | ACCEPTANCE CRITERIA: Grout used for casting Gatic frame and lids shall be only those approved by the superintendent:
label | ffb73bf9-0302-4123-9524-22acfd55e50c |  | note | Refer to Aconex Correspondence: DCWC- MGT-PMA-000099 for material approval
label | bca31514-0cac-4b9e-adfd-86b623630472 |  | note | REFERENCE DOCUMENTS: Material Data Sheets& Aconex Approval: DCWC-MGT- PMA-000099
label | 11842d29-3998-4c41-9c91-c1c8d8970ca5 |  | note | INSPECTION/TEST METHOD: Aconex Approval
label | bff18319-17d6-450d-994b-3914f43dfa0e |  | note | RECORD OF CONFORMITY: HP*
label | 2abedbd5-15e0-46ba-a11d-832e765cad75 |  | note | RESPONSIBILITY: FH Engineer and Jacobs
text | 28843508-9563-4fea-95ef-d13c7bf86230 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 Grout Type
label | 8fe60114-e4a2-4ddf-b1fc-ffce6c2b2d25 |  | note | FREQUENCY: Each Lot
label | a4c6ea2f-e610-4115-8cee-4ea086ceb17f |  | note | ACCEPTANCE CRITERIA: Grout for In-Situ structures shall be as approved by the superintendent:
label | 565e2188-cbf6-4d36-914b-3ab07cd7584a |  | note | Conbextra C – To be used for grouting in Gatic Frames and covers where the rebate is less than 150mm.
label | 60569c99-ca14-4708-ad7b-eb0199fd59c8 |  | note | Conbextra Deep Pour – To be used for grouting in Gatic frames and lids where the rebate exceeds 150mm.
label | 9200e583-128b-43d3-aefc-eff54d25de23 |  | note | REFERENCE DOCUMENTS: Drawings Aconex Correspondence: DCWC-MGT- PMA-000099
label | 95576d8c-2725-4af8-8ab7-1343b76b9657 |  | note | INSPECTION/TEST METHOD: Verify
label | f3a0b723-1390-4498-a4a6-30bcfcca43ac |  | note | RECORD OF CONFORMITY: IP
label | a9330c85-f29e-491a-b227-20c2b959e4fb |  | note | RESPONSIBILITY: FH Engineer
text | 5a1ee81e-74b1-4ae8-a3c8-c2de83a96304 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 Formwork
label | a86d03c8-7028-4c2a-b762-589758681b4f |  | note | FREQUENCY: Each Lot
label | 48cef0e3-a9f1-4148-93e5-66b5da83ba71 |  | note | ACCEPTANCE CRITERIA: Formwork / Reverse Shall conform to shapes, lines, levels and dimensions of the concrete shown or indicated on the Drawings.
label | 7d35ff22-6c93-4474-8a01-712fc5991a5e |  | note | Variation in cross sectional dimensions +/- 6mm
label | f4c4f038-9341-42b1-8802-0b68189540a0 |  | note | Misplacement from specified position +/-20mm
label | d784bb89-fe00-4542-8cff-61f59d22a388 |  | note | Permissible surface irregularities +/-10mm
label | 5c4ee9ef-c215-4ffb-b00a-95ec7325a5bd |  | note | REFERENCE DOCUMENTS: CP14038-AIR- DET-PM-SP- 0002-D-12.4.6
label | 1ff8b568-b427-402e-a412-07588e5eed19 |  | note | INSPECTION/TEST METHOD: Verify
label | ad5febd3-3501-47c0-9834-2b225875900b |  | note | RECORD OF CONFORMITY: IP
label | 18933996-11d1-4ee7-bec8-468b54cc1e9c |  | note | RESPONSIBILITY: FH Engineer Surveyor
text | 88531f4d-6772-4c9f-9cca-aa3e43b895b3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Grouting Pre-Pour Inspection
label | 1b3453f8-0d4d-47be-b737-db112ffa562e |  | note | FREQUENCY: Prior to grout Pour
label | c802ba02-776f-43f7-8b39-f75f0f53d88d |  | note | ACCEPTANCE CRITERIA: Surface to be grouted shall be free from oil, grease, or any loosely adhered material. Surface to be prepared as per manufacturer recommended guidelines
label | 35a8ee60-68f8-455d-9353-7d24008e9d40 |  | note | The surface to be grouted shall be pre-soaked with water. Prior to grouting, any free water shall be removed.
label | 5288301f-3c9e-47fb-9658-8e83152ce70c |  | note | REFERENCE DOCUMENTS: Fosroc Conbextra C TDS Fosroc Conbextra Deep Pour TDS
label | 3013f3f0-bfc4-4193-b17d-6660c5cb669a |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 6ff48dd7-f60f-4ce3-91c4-ef489ba4147d |  | note | RECORD OF CONFORMITY: IP
label | 46f3f869-866b-454e-b1ce-63021246b2a3 |  | note | RESPONSIBILITY: FH Engineer
text | 4773f360-ea69-4ceb-906a-7849437c7173 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Curing and Finishing
label | 27b72988-3e29-4d99-8bf3-2b71f47548f4 |  | note | FREQUENCY: Each Lot
label | 1ec02ed8-cb20-4a9a-b445-a4215df5ec52 |  | note | ACCEPTANCE CRITERIA: Grouted Surface to be cured as per manufacturer recommended guidelines:
label | 6e6048f7-2e1f-4109-9729-d3f0a8cb66c4 |  | note | On completion of the grouting operation, exposed surfaces shall be cured through the use of a curing membrane or continuous application of water and/or wet hessian.
label | 2ed1bc0b-929b-49de-9302-f86d95d396d5 |  | note | REFERENCE DOCUMENTS: Fosroc Conbextra C TDS Fosroc Conbextra Deep Pour TDS
label | 03078fd7-df15-4410-a726-815430c34b53 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | e979e60b-0177-446b-b849-6f550e709435 |  | note | RECORD OF CONFORMITY: IP
label | 5c4bb768-fe17-4d04-90f7-f3981de2d6db |  | note | RESPONSIBILITY: FH Engineer
text | 329e5149-eef5-4e64-ae1b-f967c7423173 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 343b39c9-4339-4f92-9fdb-d4d2aaa28520 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 6c0c2128-e1c2-44a8-b995-7324e71827a3 |  | textbox | Print Name:
text | 28d97d82-ca80-4826-ab28-9619b206198d |  | textbox | Position:
text | b1f146c1-763f-44b0-a8f9-e09649e16d76 |  | textbox | Date:
checklist-sectioned |  |  | checklist | ITP 024 Miscellaneous Structures | itp |  |  |  | Yes | ITP 024 Miscellaneous Structures | 6b7ad6b1-4f4f-4fed-89f5-a1aa8c695b18
checkpoint-group |  |  | section | ITP 024 Miscellaneous Structures
checkpoint-status |  |  | checkpoint | 1.1 The current revision drawings are being used including subcontractors copy
label | c034f0c7-99ca-4e59-9612-6abba3b855f7 |  | note | FREQUENCY: Prior to commencing works
label | 23e66015-6621-415f-a6c5-9b76245d3bbe |  | note | ACCEPTANCE CRITERIA: Current revision drawing is being used including the subcontractors copy. Current revision to be obtained via Aconex.
label | c2961d30-c897-4855-bf7c-a881abb826c4 |  | note | REFERENCE DOCUMENTS: Drawing & drawing registers
label | 953aae3c-90a2-4ce7-931a-5fe27bf5815c |  | note | INSPECTION/TEST METHOD: Visual inspection
label | af31922e-05c5-4b6d-92df-d8a04adaba4b |  | note | RECORD OF CONFORMITY: Up to date drawings and this ITP signed
label | 0c7bd9d2-fd79-4d64-b8b7-575c95d5075b |  | note | HP*
label | d300bb7a-c04d-4bb5-ac0b-aee8f22903ef |  | note | RESPONSIBILITY: FH Engineer
text | 8e289be8-5fb5-4e77-ba44-7ba78377ac9b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 Setting out for miscellaneous structures
label | 9648b03b-e52f-4f5a-8db7-db873535f414 |  | note | FREQUENCY: Prior to start
label | eb2a9774-d493-4bcb-9d42-c4d2900c1cef |  | note | ACCEPTANCE CRITERIA: Conformance with Jacobs for Construction Drawings and pipe penetrations in the correct locations.
label | a53a3808-c4f7-429d-91d0-61ef839fe298 |  | note | REFERENCE DOCUMENTS: WP 006
label | 5bfb79c9-2c8b-435b-af4c-cb8ad0b345c1 |  | note | INSPECTION/TEST METHOD: Verify
label | 0e5650ba-f822-487c-8157-e41427d61b35 |  | note | RECORD OF CONFORMITY: This ITP Signed
label | 2ce87b5a-167b-4425-a0da-5eedf43c9f9f |  | note | SCP
label | 2844e27b-b04e-497f-b381-7d0aaea4ffbc |  | note | RESPONSIBILITY: FH Engineer / Surveyor
text | 5dba8479-fc94-4420-a591-5be821c82c82 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 Materials & Source Approval
label | 7ba186ec-5eb9-453a-901c-19aec1c705fa |  | note | FREQUENCY: Pre commencement
label | 4429948b-b585-4a49-8907-5cada9b11067 |  | note | ACCEPTANCE CRITERIA: Details submitted to Superintendent regarding: • Ready mixed concrete supplier; and • Test Certificates demonstrating compliance of the reinforcement with the requirements of AS 3600
label | 5e1303f0-f52a-48ff-9417-a9cf3d424f52 |  | note | REFERENCE DOCUMENTS: CP14038-air-det-pm-sp-0002-c-8.2.3
label | 739af639-4796-417d-a20a-0d492a788225 |  | note | INSPECTION/TEST METHOD: Verify
label | c29cae7d-a1d0-48e1-83bb-31735e193e2e |  | note | RECORD OF CONFORMITY: Aconex Correspondence
label | 81b47184-9054-4ca6-a927-6f0dabdbd399 |  | note | HP*
label | b3e37585-51cd-4ae9-a8a7-325f3740db42 |  | note | RESPONSIBILITY: FH Engineer - Jacobs
text | 98f2128b-2c13-4c4a-b6d0-ed66c1c114f5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Materials
label | e5fe43a8-b3ba-496a-ad51-a2760ec20846 |  | note | FREQUENCY: Each delivery
label | aeabc632-c1bc-4942-9467-46f440177e4d |  | note | ACCEPTANCE CRITERIA: Flush-out riser covers to be shall conform to the design drawings and shall be Class G-under aircraft pavements.
label | 3173ff15-3220-437d-94c1-8cfa54634e8e |  | note | REFERENCE DOCUMENTS: CP14038-air-det-pm-sp-0002-c-8.2.3
label | 48b08f8a-f242-4863-b6bf-eab00700769c |  | note | INSPECTION/TEST METHOD: Verify
label | 9a476eb0-2222-4644-8ee9-38c43a8e56ce |  | note | RECORD OF CONFORMITY: Receival
label | 0744e7a0-b7db-45b7-acbc-4eabd97deac2 |  | note | IP
label | 353ecf35-5f0b-469a-bbfe-ef9e531947f2 |  | note | RESPONSIBILITY: FH Engineer
text | 3e6176e8-1f49-443b-9152-aa1306604f74 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Concrete Mix
label | 3e7d1321-f51f-4c0a-b138-e112dd1acd0f |  | note | FREQUENCY: Each lot
label | a3b3be1b-48ae-4409-b7a0-1ab958f5242d |  | note | ACCEPTANCE CRITERIA: Concrete for miscellaneous structures shall be as specified in drawings, typically it will be as follows; • Pipe Protection (Single Pipe): 32MPa/20mm • Pipe Protection (Multiple pipes >4 pipe): 32MPa/20mm • Pipe Protection (Multiple pipes 4 and above): 40MPa/20mm • Flush-out risers: 5MPa lean mix • Swale: 32MPa/20mm
label | 3e913164-b1b4-4e3b-bb6b-ccb785146ad1 |  | note | REFERENCE DOCUMENTS: Drawings CP14038-air-det-pm-sp-0002-c-12.3.3
label | 1c6e0590-8e29-4715-be72-d7e47eb98c68 |  | note | INSPECTION/TEST METHOD: Verify
label | c989fd15-5116-4dfd-a2ce-1cf9d40ba67d |  | note | RECORD OF CONFORMITY: Mix Design
label | aaba6604-f22d-4240-9d71-047885468b35 |  | note | IP
label | 96a62fa9-4b39-43db-b96b-293e7888d458 |  | note | RESPONSIBILITY: FH Engineer
text | cc7e3151-2e9d-499d-b63b-5c8ed64eadcf |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.1 Excavate
label | c799c25f-fa0b-4a23-9574-a7be2a95c278 |  | note | FREQUENCY: Each lot
label | 8916b6a6-dcd9-4f78-ba90-ed5c8a686965 |  | note | ACCEPTANCE CRITERIA: Excavation depth shall be as per specified or as shown on Drawings to accommodate structures.
label | 72af02c7-40d1-4f9e-9b4a-733e7ebf91af |  | note | REFERENCE DOCUMENTS: CP14038-air-det-pm-sp-0002-c-8.2.4
label | f515e4a9-bd81-46b3-86a8-602b52fd9a17 |  | note | INSPECTION/TEST METHOD: Verify
label | 8179b84c-18dc-4ba1-acd6-0e839c18b6f1 |  | note | RECORD OF CONFORMITY: This ITP signed
label | e4a413cb-b730-4003-971d-0342c03066ca |  | note | IP
label | b37e45b1-ba2b-44e6-acfe-887cdb93bd51 |  | note | RESPONSIBILITY: FH Engineer
text | 4daba287-1a76-42f2-9fb1-f5efddea847b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Confirm Ground
label | 903362cd-1ed4-497a-b465-4fb163ef2e6f |  | note | FREQUENCY: Each lot
label | 134d6744-53d6-4871-8100-df7e9cff7b7e |  | note | ACCEPTANCE CRITERIA: Completion of excavation and inspection of subgrade materials. Minimum Allowable foundation bearing pressure is 130 kPa.
label | b5a91fdd-b8d8-4901-a202-72d2b621a52c |  | note | REFERENCE DOCUMENTS: WP 006 Pit Drawings CP14038-air-det-pm-sp-0002-c-12.4.1
label | 571a3cd4-5363-4466-b4ed-d894cfe75556 |  | note | INSPECTION/TEST METHOD: Verify
label | ac4e82bc-821a-4b35-9455-842fb3fa8d52 |  | note | RECORD OF CONFORMITY: DCP Results attached and fill material (if required) Test Result
label | 8273d230-9aca-4a7b-b1ec-b1ba67984a8d |  | note | HP*
label | 48a1255c-685d-4b54-a73c-9cea090a0b1f |  | note | RESPONSIBILITY: FH Engineer
text | c3975815-62c6-4093-aa03-8565f9af6fcc |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Formwork
label | ba32b5d3-e67f-4126-bd82-05fb40ae131e |  | note | FREQUENCY: Each lot
label | c489b013-5695-41b3-a900-3635f237c616 |  | note | ACCEPTANCE CRITERIA: Formwork / Reverse Shall conform to shapes, lines, levels and dimensions of the concrete shown or indicated on the Drawings
label | 72b74ce5-6d30-4671-b38b-5c7f8534341a |  | note | REFERENCE DOCUMENTS: WP 006 CP14038-air-det-pm-sp-
label | 8ff518d6-9504-4fbe-be9e-caa4eab01a44 |  | note | INSPECTION/TEST METHOD: Verify
label | 066001a7-85a6-445d-ac80-817e5166388c |  | note | RECORD OF CONFORMITY: This ITP signed
label | 6804b2b6-b865-4b83-99a1-b75a857323d0 |  | note | IP
label | c38a0ecc-b390-4ef1-81ec-6bc8a380c6d8 |  | note | RESPONSIBILITY: FH Engineer/Surveyor
text | 6f774ab1-a8a2-449d-a9df-84ceea30ffa4 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.1 Materials
label | 601839e8-16db-4182-ad08-abea818a577e |  | note | FREQUENCY: Each lot
label | 7e9cabc9-6755-4b11-a313-d1383f4ce596 |  | note | ACCEPTANCE CRITERIA: Reinforcement shall be grade 500N hot rolled deformed bars unless noted otherwise on drawings. Steel shall not be bent or straightened on site without approval from Superintendent
label | 07591ed5-8a9b-4511-bb61-ab03829b8556 |  | note | REFERENCE DOCUMENTS: AS/NZS 4671 CP14038-AIR-DET-PM-SP-0002-C-12.3.7
label | 9545f5fa-d665-4b47-87d3-5a78a7b7cbf6 |  | note | INSPECTION/TEST METHOD: Verify
label | b264c785-17e4-410b-a273-ef17a34ffc28 |  | note | RECORD OF CONFORMITY: This ITp signed
label | bae3b47e-d77c-4ce7-b1ac-702c7260686d |  | note | IP
label | 593b313e-097e-4ccb-a36b-2b5792d8741d |  | note | RESPONSIBILITY: FH Engineer
text | 0ced4816-006f-4f8a-841d-042296398743 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Reinforcement Installation
label | 37f2e9ed-6fcf-4891-be1b-210732972756 |  | note | FREQUENCY: Prior to concrete pour
label | 26997dc0-aa8f-49a5-bd41-cd52d1628e90 |  | note | ACCEPTANCE CRITERIA: Pre Pour Checklist Completed: • Position and spacing check and recorded • Cover checked and recorded • Reinforcing supports checked and recorded • Laps at required length
label | b4a2e91f-f4ea-4de5-9658-f0ae7f28ee07 |  | note | REFERENCE DOCUMENTS: WP 006 CP14038-AIR-DET-PM-SP-0002-C-12.3.7
label | f338165e-c545-4b57-a135-218d7dfb43ba |  | note | INSPECTION/TEST METHOD: Verify
label | 3dee35d1-7981-47df-80b8-17f05c0c31cd |  | note | RECORD OF CONFORMITY: Pre-pour inspection list
label | b9f4e235-80d2-4930-8fb9-ebaf715c3066 |  | note | IP/ HP*
label | dfaa43d9-c284-4742-8e0f-2d5b1e099410 |  | note | RESPONSIBILITY: FH Engineer
text | 86cf028f-f47d-4a8c-847b-1acc5d40dcee |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.1 Pre-Pour Inspection
label | bed027cd-bde4-490c-a709-9dfb84d4c970 |  | note | FREQUENCY: Prior to concrete pour
label | e7f984c6-ad2d-465a-a392-47d41ac62383 |  | note | ACCEPTANCE CRITERIA: Superintendent to perform final Pre-pour inspection. Fulton Hogan to notify Superintendent 24 hours in advance to pour concrete to enable the formwork and reinforcement to be inspected and approved.
label | ebe49128-921b-42a7-af67-7482fb1e5a19 |  | note | REFERENCE DOCUMENTS: WP006
label | 32535374-f10c-4f0a-a8ed-127db51f51a4 |  | note | INSPECTION/TEST METHOD:
label | 20ffb631-69fb-4b96-be6a-705fcd6ba5b4 |  | note | RECORD OF CONFORMITY:
label | f448730a-d0f1-487d-9bdb-2d0d5bcf9254 |  | note
label | 2fc88d4a-ed95-4dee-8865-b8017a96100e |  | note | RESPONSIBILITY:
text | 77f58c8a-ef32-440d-97a2-5e22aeafbead |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Pour IN-Situ
label | 1d1e1528-18f5-4ec1-b135-c3ca3b5dd9ba |  | note | FREQUENCY: Each lot
label | 9d9acab0-c354-4d3c-9368-49918de38332 |  | note | ACCEPTANCE CRITERIA: Concrete shall be placed within in 90mins from batching. All concrete supplied for concrete structures shall be subject to project control testing in accordance with AS 1379.
label | 5310fc4e-04c4-46bc-bd43-aa77625748f5 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002-C-12.4.8
label | 9e34f99b-3ff2-429c-896d-1dbeff43756a |  | note | INSPECTION/TEST METHOD:
label | 95f49755-ad86-4ff3-98cd-e3b730d70bf1 |  | note | RECORD OF CONFORMITY:
label | 526d3fba-d0db-42bc-bb45-a227a7e3e10c |  | note
label | 22d1e744-97db-42b5-adb8-05abf01d88f2 |  | note | RESPONSIBILITY:
text | a804c612-feef-43d8-b0a5-b39321ad2f4a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Concrete Testing
label | 70aa6a7d-6365-496a-9b2a-ff93189842f0 |  | note | FREQUENCY: Each lot
label | b92e9206-66db-48aa-8521-53ce2841233f |  | note | ACCEPTANCE CRITERIA: Pit - Each pour 1 slump (nominated slump +/- 10mm) & 3 cylinders to be cast per test. Density cylinders?
label | afc0c2ea-07e6-4315-abf8-fa9949c6400d |  | note | REFERENCE DOCUMENTS:
label | 8357f4f8-f08f-45fd-a468-73c3f057c5d4 |  | note | INSPECTION/TEST METHOD:
label | dc423f80-0cfe-439f-b16b-a35004ae18a9 |  | note | RECORD OF CONFORMITY:
label | 2c116117-a346-4871-9bca-46f8b7590223 |  | note
label | c2b6a9f1-1b07-4d45-bf1a-bd1e53c11720 |  | note | RESPONSIBILITY:
text | 79d40d1d-5d2d-426f-b1d6-04c7634aba50 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Concrete Traceability
label | c0666a20-f4c1-413b-a4e0-968ef355bef5 |  | note | FREQUENCY: Each lot
label | aa006af8-46b1-44e7-a24a-0f18282fa556 |  | note | ACCEPTANCE CRITERIA: All concrete delivery information to be recorded on CL 006B – Concrete Pour record sheet.
label | 72568cd7-2b24-45fd-81cf-a182c2a82151 |  | note | REFERENCE DOCUMENTS: CL006B/WP006
label | 0439a5dc-e337-40e4-a62c-a1701749f3c6 |  | note | INSPECTION/TEST METHOD: Record
label | e5f2d7d0-998d-4c61-971b-2e6da47da4fe |  | note | RECORD OF CONFORMITY: CL006B
label | 242f61b1-4325-49c5-9496-884eb01e8f1d |  | note | IP
label | 0c821614-b14b-4f4e-a6d8-66b77f08dbd6 |  | note | RESPONSIBILITY: FH Engineer
text | 1d27e9c1-17f0-4420-adca-2e38d78ddcfa |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Finishing & Cutting
label | aecbc85a-8a87-415a-92ce-224515e49464 |  | note | FREQUENCY: Each lot
label | b2c05028-36f3-4d10-8818-402e1f5576b1 |  | note | ACCEPTANCE CRITERIA: Concrete to be vibrated to ensure compaction and air voids removed. Screed finish required on exposed surfaces. Concrete shall be moist cured or coated by an approved curing compound for a period not less than seven days unless approved by the Superintendent.
label | 989cb901-705a-48e9-8a55-f2bc33c2c34e |  | note | REFERENCE DOCUMENTS:
label | b1657f31-d856-4a8c-92c2-71779d3fa875 |  | note | INSPECTION/TEST METHOD: Verify
label | d6fc59b7-770a-4a76-b629-42c364909042 |  | note | RECORD OF CONFORMITY: CL006A
label | c75e5204-d21c-4a30-bda0-84119545f1b2 |  | note | IP
label | 9030862d-b036-4153-8478-89d15338ee10 |  | note | RESPONSIBILITY: FH Engineer
text | e2c9fb74-df97-4464-8ee6-9d2252295e7b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Construction Joints
label | a97ebbc1-04db-4538-8c70-8b4b1c20c370 |  | note | FREQUENCY: Each lot
label | 294c04bd-c180-4677-8833-ab86744746ca |  | note | ACCEPTANCE CRITERIA: Whenever the work of placing concrete is delayed so that the initial set has taken place as determined by the Superintendent, the point of stopping shall be deemed a construction joint and formed accordingly. All concrete lined swales shall be provided with contraction joints at not less than 3m intervals and with an expansion joint installed at 15m intervals
label | 3be3eda7-c99b-4dbc-ab0b-4fdfe9dbe300 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002-C-8.5.1
label | 484b80d5-b008-43dc-b94f-56a1a0ba4453 |  | note | INSPECTION/TEST METHOD:
label | db162fc9-9f0e-4b9e-81fb-f6aa8db1fcfa |  | note | RECORD OF CONFORMITY:
label | 74ca786f-4714-447c-80d5-abce37366468 |  | note
label | ca7eb28c-cf25-4cf1-a2a5-8ddc51e95df1 |  | note | RESPONSIBILITY:
text | 734f3a67-e24c-4b79-ae4f-33265708367a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.1 Removal of Formwork
label | 22a93014-d3e5-4729-8fcb-b6ca1c8d56a2 |  | note | FREQUENCY: Each lot
label | 00d2cf20-9401-4c51-b399-59a5dbd4216f |  | note | ACCEPTANCE CRITERIA: Forms shall remain and be maintained firmly in place until the concrete has attained the necessary strength to support its own weight.
label | 92c02692-d035-4f38-9731-f4b6325d2275 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002-C-12.4.5
label | dda83922-fa62-4d91-bb1e-1b1017bd8c37 |  | note | INSPECTION/TEST METHOD: Verify
label | f3941514-874f-4913-b8ec-ec9b9041ef4a |  | note | RECORD OF CONFORMITY: This ITP signed
label | 1b401e47-9e1f-45bb-9c2d-419e8cdf5879 |  | note | IP
label | c3093d15-c295-4082-aa93-ada35146ad4a |  | note | RESPONSIBILITY: FH Engineer
text | 30cdd9ea-4cb7-48f4-a1ef-83eb065d05d8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Post Pour Checklist
label | 6e1b6eee-cbfc-44ef-bc2e-cee9a6f23a8d |  | note | FREQUENCY: Each concrete pour
label | 55fb4da7-7218-4423-b033-598a65124d44 |  | note | ACCEPTANCE CRITERIA: CL 006C – Post-pour Checklist completed and signed by Fulton Hogan.
label | ec54f4d6-6757-4948-a633-2301a735983a |  | note | REFERENCE DOCUMENTS: WP006
label | 1f4c0468-fb57-4d83-bf3c-4e70ae1a7580 |  | note | INSPECTION/TEST METHOD: Verify
label | 160bfd80-efa5-40d9-83b5-61ddbb86cdff |  | note | RECORD OF CONFORMITY: CL006C
label | acbff331-91a1-45da-a48a-e06abef395b3 |  | note | IP
label | 5fc5558b-e349-4782-a2a3-9049f7647031 |  | note | RESPONSIBILITY: FH Engineer
text | f4fd2cd1-2eda-46d2-8f46-7d5cda6cc1f0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Quality Report
label | e6c8a06f-a404-45a6-bb1a-dbdd82b9432f |  | note | FREQUENCY: Each lot
label | 17875a44-9898-4991-b319-6306a586ffe4 |  | note | ACCEPTANCE CRITERIA: Within 3 weeks of completion (doesn’t specify time in spec) of Works, submit to Superintendent via Aconex report detailing the results of all quality control and testing
label | a6cb9313-3c39-4719-9cbd-d68ed0059906 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002-C-12.4.14
label | 6c04b17b-a35b-4d94-8801-29f3fb276be1 |  | note | INSPECTION/TEST METHOD: Verify
label | 81ebc28f-60a1-4ca6-9f90-5dcf4d46c0ef |  | note | RECORD OF CONFORMITY: This ITP Signed
label | 1581bcb2-acd7-4fc6-bf8a-b708abe18ba8 |  | note | RESPONSIBILITY:
text | 5be9760c-cc00-4b5c-97c6-5961ca74cbfe |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | FULTON HOGAN FINAL INSPECTION - On behalf of Fulton Hogan, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 7b7ecd32-c726-4590-8b3f-41a775bbd16a |  | textbox | Name:
text | a30d0d67-0f8e-4e9f-91ca-5701cbb96dfc |  | textbox | Position:
checklist-sectioned |  |  | checklist | ITP - 002 Stripping and Bulk Excavation | itp |  |  |  | Yes | ITP 002 - Stripping and Bulk Excavation | 746fed23-935b-4e4e-93da-bd6dd94cfee2
checkpoint-group |  |  | section | ITP - 002 Stripping and Bulk Excavation
checkpoint-status |  |  | checkpoint | 1.1 1 Inspection and Test Plan
label | 3e266962-e228-401a-8f3e-fac878c0681e |  | note | FREQUENCY: Prior to commencing works
label | 8b96823d-607c-4137-b5a1-a3dbf60b58a7 |  | note | ACCEPTANCE CRITERIA:The Contractor must submit an Inspection and Test Plan to the Principal’s Representative for review, outlining the tests, frequencies of tests, certifications and Hold Points
label | db6c9679-afeb-4736-9226-59020acc93fb |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DETPM-SP0002-D-Cl / 3.2.1
label | 278ed27b-be2e-40f0-bc9b-606f9c42fdff |  | note | INSPECTION/TEST METHOD: Verify
label | 34e0558b-bb1e-4431-bcde-74c2f5886cf1 |  | note | RECORD OF CONFORMITY: This ITP signed
label | ee275aa5-459a-41ac-a304-fd9068071cfb |  | note | HP
label | 8f1fb32f-803d-4292-812a-85fce99bd226 |  | note | RESPONSIBILITY: Project Engineer/ Principal’s Representative
text | 5d5716b4-9b10-4cc5-9817-dbe7c0732d88 |  | textbox | Date Completed:
label | 0071def0-9a16-4651-9559-0af2a97b4994 |  | note | Hold point sign off reference: ACONEX: FHPLTRANSMIT-000141
label | d8040a61-2cf8-4f61-b12d-41a35b4bd0aa |  | note | Date: 22/7/19
checkpoint-status |  |  | checkpoint | 1.2 Current Drawings being utilised
label | f5c5fdee-b2f3-444e-9a03-c5b6820eed81 |  | note | FREQUENCY: Prior to commencing works
label | af0f48cc-639a-46d4-a580-bc37bba0cf88 |  | note | ACCEPTANCE CRITERIA: Current revision drawing is being used including the subcontractors copy.
label | 2a99c47a-5b79-4c2f-a32b-e1c10ca4ab7a |  | note | REFERENCE DOCUMENTS: Aconex
label | 5e9fa012-2f1a-46b8-b9be-f7021c644761 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 44142649-5aa8-4cea-b23d-11742cbfce01 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 58a2eee9-0a79-476f-b72a-2bb0e7b0b99d |  | note | IP
label | fe697cfe-cf56-4cf3-a090-47e34b97ae5b |  | note | RESPONSIBILITY: Project Engineer
text | 62e0bada-c304-404d-8b69-b27f88ae4022 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 Survey
label | 7984e315-5e46-4b4f-bd0b-8b3435102db0 |  | note | FREQUENCY: Prior to commencing works
label | 2f0e4473-28ca-4cfc-8ecf-d7d447e9a7f5 |  | note | ACCEPTANCE CRITERIA: Area has been surveyed, highlighting any areas where excavations should not occur (e.g. exclusion zone)
label | 5c8eb494-6c4e-4cd9-b609-9f4fac41e1ae |  | note | REFERENCE DOCUMENTS: Drawings/Permits
label | 2f928664-e2d7-4b66-a846-23d434bfa783 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 76e2714b-fffc-439c-a45d-8125adb05f7a |  | note | RECORD OF CONFORMITY: This ITP signed
label | c5b38c9e-405a-452a-b3cc-c57f1c714896 |  | note | IP
label | 812f7cac-59f9-40e2-ac59-858246d9afd5 |  | note | RESPONSIBILITY: Project Engineer
text | dd375a74-d714-41d6-9bab-836ca0d074d6 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.4 Implementation of all measures and controls
label | fef4a7a9-b74f-4a4d-b5b2-d8e4637e0110 |  | note | FREQUENCY: Prior to works
label | be7d60e2-6316-4d7f-a7bb-6ca0bf953755 |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS and WP
label | 8540020e-ceda-41eb-8d59-21b1211a0cb6 |  | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, SWMS, WP
label | dafcb22e-2441-4cab-97cb-a12721522523 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | c66633a1-06ff-4fc9-a63e-a5448d132880 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 9d3422f4-56ea-4b58-8534-e98a4b42ea22 |  | note | HP*
label | 16e2ebf1-bd5d-411b-ba7f-f4f27236467c |  | note | RESPONSIBILITY: Project Engineer
text | dc4bdf04-bfeb-4e2b-a8f5-ac23781243ce |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.5 APAM permits
label | 0286f378-b20d-4704-a5d4-1da6e7a56be5 |  | note | FREQUENCY: Prior to commencing works
label | b38d01bc-db1f-47ae-8945-666116382c9b |  | note | ACCEPTANCE CRITERIA: Excavation permit and if working near HV electrical. An Electricity supply Isolation form and cabling permit has been issued from Melbourne Airport
label | ad284347-d9c8-4c0d-bde8-d38ee7fe4d67 |  | note | Fulton Hogan Excavation permit issued to plant operators prior to excavation works
label | 66451e74-f0b7-4fb0-b6b2-a8d6087aa89a |  | note | REFERENCE DOCUMENTS: Excavation permit
label | 684edb61-3a3e-4242-b287-9385bf8583c5 |  | note | INSPECTION/TEST METHOD: Approved permits
label | 42729625-a1c7-4099-b895-ea6482892dbf |  | note | RECORD OF CONFORMITY: This ITP signed
label | 1825b95c-c472-44b5-835c-4bd78f978fb6 |  | note | HP*
label | 2066e599-95bb-4dc4-8ca8-12dce2790b5d |  | note | RESPONSIBILITY: Project Engineer
text | e5481409-fb3b-4dad-a19b-296482f7618b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.6 Maintenance of Pavements
label | 2d94a9b8-5903-419b-b3d3-6e3ffda323fe |  | note | FREQUENCY: Prior to commencing works
label | 412d6fef-384f-490f-899d-ce47ad316b17 |  | note | ACCEPTANCE CRITERIA: Prior to the use of any existing roads within the airport boundary and site access roads, the contractor shall carry out a joint inspection with the Principal’s Representative and provide a condition survey.
label | c2a05ae1-5fa5-4d5d-a71e-c666a63cce6b |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DETPM-SP0002-D-Cl3.3.2
label | 14b4cc94-d3cb-4924-bb76-85a064774d26 |  | note | INSPECTION/TEST METHOD: Verify
label | 45d7ad1e-64f9-44e0-a57c-29272f5f5f63 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 50c7c03b-24b7-4385-9d0f-93d383f27f01 |  | note | HP
label | 868ad2b5-b3cd-4e8f-a68b-633675a896ce |  | note | RESPONSIBILITY: Project Engineer/ Principal’s Representative
text | 17160721-102f-48b2-b1e0-06b89efc1b23 |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 1.7 Plant and Equipment
label | 9d004a59-e84b-4908-ab41-51901df323e3 |  | note | FREQUENCY: Prior to Commencing Works
label | 6bc08ac4-024c-4d6b-93a5-9c641b6d9185 |  | note | ACCEPTANCE CRITERIA: Plant and Equipment used in the works are appropriate to achieve specifications requirements. All plant inducted and inspected as per Fulton Hogan’s plant safety guidelines.
label | 6827c788-df9f-4c1b-9d2d-672d55b8355f |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DETPM-SP0002-D-Cl3.6.2
label | a92bc02c-cd29-404f-9a5b-609eb3a44a0f |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 3f3f59a5-8330-430e-a933-1c7b5fc22066 |  | note | RECORD OF CONFORMITY: This ITP signed
label | e27cd7c8-1d2d-4f29-b661-e5e2c23fdd55 |  | note | HP*
label | c2b5fe58-f63f-4002-992a-e397e0695ba7 |  | note | RESPONSIBILITY: Project Engineer
text | 2292adc9-eed0-4bbd-998f-ce523b1b55ff |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 Site Preparation
label | 08002ab5-564a-4c6b-8d2e-a08357be09db |  | note | FREQUENCY: Each lot
label | 810f5b5f-54c9-4157-8cec-4de11c1fb896 |  | note | ACCEPTANCE CRITERIA: All excavation and filling will be free draining to low points clear of the Works at all times;
label | 52f4dd8d-cfa4-455a-a502-48ad1c8365f6 |  | note | Sufficient pumps, well-points or other equipment for work area de-watered during the works shall be provided where required.
label | efeed085-fc05-4514-9b7f-6683f7d668fb |  | note | Existing drainage lines and water mains found to be traversing the site must be removed as shown on drawings.
label | 5ddfa865-0bd5-4a04-99a1-3d8d626b7f11 |  | note | Contractor must provide temporary pollution control devices or ponds in existing drainage systems and receiving waters.
label | a00b2498-e58f-4df4-8f8e-3c5599f3555f |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DETPM-SP0002-DCl3.3.3
label | aa6c8292-843a-4676-92be-793f912b596a |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | c4264db7-8d3b-4304-bb9c-3df45b38c426 |  | note | RECORD OF CONFORMITY: This signed ITP
label | 3a29e35b-3fcd-4480-b885-f75fe513bb68 |  | note | IP
label | feb787b8-767e-464b-aae3-08431ced69d5 |  | note | RESPONSIBILITY: Project Engineer
text | 63d8f0aa-f730-49d3-8e01-cdb2173dc5f6 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Dust control
label | b30de841-82e2-4e5b-9f42-b89b76364721 |  | note | FREQUENCY: Each Lot
label | 34c6c44e-fbde-4798-8750-37c391feecd4 |  | note | ACCEPTANCE CRITERIA: Prevention of dust during earthworks and subgrade preparation (Water Cart, tarps etc.)
label | 19ce5196-2875-4e67-8ade-c9fd0b3ead74 |  | note | Truck mounted water sprayer keeping dust moist to allow for reliable operation 24 hours per day
label | cf050d25-18b9-4865-a0b3-d1faa7a448c8 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PMSP-0002-D-Cl3.3.4
label | 21e5ab3a-1bb9-435e-9f9c-e5b22bb474ed |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 4b26272c-54de-42c9-9915-37465eb786c8 |  | note | RECORD OF CONFORMITY: This signed ITP
label | cc908f41-4183-47f7-a75e-28341c669eed |  | note | IP
label | 55e5a731-91a4-4245-add0-0706d56f36f6 |  | note | RESPONSIBILITY: Project Engineer
text | 50c547ac-d1af-4f56-8c1f-63ebb25e439c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Excavation
label | 76b1f7fe-4132-4844-98cd-650574f1fbaf |  | note | FREQUENCY: Each Lot
label | 75ebd87b-1be3-4cb8-9da0-86b884414325 |  | note | ACCEPTANCE CRITERIA: Contractor shall excavate every type of material encountered within the limit of earthworks to the lines and levels indicated on the drawings.
label | 59ec6bba-61f3-4f08-a26e-165a68353d12 |  | note | Where over-excavation occurs or filling is required the area must be filled with Fill to Clause 3.5.2 of the Technical Specification prior to watering and rolling.
label | 8cf5abd1-abff-45fc-ad6d-56c02395168a |  | note | All materials removed from excavations are to be classified by the contractor as topsoil, fill, concrete (for recycling) or unsuitable material.
label | 8d780d8f-4439-4e55-83e0-a7219cb31420 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DETPM-SP0002-D-Cl3.4.1
label | b7414ae7-98e0-46ca-930a-28f465ea3381 |  | note | INSPECTION/TEST METHOD: Inspection Point
label | 402937de-79d8-43af-86a6-10a2c7a1b80c |  | note | RECORD OF CONFORMITY: This signed ITP
label | 83062890-4a5d-442b-9f95-3cbf1f1e238b |  | note | IP
label | f4a288d5-11ff-43ab-8d11-df606e70e42d |  | note | RESPONSIBILITY: Project Engineer
text | 04c89cf3-afe6-42d7-9967-e717ff231d38 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Fill Materials
label | 9cac7911-be88-43c4-9c87-fff8719bf5d6 |  | note | FREQUENCY: Select Fill
label | ff477e56-a82e-4202-be3d-29f347a5e035 |  | note | ACCEPTANCE CRITERIA: Fill must meet the requirements of VicRoads Standard Specification Section 204 for a Fill Material Type B. Fill Shall have a minimum 4-day soaked CBR of 5% (95% standard compaction) and swell ≤0.5%.
label | b7d389c7-f5d3-45e8-9775-d704ab4bc393 |  | note | REFERENCE DOCUMENTS: Clause 3.5.2
label | 56a43ccf-31c2-4db0-a397-5b323daf5185 |  | note | INSPECTION/TEST METHOD: Verify
label | 9c956e17-134f-41e1-9bc9-0af5fd1f3032 |  | note | RECORD OF CONFORMITY: This ITP Signed
label | 3a3e2fb1-a5f5-48a3-85c3-0f5e67308dd9 |  | note | HP*
label | 47e45fb0-5723-48c0-a03a-bc62be8360ae |  | note | RESPONSIBILITY: Project Engineer
text | 41d84816-075b-4640-bd2b-d6818be7f9ea |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 0fee2af1-ab51-4309-966a-a7b81219f8a8 |  | note | On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | fc8582fb-1ee5-4564-9728-d32a29b5e9aa |  | textbox | Print Name:
text | 9c988a07-c008-4417-9fee-6708872f2761 |  | textbox | Position:
text | 7370b40c-c90f-4efb-8e20-580626badad9 |  | textbox | Signature:
text | 5407d3b2-c35d-46cf-b096-1765086880b0 |  | textbox | Date:
checklist-sectioned |  |  | checklist | ITP 006- In-situ Pits | itp |  |  |  | Yes | ITP 006- In-situ Pits | 7acc577b-5601-47cc-9e22-fdbb2702c27c
checkpoint-group |  |  | section | ITP 006- In-situ Pits
checkpoint-status |  |  | checkpoint | 1.1 The current revision drawings are being used including subcontractors copy
label | 3984eb15-a60b-46bb-a0de-d784a8ecdf2f |  | note | FREQUENCY: Prior to commencing works
label | e263beff-c91c-43cf-9065-2c93d7f9a372 |  | note | ACCEPTANCE CRITERIA: Current revision drawing is being used including the subcontractors copy. Current revision to be obtained via Aconex
label | 09984252-7222-458d-abf8-7ee7663f3bc6 |  | note | REFERENCE DOCUMENTS: Drawings and drawing registers & RFI Responses
label | f0930887-9a9a-46d9-961f-70ffde53ba38 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | a8077af2-4ecc-4557-b542-33d570d11f5c |  | note | RECORD OF CONFORMITY: Up to date drawing sets and this ITP signed.
label | 4636090a-a228-47de-b92d-365c2660752a |  | note | HP*
label | f76c49cd-c644-4de0-8128-56a9d3b0a20a |  | note | RESPONSIBILITY: FH Engineer
text | a57ac5c0-6abf-4d7c-9fd1-2567135294a5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 Setting out for miscellaneous structures
label | 7d921946-0eb8-4e02-ac40-0aa7da6bafc8 |  | note | FREQUENCY: Prior to Start
label | 54501655-9f1d-4e96-b502-001a0f80469e |  | note | ACCEPTANCE CRITERIA: Conformance with Jacobs for Construction Drawings and pipe penetrations in the correct locations
label | 8b9b48b1-a33e-435b-943a-eefccf037b3a |  | note | REFERENCE DOCUMENTS: WP 006/Drawings
label | 7c21d59f-df1b-47d0-a257-d3e3171db3e0 |  | note | INSPECTION/TEST METHOD: Verify
label | 0e18eac9-9f0c-4296-8c42-dc40f1062049 |  | note | RECORD OF CONFORMITY: This ITP signed
label | fc8a847f-9b10-485e-872c-ce18e1e81c59 |  | note | SCP
label | 0aa07f65-0d05-4c8b-9db7-e0ff9b6b0053 |  | note | RESPONSIBILITY: FH Engineer/Surveyor
text | a038191f-6e4a-49fc-b871-a1f0be2d9d0e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 Materials & source Approval
label | a685ed8c-434c-49e0-837e-7b0365f0b2e5 |  | note | FREQUENCY: Pre-commencement
label | 3888d69a-d53d-46e6-bc05-94e5b66afbc1 |  | note | ACCEPTANCE CRITERIA: Details submitted to Principal’s Representative for acceptance:
label | 0fc6af50-32cf-45df-842d-f5480f14b16e |  | note | Ready mixed concrete supplier
label | 0a39bd5b-a4ee-449f-af9e-a1caa1a729fd |  | note | Test Certificates demonstrating compliance of the reinforcement with the requirements of AS/NZ 4671
label | 70d0916c-0ce1-4d81-9fdb-66156eb1ef61 |  | note | Concrete mix design shall be submitted to the Principal’s Representative for review and approval not less than 5 days before pouring
label | 764d0321-560f-46c2-b745-84524e9a115a |  | note | All concrete shall be manufactured by an approved supplier unless specifically approved by the Principal’s Representative
label | 76c40994-4acb-429c-a746-3ffed08384bf |  | note | Concrete for pits shall be specified in drawings, typically it will be as follows: 40 MPa/80mm Slump/20mm Agg.
label | 86a387be-0fed-4d72-939f-1a028f49c508 |  | note | Reinforcement shall be grade 500N hot rolled deformed bar unless noted otherwise on drawings.
label | 270b574d-39e7-4ebe-a2b5-b05feaa6a578 |  | note | Test certificates demonstrating compliance of the reinforcement with the requirements of AS/NZ 4671
label | 72f1ca14-a5b4-4b89-8f64-72a21ab1b14a |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002-D-12
label | 77378401-88f6-4335-803e-128e61965018 |  | note | CP14038-AIR-DET-PM-SP-0002-D-12.3
label | 99caceee-7c1b-4bb0-b934-a555676e19e9 |  | note | AS/NZS 4671
label | c63e10a5-b08a-4c49-a482-46716c759fa0 |  | note | CP14038-AIR-DET-PM-SP-0002-D-12.3.7
label | f4d9a1e0-0f25-4b2a-bcb4-cb879bc39045 |  | note | WP 006
label | ac147a2f-1100-4021-94fc-792948bd74a9 |  | note | VicRoads 610 & 611.03
label | 91719d81-80c7-43fd-842f-88a48f174fad |  | note | INSPECTION/TEST METHOD: Verify
label | 7d65b400-27bc-4173-8f7c-3eb526014f62 |  | note | RECORD OF CONFORMITY: Aconex correspondence
label | 45877c58-f208-4ae3-9c2c-dd6a77edaa70 |  | note | HP
label | b17c223d-69ad-47b1-9bd1-ebc1c268391d |  | note | RESPONSIBILITY: FH engineer and Principals Representative
text | 4c77c806-5fde-4813-a7b7-e4ca47bdc4af |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 2.2 Materials & source
label | 9c30890a-e4f5-4949-9e58-3b8d0976221d |  | note | FREQUENCY: Each Delivery
label | 69c67e1c-3435-4d58-833e-8b848ff6cd84 |  | note | ACCEPTANCE CRITERIA: Pit covers, grates, lids and lintels shall be as specified on drawings and installed as per manufacturer’s recommendations
label | e7e7fb35-5501-4426-a944-5708d6eaecbb |  | note | REFERENCE DOCUMENTS: WP 006 / CP14038- AIR-DET-PM-SP-0002-D-8.2.3C
label | 9b2ce888-651e-42c9-b3dc-c9be8c2ad269 |  | note | INSPECTION/TEST METHOD: Verify
label | 03472f7a-ce4c-4aba-8e36-44405acccc8d |  | note | RECORD OF CONFORMITY: Receival Inspection Checklist
label | 92876d5b-8da2-4c37-b961-0eef23cd9aa8 |  | note | IP
label | f7ae8a7f-a17f-46d8-83d1-29a4b2b93189 |  | note | RESPONSIBILITY: FH Engineer
text | 0d4df783-e908-4c78-b549-b2e3e90b97a4 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Acceptance Covers Frames/Grates
label | 8b8b4809-76af-4f43-9182-fcd83d5b4336 |  | note | FREQUENCY: Prior to Start
label | a3a01689-3772-4778-a49f-71a6b59a0a14 |  | note | ACCEPTANCE CRITERIA: All Pit covers shall conform to Class G- Airside standards.
label | 256ed2a9-5166-4817-983e-098cd91c2564 |  | note | REFERENCE DOCUMENTS: AS3996-1.1/CP14038-AIR-DET-PM-SP-0002-D-8.2.1
label | 96306d84-4059-4399-88ce-2005a841cb81 |  | note | AS3996-3.1
label | b83033b8-ef73-40b3-86ac-e0eed9840c15 |  | note | INSPECTION/TEST METHOD: Verify
label | c9d47eeb-986c-4418-aa8e-6b6089cce818 |  | note | RECORD OF CONFORMITY: Receival Inpsection Checklist
label | 5df3d807-2498-4605-9163-a939e42dc71a |  | note | HP*
label | 0be720e2-c5fc-4e92-82f1-0ae68f7d8b0f |  | note | RESPONSIBILITY: FH Engineer
text | 1c21a2e4-426b-4b95-8454-3d1ca23ab759 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.1 Excavate Pits
label | 99ff1cd5-4dab-4087-8720-aa527c349e55 |  | note | FREQUENCY: Each Lot
label | 0f25ed69-28c8-4758-baab-99213015f879 |  | note | REFERENCE DOCUMENTS: Excavation depth shall be as per specified on drawings or as necessary to secure satisfactory foundation. Excavation shall include undercut as directed by the Principal’s Representative. Undercut shall be backfilled with compacted hard fill or blinding concrete as specified on the drawings
label | 1cbfb1ad-4c53-4320-bb80-f1e4855b42e0 |  | note | INSPECTION/TEST METHOD: Drawings. CP14038-AIR-SCH-CI-RP-0004 Rev B. CP14038-AIR-DET-PM-SP-0002-D-12.4.1 . CP14038-AIR-DET-PM-SP-0002-D-8.2.4
label | 4b71b466-e197-420f-9596-abe868c5565a |  | note | Verify
label | c47f0fb3-1b9f-4fd1-8c5e-405010c13d38 |  | note | RECORD OF CONFORMITY: This ITP signed
label | e23611ec-8786-448a-b940-9b8df715b07a |  | note | IP
label | afea82f0-7186-4470-a956-a0cb55afad34 |  | note | RESPONSIBILITY: FH Engineer
text | a32488c2-0bbd-4ff5-a5ad-2f07dec8a34a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Confirm Ground
label | 398095ea-8ad3-4cb5-a8c9-895e0492029a |  | note | FREQUENCY: Each Lot
label | c8b3b87a-7d8b-47b3-b8f5-cbd024db3f81 |  | note | Acceptance Criteria Pits shall be constructed on firm subgrade with a minimum allowable bearing capacity of 130kPa
label | 0ffd504f-6102-408b-8ef4-7df7f0f1b62e |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002-D-12.4.1. WP 006
label | 8b693879-1cc4-4ed7-afdd-ced364ead436 |  | note | INSPECTION/TEST METHOD: Verify
label | 3a399ff8-323a-495f-8a2b-91803fde7bb2 |  | note | RECORD OF CONFORMITY: DCP results attached
label | 4448a2c1-e0a3-4624-9cc3-b5d8f5642e04 |  | note | HP*
label | b04c5d7f-30e0-4754-899c-0b09fcb2c45f |  | note | RESPONSIBILITY: FH Engineer and Principals Representative
text | 813c19c2-0642-49a0-abd8-70d7bf8fd717 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Blinding
label | 021f21ed-b54b-4df6-bb02-8a24e736f127 |  | note | FREQUENCY: Each Lot
label | a8862ce7-a5f4-4129-bd0e-921851241c98 |  | note | Acceptance Criteria: Base to be poured: Pit: Minimum 50mm blinding (20Mpa) and Grated Drain: Minimum 50mm blinding (20Mpa)
label | 6bc8df05-760b-435b-ad87-5e95570676b3 |  | note | REFERENCE DOCUMENTS: Drawings
label | 4772156e-5756-41cf-8b0b-333e1614bc71 |  | note | INSPECTION/TEST METHOD: Verify
label | ab353798-e555-4ea1-affc-dd5062629e85 |  | note | RECORD OF CONFORMITY: This ITP signed
label | ba70a9fe-8de5-417f-bb7e-afa23b939f9b |  | note | IP
label | bcc2ff4a-0253-4c7b-a359-5a1c4d69d314 |  | note | RESPONSIBILITY: FH Engineer
text | fc6fec1b-7584-419d-95fb-7c3fb69c3040 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 Formwork
label | ff2e13f0-5506-4b7e-8954-99d870963dad |  | note | FREQUENCY: Each Lot
label | 14124a17-051b-45f1-966d-4273fceb5890 |  | note | Acceptance Criteria: Formwork / Reverse Forms shall conform to shapes, lines, levels and dimensions of the concrete shown or indicated on the Drawings. Forms shall be chamfered, bevelled or filleted at external corners, typically having a 20mm
label | 6d5a8d4e-e9ff-481a-903d-2440e6e7fccf |  | note | REFERENCE DOCUMENTS: WP006. CP14038-AIR-DET-PM-SP-00002-1-12.4.2
label | 18083b18-cb2c-4864-8856-a058fc9d7bb2 |  | note | INSPECTION/TEST METHOD: Verify
label | cc75fd6e-1466-49ea-a9bb-8a38b83fdda9 |  | note | RECORD OF CONFORMITY: This ITP signed
label | d01ae9e4-0581-4f02-a898-617ac05e9eb8 |  | note | IP
label | d0a287e3-330b-4475-b45e-003dac1c7f89 |  | note | RESPONSIBILITY: FH Engineer and Surveyor
text | 2f3d2560-09aa-4fe6-894a-fa137dbf04dc |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.1 Reinforcement Installation
label | 3cce4301-5c98-4cb7-b351-5e54f881c077 |  | note | FREQUENCY: Prior to concrete Pour
label | 8ec9c21e-e90b-4428-91e2-aa1490509641 |  | note | Acceptance Criteria: Pre Pour Checklist Completed: Position and spacing check and recorded , Cover checked and recorded , Reinforcing supports checked and recorded , Laps at required length
label | 48489a58-524e-46d3-b924-6f77c5794e51 |  | note | REFERENCE DOCUMENTS: WP 006. CL006A
label | d767d448-f685-4a8e-bddf-ac63f0fb5b1e |  | note | INSPECTION/TEST METHOD: Verify
label | 3dcc0adb-78a5-4741-931a-ff1cece88004 |  | note | RECORD OF CONFORMITY: Pre-pour inspection checklist
label | e8e31c4a-bc5f-402b-b3cc-c57747888994 |  | note | IP
label | 2ad1fb0f-58b1-4eb6-b3ae-d52db7c14b32 |  | note | RESPONSIBILITY: FH Engineer and Surveyor
text | 60174ead-8834-4935-b034-44644fe435ad |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.1 Pre-pour Inspection Base
label | ae56a4a6-8e09-4ea0-ae4c-a89b2b859222 |  | note | FREQUENCY: Prior to concrete pour
label | 194367e1-75b6-48b0-9796-7c877b611977 |  | note | Acceptance Criteria: Principal’s Representative to perform final Pre-pour inspection. Fulton Hogan to notify Principal’s Representative 48 hours in advance to pour concrete to enable the formwork and reinforcement to be inspected and approved
label | 9f5f60ab-77a3-4ffa-a6cf-1d9b5e3348fd |  | note | REFERENCE DOCUMENTS: WP 006. CP14038-AIR-DET-PM-SP-00002-C-12.4.8. CL006A
label | 46e648ff-263a-41e2-a5be-eb70ac588959 |  | note | INSPECTION/TEST METHOD: Inspection
label | 467cbc05-7791-4560-aa4b-f52067447bc3 |  | note | RECORD OF CONFORMITY: This ITP signed and CL006A
label | 0eff66b8-80b5-44da-92d6-88abc0e4af3c |  | note | AP
label | d53c675d-fe54-447e-acee-e66835e07eda |  | note | RESPONSIBILITY: FH Engineer and Principal’s Representative
text | 3a359805-8aff-491f-96f5-7883ee08edd8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Pour in-situ Pits
label | 8378c7ea-5c61-4b12-9699-64c1444aced8 |  | note | FREQUENCY: Each Lot
label | 79005919-6a81-4f8d-a667-dca9f943f43b |  | note | Acceptance Criteria: Concrete shall be placed within 90mins from batching.
label | 0c9f5910-9a92-4f53-b157-524fb6f8d15a |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002-C-12.4.814 . WP 006. Concrete Pour Record Sheet
label | 99a673fa-401e-493c-baf9-5ca06f9d8f6c |  | note | INSPECTION/TEST METHOD: Record
label | 699fea20-8988-4e84-a928-178b118fdb7b |  | note | RECORD OF CONFORMITY: CL006B - Concrete pour record sheet
label | 339086f3-aab9-4bdb-9520-04360c17ab9a |  | note | HP*
label | 1f9ea8e7-ad3f-480e-b15d-368291402196 |  | note | RESPONSIBILITY: FH Engineer
text | 8e094cf4-5c78-4ee6-90af-538e84de3735 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Concrete Testing
label | e0481fb0-f2f3-4ba6-8b2d-66c1c499dddd |  | note | FREQUENCY: Each Lot
label | 4edfa0b9-6a5a-4456-93cd-dbadb55dd6f7 |  | note | Acceptance Criteria: Pit - Each pour 1 slump & 3 cylinders to be cast per test.1 test per pour containing the following: 1 Slump and, 3 Cylinders. All concrete supplied for concrete structures shall be subject to project control testing in accordance with AS 1379 and the relevant parts of AS1012
label | b1cc74f4-c381-4c25-9f50-5778b497c65e |  | note | REFERENCE DOCUMENTS: WP006. Field Test Docket/Delivery Docket. CP14038-AIR-DET-PM-SP-0002-C-12.4.14. CL006B. Drawings
label | 3ddb2784-ce09-4ea5-928c-e5d006cab07d |  | note | INSPECTION/TEST METHOD: Record
label | a126ef8b-c1ef-44c2-8737-371679939172 |  | note | RECORD OF CONFORMITY: Concrete Test Report
label | 79949e06-54d4-4e89-bf95-7ef965b84b48 |  | note | TP
label | c8da0a1e-6711-48cc-9fa3-d296e1835c1a |  | note | RESPONSIBILITY: FH Engineer
text | cd0fa22c-f515-4e9a-b86b-56b48b0cad6c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Concrete Traceability
label | 906339db-e234-41aa-9b5f-6bed4e91e451 |  | note | FREQUENCY: Each Lot
label | 9df9af02-d3a0-469f-8225-3de8f0456cd3 |  | note | Acceptance Criteria: All concrete delivery information to be recorded on CL 006B – Concrete Pour record sheet
label | 720408c0-440b-47e0-b40a-071f25db8551 |  | note | REFERENCE DOCUMENTS: WP 006 CL006B
label | e15f52b8-9da4-4be9-9f6f-866775c64c58 |  | note | INSPECTION/TEST METHOD: Record
label | c5c5c58d-8e15-43b0-bf61-9dbda329f4b8 |  | note | RECORD OF CONFORMITY: CL006B - Concrete pour record sheet
label | 5d1a924f-8b4c-4bb9-a13c-dc43f5ca4041 |  | note | IP
label | 05dc523a-b3a7-48d0-a95c-f671daa5c4d8 |  | note | RESPONSIBILITY: FH Engineer
text | 7a1193c0-f7a0-45c4-ba2d-88f89757a574 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Finishing & Curing
label | 7bf53a3d-7e93-4194-b9de-d49f0449f8bd |  | note | FREQUENCY: Each Lot
label | 486bd0ad-2aa2-413f-9090-ad30a51fc1c0 |  | note | Acceptance Criteria: Concrete to be vibrated to ensure compaction and air voids removed.
label | 03332081-026c-47c3-8343-f8c5ec946d79 |  | note | Screed finish required to top surface of concrete to multiway ducts and storm water drains.
label | 9c6b2e00-fe35-43c2-9996-9b007bf3ed77 |  | note | Concrete shall be moist cured or coated by an approved membrane curing compound for a period not less than the period specified in section 12 of the specification unless approved by the Principal’s Representative.
label | c5379320-7ea5-45c3-ae22-a19feba96d7d |  | note | Pit floors and joint areas shall be smoothly finished. Mortared joints and recesses shall be cured no less than 48hrs.
label | 8ccc00bc-9f08-4005-856a-557ed82c603f |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002-C-12.4.11-12.4.12. CP14038-AIR-DET-PM-SP-0002-D-8.2.9. VicRoads 610
label | a84d1024-f22d-4c82-bc44-020733a66f2f |  | note | INSPECTION/TEST METHOD: Verify
label | 938a5bc5-0042-42a9-b385-62929f179d25 |  | note | RECORD OF CONFORMITY: This ITP signed
label | fc728ac1-9e7a-483e-b7e4-0cb1c8b7af76 |  | note | IP
label | 8753e783-193e-4ced-a18a-194f5cbd77a6 |  | note | RESPONSIBILITY: FH Engineer
text | f6df7133-1398-4d17-a56b-838e35151389 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.1 Reinforcement Installation
label | 7bd416a1-c4b0-4b0d-9d22-a6d57e9479cf |  | note | FREQUENCY: Prior to concrete Pour
label | d6e9e768-0456-44eb-aab5-f65d1f7267af |  | note | Acceptance Criteria: Pre Pour Checklist Completed: Position and spacing check and recorded, Cover checked and recorded, Reinforcing supports checked and recorded, Laps at required length
label | 686eb3ff-5428-4389-ba91-9df2a13aae55 |  | note | REFERENCE DOCUMENTS: WP 00. CL006A
label | 995d6e4e-d908-4587-b313-bc08cc3c2fce |  | note | INSPECTION/TEST METHOD: Verify
label | e94b3f44-0ec1-4923-a27e-cd54e73089f4 |  | note | RECORD OF CONFORMITY: This ITP signed and CL006A
label | c2f0ee96-ccae-4ff3-b1ab-9dbc50ff5155 |  | note | IP
label | 92d88865-6513-4137-8c15-e873e9e54ad2 |  | note | RESPONSIBILITY: FH Engineer
text | 34d6e7a9-3825-4605-942d-954b53f8a7ea |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 7.1 Pre-Pour Inspection Walls and Covers
label | 01541b84-15d0-4b05-873f-5d24ffb233f3 |  | note | FREQUENCY: Prior to concrete pour
label | 2b417e2b-b0bf-4736-ae98-e45eccad3d73 |  | note | Acceptance Criteria: Principal’s Representative to perform final Pre-pour inspection.
label | 96aa3425-187b-4d1c-8505-1332922db4f4 |  | note | REFERENCE DOCUMENTS: WP 006. CL006A. CP14038-AIR-DET-PM-SP-00002-C-12.4.8
label | 6f07a4e1-e49d-498d-bb54-fad68d63dbdc |  | note | INSPECTION/TEST METHOD: Inspection
label | c7b13fee-cf18-4cb3-8d44-9f1694d7fb55 |  | note | RECORD OF CONFORMITY: This ITP signed and CL006A
label | 0dda6211-73d9-43d6-ae1b-dd3d184b32ff |  | note | AP
label | 4dad3b04-f8b4-4a43-bc1a-e56794a3a87e |  | note | RESPONSIBILITY: FH Engineer
text | 8119c256-36b2-49e6-b30d-81d8940f54fa |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 7.2 Pour in-situ Pits
label | ee79e1c6-71d2-44a7-876d-94a2dc2547d6 |  | note | FREQUENCY: Each Lot
label | a16fdcc3-e9a7-4ec8-a68e-a46c2fcc4521 |  | note | Acceptance Criteria: Concrete shall be placed within in 90mins from batching
label | 7e5a8545-2e63-43bd-80d5-ca8385be19e5 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002-C-12.4.8.14. WP 006
label | 03be279c-a4d7-4c4b-82c4-4018ebe133c4 |  | note | INSPECTION/TEST METHOD: Record
label | a087f911-86f3-4256-9a99-1a2d7b3fb832 |  | note | RECORD OF CONFORMITY: CL006B - Concrete pour record sheet
label | 8b0d276f-bc15-46b9-86e9-b1774f1dde4e |  | note | HP*
label | db121eb0-e0b8-4c28-8cdc-0db7d7386f71 |  | note | RESPONSIBILITY: FH Engineer
text | 992b2ae7-e492-4696-8d11-60fb1640eff1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 7.3 Concrete Testing
label | 676ebac7-0db4-492c-b614-badc2f4b8c82 |  | note | FREQUENCY: Each Lot
label | 5ba40bc9-ae71-4acb-9d04-0a131e7dedc5 |  | note | Acceptance Criteria: Pit - 1 Test per pour containing the following: 1 Slump and, 3 Cylinders.
label | 03e073f0-496f-41ae-96e0-054b33d2aa32 |  | note | REFERENCE DOCUMENTS: WP006. CP14038-AIR-DET-PM-SP-0002-C-12.4.14. VicRoads 610 . CL006B. Drawings
label | 9399d9e3-451b-45ce-baac-94e01ebb3794 |  | note | INSPECTION/TEST METHOD: Record
label | a3428196-1d61-4981-8ca9-4b30b7925588 |  | note | RECORD OF CONFORMITY: Concrete Test Report
label | d9146ee2-9aba-4428-b934-9530ee2368d5 |  | note | TP
label | 1e660cc6-6db2-499a-87d4-7db1a7a517aa |  | note | RESPONSIBILITY: FH Engineer
text | cfc152f8-72a0-434a-9333-a5e8b9916976 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 7.4 Concrete Traceability
label | e00dd2fb-de3f-4c7d-b2d7-c68ce2df157e |  | note | FREQUENCY: Each Lot
label | f8aa2f5c-e71f-43f3-bddd-4037c6e53455 |  | note | Acceptance Criteria: All concrete delivery information to be recorded on CL 006B – Concrete Pour record sheet.
label | 321c9ea1-f7ac-49e4-bb1a-e07905d4ce14 |  | note | REFERENCE DOCUMENTS: CL006B
label | b214b8b5-6937-426f-96ba-9fff68cd9b76 |  | note | INSPECTION/TEST METHOD: Record
label | 03ab2d09-7a08-426c-814d-4ecc555894f5 |  | note | RECORD OF CONFORMITY: CL006B - Concrete pour record sheet
label | 0ede53b6-6148-4d84-918a-fe3715766f4d |  | note | IP
label | f7f213ba-cc4f-4538-855b-2b9f46c7dc47 |  | note | RESPONSIBILITY: FH Engineer
text | 707695a7-ed60-4530-b2a5-8e53f45fa3c7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 7.5 Finishing & Curing
label | 87c6b45a-9088-43d0-aea1-af16ed3a6314 |  | note | FREQUENCY: Each Lot
label | 110d3c76-b292-4518-9b77-95c3c3476a14 |  | note | Acceptance Criteria: Concrete to be vibrated to ensure compaction and air voids removed.
label | f3e4768a-ba57-468b-b7c4-ae43988ab3b8 |  | note | Screed finish required to top surface of concrete to multiway ducts and storm water drains.
label | 6e0ab646-6a00-43c9-b978-b19cdd5dd829 |  | note | Concrete shall be moist cured or coated by an approved curing compound for a period not less than the period specified in section 12 of the specification unless approved by the Principal’s Representative.
label | eedd41b5-56b2-43dd-a2fc-cbb6f2208a8b |  | note | Pit floors and joint areas shall be smoothly finished. Mortared joints and recesses shall be cured no less than 48hrs.
label | 02855c4e-79a6-4f49-b844-e93d44e0a177 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002-C-12.4.12.1. CP14038-AIR-DET-PM-SP-0002-D-8.2.9 . VicRoads 610
label | 85c474ca-79b4-4013-84a5-729ddf45ffa3 |  | note | INSPECTION/TEST METHOD: Verify
label | 4e923f9d-b41d-4bb4-afff-1cdf669b11e5 |  | note | RECORD OF CONFORMITY: This ITP signed
label | f5738a54-7b48-470a-a7e5-7997a9cbd2ea |  | note | IP
label | 5524245a-938d-4cb0-a93c-427cb00b9d7f |  | note | RESPONSIBILITY: FH Engineer
text | 68c03433-91de-46a1-bd40-b0325b557451 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 7.6 Pit lid frame and Covers
label | 45b10805-d1ed-448f-b576-f622f2d21b7d |  | note | FREQUENCY: Each Lot
label | b77c825d-6d9e-46fe-8a9f-8a7715fff459 |  | note | Acceptance Criteria: Frames for pit covers shall typically be cast into the top of the pit, however may also be grouted in as approved and as per the locations instructed by the Principal’s Representative
label | 273b9dfa-8b97-417b-9ea6-f5f25dd1b952 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002-C-8.2.10. WP 006
label | 8d9c67f8-7561-4e4b-b920-22bd4c5f4c4e |  | note | INSPECTION/TEST METHOD: Inspection/ verify
label | 1d7af4e0-4ea3-43d8-b4bc-e1434811e814 |  | note | RECORD OF CONFORMITY: This ITP signed
label | b4a76295-1814-4fc4-8e5b-24f559228482 |  | note | IP
label | 4f786dd3-1a34-4113-96a0-4477187656cb |  | note | RESPONSIBILITY: FH Engineer
text | 8d54d440-59f2-4136-95a3-00cc564700f3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 8.1 Removal of Formwork
label | d7131b54-d1ea-4338-b712-f54c51a5f2d2 |  | note | FREQUENCY: Each Lot
label | d721f89e-e2fb-4d4c-84f4-73ebc1346cbc |  | note | Acceptance Criteria: Forms shall remain and be maintained firmly in place until the concrete has attained the necessary strength to support its own weight. Refer at attached table 12-4 Form Removal Information
label | 8c8afb84-6735-40d7-9eab-af462077ca59 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002-C-12.4.5. 12.4.5
label | 7d3bb195-7c46-4d2b-a621-a9240248b88b |  | note | INSPECTION/TEST METHOD: Verify
label | c6324872-5436-46d1-bcd6-0da5653ed488 |  | note | RECORD OF CONFORMITY: This ITP signed
label | ac9b983e-1c65-4f18-9fb6-83b50f90d2c5 |  | note | IP
label | 5b2aa813-426f-43fa-b96e-7895f56d90d9 |  | note | RESPONSIBILITY: FH Engineer
text | 557de497-462f-4d11-967f-6e802f41a894 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 8.2 Finishing and Curing
label | ce15b8c7-bdea-4ee1-af17-28231bfd7821 |  | note | FREQUENCY: Each Concrete Pour
label | 62bcb0c6-a006-4cb7-8e1c-674b23c11cc7 |  | note | Acceptance Criteria: Check finish behind formwork. Defects such as honeycombing or cracking to be recorded and repaired as per Principal’s Representative’s direction
label | 3be95705-862d-468f-ae8e-1527afc7f8b4 |  | note | REFERENCE DOCUMENTS: WP 006 . CP14038-AIR-DET-PM-SP-00002-1-12.3.4
label | 3c58cdc1-39e3-4dcd-90ba-538e95719347 |  | note | INSPECTION/TEST METHOD: Verify
label | 6fd9a47f-6a34-42b6-8b46-ed25ab6143a4 |  | note | RECORD OF CONFORMITY: CL006C - Post-pour inspection and this ITP signed
label | 66fead72-29ba-4aa9-b210-3e8417c2c71b |  | note | IP
label | 8168004c-2dc8-4d00-a9a8-50b931cf56ae |  | note | RESPONSIBILITY: FH Engineer
text | deaf5c26-4257-4bb7-b607-2e3121544302 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 8.3 Step Irons (If applicable)
label | ab08b78b-4d9d-48a1-892c-54e3a3e2aed5 |  | note | FREQUENCY: Each Lot
label | 631fff34-86ae-49bf-b927-7982a0aadd8f |  | note | Acceptance Criteria: Where pits are greater than 0.9m deep, step irons are required.
label | 153602e7-9c29-4936-86a2-8cd548e87d76 |  | note | Steps shall be set into a wall; Which has no openings ,Beside an opening and Across the pit corner
label | b05d86b4-7ff3-40f2-8d5f-e3d391978818 |  | note | Steps shall be; 225mm wide tread, Installed uniformly from pit walls, 1st step to be 450mm from bottom of pit and 300mm between rungs
label | a1213453-cbcc-4a2d-a9ef-4eb2d9d07c75 |  | note | Top rung at least 600mm below top of pit
label | a8c94583-6891-4a22-93ac-185f7cbfbe7a |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002-C-8.2.8
label | 7fbf805a-27dd-4a14-963a-0eb6f1736936 |  | note | INSPECTION/TEST METHOD: Verify
label | 0ef94ddc-9a0f-4885-8fdd-ccfcf3d49cb3 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 181a2ec5-e6d8-452a-b305-77275c5c57ed |  | note | IP
label | 102dc2d3-2feb-4544-9132-d589594343f0 |  | note | RESPONSIBILITY: FH Engineer
text | 7b22c14a-f591-4614-b790-5531913b46fa |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 8.4 Quality Report/Concrete test results
label | e5201089-8ecd-43d9-81b5-5db3e37b7fda |  | note | FREQUENCY: Each Lot
label | 314e164b-6595-4f97-8360-1ef3fdd963fa |  | note | Acceptance Criteria: All quality control and concrete test results obtained and attached to ITP.
label | 2bc6f430-75fc-462c-88a3-9d5244dce0c6 |  | note | All quality control and concrete test results submitted on Aconex
label | b9eeadf3-77e1-470a-8ba3-16f6707bc3a8 |  | note | Check all results compliant as per specifications
label | 0bb2a70f-b910-41c8-a71a-fe226066cedd |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002-C-12.4.14
label | 2c781eee-f792-4e59-a1ef-0f4be8d46938 |  | note | INSPECTION/TEST METHOD: Verify
label | c0a2160f-1272-4f60-bb10-589aa8ded79a |  | note | RECORD OF CONFORMITY: This ITP signed
label | f613b96c-8dcc-4aef-826d-408f5c1143d7 |  | note | TP
label | 2280c83c-a9de-4a1a-b41b-77b3c2db2c91 |  | note | RESPONSIBILITY: FH Engineer
text | dac3ecb7-78e9-4aa2-b307-da889668d1d0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | FULTON HOGAN FINAL INSPECTION - On behalf of Fulton Hogan, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 7d8890c1-676d-44d5-916a-1c717af987a2 |  | textbox | Name:
text | 8d0ef8cf-1c22-47b8-8be9-85e6726e28f6 |  | textbox | Position:
checklist-sectioned |  |  | checklist | ITP 019 - Grassing | itp |  |  |  | Yes | ITP 019 - Grassing | ac6b7362-9a61-4a50-97ca-848797a3ba88
checkpoint-group |  |  | section | ITP 019 - Grassing
checkpoint-status |  |  | checkpoint | 1.1 - Check for correct documentation
label | b786900e-d18b-4c34-ae3b-47889bb15c45 |  | note | FREQUENCY: Prior to commencing works
label | 00e7bb61-c45b-464d-adc5-dfb1ca2529ac |  | note | ACCEPTANCE CRITERIA: Current revision drawing is being used including the subcontractors copy. Current Revision to be obtained via Aconex
label | 70335a44-1712-4842-97f7-3521036147cf |  | note | REFERENCE DOCUMENTS: Aconex & Drawings
label | e6d770d9-2f48-48f5-be1b-cb2b590718e1 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 43b71d50-5465-427a-a36c-9789f29c5b3c |  | note | RECORD OF CONFORMITY: This signed ITP
label | 39689aad-d3fd-4e86-ad6c-e55d4ca3f7c0 |  | note | HP*
label | 4f146ce9-ec90-4d1d-a79f-6db617d943b2 |  | note | RESPONSIBILITY: Project Engineer
text | 9ca9a0e2-96b7-4505-ac1e-dd33594196e0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 Implementation of all measures & controls
label | 8521dd5d-d2b5-4493-8787-1aa0482bd57f |  | note | FREQUENCY: Prior to works
label | b53cd6a8-781c-4734-95b8-be797ae79d5e |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | bcdba84f-5ab8-495d-be25-68e10d12cd76 |  | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, WP SWMS
label | 0313aa14-d5d5-4b98-9f97-0344f8a3b58c |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 7bd540e7-ff39-4e34-bdc3-1d36f5486177 |  | note | RECORD OF CONFORMITY: Site inspection
label | 3a176f42-f86f-4cc2-8b2f-5a7dc90ef7dc |  | note | HP*
label | 6422d4ed-820f-4466-9afe-518bc0402aa6 |  | note | RESPONSIBILITY: Project Engineer
text | 969ef012-7cd3-481e-a061-123f1c83f7e0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 Material Approval
label | 179f384b-b717-4f03-8a39-fde80a2e7763 |  | note | FREQUENCY: Prior to hydro seeding
label | 5556afa7-e066-4da5-9ed4-7dcd24c62218 |  | note | ACCEPTANCE CRITERIA: Grass seed shall be “50% Common couch, 50% Colosseum Ryegrass” with Wildlife deterrent endophyte unless agreed otherwise by Melbourne Airport.
label | 2c6bfdc9-6d83-406c-bbb9-a2eea9b98286 |  | note | Hydro mulch application to be Flexterra or Vital-Bon unless agreed otherwise by Melbourne Airport.
label | 111775fc-9b96-488d-ae21-95a306cd7684 |  | note | REFERENCE DOCUMENTS: Cl3.7.2 Cl8.5
label | 86c2b587-546f-4b2f-8593-4918ce06c2ec |  | note | INSPECTION/TEST METHOD: Verify
label | 95a32468-a5cc-4d71-8ed9-79e8fee5508d |  | note | RECORD OF CONFORMITY: This signed ITP - Aconex
label | 189d587b-6897-4bcd-b52e-312ac222da2e |  | note | HP*
label | 6beb9211-a4db-4613-b1b2-5c454d91aca6 |  | note | RESPONSIBILITY: Project Engineer
text | aacebf5f-6c6a-45b0-8f33-2c9a070c92d5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 Application of Round Up
label | a381ad13-38c5-4698-8bdc-d4f9cae78463 |  | note | FREQUENCY: Prior to topsoil placement
label | 334ef79e-14e4-48f3-b530-2ad5053ec185 |  | note | ACCEPTANCE CRITERIA: Apply Round Up to existing grass at least 4 weeks prior to hydro-mulching, then 2 weeks before seeding
label | 61d370e1-73e2-4b68-838e-2f916566fc59 |  | note | REFERENCE DOCUMENTS: Cl3.7.2 Cl8.5
label | 1dc9c2dc-b2c3-4453-9f2c-8071ecaa417c |  | note | INSPECTION/TEST METHOD: Visual inspection
label | ff9f9759-49dd-4225-bf77-aa2b7fc2df4b |  | note | RECORD OF CONFORMITY: This signed ITP
label | 75a9c9a1-a929-46f0-acdb-67c79027e9bb |  | note | HP*
label | 429a4d78-83a9-4881-a0cf-816aab1c41c0 |  | note | RESPONSIBILITY: Project Engineer
text | 90e08601-9c79-4ebc-83ad-28263aeeb7c1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.1 Topsoil Placement
label | 5df7b077-4bd5-4e4c-9752-3b2f9b5e3cf4 |  | note | FREQUENCY: Each lot
label | eec3677d-e9e1-4a64-bc09-d18c92c9dd82 |  | note | ACCEPTANCE CRITERIA: Filling of grassed areas will comply with specification.
label | 266d4dbc-05e3-4c4b-aa0c-ea8f7eabb164 |  | note | FHPL-RFI-000556
label | de613390-9454-4ecd-971a-93b1bbb9727f |  | note | APAM engineering standard (MAS-CVL- 001-V1-1-Grassing-Standard - Feb 2020) calls for a uniform thickness of not less than 100mm of topsoil prior to seeding and subject to the Contractor making necessary allowance for compaction of the topsoil prior to Hydromulching.
label | 511daf7b-9d24-4772-8699-657bd2e9a7f5 |  | note | REFERENCE DOCUMENTS: Cl3.7.2 Cl8.5
label | e448d7ec-3645-45ff-ac9c-bd92be17f04f |  | note | INSPECTION/TEST METHOD: Verify
label | b851057e-e4cd-4cd2-b14d-2ab7c017c42e |  | note | RECORD OF CONFORMITY: This signed ITP
label | e7223041-2a64-48ea-8673-aed5e6bb2864 |  | note | HP*
label | 7f49968a-8d75-406c-9e9c-36aeb024d4f0 |  | note | RESPONSIBILITY: Project Engineer/Foreman
text | 50ea82a5-f25d-447a-8f3d-275f35f12227 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.1 Coverage/Tolerances
label | 3b256ecc-6616-4f5f-9180-b5dfa387aab6 |  | note | FREQUENCY: Each lot
label | a490c23e-b4b2-4c7e-b564-3cbff392c969 |  | note | ACCEPTANCE CRITERIA: A minimum of 95% healthy cover it to be achieved
label | 72e8ba86-1665-4742-9f3d-1d95ab660cc1 |  | note | REFERENCE DOCUMENTS: Cl3.7.2
label | 9c7263dc-19f4-47b1-84cf-e855df96b9f1 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | df4ef156-b93c-4f31-8190-e02b679b187b |  | note | RECORD OF CONFORMITY: This signed ITP
label | c5e76aba-2d93-426a-ba14-2e39648a5c13 |  | note | HP*
label | 5e0eae34-fea8-4ebf-8b6c-70d73859d38c |  | note | RESPONSIBILITY: Project Engineer
text | aba5c3f1-16aa-41bf-b5de-3919b525d19f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Bitumen Emulsion
label | cf961677-72ef-4f23-a1ff-4339e75dfbf2 |  | note | FREQUENCY: Prior to opening area to airport trafic
label | 604c16d3-d997-41c1-a511-a10e1fda8b32 |  | note | ACCEPTANCE CRITERIA: Bitumen emulsion to be utilised in areas prone to jet blast following seeding if significant grass strike has not been achieved.
label | 944f22f1-65ea-4a5a-8e7a-e7f391a41c89 |  | note | REFERENCE DOCUMENTS: Cl3.7.2 Cl8.5
label | bf5f8888-4894-4ffe-8a24-0cdc41336e33 |  | note | INSPECTION/TEST METHOD: Verify
label | 6a614474-a346-414e-ab2a-9fb3c163e5c5 |  | note | RECORD OF CONFORMITY: This signed ITP
label | bff78020-0f37-420a-af55-db8c731b215d |  | note | HP*
label | 46628a3c-8b9e-4d8f-99c3-c78a3abb8979 |  | note | RESPONSIBILITY: Project Engineer
text | d48518f7-11c2-49d5-ac96-6adb44d5ab56 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.1 Maintenance
label | 590dce4c-aedd-4813-91f3-428df33800b2 |  | note | FREQUENCY: Each lot
label | ac730eff-e355-46a4-8721-c41a3d9df008 |  | note | ACCEPTANCE CRITERIA: Contractor responsible for maintenance of grass cover until such time as the grass is established to an average height of 100mm. Maintenance is defined as fertilising, weeding, mowing, repair and watering
label | addd6bff-b9c8-4dda-a719-8e248f46301f |  | note | REFERENCE DOCUMENTS: Cl3.7.2 Cl8.5
label | 39ed39d1-b3a1-418d-a53a-0df9965d4c47 |  | note | INSPECTION/TEST METHOD: Verify
label | 4426f45c-1f4b-4038-8077-c230f876f06c |  | note | RECORD OF CONFORMITY: This signed ITP
label | 6248319a-f718-48c3-825f-f21e216c7217 |  | note | IP
label | 778211e5-c0ac-4d16-90f2-4ce0137bd3cd |  | note | RESPONSIBILITY: Project Engineer
text | ae19d59d-4cd7-4c82-8358-0d20fbfad501 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | FULTON HOGAN FINAL INSPECTION - "On behalf of Fulton Hogan, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract".
text | 629caacf-06fc-48c6-8e38-fbd2447560ab |  | textbox | Name:
text | 217d338e-76fa-4593-ac9f-eee220260940 |  | textbox | Position:
checklist-sectioned |  |  | checklist | ITP 020 - Precast Pits | itp |  |  |  | Yes | ITP 020 - Precast Pits | aecf76fb-f11f-4ceb-a02c-d50ad51b79d5
checkpoint-group |  |  | section | ITP 020 - Precast Pits
checkpoint-status |  |  | checkpoint | 1.1 The current revision drawings are being used including subcontractors
label | 01bc25ca-da5f-478f-83b1-56c7977be1bb |  | note | FREQUENCY: Prior to commencing works
label | 1afac462-35f5-4828-8b11-9f98fe1608fb |  | note | ACCEPTANCE CRITERIA: Current revision drawing is being used including the
label | 7206034d-d4ef-44b6-9726-29322ac1cc5c |  | note | REFERENCE DOCUMENTS: Drawings and drawing registers
label | 315aa05b-953a-4c9e-a3bb-190d0c356165 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | f1cd9ad0-6685-4858-92d9-6eaa53cce022 |  | note | RECORD OF CONFORMITY: Up to date drawing sets and this ITP signed
label | f03dfa06-137b-4cba-9bb4-010d6490affc |  | note | HP*
label | bbac2582-b3a2-44d2-9b8d-e703f0b89ad7 |  | note | RESPONSIBILITY: FH Engineer
text | 992fe335-c181-472c-bda8-8156765ab480 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 Setting out for miscellaneous structures
label | 3bcdf3a4-bacb-42ea-8259-d85ecdefc592 |  | note | FREQUENCY: Prior to Start
label | 004c8ad9-bb3f-4c0c-9b12-ca79c0aa30f7 |  | note | ACCEPTANCE CRITERIA: Conformance with Jacobs for Construction Drawings and pipe penetrations in the correct locations.
label | 4f434f19-823c-4349-841e-8416cc94e379 |  | note | REFERENCE DOCUMENTS: WP 020
label | b4725991-2efc-4405-9881-9487277fb897 |  | note | INSPECTION/TEST METHOD: Verify
label | 5a003948-43cf-4368-a274-554846594483 |  | note | RECORD OF CONFORMITY: Asbuilts drawings
label | bfd14221-e183-4a07-bfe2-fe4ced24fdc0 |  | note | SCP
label | fd8d3740-56e9-4aee-840b-545d240c3268 |  | note | RESPONSIBILITY: FH Engineer Surveyor
text | 4ee36296-d8a2-4278-bfd4-4eb5cdddad29 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 Materials & source Approval
label | 96b15dab-0f4b-4ec3-acb3-4a0cd0d00db2 |  | note | FREQUENCY: Pre- commencement
label | c88892c0-9606-4302-9710-504b2be284ad |  | note | ACCEPTANCE CRITERIA: Details submitted to Principal’s Representative regarding: Test Certificates demonstrating class G load rating and compliance of the pit to AS 3600 & AS 3996
label | be830bba-ef70-4c61-a4c4-d4c1a3319cbc |  | note | REFERENCE DOCUMENTS: CP14038- AIR-DET- PM-SP- 0002-C- 12.2
label | 8e1c70aa-2613-40a1-b519-20c2fd1c3673 |  | note | INSPECTION/TEST METHOD: Verify
label | 83156e18-4922-4c91-91b6-8321893703bb |  | note | RECORD OF CONFORMITY: Aconex correspondence
label | 543a9f0d-b90a-4903-8bd5-8e574bd4ef56 |  | note | AP
label | d93de754-9809-423a-8222-168bf0d7101e |  | note | RESPONSIBILITY: FH engineer and Principal’s Representative
text | c966ab42-ac0d-41f1-b17d-684f773f6e3e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Materials & source
label | f7ab8cb7-95aa-4a42-8ed2-fd130b667c7c |  | note | FREQUENCY: Each Delivery
label | a11bdfc5-c00f-4412-bc7d-ec6a9abb0f7a |  | note | ACCEPTANCE CRITERIA: Pits, pit covers, grates, lids and lintels shall be as specified on drawings and installed as per manufacture’s recommendations
label | a0a908fa-07f1-491a-b29d-a75a083f70cb |  | note | Each pre-cast unit shall be marked with:
label | 6a668ea5-a7e1-42ac-8f12-d72ea1710ca1 |  | note | Date of manufacture
label | abde468f-c36d-4e85-8e21-2e0492da2d28 |  | note | Manufacturer’s name or registered mark and location of manufacture.
label | 8a2cca3e-dd1c-4808-9028-58dd02fa4104 |  | note | Maximum mass of unit in kg
label | fd93e844-036c-4255-ae45-cecf284b1d51 |  | note | Batch number
label | a31a4903-8d1d-4985-940e-eb04f76fb736 |  | note | Inspection status
label | b47e4755-25c7-4f96-b153-88cf32854c25 |  | note | REFERENCE DOCUMENTS: WP 006, WP020, CP14038- AIR-DET- PM-SP-0002-C-8.2.3c
label | 9671467f-0ca2-4917-a07f-3a9c3a34efdb |  | note | INSPECTION/TEST METHOD: Verify
label | 4dbb8211-0808-4d61-b4d1-d9845706ecfd |  | note | RECORD OF CONFORMITY: Receival
label | 152f115c-cafa-46df-abb6-369c6f08d216 |  | note | IP
label | a32ad354-4b02-4645-8d6c-5935ea028cfc |  | note | RESPONSIBILITY: FH Engineer
text | 16274205-7232-4b9c-b39d-f6588c25a3d9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Acceptance Covers Frames/Grates
label | f7e765fe-c326-4c88-9b1e-0692149ffc34 |  | note | FREQUENCY: Prior to Start
label | 8c39bd95-92a9-4416-b67b-52374009e5a1 |  | note | ACCEPTANCE CRITERIA: All Pit covers shall conform to Class G- Airside standards.
label | bb3c5ad1-f1fd-469c-8903-809e13ba5b59 |  | note | REFERENCE DOCUMENTS: AS3996 CL3.1, CP14038- AIR-DET- PM-SP- 0002-C-8.2.1
label | 6e247bd3-8a91-4632-ab2b-fabb0e744a95 |  | note | INSPECTION/TEST METHOD: Verify
label | 920097d2-31ae-4ef9-8cfe-5f5b21ae7177 |  | note | RECORD OF CONFORMITY: Receival inspection checklist
label | 4fb1b637-ae31-4eca-84c4-de7030d820a7 |  | note | HP*
label | d7d87e00-01e4-40e1-932e-f660ea11287b |  | note | RESPONSIBILITY: FH Engineer
text | da49d8ea-ee9b-47f0-96f3-71791f010085 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.1 Excavate Pits
label | 41146a58-faf6-4363-9d61-077473819fca |  | note | FREQUENCY: Each Lot
label | abefe314-0840-4b33-adcd-3c581341b2cf |  | note | ACCEPTANCE CRITERIA: Excavation depth shall be as per specified on drawings or as necessary to secure satisfactory foundation.
label | 9fbbe73b-662d-4ace-9646-2a05db122c33 |  | note | Excavation shall provide a clearance from all external faces of the pit to each face of the excavation of not less than 400mm.
label | 027380e0-b3b8-4534-a47c-5afb340c047b |  | note | REFERENCE DOCUMENTS: CP14038- AIR-DET- PM, SP-0002-C-8.2.4
label | dc065e85-ae0a-41c8-a3b3-0b909a10bae1 |  | note | INSPECTION/TEST METHOD: Verify
label | a3b535a6-5c26-4de7-b48c-afeb8f544009 |  | note | RECORD OF CONFORMITY: This ITP signed
label | b18f30d8-2a9c-4ddf-ad77-17f804a2e884 |  | note | IP
label | eadb2588-19b5-4540-9693-fc58fcc287d0 |  | note | RESPONSIBILITY: FH Engineer
text | fc46f3af-9fca-4174-82a1-f859c3bfd362 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Confirm Ground
label | 02e6f833-b35b-4b12-97fb-1a040f944e56 |  | note | FREQUENCY: Each Lot
label | 17d32989-6cf8-413f-947d-8d988be1e7d5 |  | note | ACCEPTANCE CRITERIA: Pits shall be constructed on firm subgrade with a minimum allowable bearing capacity of 130kPa and in accordance with manufacturer's instructions
label | a442e66b-c657-4ad4-b48b-436488e95575 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET- PMSP-0002-C-12.4.1, WP 020
label | 3f758e97-4b3c-4d5c-872e-db06451a6ff1 |  | note | INSPECTION/TEST METHOD: Verify
label | 10cb9bac-46b7-4986-8801-942b91acc341 |  | note | RECORD OF CONFORMITY: DCP, Results attached, Test result
label | 28e6b812-4fbc-4f25-a2a9-4a33cb255dcf |  | note | HP
label | 1ab52695-508a-4c6f-9331-db24683d7a1d |  | note | RESPONSIBILITY: FH Engineer and Principal’s Representative
text | afd49cd6-ad20-45fd-aad7-e7e658c39f8e |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 3.3 Blinding
label | 547270a7-d31b-4fdb-b5a6-2b3fcbbd4358 |  | note | FREQUENCY: Each Lot
label | 04978606-b5f9-44fe-8fda-09487927138f |  | note | ACCEPTANCE CRITERIA: Blinding to be installed in either of the following methods:
label | bceb54d2-8c10-40ad-8d53-407d1393784e |  | note | 50mm 20Mpa Concrete
label | 60186c2e-48de-49c8-a387-8b54ef49911e |  | note | 100mm Class 2 Wet Mix Crushed Rock – Compacted to refusal using handheld mechanical aid (DPU / Wacker Plate)
label | a8de82d4-97b5-42e4-ad8f-0916a1967b01 |  | note | Installed blinding layer is to be stable and level to ensure the precast pit is vertical
label | 3dec9b46-83c2-47c8-92d4-8176520218ab |  | note | REFERENCE DOCUMENTS: Drawings
label | 5f1a6e81-c40c-4371-abfa-b8a0923f4b43 |  | note | INSPECTION/TEST METHOD: Verify
label | a344450f-c31e-433a-a0d6-df7df4aa262e |  | note | RECORD OF CONFORMITY: This ITP signed
label | 1e5e651e-157c-478e-a76c-bcc4d9c9eace |  | note | IP
label | 4b248813-a552-45a5-a8fc-cce7a83c1ba0 |  | note | RESPONSIBILITY: FH Engineer
text | 3d0020d8-096e-4186-98a1-777f6e2534a5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.1 Drawing Approvals
label | 5d2046a3-15ee-424c-b0d5-e3e4a55d1acb |  | note | FREQUENCY: Each Lot
label | b3c92a14-2812-4fd2-8fa8-9fe70c71ba79 |  | note | ACCEPTANCE CRITERIA: Ensure manufacturer drawings are supplied with correct dimensions and blockouts to suit all services to be installed into the pit designated in Jacobs Design Drawings
label | 75d991be-468d-4f0c-8ae1-1533766c4781 |  | note | REFERENCE DOCUMENTS: Manufacturer Drawings
label | 70f4baef-94c7-47b2-979b-8d03c475ea8f |  | note | Jacobs Drawings
label | 51e10d64-7bd4-4689-a17e-752ae2ce8a2e |  | note | INSPECTION/TEST METHOD: Verify
label | 13a81b1b-7637-44a8-afef-c04c9671e640 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 002fcc1a-8dde-45d5-beff-6711dbf55275 |  | note | IP
label | ea991bd3-20ca-46c9-9b3a-b82dca5a1309 |  | note | RESPONSIBILITY: FH Engineer
text | c03e74dd-f5b6-4383-950d-9fb0c1d2ab53 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Pit Delivery
label | 8dd02dac-6d45-42e6-ad6f-f766b271bf56 |  | note | FREQUENCY: Each Lot
label | 83751485-3ad2-493e-8b44-2a69693f37ce |  | note | ACCEPTANCE CRITERIA: Ensure each pit component is inspected upon arrival ensuring:
label | 131191ff-62da-4342-bce6-ef1f7a61720f |  | note | Dimensions are as shown on manufacturer drawings
label | e7b8dfec-e07e-4ea5-a629-9e7cc5182d84 |  | note | All blockouts in correct positions and to dimensions
label | 76fbd64b-3267-4683-860c-89b4951ec606 |  | note | No damage to any pit component to the satisfaction of FH Engineer
label | fec7b76b-3d94-4d9a-8660-217fe613d145 |  | note | No modifications to the pits are to be made without written approval from manufacturer
label | 883ad45f-0758-4884-84e6-4f1614841644 |  | note | REFERENCE DOCUMENTS: WP020
label | 7e865a94-1f76-4f5b-a3d0-96745d8f2874 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | c33ee761-30f5-4740-bad3-a0aab7546ddc |  | note | RECORD OF CONFORMITY: This ITP Signed
label | 85bb65cd-8a55-4f84-afd4-be9c2b0eda74 |  | note | HP*
label | d89a947a-f7c2-4274-8dc9-5f71a8d549aa |  | note | RESPONSIBILITY: FH Engineer
text | 5223ea4a-d35c-4cfe-8b22-337a08a2e9cf |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.1 Positioning Pit Components
label | bc2a0be2-3368-4aec-b06f-441ed022b6d1 |  | note | FREQUENCY: Each Lot
label | 5c56c4b7-e5d9-40d3-8ec7-0fc71ac3d7f9 |  | note | ACCEPTANCE CRITERIA: Precast Pit installed as per survey set out points marked on blinding layer
label | 5b713fe9-d604-4d98-b38d-db05639a01f4 |  | note | REFERENCE DOCUMENTS: WP020
label | 4ee20430-4b2e-40b9-983c-ca31536482bc |  | note | INSPECTION/TEST METHOD: Verify
label | 3f919bbc-6a52-41ce-948a-4bb463d2aa66 |  | note | RECORD OF CONFORMITY: This ITP Signed
label | 9bfa7d14-155e-40b3-9b88-670957e16b4c |  | note | HP*
label | 440f4e2b-4e59-4349-a197-3fcaaa6a791c |  | note | RESPONSIBILITY: Surveyor
text | 4828a0de-febd-43a0-9aba-96b3d4aa597d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Lid Encasement Slab Installation
label | ba7ac8db-a420-42d5-a88f-e22ffd5edff2 |  | note | FREQUENCY: Each Lot
label | 88961494-721e-47ac-9a2d-61b3feab5669 |  | note | ACCEPTANCE CRITERIA: Seal Pit Wall and Lid encasement slab using mastic type sealant ensuring no gaps remain.
label | 9ecb5f3e-be0c-4254-b71e-04e6b43dc501 |  | note | Any encasement slab on a slope is to be checked by the surveyor and achieved using packers and infilled using non-shrink grout – Conbextra C or equivalent.
label | 28defd3b-d7fb-4b53-893f-2e2e451fc134 |  | note | A recessed bituminous sealant (DC890) as shown on the Concrete- Asphalt Joint Sealant Detail D is to be adopted on the asphalt/concrete interface
label | 256e51ee-6fe8-4e1f-b522-569a73d10983 |  | note | REFERENCE DOCUMENTS: Manufacturer Guide, DCWC Mgt- RTRFI- 000630
label | 8af1be09-fb2d-42ff-b3fe-1fb671be1dbf |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 2df806d1-26a4-4556-a17a-895fa70c618d |  | note | RECORD OF CONFORMITY: This ITP Signed
label | b25560b6-0f1e-49fa-ad01-36d07c03145e |  | note | IP
label | a670b0ad-8060-423a-8412-b7a1fc2e9a6b |  | note | RESPONSIBILITY: FH Engineer
text | cd893d99-edd6-42e8-827a-771eeba3ec86 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Quality Report
label | 9ccfd3c2-554a-440b-bed1-3d9bfe81fe25 |  | note | FREQUENCY: Each Lot
label | 4884c0cc-2294-4238-b0df-3cde1f905c42 |  | note | ACCEPTANCE CRITERIA: Submit to Principal’s Representative via Aconex report detailing the results of all quality control and testing
label | b1d78292-1f49-4f2d-9103-69f23496f327 |  | note | REFERENCE DOCUMENTS: CP14038-AIR- DET-PM- SP-0002- C-12.4.14
label | 56d49e55-f21a-4d16-a952-ee3820891817 |  | note | INSPECTION/TEST METHOD: Verify
label | 317a627f-1577-46fd-bb33-18c5c8149a82 |  | note | RECORD OF CONFORMITY: This ITP Signed
label | ee250ffc-18c0-42d7-960b-adb67be79e21 |  | note | HP*
label | 6bd64609-4b9c-482a-86e3-9768f7109663 |  | note | RESPONSIBILITY: FH Engineer
text | 65e7c3c6-be54-40bb-81e7-246379d07602 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 00e6b9a0-0e86-4150-9c0d-424ceb3b2c74 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
text | 0bce66bc-dc4a-42be-8270-3402ef512056 |  | textbox | Print Name:
text | bb4d0523-9172-4cca-ac42-7e9adf363576 |  | textbox | Position:
text | 38da49b3-c895-4e6e-bb38-65f19919ad20 |  | textbox | Date:
checklist-sectioned |  |  | checklist | ITP 005 - Subgrade Improvement, Lime Stabilisation and Prepared Subgrade | itp |  |  |  | Yes | ITP 005 - Subgrade Improvement, Lime Stabilisation and Prepared Subgrade | b1749e76-4f36-4f83-a133-ffe17c44dc45
checkpoint-group |  |  | section | ITP 005 - Subgrade Improvement, Lime Stabilisation and Prepared Subgrade
checkpoint-status |  |  | checkpoint | 1.1 - The current revision drawings are being used including subcontractors copy.
label | 3dd57fe9-d1bb-47a5-a500-9988f4f1270a |  | note | FREQUENCY: Prior to commencing works
label | 4d88253d-5f92-49ab-80c0-973ccf4a70da |  | note | ACCEPTANCE CRITERIA: Current revision drawing is being used including the subcontractors copy. Current Revision to be obtained via Aconex
label | 8906f251-c2dd-4f51-908f-8948c4ac36b9 |  | note | REFERENCE DOCUMENTS: Aconex
label | b89d8591-39f0-444c-9b21-20aaad0d9712 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 899c0b88-54c6-4bf4-b90e-c33404141af9 |  | note | RECORD OF CONFORMITY: This signed ITP
label | ffc9ae55-ede1-4595-b3f6-6c27b2eba34d |  | note | HP*
label | 7dd657c4-d244-439e-b598-ba86ddb7c2b4 |  | note | RESPONSIBILITY: Project Engineer
text | ac6e5515-fdbf-4666-8f5c-0156757101ba |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 Preceding Lots (ITP 002) closed out
label | 887977e8-bd69-4ff7-b811-c4814e45400f |  | note | FREQUENCY: Prior to commencing works
label | 9a348a41-71f4-4f42-a361-5d6291d798b5 |  | note | ACCEPTANCE CRITERIA: ITP 002 Generated for area
label | 14766201-76e3-4808-ade9-29cc58b71d78 |  | note | REFERENCE DOCUMENTS: ITP 002
label | d91b9185-8312-4ae4-8e86-091279bfea64 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 2181c248-0810-4201-8e9f-cf4590063a68 |  | note | RECORD OF CONFORMITY: This signed ITP
label | 14ec7f8a-a859-4e27-bb28-cf4dd10273e6 |  | note | HP*
label | 0048a655-1aa1-430b-80af-13be826ff4c9 |  | note | RESPONSIBILITY: Project Engineer
text | 8ef8bf0d-ccee-432c-9a4d-323f03117bc5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 Implementation of all measures and controls
label | 6dc3ca4b-87d5-430b-9e2c-d74189f68563 |  | note | FREQUENCY: Prior to commencing works
label | a4872d33-c8bc-4cfd-afa7-2b43cfd858e5 |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | 4b9d8458-3423-46da-9a39-7fdccfe6bd8d |  | note | REFERENCE DOCUMENTS:PSP, EMP, TMP, SWMS, WP
label | 46455438-eeef-49b9-827f-ce31237ddc8e |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 79bfb973-e052-4c88-a911-0c020d1bf9f0 |  | note | RECORD OF CONFORMITY: This signed ITP
label | 38f846c0-9797-43d1-9e72-dc45c879b284 |  | note | HP*
label | d528261a-d3ae-41ba-bc9d-42d06244694e |  | note | RESPONSIBILITY: Project Engineer/Site Supervisor
text | d6a5e0a4-58ab-42e2-9f79-205cf734fb1a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.4 Current excavation and isolation permit has been issued
label | edc24515-5a3c-4eb6-a3e6-85d0cf5b2309 |  | note | FREQUENCY: Prior to commencing works
label | 0c2389c0-fca7-4adc-9ca1-3569aa5f81b0 |  | note | ACCEPTANCE CRITERIA: An Excavation Permit and an Isolation permit issued by Melbourne Airport. Fulton Hogan Excavation permit issued to plant operators
label | 88d27473-a921-49ca-8828-68930d4c77a7 |  | note | REFERENCE DOCUMENTS:Excavation Permit
label | 48a8372d-2ed8-4984-ad17-30ccc310683e |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 44419115-f632-476d-8d25-1048677a520c |  | note | RECORD OF CONFORMITY: Permits
label | bd086525-9ee9-4f8e-aae7-874f5bf0fbb5 |  | note | HP*
label | 0b5eac37-7f63-4958-91c3-2941a4fa84ae |  | note | RESPONSIBILITY: Project Engineer/Foreman
text | bf85bd56-5150-42c3-875e-22deef380f71 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 Stabilised Subgrade Replacement
label | d39b3eb2-23c7-4290-afb7-cf61e8968522 |  | note | FREQUENCY: Prior to commencing works
label | 660f7a16-e862-4e48-839d-61258f14b2b6 |  | note | ACCEPTANCE CRITERIA: Methodology & scope agreed with Principal’s Representative prior to works commencement, outlined in Work Procedure and design drawings
label | 61bcdb1c-85b8-4e4c-9a6d-90645d347f2b |  | note | REFERENCE DOCUMENTS:VicRoads section 290
label | 9387357c-663c-4ae8-8bac-6d054722820b |  | note | INSPECTION/TEST METHOD:Testing
label | fb3168d7-a44d-4306-9a12-d09394853dbf |  | note | RECORD OF CONFORMITY: This signed ITP
label | dffe641a-ae78-460d-851b-3a2f150424a2 |  | note | HP*
label | bec9e3cb-42b2-41db-8cee-12268d5a8aa2 |  | note | RESPONSIBILITY: Project Engineer
text | a11cd44b-34d8-4232-9f88-d55221ff62ac |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Investigation and determination of design lime spreading rate
label | 50bd87df-63c4-41cb-a085-ddddfad11a64 |  | note | FREQUENCY: Each lot
label | 75278c20-498d-46f4-8e95-c07c232eabe5 |  | note | ACCEPTANCE CRITERIA: Lime spreading rate to be presented to Principal’s Representative for review. Evidence shown to indicate Lime stabilisation to result in a soaked CBR not less than 15% when compacted to 95% relative compaction and a swell no greater than 0.5%
label | b4fed25b-83f1-4ba4-b616-25c80dc1d8e5 |  | note | REFERENCE DOCUMENTS:VicRoads section 290
label | 7315ed34-fe39-403e-b169-449be8daacf2 |  | note | INSPECTION/TEST METHOD: Verify
label | a75ca0c9-0682-49eb-97d9-01fdd79a7701 |  | note | RECORD OF CONFORMITY: Subcontractor Quality Docs
label | ef393afc-268b-4635-bd43-30a25da6b4a9 |  | note | HP
label | 7b5284e6-d30c-47fe-8bc4-facb26ce3151 |  | note | RESPONSIBILITY: Project Engineer - Jacobs
text | d3481750-31d0-4c38-b981-5782627375dd |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 2.3 Preliminary Trial
label | 8eddade4-cc96-4ef3-8a6e-c945bfea3482 |  | note | FREQUENCY: Each lot
label | d787ae81-50de-49c5-83fe-6a5ea22a7aeb |  | note | ACCEPTANCE CRITERIA: Preliminary trial to be undertaken of the proposed stabilisation operation. Trial to determine: - Effectiveness of plant - Number of passes required by the stabilisation to achieve uniform pulverisation - Field moisture required to achieve specified compaction requirements. - Rolling routine required to achieve specified compaction requirements Lime stabilisation not to proceed until reviewed by the Principal’s Representative, with an outcome received within three working days.
label | a31e6aa3-18b8-43de-859b-b5990aebe8a3 |  | note | REFERENCE DOCUMENTS:
label | fefef86f-2634-44c9-aaad-c048a84243e0 |  | note | INSPECTION/TEST METHOD: VicRoads section 290
label | 22b2fcb6-8b70-4d04-aad5-a75ad1266fff |  | note | RECORD OF CONFORMITY: Subcontractor Quality Docs
label | bfecd50f-7102-4659-a555-cb9e2249cad5 |  | note | HP
label | 77a21a09-f9e8-45d9-989e-e8bb0a26a538 |  | note | RESPONSIBILITY: Project Engineer - Jacobs
label | f267505b-ff28-452b-823c-64d4cc154e85 |  | note | Hold point sign off reference: Aconex: FHPL-RFI-000407
label | aaf748d6-8e09-4a4e-a291-5accf2c5c6da |  | note | Date: 15/09/2019
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 3.1 Subgrade Preparation
label | d4dfbf93-f691-47b2-a064-dc0f2c0f902f |  | note | FREQUENCY: Each lot
label | a59c7242-be5d-4fb0-aeaf-92cd68efd919 |  | note | ACCEPTANCE CRITERIA: Cutting and filling as required to achieve surface levels and shape as shown on the Drawings Lightly rolling and proof rolling surface to identify any soft areas.
label | 53d65607-1405-4a76-b212-98bde76178cf |  | note | REFERENCE DOCUMENTS: Clause 3.6.1
label | 52431487-e4e4-4226-8900-f24607113579 |  | note | INSPECTION/TEST METHOD: Verify
label | 6a007c82-addf-4414-8320-665413bcde0b |  | note | RECORD OF CONFORMITY: This signed ITP
label | 6fc009bc-9195-4927-a9ba-a57192de7a48 |  | note | HP*
label | 3485e99b-de48-40d0-8c08-20af5ab9facc |  | note | RESPONSIBILITY: Project Engineer
checkpoint-status |  |  | checkpoint | 3.2 Proof Roll
label | ab9a0b24-44c0-4d03-850c-149ae54fb629 |  | note | FREQUENCY: Each lot
label | c5d45364-f7d4-4eb1-8474-37d04a18ca36 |  | note | ACCEPTANCE CRITERIA: Lightly rolling and proof rolling the trimmed surface to identify any soft areas.
label | db6e0d59-1058-4d7b-8638-f12d85e1421c |  | note | REFERENCE DOCUMENTS: Clause 3.6.1
label | f8d63748-c1da-4fdd-9b62-61fd1a5b79a8 |  | note | INSPECTION/TEST METHOD: Verify
label | 18d879a3-6633-4e09-bed1-2f77936ed824 |  | note | RECORD OF CONFORMITY: This signed ITP
label | 1cf43cea-fc64-40b0-95b7-95c9557f09b0 |  | note | HP*
label | 94780b52-b35c-44a6-92a6-2ebb490de102 |  | note | RESPONSIBILITY: Project Engineer
checkpoint-status |  |  | checkpoint | 3.3 Proof Roll Failure
label | 7b7f1e13-acb7-4fb1-a349-fd4f169abfac |  | note | FREQUENCY: Each lot
label | 1e42e1bd-765d-4d6b-96bd-4de19dcc8002 |  | note | ACCEPTANCE CRITERIA: Identifying and removing soft areas to a minimum depth of 300mm and replace with fill compacted to 95% (standard compactive effort), as part of the subgrade preparation. A hold point is to be installed in this instance.
label | 06b2757b-78b0-4a39-800a-5f5a8b66d746 |  | note | REFERENCE DOCUMENTS: Clause 3.6.1
label | 1d2dab67-a8bd-4323-9059-cdbcba9ae226 |  | note | INSPECTION/TEST METHOD: Verify
label | ecae4b09-0301-44fd-bcee-5af119b2940f |  | note | RECORD OF CONFORMITY: This signed ITP
label | 5bd0fabf-ee60-4159-a2dd-85aa1a826f36 |  | note | HP
label | 830d3317-429f-45b0-bd0f-6892102d1258 |  | note | RESPONSIBILITY: Project Engineer & JACOBS
checkpoint-status |  |  | checkpoint | 3.4 Pre-treatment of earthworks
label | e3656799-019a-43fb-92f2-b66b0971aba4 |  | note | FREQUENCY: Each lot
label | 4ace43cb-65c0-41a4-806f-75381189eaa8 |  | note | ACCEPTANCE CRITERIA: Area to be scarified/pulverised to a depth of 300mm. Any rock particles greater than 75mm to be removed from the soil.
label | b7c89041-931e-448d-8ebd-5574833cc837 |  | note | REFERENCE DOCUMENTS: VicRoads section 290
label | d5d1ec8e-69ca-4178-9a53-8b8355252ed0 |  | note | INSPECTION/TEST METHOD: Verify
label | c58e74ac-c6ec-4bd6-a1f0-0e8f4642eb52 |  | note | RECORD OF CONFORMITY: This signed ITP
label | 06f0b387-e6d3-4835-837f-738860554bbe |  | note | IP
label | 47d691ab-8dd3-4e8e-9462-a8bd2b239874 |  | note | RESPONSIBILITY: Project Engineer
text | 01146527-45ba-4efe-b2f6-019682803413 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.5 Spreading of Lime
label | 33b9ba0e-ee3b-440a-8c02-fafb9118906e |  | note | FREQUENCY: Each lot
label | 496070c0-69d2-40fd-b98b-4aa780353796 |  | note | ACCEPTANCE CRITERIA: Lime to be spread uniformly over the prepared surface at the Lime spreading rate calculated.
label | 8d05583d-3e76-4a32-b1a3-d8eb53741510 |  | note | REFERENCE DOCUMENTS: VicRoads section 290
label | 19175551-7e2a-4b48-aa23-a039d41cd705 |  | note | INSPECTION/TEST METHOD: Verify
label | 77d5338b-27a8-466f-87ed-f031069abbff |  | note | RECORD OF CONFORMITY: This signed ITP
label | 3b441b6b-dcee-4f1a-a304-b22d92422b6f |  | note | IP
label | 0ebadb45-e93a-49be-851b-f131ef2be6bc |  | note | RESPONSIBILITY: Project Engineer
text | 2643e5af-03ff-4b31-bf4b-db3ca695d745 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.6 Slaking of Quicklime
label | 3678f49e-8723-4cfa-ac43-cd82a36c33c0 |  | note | FREQUENCY: Each lot
label | f84eab7c-52cc-4caf-a674-2941c386e5ef |  | note | ACCEPTANCE CRITERIA: Quicklime shall be slaked with sufficient water to allow full hydration to take place.
label | 16e76323-79f6-4c8f-a8ea-5a59f84a8e06 |  | note | REFERENCE DOCUMENTS: VicRoads section 290
label | 940fa020-84a9-461a-bda9-e9c37d5af3db |  | note | INSPECTION/TEST METHOD: Verify
label | a221ad97-580a-458a-9f30-a83ba5f1856d |  | note | RECORD OF CONFORMITY: This signed ITP
label | af3ad100-8c54-48ee-9c63-487407a2a850 |  | note | IP
label | c823fc19-961c-4cad-8e43-3b67b0382f54 |  | note | RESPONSIBILITY: Project Engineer
text | ffcecb24-4e5a-43c7-a381-c5e5793e1c94 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.7 Mixing
label | 5b546b88-440a-4f50-b6ad-b47eec987ae7 |  | note | FREQUENCY: Each lot
label | d419d9ba-c252-4a53-b716-e4b1f4e5d0e8 |  | note | ACCEPTANCE CRITERIA: All lime to be mixed to the specified depth within 6 hours of spreading. The stabilised material shall be visibly inspected for uniform mixing by excavating test holes to the full depth of the loose material at six random locations within each lot.
label | ac5eb560-74b4-4813-bdca-669e3ef78003 |  | note | REFERENCE DOCUMENTS: VicRoads section 290
label | 94ecc4db-2627-46de-8a76-c0bd56c388a0 |  | note | INSPECTION/TEST METHOD: Verify
label | e9120803-6ee9-48e0-904c-12924c529938 |  | note | RECORD OF CONFORMITY: This signed ITP
label | 2208cd26-bbad-494e-a3ff-d805bcdad663 |  | note | HP*
label | 160e5e2b-d306-4505-b84f-690b4f5ab168 |  | note | RESPONSIBILITY: Project Engineer
text | 59b34922-51f6-48f6-b370-73f8ea0be802 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.8 Trimming
label | da4277f7-17ce-48c5-9dd8-e05158d5fcb7 |  | note | FREQUENCY: Each lot
label | 383b6353-d404-4068-89d3-7f15b54cd226 |  | note | ACCEPTANCE CRITERIA: Surface may be trimmed before or during compaction to conform to surface level tolerances.
label | 607d3380-70ab-49f8-8b3a-d182305fcb98 |  | note | REFERENCE DOCUMENTS: VicRoads section 290
label | 7e748920-f672-4c3c-88a1-115da389dbc3 |  | note | INSPECTION/TEST METHOD: Verify
label | e912490b-ada5-4804-a255-9cfc9aa308ce |  | note | RECORD OF CONFORMITY: This signed ITP
label | 6947d28f-562c-4447-a456-c0b047288ad2 |  | note | HP* SCP
label | 1797cb04-79f7-423c-bf9c-502e78ba51ba |  | note | RESPONSIBILITY: Project Engineer
text | 7b29ec2a-25fc-4b63-9cf8-6fea22e296f6 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.9 Compaction
label | 0b008de5-2b0b-4316-8889-6bd7343eec34 |  | note | FREQUENCY: Each lot
label | a1d62d3c-0997-4712-8793-88c7bb0ae8b5 |  | note | ACCEPTANCE CRITERIA: After satisfactory mixing in accordance with VicRoads Clause 290.08(e), compaction shall commence within two hours and be finished within eight hours of mixing completion. Additional moisture may be added if required to achieve the specified density ratio.
label | 419dc3e5-e217-4f40-8870-bd5b5df05a7e |  | note | REFERENCE DOCUMENTS: VicRoads section 290
label | 051051ef-a3e8-4dd8-b47f-1cfcf1efb005 |  | note | INSPECTION/TEST METHOD: Verify
label | dbecd910-920e-4d26-b22e-e45fc4fa1667 |  | note | RECORD OF CONFORMITY: This signed ITP
label | ae8adcac-e177-4d4e-b161-c3f3acc665a6 |  | note | HP*
label | 73bc627e-5cd4-48e5-91f0-e86a87043c88 |  | note | RESPONSIBILITY: Project Engineer
text | 8d87048a-6e2c-4669-8801-0ddab942a63b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.10 Protection of Subgrade
label | e471e76d-ad72-4148-88fe-891851797b87 |  | note | FREQUENCY: As Required
label | 73016ec7-6eb0-42fc-b3ee-56be35312254 |  | note | ACCEPTANCE CRITERIA: Undertake necessary precautions to protect subgrade from wet weather and traffic
label | 982e9f11-5d6c-43ae-b3e1-98f36c38ea53 |  | note | REFERENCE DOCUMENTS: VicRoads section 204
label | 30ecd373-e6cf-4023-947e-0ab8b4285013 |  | note | INSPECTION/TEST METHOD: Inspection Point
label | 7d6991b4-7fd3-4463-a597-2ca3ddbeb350 |  | note | RECORD OF CONFORMITY: This signed ITP
label | d38b5e9e-362e-4cf3-96f9-838df010aa76 |  | note | IP
label | 7abb0df4-feff-4ccf-bcc6-6e339dfcc30c |  | note | RESPONSIBILITY: Project Engineer
checkpoint-status |  |  | checkpoint | 4.1 Subgrade Preparation
label | c742d702-ffff-4ed0-98f2-a2707facae58 |  | note | FREQUENCY: Each Lot
label | e1b567ee-ad13-4852-81d1-8b4c3da4f55c |  | note | ACCEPTANCE CRITERIA: Cutting and filling as required to achieve surface levels and shape as shown on the Drawings Lightly rolling and proof rolling surface to identify any soft areas.
label | 33a87889-c068-454d-bdcb-b282239ede61 |  | note | REFERENCE DOCUMENTS: Clause 3.6.1
label | d4bb5e48-dca5-45de-a557-e6e05b503e81 |  | note | INSPECTION/TEST METHOD: Verify
label | 23109f6f-6013-41ca-ab82-66349a98ab5c |  | note | RECORD OF CONFORMITY: This signed ITP
label | 81278511-ab54-484a-b5cf-95ea38ad3ba7 |  | note | HP*
label | c89f16fc-f4a4-4a66-9e84-58d65e1e1c98 |  | note | RESPONSIBILITY: Project Engineer
checkpoint-status |  |  | checkpoint | 4.2 Subgrade replacement
label | 2d40f4e6-8e6a-4de4-9d7c-2aaa2db1f205 |  | note | FREQUENCY: Each Lot
label | 44c1b15f-ef15-4f9f-ae84-c8dad671b66a |  | note | ACCEPTANCE CRITERIA: Where lime stabilisation cannot be completed, or is deemed impractical, the subgrade is to be replaced with 200mm of Class 1 Crushed Rock. This is to extend the Crushed Rock Working Platform depth to 500mm. Lime stabilisation works will not be required where this has taken place.
label | 791be843-2ad1-4bf7-b479-3f2882479129 |  | note | REFERENCE DOCUMENTS: Clause 3.6.1 & ACONEX: FHPL-RFI000280
label | b83f9c88-45ed-4e85-9223-3eacd7195af8 |  | note | INSPECTION/TEST METHOD: Verify
label | a9d0bdc5-293f-489b-9f84-114ba27684f2 |  | note | RECORD OF CONFORMITY: This signed ITP
label | 251550b5-cd43-4bbe-8f1c-0d381468385c |  | note | HP*
label | 25d283c5-696f-4066-b869-d75723462b55 |  | note | RESPONSIBILITY: Project Engineer
checkpoint-status |  |  | checkpoint | 5.1 Requirements and Acceptance of Lime Spreading Rate
label | c726e6ca-fa53-4f3d-a01b-c4f9a27c8d25 |  | note | FREQUENCY: Each lot
label | 3be78971-adf7-4ce9-baff-979d983fb043 |  | note | ACCEPTANCE CRITERIA: The Average Lime Spreading Rate and Uniformity of Lime Spreading Rate are to be determined by either the Mat/Tray System or the Continuous Weighing System, as described in VicRoads Clause 290.12. Evidence of results to be presented to the Principal’s Representative upon request.
label | a2242ee6-3b6d-484b-8b72-10400dcfc76d |  | note | REFERENCE DOCUMENTS: VicRoads section 290
label | fa8e71ff-dda7-4246-9f36-9935ffb8cfb9 |  | note | INSPECTION/TEST METHOD: Verify
label | 6d0813e0-e33c-4cce-95aa-0778f52a6885 |  | note | RECORD OF CONFORMITY: This signed ITP and Test Results
label | 8d4d652e-cae5-4046-8468-60b09606c0ae |  | note | HP*
label | 629cd196-3be6-4c2f-b3af-9cd6304a98d4 |  | note | RESPONSIBILITY: Project Engineer
text | 4a586f31-57be-489c-8d22-3db544c282a5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Subgrade Testing
label | 982e6198-d18d-4a3e-9367-498bdd911229 |  | note | FREQUENCY: Each lot
label | 08af7bd2-b284-4b78-8624-3482c50ca3e7 |  | note | ACCEPTANCE CRITERIA: Average dry density ratio of not less than 99% MDD (Standard) for lime stabilised subgrade material.Field dry density at three random locations throughout each uniform section, per scale B requirements. Where the subgrade has been replaced with 200mm of Class 1 Crushed Rock, the field dry density is to be compacted to 99% (standard compactive effort).
label | bb9a9af9-c9ce-4a96-960c-f754296dd691 |  | note | REFERENCE DOCUMENTS: Jacobs - Zulu Spec. Cl – 3.6.1
label | 6f711f68-333d-4e2d-b81e-46d6b78bf722 |  | note | INSPECTION/TEST METHOD: Verify
label | 88ea53bc-c548-4ed4-ad5a-f9ce71cec419 |  | note | RECORD OF CONFORMITY: This signed ITP and Test Results
label | 7bba5589-6c68-468d-be3e-df6ce44e814f |  | note | TP
label | 7f9dee8b-43e2-4600-83c8-a1e7afb26d32 |  | note | RESPONSIBILITY: Project Engineer
text | 392edf00-8aba-43f5-88df-ea3474eae916 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Test Rolling
label | 1ca748f3-1541-4202-ae1c-7bef9826a798 |  | note | FREQUENCY: Each lot
label | 0f9901d1-7805-4a0d-9693-8b2185e6779d |  | note | ACCEPTANCE CRITERIA: Surface to be test rolled following completion of compaction. Plant utilised is to conform to the following requirements at a minimum; - 12T Smooth Drum Steel Wheeled roller. Minimum load intensity 6T per metre width or; - 20T Pneumatic Tyred Roller. Ground contact pressure 450kPa per tyre. Area of ground contact pressure not less than 0.035m2 per tyre (either front or rear wheels). Compliance with the test rolling requirements shall be when an area withstands test rolling without visible deformation or springing.
label | f116b9c3-a016-4747-88e2-99ebd7d71aa4 |  | note | REFERENCE DOCUMENTS: VicRoads section 290
label | 9aa07e90-bd0f-4a69-a809-d82fc2039119 |  | note | INSPECTION/TEST METHOD: Visual Inspection and mapping data
label | 294e9879-4f8e-491c-be57-5df811addbea |  | note | RECORD OF CONFORMITY: This signed ITP
label | 4d9a5baa-9818-42fe-abce-1e9a6f221298 |  | note | WP
label | e05bef42-1913-4a6d-a844-e9d8469c8e60 |  | note | RESPONSIBILITY: Project Engineer - Jacobs
text | 6232c003-5f9d-4970-9582-9466ac538763 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Conformity with Drawings
label | bd18701a-5a5b-49d4-9671-7a9392e63a44 |  | note | FREQUENCY: Each lot
label | df4fe759-3fc5-4159-8db9-8537b28ae85c |  | note | ACCEPTANCE CRITERIA: Surface Level: +0, -25mm from design level. FHPL-RFI-000280 – “Jacobs also has no technical objection to additional thickness of class 1 crushed rock being laid where low spots in the subgrade are encountered. Contractor to ensure crushed rock is placed within a minimum and maximum layer thicknesses (80mm to 200mm) in order to achieve compaction.”
label | c48be19a-c085-4d13-adc0-bb16f75c6b78 |  | note | Depth of Stabilisation: -15mm from design depth and average depth not less than specified
label | ab8e3a4d-f291-4d95-b96a-afea9d157639 |  | note | Fulton Hogan to submit all results of quality control and testing undertaken via Aconex. Frequency of testing taken as per VicRoads section 290, table 290.131.
label | 6bd5b84b-38a5-4414-b18b-6dae2d5d1519 |  | note | REFERENCE DOCUMENTS: VicRoads section 290
label | 946e4811-3630-4061-af9b-a93a4fefe206 |  | note | INSPECTION/TEST METHOD: Verify
label | 9f5a7983-334f-42cd-b66b-5bcfc136bc5d |  | note | RECORD OF CONFORMITY: This signed ITP / Survey Report
label | d5b4e84a-2333-4e9a-9c52-806e71663538 |  | note | IP/SCP
label | 9f7102a4-f068-4584-837b-f0a2d27fed19 |  | note | RESPONSIBILITY: Project Engineer
text | cb80944b-4283-4e3f-9b8d-725982087eda |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | FULTON HOGAN FINAL INSPECTION - On behalf of Fulton Hogan, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | a0d8f4af-0421-4f64-bec7-7f128ddf4b4a |  | textbox | Name:
text | 098a3112-c7dd-4225-a9f8-55f34ac4769d |  | textbox | Position:
checklist-sectioned |  |  | checklist | ITP 038 - Spall Repair | itp |  |  |  | Yes | ITP 038 - Spall Repair | b79345a5-978b-4681-aa41-84121f8069d7
checkpoint-group |  |  | section | ITP 038 - Spall Repair
checkpoint-status |  |  | checkpoint | 1.1 Check for correct documentation
label | 10bb7dea-c0d5-4f2a-b848-324ffba90ca7 |  | note | FREQUENCY: Prior to commencing works
label | b85891b1-b8b2-4650-bbc5-3b82f87ca453 |  | note | ACCEPTANCE CRITERIA: Current revision of drawings, technical specifications and any other construction documentation is being utilised by Fulton Hogan and subcontractors obtained via Aconex
label | 329a9a0f-8464-428b-8e32-90e511c5e2ab |  | note | REFERENCE DOCUMENTS: Jacobs Technical Specifications & Drawings
label | 453ddc88-a327-4fd3-b17d-cfd932182226 |  | note | INSPECTION/TEST METHOD: Verify
label | 006f237a-320e-4c13-8066-bd87ab535ca5 |  | note | RECORD OF CONFORMITY: This ITP signed
label | ebf62a31-fbc7-40b4-b0cb-30f97468605f |  | note | IP
label | 17423e88-b524-4979-a1a4-978a2614c63e |  | note | RESPONSIBILITY: FH Engineer
text | c82d831a-37c5-4ec7-bb21-83ee02a874d5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 Implementation of all measures and controls
label | 375f6f2f-806b-432b-9cb1-a03335cbf4f9 |  | note | FREQUENCY: Prior to commencing works
label | 2ade5e52-42c4-44e7-85e7-3515030db4db |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented in accordance with PSP,EMP, TMP, JSEA, SWMS & WP
label | a66937ae-e0c8-440f-a065-037821b537cc |  | note | REFERENCE DOCUMENTS: PSP, EMP,TMP, JSEA, SWMS, WP
label | d96e938a-11db-4fe0-b8f9-cf672b386144 |  | note | INSPECTION/TEST METHOD: Verify
label | 7d3ae003-0e32-4116-90fe-7d8c027e1cb6 |  | note | RECORD OF CONFORMITY: This ITP signed
label | b300a558-52a1-4c98-836d-f48d4a52f69b |  | note | HP*
label | 276231a0-fe94-4b8e-81c6-3980a51022ca |  | note | RESPONSIBILITY: FH Engineer
text | 22433cf6-e89e-413c-add0-24cb72cfa2f3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 Material Sample
label | 949d9aaf-7ee1-4b72-8e04-4c4509b94b2e |  | note | FREQUENCY: Prior to commencing Production and Construction Trial
label | 41175920-894f-4313-ad01-41b22bed854f |  | note | ACCEPTANCE CRITERIA: Semi Rigid Epoxy materials report has submitted and approved for use on the project.
label | c42b2ba9-03e1-4ade-8bdd-fa8879468b3b |  | note | REFERENCE DOCUMENTS: TDS
label | 606726eb-e6a3-44d3-84ed-d20472c9109f |  | note | INSPECTION/TEST METHOD: Verify, Aconex Approval
label | d18e5816-552d-46aa-85e9-f5583700d3c2 |  | note | RECORD OF CONFORMITY: Aconex Mail Number
label | 0c0835d1-4f7e-4d4f-be3a-1024c8c9501e |  | note | AP
label | fe7e6fab-6f08-4053-bcee-11fd98573fd1 |  | note | RESPONSIBILITY: Principals Representative
label | 2fdf587e-3e19-4533-85b5-7106f02171a0 |  | note | COMMENT: Refer to Aconex: FHPL-TRANSMIT-000228
text | 565d6618-ac31-4f33-8df8-e56bb25aea6d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 Define area of works.
label | f33c8c94-64fc-4a87-a182-30a6ab4727c0 |  | note | FREQUENCY: Prior to commencing works
label | 83e8b3ea-137b-49c7-9f7c-08ed23ee2439 |  | note | ACCEPTANCE CRITERIA: Undertake inspection with the Principles Representative of slabs and mark out areas requiring SRE repairs and/or full depth cores. Locations that require SRE repairs and/or full depth cores to be marked up on a plan and included as part of the ITP. Repair locations and scope of repair to be specified and agreed on the attached plan prior to any repair works being undertaken.
label | 3a677453-6dda-4401-89fc-287ff9e9b581 |  | note | REFERENCE DOCUMENTS: FHPL-RFI-000875
label | adcddfdf-076d-463a-9fa6-3a6c60f1d75d |  | note | INSPECTION/TEST METHOD: Verify
label | fd999074-32a2-49bf-961d-11a68f22d9fe |  | note | RECORD OF CONFORMITY: This ITP signed
label | b41d72b4-f7fd-42c0-9376-13c92de0e5db |  | note | WP
label | cd555350-bae3-440a-83c9-f8af69f28658 |  | note | RESPONSIBILITY: Principals Representative
text | 32c018ca-7ff9-445d-9c7e-ce44d27f8a39 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.1 PCC cure
label | 05159e1f-c9c3-4444-a562-7a6790f6375a |  | note | FREQUENCY: Each Lot
label | fdb85748-f1ed-43e0-90e2-60dc3400bc4b |  | note | ACCEPTANCE CRITERIA: Check PCC pour lots for area of works to ensure concrete has been allowed to dry and cure. At least 7 days curing should be allowed prior to works.
label | 688a24db-6c2c-4286-92ac-0a52cfaf4617 |  | note | REFERENCE DOCUMENTS: 6.7.5.7
label | c01b6812-671c-477c-84d2-44f1eb6c7bb4 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 63c8caf6-d9f3-4e01-950f-1892880dba60 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 3ba4a16e-a535-445c-aa48-34a14a91d2d9 |  | note | HP*
label | eb297eaf-e5bd-4f35-b1ed-452a558f3d2a |  | note | RESPONSIBILITY: FH Engineer
text | 5a0bfaff-835a-4a32-830e-6e15f5e4bcef |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 SRE - Prepare recess
label | 69ab1114-5bae-4dfe-97b6-fc2436ceffe4 |  | note | FREQUENCY: Each Lot
label | 310d4c51-b583-4402-be14-77f06d530ef8 |  | note | ACCEPTANCE CRITERIA: SRE’s - Saw cut and break out the area to a regular shape encompassing the full area of damage plus 15mm outside spall area or to an area of 150mm by 300mm whichever is greater. Minimum depth of cut out to be 75mm or 15mm below deepest portion of spall. Record location.
label | 3f5ed62a-980b-42b6-abb6-18d12946630a |  | note | REFERENCE DOCUMENTS: FHPL-RFI- 000875
label | 8503d4b1-1fb3-45a2-934c-59ab7755f57e |  | note | INSPECTION/TEST METHOD: Inspection
label | d6e8dbe2-a218-46f7-b1fd-51e32bff5ad6 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 34c64e99-4bd7-431a-8963-3bf6e9ff0a52 |  | note | IP
label | afa54282-ecf7-473f-ba6a-9f6f3cb72f21 |  | note | RESPONSIBILITY: FH Engineer
text | 973733d4-b3b8-44b6-8e5f-dcd68285d2f9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Core Hole - Prepare Core
label | 9985020a-5100-46c8-940f-fdd6bc6c072c |  | note | FREQUENCY: Each Lot
label | a3002b41-5185-4e20-b74e-bca6c6cca173 |  | note | ACCEPTANCE CRITERIA: Core Holes – Drill a full depth core hole up to a max 150mm diameter. Record location.
label | b6c9e23d-1a9d-4b94-a4a7-a03be62c9369 |  | note | REFERENCE DOCUMENTS: FHPL-RFI- 000875
label | ae74b19b-9bce-4975-8ce7-c63e342b2142 |  | note | INSPECTION/TEST METHOD: Inspection
label | fbec2e07-8e89-4220-882a-a0b2aa6ac36e |  | note | RECORD OF CONFORMITY: This ITP signed
label | 403fc193-d260-44a2-b1d8-092c29c019e3 |  | note | IP
label | 0a6d0d8b-c8b0-4b4f-966f-c312992dd80c |  | note | RESPONSIBILITY: FH Engineer
text | ceab0cae-0371-4d3a-951c-0026c6cea7d2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 Clean and Dry
label | 1802cfb0-f383-4a35-b72d-92b5a923058f |  | note | FREQUENCY: Each Lot
label | f5d9712f-c445-4e2d-a61e-4b47da2f3b7f |  | note | ACCEPTANCE CRITERIA: SRE’s - Recess clean, dry and free from dust – Wash and/or Air Blown. Core Holes – Clean core holes from any slurry and debris. Soak with water up to 4 hours.
label | 675a5025-3b39-43bc-99e3-c70548e94883 |  | note | REFERENCE DOCUMENTS: FHPL-RFI- 000875
label | 9122d843-1b66-43a4-83a9-bb481adf3a10 |  | note | INSPECTION/TEST METHOD: Inspection
label | b3e80daa-62b6-4e73-92be-c42b1984af4a |  | note | RECORD OF CONFORMITY: This ITP signed
label | 62386d0d-8841-4428-a320-001b1af44011 |  | note | IP
label | 080e1143-34fb-489c-bfa9-582a6e59c582 |  | note | RESPONSIBILITY: FH Engineer
text | dbecc577-5864-4c97-9811-e13376987836 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.5 Pre Installation Inspection
label | f3998a6f-8d58-43bb-ab7a-f6627b2c8245 |  | note | FREQUENCY: Each Lot
label | 9d219c32-6ae0-4761-ba2f-4cceb6444534 |  | note | ACCEPTANCE CRITERIA: Inspection of cut and cleaned SRE’s and core holes prior to placement of SRE(S) material and backfill.
label | cedbd9eb-3ba3-49b5-b5c6-609e9a5543a0 |  | note | REFERENCE DOCUMENTS: FHPL-RFI- 000875
label | 16a7235a-c913-4421-90bb-ca792765c4a5 |  | note | INSPECTION/TEST METHOD: Inspection
label | df876d1e-8f79-4b13-a9fe-4bfec4ad0106 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 15b3d859-fb14-4b1e-b212-2ebb0f980b70 |  | note | HP*
label | 02f25220-12f0-4739-be83-ed5b394115c6 |  | note | RESPONSIBILITY: FH Engineer
text | e7e10190-3143-46cf-9bb5-be126ff50d70 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.6 Install Repair material
label | a4fb71fd-3260-4e55-b43a-47ed2e93a22a |  | note | FREQUENCY: Each Lot
label | 853e0f4e-47c7-41d2-a427-c3b58627de97 |  | note | ACCEPTANCE CRITERIA: SRE - The SRE(S) shall be mixed, placed and finished strictly in accordance with manufacturer’s instructions. The material shall completely fill the recess and be finished flush with the pavement surface. Core Hole – Core hole shall be backfilled with approved methods
label | 0a4d6d57-1ba5-4ddf-961e-6d057ab2d7ab |  | note | REFERENCE DOCUMENTS: TDS
label | 8c623083-e3ee-45bc-87b8-60fe8da807bb |  | note | INSPECTION/TEST METHOD: Inspection
label | ab2fa460-311a-4fde-a806-98a6fa2894a5 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 757292a5-3d0b-429d-b773-341faa317e8a |  | note | IP
label | ef9fef65-b3e5-4ed8-8061-aad5e649b8cf |  | note | RESPONSIBILITY: FH Engineer
text | 4fcbe640-2c3b-4ed4-9f64-408d5c12e620 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.7 Replace Joint Sealant
label | 64a46cd2-357c-47cf-ac7c-6861e48a0ac5 |  | note | FREQUENCY: Each Lot
label | fef05346-76f4-40f0-b914-6cdf90f80618 |  | note | ACCEPTANCE CRITERIA: If the repair involves the removal of any joint sealant, then joint sealant must be reinstated.
label | c6209e2d-c1d9-4921-82cf-5866440e1f02 |  | note | REFERENCE DOCUMENTS: ITP014
label | 608974f1-3d0d-4fb8-9d59-ec7f16c2c4c7 |  | note | INSPECTION/TEST METHOD: Inspection
label | c329a3a5-0c96-427b-878c-916d8326f08a |  | note | RECORD OF CONFORMITY: This ITP signed
label | 55ba7fd4-2fc7-4696-bf60-ce25831ebd08 |  | note | IP
label | 079e5510-cda5-404b-acd7-1730badfb1b8 |  | note | RESPONSIBILITY: FH Engineer
text | b8bf7700-3240-44b1-89f1-80bf1541cf3c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.8 Clean Area
label | 28c82b4e-9f30-45c6-aee4-dd4e0f34e4da |  | note | FREQUENCY: Each Lot
label | cca0f591-4c4a-4425-bba5-e64056e87973 |  | note | ACCEPTANCE CRITERIA: Any overlapping/spillage of the repair material onto the adjacent pavement surfaces shall be removed. The repair material shall be allowed to cure for the full duration recommended by the manufacturer.
label | 8e436a6b-ecf0-40df-b91c-a9a156551fb0 |  | note | REFERENCE DOCUMENTS: This ITP
label | bdaf3c9e-f7f7-4e25-90dc-5fc687e27e6f |  | note | INSPECTION/TEST METHOD: Inspection
label | 4417345a-8615-4d29-bfb0-9b49a12b96e0 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 6b377b5b-fd6d-4e29-a067-855c8a423929 |  | note | IP
label | 649214a9-aa35-4d32-addc-f86f002546e3 |  | note | RESPONSIBILITY: FH Engineer
text | 66a0ce21-b7cd-44eb-aab5-98ce6d546a67 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.9 Final Inspection
label | 81643ff1-c424-4d05-ba17-bbd3c601d9e5 |  | note | FREQUENCY: Each Lot
label | 129b8b76-31a3-41e0-9370-0609c8c1e67f |  | note | ACCEPTANCE CRITERIA: Final inspection post completion to ensure SRE and Core holes are installed as per this ITP and any observations noted.
label | 264e7a1b-729a-48a1-b73a-5816ccbcc15f |  | note | REFERENCE DOCUMENTS: This ITP
label | 0b17fd79-5f3f-4ac2-88b5-3d53ace10cea |  | note | INSPECTION/TEST METHOD: Inspection
label | f64e67d4-72ad-4e7a-9882-18bcac3cd534 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 267f02c5-d86f-4022-8578-308960c8cf0a |  | note | IP
label | c9db43e1-8950-48e8-86bd-f875f55dcb39 |  | note | RESPONSIBILITY: FH Engineer
text | 3efc8ba3-619e-4d40-8b1e-d46e93cb3039 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection: Fulton Hogan
label | 865842bb-e519-4579-8f6f-ec9498e895e9 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 8011fb15-1d91-4ff6-98fd-24715b4b2a91 |  | textbox | Print Name:
text | cf3dda78-0aa8-4017-ac5a-ad0b78b411cd |  | textbox | Position:
text | 229ce69f-9bba-4a29-9ee6-4b035ca690cb |  | textbox | Date:
checklist-sectioned |  |  | checklist | ITP 013A - Aeronautical Ground Lighting (AGL) - General, Testing & Commissioning | itp |  |  |  | Yes | ITP 013A - Aeronautical Ground Lighting (AGL) | b8cf85d3-9ba3-4b1a-8e3a-e1b5064ce370
checkpoint-group |  |  | section | ITP 013A - Aeronautical Ground Lighting (AGL) - General, Testing & Commissioning
checkpoint-status |  |  | checkpoint | 1.1 Enabling Works
label | b7e238fb-18be-4534-8020-28c26cc2b782 |  | note | FREQUENCY: Prior to Start
label | d2108f35-b376-4ebb-bb7d-fef465d1ea01 |  | note | ACCEPTANCE CRITERIA: The contractor shall provide enabling work details for approval before commencing of any works where existing services to taxiways not part of the works will be affected.
label | 3a69d6ff-70a5-4031-ad27-b070f1feb1b2 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002 cl.10.6
label | 2232dbad-d857-4a0a-9d59-b5086e217277 |  | note | INSPECTION/TEST METHOD: Verify
label | 3f426135-616a-4fd6-924d-a40dec1b5e07 |  | note | RECORD OF CONFORMITY: Aconex
label | 0f7da949-515e-46a8-b6e9-6a79c61f5631 |  | note | AP
label | 1ac5c7ee-10fb-4184-9bb8-aa51abfde770 |  | note | RESPONSIBILITY: Project Engineer / ADB Safegate / Principal’s Representative
text | fb035a1e-baeb-4182-8fb5-619f23f88a31 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 AGL Control System
label | 5c8efd31-e8ef-4cce-8aba-06d85003c9d3 |  | note | FREQUENCY: Prior to Start
label | 083f6a9c-fb2b-42a5-ac7d-62a492a10a2d |  | note | ACCEPTANCE CRITERIA: Changes to existing AGL or new AGL being integrated into the existing system must be done so in a manner, which allows continual operation of the existing system.
label | 0bf46e43-567a-44c3-8a23-76ffcee9aa44 |  | note | Prepare and submit for review, a detailed implementation plan showing proposed works methodology allowing continual operation of existing systems. This plan must include contingency to revert to a suitable system in the event of faults.
label | 97b66cd6-af8b-411c-891a-90e43e204178 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002 cl. 10.3.13
label | 906da60f-67dc-466a-a8c1-ba201cac3ff5 |  | note | INSPECTION/TEST METHOD: Verify
label | 94b70b87-57a2-4ef8-9df8-86c12be2f8f7 |  | note | RECORD OF CONFORMITY: Aconex
label | 6bc254fe-a01a-4062-b186-3d97f694e592 |  | note | AP
label | c0a6bb76-2163-4f02-b8a5-e1ed6ae49310 |  | note | RESPONSIBILITY: Project Engineer / ADB Safegate / Principal’s Representative
text | 41c91d26-fa2a-42f4-8ecc-38ae3b501712 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 Minimum Commissioning Datum Level
label | 5014c27b-dac8-4e03-92cb-486ef00dc3d7 |  | note | FREQUENCY: Prior to Start
label | c85e2ee4-4c36-4d24-ada4-bb02355f4c67 |  | note | ACCEPTANCE CRITERIA: Provide 7 days’ notice to the Principal’s Representative prior to commencement of the test.
label | c67d7c9f-139a-4a71-8069-d7ef5c02becd |  | note | Conduct and record insulation resistance test on existing circuits that are to be modified. These values shall be the acceptable level after the circuits have been modified.
label | cb6f1897-dd70-4a0b-bdc3-59c18e386343 |  | note | Where only part of a circuit is being modified, the same commissioning criteria apply, and tests to be documented separately for new elements prior to connection to the old.
label | 4214e5f5-3066-4fcb-853a-10815a4f7077 |  | note | Photometric performance of existing AGL fittings to be measured prior to commencing works.
label | 0f11fe24-8929-4486-9460-7da8b92b9bb3 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002 cl. 10.7.2.3
label | ee841fa4-6ea8-48ca-bc3f-ac83f654bead |  | note | INSPECTION/TEST METHOD: Verify
label | 3ed5c6ae-51b9-4a99-a176-91a28966c5a8 |  | note | RECORD OF CONFORMITY: Test Report
label | bf052e44-8dbb-40e3-95c6-edd63d5c6394 |  | note | TP
label | 1d9950fe-eba1-46c0-b945-6194ac4cf44f |  | note | RESPONSIBILITY: Project Engineer / ADB Safegate / Principal’s Representative
text | 18ccc238-d0f9-4bb1-9826-de12fcdbb113 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 Constant Current Regulators
label | 2b8f3ce2-9a72-427e-b210-ff75a17a412d |  | note | FREQUENCY: Each Lot
label | fbd1c65d-dbf6-4f6d-891a-938374f2a71b |  | note | ACCEPTANCE CRITERIA: Tapped voltage on recommissioned or new CCR’s installed shall not be greater than 1000V.
label | 0617a270-ee7b-447d-8d5d-5679501550f9 |  | note | Commissioning shall include:
label | 43d2a2b8-f32c-43ac-a961-d71626c75748 |  | note | - Checking all connections
label | c9bf2cf1-1b65-457f-93b2-212cbb532834 |  | note | - Input voltage check
label | a30293e1-ffc1-4a5b-9357-808569946dd6 |  | note | - Output tapping check
label | 5bc99335-ba41-4711-a3d6-625f53c7ce08 |  | note | - Open circuit trip
label | e4ed742e-c62f-4f46-89f3-6390f3edbac1 |  | note | - Over Current trip
label | 9f0d30b4-6a90-4223-932a-84f55e8cc333 |  | note | - Brilliancy Check
label | 1aa82418-4417-4410-9669-31d4d0bf6120 |  | note | - Lamp Outage alarms (if applicable)
label | 7929233d-ca1a-4ef8-b41f-5a203a47408b |  | note | - Earth Fault Alarms (If applicable)
label | a2c65193-4368-4710-a7b2-595595b48996 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002 cl.10.4.1
label | 9175ffd3-14d7-401f-9df2-b9dac803d784 |  | note | INSPECTION/TEST METHOD: Verify
label | ed2bf39c-a162-4773-aa49-b5b1bbce2d0c |  | note | RECORD OF CONFORMITY: Aconex
label | e19e0ccd-4c11-402d-a6c4-48277f3f250f |  | note | TP
label | 3e12d4ca-2975-4719-bf3b-37f69794af38 |  | note | RESPONSIBILITY: Project Engineer / ADB Safegate
text | 733d0824-340a-482d-b0ce-dbf43b7a0e1a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Series Transformers
label | 9d1057da-8e9c-436f-98b2-30517a49cc49 |  | note | FREQUENCY: Each Lot
label | 69e27f65-3085-45af-a61e-dfdf37546ca2 |  | note | ACCEPTANCE CRITERIA: Transformers shall be subject to a 24-hour soak test prior to any testing.
label | 39c05ffe-d66d-451d-95c4-1e3dea9756c2 |  | note | New series circuit transformers shall have an insulation resistance of at least 7.5GigaOhms with a 1kV insulation tester.
label | 75275d28-6606-4f92-85b2-6569915676f5 |  | note | Transformers not meeting this value shall not be used without approval from the Principal’s Representative.
label | ae0eb840-f6fc-494f-8695-1cf021996b51 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002 cl.10.7.1
label | ada5a6e2-b9a3-477f-b7c9-21718b9f2ec3 |  | note | INSPECTION/TEST METHOD: Verify
label | 503f6302-f6f9-4f09-9909-8dc13a7b34ad |  | note | RECORD OF CONFORMITY: Test Report
label | b1dcd649-844b-4190-ba61-0960b5638ddb |  | note | TP/AP
label | ceb2dffd-02dd-48f8-8fc0-ad4d9867baf2 |  | note | RESPONSIBILITY: Project Engineer/ ADB Safegate/ Principal’s Representative
text | 12d7229b-0d01-4b40-a117-b93cd203a0bf |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Circuit Insulation Tests
label | 64662ecf-5132-46f7-b1de-2a6405e48f9d |  | note | FREQUENCY: Each Lot
label | 480dea16-4277-4fd2-aa6f-989bcf29392d |  | note | ACCEPTANCE CRITERIA: The minimum insulation resistance level at commissioning shall be 3GigaOhms for each new circuit
label | 9c3a57c4-c71d-4ad2-bef5-2f52ee83a131 |  | note | Test to be taken with a 5kV Megger.
label | 1cb4d73a-c5ee-4187-8973-70ebd1735853 |  | note | Three tests to be taken and recorded consecutively at the following times:
label | 2d4e3e58-1807-4346-9dd3-069cd40a6703 |  | note | - Initial insulation resistance test prior to energising the circuit
label | f85627a4-3a47-4436-ad0d-efa6726d8f9f |  | note | - After the circuits have operated for min. 6 hours continuously.
label | 8838cd72-99f3-47c5-bac9-58d58c12f277 |  | note | - At least three hours later when the circuits are still warm.
label | 46e1fddf-5a52-444e-a766-f4ea08061ba5 |  | note | Each test result must be accepted by the Principal’s Representative before the next test is made.
label | d9d2550a-aaa0-4373-827e-22548614bb5d |  | note | Tests to be performed as per the works procedure.
label | 90c26313-16cf-491e-8d1e-682c0612ff27 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002 cl.10.7.2 & WP013
label | a3c0dde5-d130-4024-b68f-30bea266e4bb |  | note | INSPECTION/TEST METHOD: Verify
label | 0ea1164d-990f-42db-afbe-2dbaf4f94833 |  | note | RECORD OF CONFORMITY: Test Report
label | 84ddc0f0-fa69-46d3-b90a-47ae99204a95 |  | note | TP
label | 9c9c2ff3-9110-45a9-9d75-2115bf466332 |  | note | RESPONSIBILITY: Project Engineer / ADB Safegate / Principal’s Representative
text | b4444c94-c252-43eb-b291-ca3640fb7cd3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Photometric Performance
label | e39c1349-2def-422b-9551-d0cef00dabf2 |  | note | FREQUENCY: Each Lot
label | d0843281-5387-419a-bf7c-b4a93d3c54bc |  | note | ACCEPTANCE CRITERIA: Photometric output performance of all AGL light fittings to be in accordance with the requirements of MOS 139.
label | 5d6928c0-7f49-48fa-a556-0e36a99a207c |  | note | Results to be compared to values obtained prior to commencement of works and provided to Principal’s Representative. Any issues identified shall be resolved to the satisfaction of the Principal’s Representative as per the agreed process for approving reinstatement of fittings.
label | c45f3dd3-5f96-4406-8637-1b3e9cc36214 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002 cl.10.7.4
label | 9adea08e-1390-40dd-afd7-b92c8930c3be |  | note | INSPECTION/TEST METHOD: Verify
label | a6680839-1a00-4a5e-b2d6-f4ad26569488 |  | note | RECORD OF CONFORMITY: Test Report
label | 072dc84e-af1f-4801-9408-b0574cf35a43 |  | note | TP
label | cad6c64a-0dca-4e62-983b-81b5cf3c460b |  | note | RESPONSIBILITY: Project Engineer / ADB Safegate / Principal’s Representative
text | cdd01f6e-d4ad-42df-8082-d8bf685e35fa |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.1 Independent Inspection
label | 3c5a3ed2-fac1-461a-98b3-5cd1b4ec9a00 |  | note | FREQUENCY: Prior to Practical Completion
label | ffcb4cc7-cb86-4066-aa27-72d6105cc77b |  | note | ACCEPTANCE CRITERIA: The whole of the electrical services installation shall be inspected and certified by an appropriately qualified and registered independent electrical inspector.
label | 8595fad5-f66a-473c-8b08-c18b8cf13529 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002 Cl.9.3.3
label | a00b2aac-3844-474a-b169-f755bfa567b3 |  | note | INSPECTION/TEST METHOD: Verify
label | 145a29ee-72b0-4c60-b8c6-3e7b62f1fc17 |  | note | RECORD OF CONFORMITY: Aconex
label | 86ed5c35-17dc-4833-bf84-dcb0e693ab10 |  | note | IP
label | 8f07afc4-54e6-4f40-91f1-4a234c5d71b7 |  | note | RESPONSIBILITY: Project Engineer / ADB Safegate
text | 92209ead-87bd-4886-bc9e-a924aa5bb36a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.1 AGL Maintenance Plan
label | 4e17b140-3261-4369-840e-b954fd2e9fc1 |  | note | FREQUENCY: Prior to Practical Completion
label | c6f93497-dbb7-4d5d-8a81-b390fe3dcd5b |  | note | ACCEPTANCE CRITERIA: Submission of a maintenance Plan detailing all recommended routine maintenance to ensure proper operation and suitable life of the equipment.
label | aabb0ac4-3638-4d37-ac17-06fd4de94fcb |  | note | - This shall include submission of eight complete sets of the final operating and maintenance manuals in hard copy and four sets in soft copy.
label | 70dbe6bf-cdc0-46cf-8d60-a2db2859645f |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002 Cl.10.1.6 & 10.1.8
label | cd660047-bf9b-4330-b715-27691ae428e4 |  | note | INSPECTION/TEST METHOD: Verify
label | 3adbc543-0622-4637-aaff-1c993c077bce |  | note | RECORD OF CONFORMITY: Aconex
label | 48d95b6c-d5e2-4d8d-a138-795763e0de84 |  | note | IP
label | a52b6d73-e0a5-4d2f-8eb2-4ec82128f200 |  | note | RESPONSIBILITY: Project Engineer / ADB Safegate
text | 729f752b-8a86-45f7-8afd-373f87434d7c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 AGL Components List & Spare Parts
label | 75b061a0-c6a3-4af6-a774-858fbca7f207 |  | note | FREQUENCY: Prior to Practical Completion
label | 1eceb829-19b1-4622-a250-9247bb1e22be |  | note | ACCEPTANCE CRITERIA: The AGL Works contractor shall supply a complete component list for all facilities installed detailing identifying attributes
label | 07a776ea-b5a5-48bb-907c-db01a7191a93 |  | note | - Contractor to provide spare parts for all modular components of all installed facilities and equipment equalling 10% of the particular modular components installed.
label | 88ce62ac-4733-495f-b1d0-aaa7c5ec94e7 |  | note | REFERENCE DOCUMENTS: CO14038-AIR-DET-PM-SP-0002 cl. 10.1.7
label | 9656bad1-6b7c-44f7-841e-a56fb110f506 |  | note | INSPECTION/TEST METHOD: Verify
label | c4e5e169-1837-4d9c-8716-75778a4a8814 |  | note | RECORD OF CONFORMITY: Aconex
label | ad0a60a2-9190-4d57-b5a7-202221232aa0 |  | note | IP
label | cd27a407-1b40-4d6e-882c-2a688b1a89b5 |  | note | RESPONSIBILITY: Project Engineer / ADB Safegate
text | adb3a94c-2800-44c1-97f5-d99c976fd124 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Training Airfield Maintenance.
label | b552a060-0ecb-46d2-a2b6-5f9bb0b19112 |  | note | FREQUENCY: Prior to Practical Completion
label | 7c0e0dda-f49b-456c-8a26-1ad9df7613a9 |  | note | ACCEPTANCE CRITERIA: Provide training on all equipment installed under the project to the satisfaction of the Airfield Maintenance team.
label | 31ffcfd4-3f5f-427d-919c-1db535f8967e |  | note | Contractor to submit a training plan outlining items to be covered during training.
label | 20baf430-2c21-4259-84f6-49f7a2d0dc8c |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002 cl. 10.1.9
label | 532e1bfa-0a91-46df-a6d8-e3022c669d75 |  | note | INSPECTION/TEST METHOD: Verify
label | e4b00359-de6d-4231-b68c-18b282f11b38 |  | note | RECORD OF CONFORMITY: Aconex
label | e680946e-c2c9-453b-902f-34202ca8a4bb |  | note | IP
label | 4fd2a191-43ae-4c1b-a8b3-bd06c78cb48d |  | note | RESPONSIBILITY: Project Engineer / ADB Safegate
text | 6aa5e355-a739-4d36-9bca-5a5b3e69f47e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 Certificate of Electrical Safety
label | cbe5c92e-8984-4e83-a779-6461859ce77f |  | note | FREQUENCY: Prior to Practical Completion
label | 0a6ded98-8665-41d4-8d67-a66f2245cda5 |  | note | ACCEPTANCE CRITERIA: Submission of a certificate of electrical safety for all new electrical systems installed in the project
label | 5374de20-8a13-4607-a485-b66681444d85 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002 cl.9.3.3
label | 14decace-0f0f-472b-95c3-33d676fc3e21 |  | note | INSPECTION/TEST METHOD: Verify
label | c63ce241-d183-42e4-931a-bb5eed5e7433 |  | note | RECORD OF CONFORMITY: Aconex
label | 08a14179-d53a-4e0b-985d-54d5ebad5582 |  | note | IP
label | 73adab3c-eb70-4448-9c60-a09160f36e01 |  | note | RESPONSIBILITY: Project Engineer / ADB Safegate
text | 16342a51-1155-4dd1-9344-6d693883090c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.5 Handover Documentation
label | 44cfb3e6-6b82-47f4-ad0a-bc8864f80da4 |  | note | FREQUENCY: Prior to Practical Completion
label | c52d5b49-4803-4967-95c1-98ae3a775f5e |  | note | ACCEPTANCE CRITERIA: Submission of all quality assurance documentation including as builts and schedules to the project manager.
label | 94f130a8-c26e-4dda-a8a8-051735c2e500 |  | note | Information provided shall include:
label | 38320619-4fc2-429a-843e-04bf9cf5905d |  | note | - Circuit details including cable route, loading, Quantity per conduit, origin & destination.
label | 047952f0-128f-4e8f-9491-5323198891ae |  | note | - Number of series transformers and location of joints.
label | 5d030565-e7ee-4030-b0a0-74cb4bff4a98 |  | note | - Equipment and materials used.
label | 9a72770a-afe6-4407-bd52-2717cb4e6f6e |  | note | - Testing and commissioning values for all modified or new equipment.
label | a5cba558-63a1-4b03-ad0d-612baf043e91 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002 cl. 10.7.6
label | 8d63f972-df3e-4053-a106-9c38d035a733 |  | note | INSPECTION/TEST METHOD: Verify
label | cd5f938e-9e58-4e01-a003-1fcae701c08b |  | note | RECORD OF CONFORMITY: Aconex
label | 717f3e35-0e0f-4adf-b7b0-31ffb2848385 |  | note | HP*
label | e41cfae6-2ee8-4576-a877-b7a48c37dcbb |  | note | RESPONSIBILITY: Project Engineer
text | b3dd7b0a-2175-468b-901f-d3226d410cdd |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 3d05b833-08dc-4fbb-b237-87963993a1c3 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 7093d627-4674-4324-a6bf-bdc0cead2ba6 |  | textbox | Print Name:
text | b402760f-c8a8-4c0a-9c24-bfc28390aecf |  | textbox | Position:
text | faaca962-767b-46c8-9107-2bee05332a69 |  | textbox | Date:
checklist-sectioned |  |  | checklist | ITP 011 - Hot Mix Asphalt Placement | itp |  |  |  | Yes | ITP 011 - Hot Mix Asphalt Placement | cb4ba539-2f1b-4ccb-86b7-585a23c085ed
checkpoint-group |  |  | section | ITP 011 - Hot Mix Asphalt Placement
checkpoint-status |  |  | checkpoint | 1.1 The current revision drawings are being used including subcontractors copy.
label | 93e60142-34f7-4e07-a120-99eb410a730d |  | note | FREQUENCY: Prior to works
label | 128b3ae3-87c3-429c-a3c6-f549b7cf5506 |  | note | ACCEPTANCE CRITERIA: Current revision drawing is being used including the subcontractors copy. Current Revision to be obtained via Aconex
label | aa1472e8-6e8b-4964-a1c1-7480d062f4d0 |  | note | REFERENCE DOCUMENTS: Aconex
label | a711ea4f-029b-4241-849a-429e3162f8c7 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | be461805-9039-4c30-952a-7704fabea74d |  | note | RECORD OF CONFORMITY: This signed ITP
label | 9d983537-d39a-472a-94f9-95eab5b586bb |  | note | HP*
label | 5088303c-d98b-4f28-8aae-091149ac9a0d |  | note | RESPONSIBILITY: Fulton Hogan
text | 50a4f7d6-aa07-4a25-bf08-4949f70b1802 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 ITP and Construction procedure documentation
label | cff52c34-b7cc-4225-a861-4a2e3d2a9001 |  | note | FREQUENCY: 28 Days Prior to works
label | 744ac9bf-733d-4827-ad43-b0d984e13fae |  | note | ACCEPTANCE CRITERIA: ITP and Construction procedure for Asphalt placement to be provided to the Principal’s Representative for review.
label | 51116122-4a69-4284-ac48-d8f3c6aedb6d |  | note | REFERENCE DOCUMENTS: Spec cl. 7.4
label | c18abeb4-f23a-49e2-aa23-448b87f46459 |  | note | INSPECTION/TEST METHOD: Verify
label | 97158f80-2038-4375-bee3-916050a72fb4 |  | note | RECORD OF CONFORMITY: Approved Work procedure report
label | f71af730-5581-47c0-af74-5716b85da0d0 |  | note | HP
label | 6c8eff08-4c7d-4bc4-b1ae-9df033e76010 |  | note | RESPONSIBILITY: Fulton Hogan Jacobs
text | cebf1a13-b22a-464b-a40d-54a056a66451 |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 1.3 Submission of mix design
label | 5605eac9-5d65-471a-bce9-b01d501223fd |  | note | FREQUENCY: 48 hours Prior to Mix design
label | b2ec2910-c599-4ce4-92f1-030c015d26e3 |  | note | ACCEPTANCE CRITERIA: The Principal is to be notified 48 hours prior to commencement of mix design
label | eb734439-a714-42e4-949b-f893c218bddf |  | note | REFERENCE DOCUMENTS: Spec cl. 7.5.6.1
label | 909c6154-5322-4c34-aa30-19a7c50b1152 |  | note | INSPECTION/TEST METHOD: Verify
label | 30e1e2a3-4dba-4081-9fd5-a2c986ee3d9d |  | note | RECORD OF CONFORMITY: Approved Mix design report
label | db84c410-6d1d-484b-b071-951f3d39ca57 |  | note | WP
label | 7b1289ed-1173-4112-ab18-efcfc4a785a7 |  | note | RESPONSIBILITY: Fulton Hogan Jacobs
text | 1aea396a-0a89-4549-99bb-beec61d80344 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.4 Construction trial
label | eaa41fb5-6534-486b-9c6d-23392152c174 |  | note | FREQUENCY: Prior to works
label | 28cbfd91-9e1b-444a-93f8-9a36f41c4218 |  | note | ACCEPTANCE CRITERIA: 14 days prior to asphalt paving is due to commence, all proposed mixing and paving plant and personnel details are to be submitted to the Principal
label | d549529c-9a01-4b94-ba5e-ed9647d83b0d |  | note | REFERENCE DOCUMENTS: Spec cl 7.7.1
label | e71872b2-a9b3-4fd2-a659-7986947f5960 |  | note | INSPECTION/TEST METHOD: Verify
label | 24a5cb52-d077-4a4e-acf5-81ea8a160830 |  | note | RECORD OF CONFORMITY: Approved Construction trial report
label | 8bf9569e-ca13-425d-8a28-b3f10c560716 |  | note | WP
label | 337af921-7c16-4fcf-846f-6763e6eabd45 |  | note | RESPONSIBILITY: Fulton Hogan Jacobs
text | 007597eb-22ce-4e4d-8106-fa2fbec687d5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.5 Asphalt Production Trial
label | a33215eb-036a-4eba-b99b-a11fa7858d1d |  | note | FREQUENCY: Prior to works
label | 29a90982-bda7-44a4-ba35-e9ce924cc959 |  | note | ACCEPTANCE CRITERIA: Asphalt production trial is not to commence until acceptable mixing plant calibration charts are provided to the Principal’s representative.
label | 1ad88f20-b45a-4096-9ff9-fd118a929803 |  | note | REFERENCE DOCUMENTS: Spec cl 7.7.2
label | 2bae8c82-74fd-4609-8e2a-dad334d0bc4b |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 5b8ee65a-1376-4e63-86b8-fd045b7b5cda |  | note | RECORD OF CONFORMITY: Site Inspection
label | 0ed49238-edd4-4678-a68d-707f34983bf0 |  | note | HP
label | e86818db-5129-49be-ac2a-d232175dcf2f |  | note | RESPONSIBILITY: Fulton Hogan
text | b0a7a8e7-dc00-4079-8577-b644d1366481 |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 1.6 Production and Construction Trial Report
label | 93be0b9f-7450-41eb-a189-d588d34e537d |  | note | FREQUENCY: Prior to works
label | a00e9bb7-6d50-4c3f-a4bf-16f38a041144 |  | note | ACCEPTANCE CRITERIA: Within seven days of the Production and Construction Trials a Production and Construction Trial Report is to be submitted to the Principal’s representative.
label | 6dbd0982-1982-45a7-a4bf-7eaccdac4c7e |  | note | REFERENCE DOCUMENTS: Spec cl 7.7.4
label | e1e80f86-a116-47a1-b0de-325e4a3ab15c |  | note | INSPECTION/TEST METHOD: Verify
label | e8c9b264-3934-4e8d-b45c-de5816edfc63 |  | note | RECORD OF CONFORMITY: This Signed ITP
label | df04266e-c0e2-41d3-a230-d60000f65dd0 |  | note | HP
label | 397fce81-5a9e-411c-8728-3c411731dde8 |  | note | RESPONSIBILITY: Fulton Hogan Jacobs
text | 181a8e8b-3010-448f-a339-65f147b6d1b9 |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 1.7 Approved fine and coarse aggregates
label | 5acb3cdd-3d3d-47f7-bee3-ee6648788eae |  | note | FREQUENCY: Prior to Placing
label | 9d8921cf-1a42-4ae0-a412-1692376745a8 |  | note | ACCEPTANCE CRITERIA: Coarse and fine aggregates to comply with design specifications
label | afb897e4-3716-4c42-ac5b-16591e3bef54 |  | note | REFERENCE DOCUMENTS: PBAA Spec 7.1 Jacobs 7.10.2.1, 7.10.2.2
label | d420875b-4bd7-457d-a6f9-d9bfaeeb6fa0 |  | note | INSPECTION/TEST METHOD: Verify
label | 421098cf-e6ff-4238-8c5a-b34615b292a6 |  | note | RECORD OF CONFORMITY: Supplier's Declaration of Conformance.
label | 84b1abdf-d4d9-47fb-8be4-dfd415789da5 |  | note | HP*
label | 1a7b1f98-cc0d-4d64-ad84-9274c415b816 |  | note | RESPONSIBILITY: Fulton Hogan
text | 5c4e902b-a403-46f3-937b-1bec7347c77e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.8 Binder Sampling
label | 41597c03-4073-415c-8706-7b1b56b0bc26 |  | note | FREQUENCY: Prior to Placing
label | c26e46d8-3301-42d3-9d45-3e233058334f |  | note | ACCEPTANCE CRITERIA: Samples of bitumen are to be obtained in accordance with AS 2008; A minimum of three samples each not less than 1.0L;
label | 3df415bf-603e-4b93-ab19-ec17148b3c09 |  | note | REFERENCE DOCUMENTS: Jacobs 7.10.2.4
label | a8533e75-6ddb-445f-b24c-3970aaf54bd7 |  | note | INSPECTION/TEST METHOD: Verify
label | 07ab180b-22de-4f27-9e7c-612bc2658ec7 |  | note | RECORD OF CONFORMITY: This Signed ITP
label | c3304e41-7bea-491b-ad8d-55e77e81f8b8 |  | note | HP
label | 286a7aba-47f9-4c14-a1cd-cf3db6d655ee |  | note | RESPONSIBILITY: Fulton Hogan Jacobs
text | 2843622c-0362-430a-9a7d-7701bcf5072c |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 1.9 Binder Testing
label | 15dadc70-bef3-4995-8262-98dc599c58f0 |  | note | FREQUENCY: Prior to works
label | c00359c5-563f-4d0b-8d78-a371be611e59 |  | note | ACCEPTANCE CRITERIA: Bitumen is to be tested at the point of delivery. The sample is to be tested for the following: - Viscosity at 165°C according to AG:PT/T1 11. - Torsional recovery at 25°C, 30 s according to AG:PT/T1 22 - Softening Point according to AG:PT/T1 31
label | 5fe9c5c5-f40f-4601-853a-1a80983a3d79 |  | note | REFERENCE DOCUMENTS: Jacobs 7.10.2.4
label | 5cd19bd1-0a9b-4667-993d-ef2c12477f08 |  | note | INSPECTION/TEST METHOD: In Situ testing
label | 04bfa32e-68ca-4421-b6b1-59ef08f048e6 |  | note | RECORD OF CONFORMITY: Test Report
label | 28411074-4498-4e5e-9a0f-0b57fff24d77 |  | note | TP
label | 1f1c77b4-1e3f-4a44-8945-b4c8ecde2346 |  | note | RESPONSIBILITY: Fulton Hogan
text | 2b899950-65d7-495c-94dc-f503a8fc7f93 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 Equipment
label | bd88372c-c830-4dd2-a4ad-9afc1391b6dc |  | note | FREQUENCY: Prior to Commencing
label | a58d95d3-29c4-4424-af02-89955376bc33 |  | note | ACCEPTANCE CRITERIA: Pre-Start checks completed by Operators. All plant equipment acceptable for use. Report any faults. Back up equipment in place where required.
label | 83083ca7-2ff2-4240-94a9-7031f5f8ce12 |  | note | REFERENCE DOCUMENTS: PBAA Spec 7.1Jacobs 7.6.1
label | dc1d739c-99f1-4f67-9d68-f4490eb1011e |  | note | INSPECTION/TEST METHOD: Site Inspection
label | 65f431b0-3059-4431-bfa9-08e84bd516ab |  | note | RECORD OF CONFORMITY: This ITP
label | 1d8a26ff-28f6-4940-850c-c6902c902f86 |  | note | WP
label | 0f9f5169-7638-4b73-867c-575ef9069f25 |  | note | RESPONSIBILITY: Fulton Hogan Jacobs
text | babee310-cc97-42ae-a0e3-22440dfbab70 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Site Inspection and Base Condition
label | 11e08ff5-9482-48c0-80ae-470886fc425d |  | note | FREQUENCY: Prior to Commencing
label | 0745cbed-b7e6-4bfe-b025-6b8d4538b832 |  | note | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from puddles and defects (holes, cracks, unstable material and edge irregularities)
label | 8d6f64a7-c1de-400b-a546-1e0dd105dace |  | note | REFERENCE DOCUMENTS: Jacobs 7.9.2
label | cfa0689b-8c2a-4d15-99de-006bab534f88 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | e89d0147-a266-4ca2-82e1-7e3f71b1bf59 |  | note | RECORD OF CONFORMITY: This signed ITP
label | d7b149a2-e9c1-4548-9432-ba1715872512 |  | note | WP
label | ef5ad3b5-10d3-444e-b18a-b457db768381 |  | note | RESPONSIBILITY: Fulton Hogan Jacobs
text | bdbc1fee-b57d-4b7f-b496-f798dd8f23a3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Ambient Conditions for Placing
label | 2f72331d-c510-4566-9c49-7d93c9a764af |  | note | FREQUENCY: Prior to Commencing
label | dd71dbc4-8b5e-443a-9c1b-140a537f872b |  | note | ACCEPTANCE CRITERIA: Asphalt must not be produced and constructed during weather, or expected weather, that may be detrimental to the quality of the finished asphalt surface. Where surface temperatures are < 15°C, an approved cold weather construction procedure must be in place.
label | aed8cc7a-8c07-42c7-8c62-883e5f28bee8 |  | note | REFERENCE DOCUMENTS: PBAA Spec 10.1 Jacobs 7.9.1
label | ddeb17d5-1aca-40e0-8db1-3c115bdb018b |  | note | INSPECTION/TEST METHOD: Calibrated thermomet er Weather Forecast
label | 45d303ab-b12d-44fb-a0d9-f9a7cdd2c74f |  | note | RECORD OF CONFORMITY: This signed ITP
label | 773247f6-90a7-46c9-833d-f3d25351b7aa |  | note | IP
label | c89deeb2-f37c-4c6a-837e-19f18cdcb8a0 |  | note | RESPONSIBILITY: Fulton Hogan Jacobs
text | a0b881b1-3599-4573-a948-a2b2d9226c1d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Surface Preparation
label | 02f1f2b8-2e5e-4aa2-ba36-1ce3658296b4 |  | note | FREQUENCY: Prior to Commencin g
label | df7e6e1b-4da5-4287-b493-adc2e1a3aba8 |  | note | ACCEPTANCE CRITERIA: The area to be paved is free of all loose and deleterious material. Any required surface texturing is completed. Joint inspection to be completed by Principal & Contractor.
label | fdc6a87c-8232-4d2d-91a6-810518dd1bdc |  | note | REFERENCE DOCUMENTS: PBAA Spec 10.2 Jacobs 7.9.2
label | cb2e8d3b-de9f-4ca6-8267-096742d322ac |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 00ab6e96-140e-461e-9aa4-344a8df915d3 |  | note | RECORD OF CONFORMITY: This signed ITP
label | 36248a06-7b2c-4510-a26d-8696ec9e97ca |  | note | HP
label | e83b8168-839e-4cc9-b94c-e300d72d7cda |  | note | RESPONSIBILITY: Fulton Hogan Jacobs
text | d2b7b64a-5fdf-4d35-a6ba-6c87e418d6c2 |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 2.5 Tack Coat
label | 6018eaba-b66b-46e1-9208-eb737ffcb1e9 |  | note | FREQUENCY: Prior to Commencing
label | 27942a31-06d5-45e1-a5a9-6ba99485c4f3 |  | note | ACCEPTANCE CRITERIA: Tack coat to be sprayed over the prepared surface to be paved at a rate of 0.20-0.30 L/m2 of residual binder. Longitudinal joins must have a single uniform hand application applied with a double uniform application applied to transverse joins. Tack coat must be substantially broken over > 80% of the surface of the paving run.
label | c7c6d9a3-7fd7-4932-907b-f1f06db674c4 |  | note | REFERENCE DOCUMENTS: PBAA Spec 10.3 Jacobs 7.3.4
label | c7be869a-cc7d-403d-96cf-8759d2488cfd |  | note | INSPECTION/TEST METHOD: Spray area and inspect
label | 6e6e28ab-4873-41db-83e2-2928a1b23d09 |  | note | RECORD OF CONFORMITY: Test Certificate
label | 13412b88-fc3a-4319-8fc8-c471f59b2371 |  | note | WP
label | 23fc8936-da88-4ba5-be1b-65dc0b882caa |  | note | RESPONSIBILITY: Fulton Hogan Jacobs
text | 7455a5d1-c5f1-4f48-ac97-8688c56f31b3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.6 Planning of Joints
label | acda0c03-8b29-42c9-91f3-fa7171ee8190 |  | note | FREQUENCY: Prior to commencing paving
label | 7b05b04e-c358-4a7c-b09a-56fa3e4c4401 |  | note | ACCEPTANCE CRITERIA: Runs to be marked to ensure placement of joints satisfy the following unless otherwise approved by the Client: Lanes of asphalt must be placed continuously within each work period and follow the general sequence detailed in the approved construction procedure. Any free longitudinal edge must be removed by cold planer by a minimum of 50mm or greater to remove any out of shape material.
label | 1f1552ab-875a-4b6a-a7bc-59f7ea94036e |  | note | REFERENCE DOCUMENTS: PBAA Spec 10.4 Jacobs 7.9.3, 7.9.7, 7.9.8
label | ade0e5a3-5d53-4df7-b893-d73c38f7b617 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 79ec725e-c63b-4a45-a1f0-9bcaa58603f1 |  | note | RECORD OF CONFORMITY: Site inspection & this signed ITP
label | a23d90a4-6864-4d80-a92a-e25f0eba01dc |  | note | WP
label | 1060342f-d8ff-4ed6-9f6e-713ce3dacd22 |  | note | RESPONSIBILITY: Fulton Hogan Jacobs
text | d128d3d0-d47d-4d25-bff2-b213bcecb311 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.7 Commencement of Placing
label | f93a4061-8021-4ace-9989-4e01f8f8c909 |  | note | FREQUENCY: Prior to commencing paving
label | e040ba08-76db-4605-b7dd-92837eb64401 |  | note | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client.
label | 411c43d1-4155-4ba0-8bcc-978e56bf0ea2 |  | note | REFERENCE DOCUMENTS: Jacobs 7.9.2
label | fea218e3-8af3-403c-a64a-d30e621dfea4 |  | note | INSPECTION/TEST METHOD: Verify
label | fa5cce5a-8db0-43df-9aab-4f31dad73454 |  | note | RECORD OF CONFORMITY: This signed ITP
label | f8f1f8a8-cef5-4b08-b310-a8440e4fc261 |  | note | HP
label | 69fa8d59-6cb7-4b22-ab1a-eba8539511ca |  | note | RESPONSIBILITY: Fulton Hogan Jacobs
text | 009810e0-da8a-4340-90f6-957a7e2c690e |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 2.8 Delivery of Mix
label | f260f6dc-2272-4465-8399-4b298a6c9515 |  | note | FREQUENCY: Each load
label | b3f375a6-8524-44e3-a32f-f145639faae3 |  | note | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles. The temperature of the delivered asphalt prior to initial rolling must be greater than 125°C.
label | f401c29e-200d-40be-a6d7-274e31562300 |  | note | REFERENCE DOCUMENTS: PBAA Spec 9.1 Jacobs 7.11.1, 7.11.4
label | 60431332-2e9c-4ac9-a089-0c2e52606826 |  | note | INSPECTION/TEST METHOD: Verify
label | ee0def7c-632d-40a6-a14e-66ab94e0d879 |  | note | RECORD OF CONFORMITY: This ITP
label | 1d8371eb-32b0-4c72-a7b8-9337dbff348c |  | note | WP
label | 077de972-d5da-4c1a-9616-fefa3a1bd97b |  | note | RESPONSIBILITY: Fulton Hogan Jacobs
text | 58b50e3f-770d-4749-9bf2-ada4fa2bcd24 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.9 Layer Thickness and Level Control
label | 75037d91-a29e-489c-a09f-748b8b42a065 |  | note | FREQUENCY: Regularly during paving
label | 11c70c40-1721-4ddd-a3e0-5777394e9d7c |  | note | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications. Surface Course = 50-65mm. Intermediate Course & Corrector Layers = 45- 70mm
label | 38ca7fca-3a33-4e0f-af72-0108bb9956fd |  | note | REFERENCE DOCUMENTS: Jacobs 7.9.4
label | 8f05364b-fd79-4a10-968a-c6a345d1484b |  | note | INSPECTION/TEST METHOD: Dips / Survey Reports
label | 10460213-8f0d-4c8e-955d-2e80d31f342b |  | note | RECORD OF CONFORMITY: This ITP & Survey Report
label | 75402643-9a1a-463d-b656-3b9108222500 |  | note | WP
label | 596eeb19-ee14-4bda-82d7-550772eb6a89 |  | note | RESPONSIBILITY: Fulton Hogan Jacobs
text | 0a059244-5040-4dc9-9db5-600cf1cfe965 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.10 Cold Joints
label | 4dbf8e56-911b-4a1d-9dd6-6ce790cdcfa9 |  | note | FREQUENCY: Each Lot
label | 0836ec5c-3fea-4ddc-a661-05191deebef7 |  | note | ACCEPTANCE CRITERIA: Longitudinal & Transverse joins are to be treated as cold joins if the asphalt at the joins falls below 110°C prior to any adjoining asphalt being placed .
label | ef38ed01-58a9-4aae-949d-847054ba3282 |  | note | REFERENCE DOCUMENTS: Jacobs 7.9.7, 7.9.8
label | d8fbd345-2ae2-4bd5-9386-1c43d020bf6e |  | note | INSPECTION/TEST METHOD: Thermome ter Reading
label | 84fb3a30-7308-46d1-85c4-2479eabcd3fd |  | note | RECORD OF CONFORMITY: This signed ITP
label | 6b07a9fa-a775-4b62-ad3a-d11a4caf17c3 |  | note | WP
label | 023937b3-36bf-4627-8406-89eeb2468a05 |  | note | RESPONSIBILITY: Fulton Hogan Jacobs
text | 45d25e63-7e51-4d3d-a7b4-afd66af891a9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.11 Surface Finish of Wearing Course
label | 42add965-7efb-494e-b11a-fc3242343623 |  | note | FREQUENCY: During paving and after final roll
label | 5ab97ada-1a9a-4bca-ade2-add67bafc530 |  | note | ACCEPTANCE CRITERIA: The finished surface of the asphalt surface courses shall present a tightly bonded closed textured surface of uniform appearance, free of dragged areas, cracks, segregation and open textured patches. Joints shall be tightly closed.
label | e9d4fa0d-4056-4b34-8441-eb54ffd0f57f |  | note | REFERENCE DOCUMENTS: Jacobs 7.11.5
label | 17c6e0bd-02f3-4878-bb0f-63bfc249217d |  | note | INSPECTION/TEST METHOD: Verify
label | 9f2cbe85-36b7-42d2-a0cb-100be9d74433 |  | note | RECORD OF CONFORMITY: This signed ITP
label | 3f16e3f4-3a0e-4f6c-ae7a-da562037c5bc |  | note | WP
label | bddf9d14-1d21-4dc0-aa59-0b0863ee5de0 |  | note | RESPONSIBILITY: Fulton Hogan
text | 443ab5da-12b3-4f10-a51f-cd461d406bbe |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.12 Shape / Surface Smoothness
label | b5b2a3a3-5d94-477c-a9c2-729af199e987 |  | note | FREQUENCY: After final roll at agreed intervals
label | 4bdc11e1-8253-4899-ae83-b9f16570b778 |  | note | ACCEPTANCE CRITERIA: No point on the finished surface shall lie more than: 6mm on shoulders & blast protection and 3mm on the Taxiway below a 3.5m straight edge placed on the surface in any direction accept in directions where a grade change occurs.
label | f8250277-3a80-4e70-829d-f9db3b6fdeb4 |  | note | REFERENCE DOCUMENTS: Jacobs 7.11.6
label | 3d8a1629-1f8a-4b0a-89d0-9946bbe81671 |  | note | INSPECTION/TEST METHOD: Verify
label | eb825140-8bc6-4e9b-bb77-f521d1f1e343 |  | note | RECORD OF CONFORMITY: This signed ITP
label | bcf89508-aa90-4cd1-8def-44017232de9a |  | note | WP
label | 6e09acff-4e73-4021-be19-3dc4a94847fd |  | note | RESPONSIBILITY: Fulton Hogan Jacobs
text | 6fc22fd4-b9b8-44f7-a9e8-90c851c4507d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.13 Edges and Tie-ins
label | 764ec271-8359-4e36-b9d6-11429bddc870 |  | note | FREQUENCY: During paving and at completion of work
label | 2626d7fd-40e4-4442-a7c5-e14addebedec |  | note | ACCEPTANCE CRITERIA: Free edges without adjacent lanes of asphalt must be tied in flush with the adjacent asphalt or verge Any temporary tie-ins must not exceed:
label | 71fd928e-bd3c-4502-a946-5b232856ede9 |  | note | - 0.5% where the difference between existing surface level & design surface level is > 50mm
label | 29448a8f-32ee-4a8c-a4a1-287d16623a01 |  | note | - 1.0% % where the difference between existing surface level & design surface level is 50mm or less
label | 020cefdc-9df9-49e0-bdb0-b529a002ab07 |  | note | REFERENCE DOCUMENTS: PBAA Spec 10.4.3 Jacobs 7.9.6
label | cb2cda1e-a036-4ce4-af68-148c84142d0c |  | note | INSPECTION/TEST METHOD: Verify
label | 02a11369-4e9c-41db-ad4b-6b5e83b59bb5 |  | note | RECORD OF CONFORMITY: Visual Inspection & Measurement
label | d025a8c6-a1aa-4cf4-9f19-44c551962bce |  | note | SCP
label | ce7f6ffb-e3f3-41c0-8f61-6b35213278e6 |  | note | RESPONSIBILITY: Fulton Hogan
text | 36916e4d-3b89-48cf-8894-9a1303999c61 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.1 Compaction Testing
label | 83346a9c-d0f8-4b76-a783-8e10de0f5fa7 |  | note | FREQUENCY: Completion of placement and compaction of Asphalt
label | 8986127f-f7d6-4360-9f23-1aead73d18ad |  | note | ACCEPTANCE CRITERIA: All asphalt that does not meet all the specified requirements will be rejected. Materials to be removed full depth of the layer and reinstated.
label | a4a03a8e-98dd-44ff-adbf-2e8cf19fa255 |  | note | REFERENCE DOCUMENTS: AS 2891.7.1 Jacobs 7.11.8.1
label | 9a441b55-9667-434c-ab03-fbe80085826d |  | note | INSPECTION/TEST METHOD: Compactio n Testing
label | f35193e7-6383-40ba-b3c7-7031c22a7e5f |  | note | RECORD OF CONFORMITY: Test Report
label | 20bd958f-21d2-4043-ab4a-c2c3f0ac8058 |  | note | TP
label | a8b20b28-07f7-46bc-b763-194b7b97b1b3 |  | note | RESPONSIBILITY: Fulton Hogan
text | c134b0b5-76d7-4e79-86df-19cae0a8ea82 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Core (where requested)
label | 89b1b65f-c6ef-4685-910b-47a7fa52c571 |  | note | FREQUENCY: Completion of placement and compaction of Asphalt
label | f961ee9e-44c6-4e3f-b4a5-d78a57bfa91a |  | note | ACCEPTANCE CRITERIA: Bulk density is to be determined form the core in accordance with AS 2891.9.1. In Sit
label | 30e99b9d-97e6-48f8-815d-f045d15ef53f |  | note | REFERENCE DOCUMENTS: AS 2891.7.1 Jacobs 7.11.8.4
label | c09f46cf-d76f-44f5-977d-5c845cac472e |  | note | INSPECTION/TEST METHOD: Bulk Density Testing
label | c4e53316-3cf0-4a7f-87b5-31797954413b |  | note | RECORD OF CONFORMITY: Test Report
label | 7c418fdd-c591-4867-828a-e149448fd1f8 |  | note | TP
label | fcae396d-0197-4fca-b004-76eeb97c09b3 |  | note | RESPONSIBILITY: Fulton Hogan
text | 66234ca1-0245-4166-ba6c-069917e4133a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Core (where requested)
label | 8b15d99d-de1c-497d-863d-5e5cd2eccdb0 |  | note | ACCEPTANCE CRITERIA: In Situ air voids testing is to take place and must meet the following criteria:
label | 71dcaaa8-0aba-4430-a921-4fd481901162 |  | note | Lot mat location: min 3% max 7%
label | 95276d9a-1e29-4958-8383-aa07d2880bce |  | note | Lot joint location: < 7%
label | de1b54d6-d9ce-49dc-bb37-8921a4209ccf |  | note | REFERENCE DOCUMENTS: AS 2891.7.1 Jacobs 7.11.8.4
label | e6592df3-f405-4a92-820c-1e433717f7f6 |  | note | INSPECTION/TEST METHOD: In situ testing
label | d83298cb-0497-4c07-9eac-cc456b50f6ea |  | note | RECORD OF CONFORMITY: Test Report
label | 46d40023-ed84-4c9b-a139-c3a9e453967c |  | note | TP
text | 4c6a7c0c-39a0-4f9b-85c3-5812f278d43e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.1 Surface Levels
label | a91f4a16-ee4f-4f89-8dd6-b3f4f971c41d |  | note | FREQUENCY: Per Lot & Asphalt Layer
label | efe9fbb6-cc71-40a3-86cf-4592ee9d8fde |  | note | ACCEPTANCE CRITERIA: Individual departures from design not to exceed ±5mm. No standing water shall be evident on the finished surface after rain.
label | 8ee676a7-7a61-4cc8-acd4-d622c530b684 |  | note | REFERENCE DOCUMENTS: Jacobs 7.11.7
label | 243f8180-8000-46b2-96cf-2edaae2599da |  | note | INSPECTION/TEST METHOD: Verify
label | dfe94893-d34e-4dcb-9fa6-9b3b508d57dc |  | note | RECORD OF CONFORMITY: As-built survey records
label | 96004237-34b9-4f7b-83ed-fc38d0fe1bd4 |  | note | SCP
label | ff409a3f-8022-497d-a298-37e4ab375ed9 |  | note | RESPONSIBILITY: Fulton Hogan
text | dce53c1f-def0-4df8-a66f-2de54cbc7aa6 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | e778e5d9-6b48-42c7-a9f5-534f98ecaf1f |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | a81a400d-d484-4cc8-90de-c23230f1e52c |  | textbox | Print Name:
text | 6dd702d3-1d84-4cdd-8ba7-bb835feac0ab |  | textbox | Position:
text | d522596d-7a49-4dcb-885d-064752b8a29c |  | textbox | Date:
checklist-sectioned |  |  | checklist | Order Acceptance Certificate - Lot: | itp |  |  |  | Yes | Order Acceptance Certificate | ce5e2379-264a-40cb-b42d-546e04a4b1cb
checkpoint-group |  |  | section | Order Acceptance Certificate
checkpoint-no-status |  |  | checkpoint | Order Acceptance Certificate - Details:
text | aff52a93-5f83-4e1f-af90-a94c164c77a7 |  | textbox | Subcontractor (full name of Subcontractor, ABN, Subcontractor's ACN and ABN)
text | 25709e53-f8b0-42a7-9600-3f7297f21245 |  | textbox | Order No.:
text | b4403f3d-1d60-4120-8572-2873d4d463ba |  | textbox | Delivery Site:
text | 4b602621-52e9-4c8e-b0da-7bfda9471a94 |  | textbox | Date on which materials delivered:
text | 695583af-6f34-480a-9bf5-55a371c3a38a |  | textbox | Delivery vehicle (registration number):
text | 8a40a7e2-014c-4fac-9970-fef065e0f3dd |  | textbox | Subcontractor's delivery personnel (full name)
checkpoint-status |  |  | checkpoint | The Subcontractor has checked all Materials included in this delivery and is satisfied that all of the Materials comply with the Subcontract.
checkpoint-status |  |  | checkpoint | 1)
text | d6b09040-fd60-4400-b8f0-5c00c55287d2 |  | textbox | Item ID:
text | ee4f221b-530a-4d14-af75-a709c5235f6f |  | textbox | Item description:
text | 45493357-7e6d-4949-b71d-78ca1aa95c76 |  | textbox | Units ordered:
text | 319fcfdd-b63e-4311-9b4c-8d3d6907dacc |  | textbox | Units delivered:
text | 6bc4c191-e712-49b9-9fab-8bd40c3b65ce |  | textbox | Special Storage/ Handling Requirements?
label | 8f2d271d-d97f-44e9-8e5a-26dfc5667455 |  | note | The following is for completion by Fulton Hogan
text | 91da4c09-4b90-4c58-b19d-1e05d92cdda5 |  | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
text | 2f8aa5bc-3aea-4d27-a4c9-edae5be0fcf5 |  | textbox | QA Docs Delivered?
text | 50835eaa-cb08-418f-93d4-e9854e1c45b8 |  | textbox | Defective?
text | f300cee9-bd92-4013-b580-a91c315989a0 |  | textbox | Number Accepted / Number Rejected?
checkpoint-status |  |  | checkpoint | 2)
text | a625fd39-09b4-4178-89d5-fdbb1c731706 |  | textbox | Item ID:
text | 0c775e20-608c-4557-96c5-f7840384f543 |  | textbox | Item description:
text | 10f75d1d-37fa-4ac8-b50f-2876d3c0de67 |  | textbox | Units ordered:
text | 0d697c64-0eb9-4958-a2d0-07e62ec5c8ec |  | textbox | Units delivered:
text | 71d37a9a-e294-4b95-b9ca-cf63ed551560 |  | textbox | Special Storage/ Handling Requirements?
label | fb380c7a-252a-4d66-8b2b-f7fc306aa5cb |  | note | The following is for completion by Fulton Hogan
text | ebce679a-16fe-48fa-9f62-049231f2abff |  | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
text | 5e323372-0246-425e-8988-34489ec46c03 |  | textbox | QA Docs Delivered?
text | 1f9ece92-557f-4183-864f-cd897d0626ff |  | textbox | Defective?
text | 25101864-62cd-4c3e-8044-0ba75e51ce62 |  | textbox | Number Accepted / Number Rejected?
checkpoint-status |  |  | checkpoint | 3)
text | 766d7677-eb9f-4088-bd60-c467911d2f5e |  | textbox | Item ID:
text | 742e5725-8365-4fde-bfb9-25feafc36874 |  | textbox | Item description:
text | bcb5cdf1-886e-4e68-94bd-e2484c259aef |  | textbox | Units ordered:
text | ba045aaa-cc0d-4371-a865-c21f7ad8b1ca |  | textbox | Units delivered:
text | a1940aea-eb7f-491a-a8ec-73b31e626d4a |  | textbox | Special Storage/ Handling Requirements?
label | 1b0be734-60b7-4383-8854-adbe1e857781 |  | note | The following is for completion by Fulton Hogan
text | 37ff5fe3-d6fb-4872-9eb0-415c4b940368 |  | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
text | 5e80b0b6-06df-4423-a391-384192fa2efd |  | textbox | QA Docs Delivered?
text | ba0b94d4-195d-4d3f-a7f7-3769ff45da9f |  | textbox | Defective?
text | 8e6ef2ad-f8e5-4577-94b9-e3e9234f50e4 |  | textbox | Number Accepted / Number Rejected?
checkpoint-status |  |  | checkpoint | 4)
text | 34b1c7cb-fc31-4b8a-8ef4-7b9f35003540 |  | textbox | Item ID:
text | cc11dafc-cd38-446b-bf40-a4fedee79c82 |  | textbox | Item description:
text | e23b03a8-bc11-4bad-a639-57339ee4f90c |  | textbox | Units ordered:
text | 07001d35-e567-404e-872d-7d1d40a3309e |  | textbox | Units delivered:
text | 34889111-f3ae-4c8d-b18e-9cf26e843ece |  | textbox | Special Storage/ Handling Requirements?
label | 5f48a5bf-6a0f-497b-84a4-e1a70d592822 |  | note | The following is for completion by Fulton Hogan
text | d074a9b5-c50c-4b26-b4c1-38f40afc9af6 |  | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
text | 04382026-80fe-4856-9527-ab46fd085d20 |  | textbox | QA Docs Delivered?
text | 2c7d6f7a-8024-4b9b-b521-46efec889e0c |  | textbox | Defective?
text | f1d0bac0-ad80-4a8a-bc87-d3e55b0484ad |  | textbox | Number Accepted / Number Rejected?
checkpoint-status |  |  | checkpoint | 5)
text | f0f0c70c-bb4d-42c5-b26d-527ed4803af2 |  | textbox | Item ID:
text | 9ae66eae-0ad1-4597-afd3-aa3f631faa04 |  | textbox | Item description:
text | 199453c2-08d9-49aa-93a4-3260c6295105 |  | textbox | Units ordered:
text | edbed206-dca6-4944-afb7-453709e7e4bc |  | textbox | Units delivered:
text | ff5d0180-224f-495b-bfd4-fda1ca78c206 |  | textbox | Special Storage/ Handling Requirements?
label | e4b1cd09-c797-4d50-88b0-1444f037326f |  | note | The following is for completion by Fulton Hogan
text | c05ff9e1-ee29-40fb-b6ef-d5f37428af8d |  | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
text | f638f0fa-2b4f-490b-b6ba-963cd91ac95c |  | textbox | QA Docs Delivered?
text | b3b90d94-f59a-4a0f-ad25-f5132948c64a |  | textbox | Defective?
text | 4665ce88-79a0-42ea-9da6-50e3f69bb384 |  | textbox | Number Accepted / Number Rejected?
checkpoint-status |  |  | checkpoint | 6)
text | 01a51b7b-4006-4423-b8be-d9fd29de264a |  | textbox | Item ID:
text | baa71d54-e3c1-40e9-829d-828865428e36 |  | textbox | Item description:
text | aacbde66-09fc-49fd-9ecb-7d795377626a |  | textbox | Units ordered:
text | 25e3ebda-b80a-458b-91ec-90564c94f4ba |  | textbox | Units delivered:
text | 6854ee16-abf3-4bc2-b678-1ad7126620b2 |  | textbox | Special Storage/ Handling Requirements?
label | 20182d8b-fd80-4224-9eaa-90f4f28cf40b |  | note | The following is for completion by Fulton Hogan
text | 019ab10b-9cfe-4973-8cf2-72cc70304bc6 |  | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
text | 5101d9c3-ef22-4f7f-8acb-9aec27b43d91 |  | textbox | QA Docs Delivered?
text | 78cefe81-495e-4577-ac5c-04524a3681f8 |  | textbox | Defective?
text | 4f755334-5a4a-434f-9858-0bb65aa33e80 |  | textbox | Number Accepted / Number Rejected?
checkpoint-status |  |  | checkpoint | 7)
text | 07b750ca-05c1-42f7-af14-e45ab1face90 |  | textbox | Item ID:
text | 46efe783-32a9-468c-829f-ebdee2d41061 |  | textbox | Item description:
text | 314cd6d2-78c7-4e7c-a785-a19a41d41aa8 |  | textbox | Units ordered:
text | cf1481a2-f616-4f23-a004-ff424979f815 |  | textbox | Units delivered:
text | 0e5bb1ba-1358-457b-a55d-dde239d390c5 |  | textbox | Special Storage/ Handling Requirements?
label | b5c53f46-f073-4c0f-b402-95f5962472e0 |  | note | The following is for completion by Fulton Hogan
text | a772d747-b7b7-40a7-9ee6-aacf51c308bb |  | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
text | beaa554a-26cb-4005-b570-adc1ab07d0cf |  | textbox | QA Docs Delivered?
text | c2f2a68d-19fb-47b5-9829-74e052bf43e4 |  | textbox | Defective?
text | 9cffefad-cb1b-40da-b3ba-f44e6ed07d43 |  | textbox | Number Accepted / Number Rejected?
checkpoint-status |  |  | checkpoint | 8)
text | e963c054-8042-4681-9511-80ca1da30b4f |  | textbox | Item ID:
text | 71e4290e-6ef0-4d0e-a0f1-350f78d70b29 |  | textbox | Item description:
text | b850724d-f7d8-49e8-9f42-efc6543f2071 |  | textbox | Units ordered:
text | 478da830-8e99-4af8-a761-96ccf8e38c7d |  | textbox | Units delivered:
text | c93f7d2e-7a90-4534-8b8d-0b200afb1f74 |  | textbox | Special Storage/ Handling Requirements?
label | 7477a71f-f9c5-4010-8c94-2f8881796d4c |  | note | The following is for completion by Fulton Hogan
text | e09aa68a-6b06-4fec-a064-cff9a6408be3 |  | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
text | ef0166a5-856d-44c1-a319-c595c77a5b28 |  | textbox | QA Docs Delivered?
text | 326ca8c5-efe5-47f5-9b68-ff3ee24b97b0 |  | textbox | Defective?
text | 80112e6c-1113-4841-ad84-6da76ddf4725 |  | textbox | Number Accepted / Number Rejected?
checkpoint-status |  |  | checkpoint | 9)
text | 7d8e163c-b192-4f09-9e0a-6a2ffe63383b |  | textbox | Item ID:
text | 93813169-812f-4fa4-b581-500fa1e46380 |  | textbox | Item description:
text | 425c24c5-9c31-4e54-b2ab-dc897c460d7f |  | textbox | Units ordered:
text | 46617760-835c-4d86-b0a0-2530b7440ccd |  | textbox | Units delivered:
text | ee433ab8-50b9-4a70-a7ac-4fd017482eb4 |  | textbox | Special Storage/ Handling Requirements?
label | eaa255b8-4137-4a74-afe8-70b81be77bd0 |  | note | The following is for completion by Fulton Hogan
text | 402e03bf-5d82-47cc-90e6-23d18ad01314 |  | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
text | 93587b41-f040-4c90-802d-508ba1ad574c |  | textbox | QA Docs Delivered?
text | 964c072b-4bb6-4264-879c-5d28e0f2df4f |  | textbox | Defective?
text | 444ceba8-c95f-4a80-b009-715b1c6eee79 |  | textbox | Number Accepted / Number Rejected?
checkpoint-status |  |  | checkpoint | 10)
text | 48a3d341-1bd9-4a4d-8cd6-109e34508ccf |  | textbox | Item ID:
text | 7a8104ca-3f41-4d82-a31a-ec7d93b2ea38 |  | textbox | Item description:
text | 7a2c1214-ac15-4ce1-8b6e-d55b634412ad |  | textbox | Units ordered:
text | d3c5bb98-16f8-43ac-a8ec-3f5bdf33e7dc |  | textbox | Units delivered:
text | 99884a66-291d-4a08-8dc0-916f9d3254d4 |  | textbox | Special Storage/ Handling Requirements?
label | cc211c7d-b7e2-4662-8a71-93f73ac918e0 |  | note | The following is for completion by Fulton Hogan
text | a904014f-f523-45f2-a3b5-12511417a4b0 |  | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
text | e1d676af-4149-44fa-acfc-ec6425c9ea96 |  | textbox | QA Docs Delivered?
text | 54cfbb8c-efbc-4779-9ea4-9a545141ffee |  | textbox | Defective?
text | 13a85a2f-c7bf-46f7-90b7-e64f718b9447 |  | textbox | Number Accepted / Number Rejected?
checklist-sectioned |  |  | checklist | ITP 007 - Unbound Pavements and Crushed Rock Working Platform | itp |  |  |  | Yes | ITP 007 - Unbound Pavements and Crushed Rock Working Platform | cf143727-7e51-48c9-aee5-c504cc43bc7a
checkpoint-group |  |  | section | ITP 007 - Unbound Pavements and Crushed Rock Working Platform
checkpoint-status |  |  | checkpoint | 1.1 - The current revision drawings are being used including subcontractors copy.
label | a342b376-848c-47c9-b37d-672769df4da2 |  | note | FREQUENCY: Prior to commencing works
label | 66af52e3-d13a-41c0-9704-628c84b5cefe |  | note | ACCEPTANCE CRITERIA: Current revision drawing is being used including the subcontractors copy. Current Revision to be obtained via Principal’s Representative
label | 8a6096eb-1aab-45cc-9821-a65c17f8d816 |  | note | REFERENCE DOCUMENTS: Aconex
label | bbe01a5b-df5a-41b1-9e3a-1628317ecaaa |  | note | INSPECTION/TEST METHOD: Visual inspection
label | c8ff8012-9097-47fe-9d98-70a085c9bcb5 |  | note | RECORD OF CONFORMITY: Up to date drawings
label | 28c2107d-4345-4a3d-b751-9674f90612cb |  | note | HP*
label | b4f5b88c-62cf-415d-9374-8cb173249ea1 |  | note | RESPONSIBILITY: FH Engineer
text | 69470b17-5a78-4005-b693-398cba2cec20 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 ITP and Construction Procedure Documentation
label | 945924a9-5984-4965-a3ce-6fe36808bc91 |  | note | FREQUENCY: Prior to works
label | a80a0e21-6730-470a-9ad0-5cfcf0a6abeb |  | note | ACCEPTANCE CRITERIA: ITP and Construction procedure for unbound pavement material placement to be provided to Principal’s Representative for review.
label | 9fdeb029-d783-437d-a183-4907904a67ce |  | note | REFERENCE DOCUMENTS: Spec CL. 4
label | c2bb5e01-1fca-4e90-9c98-6ca00e691114 |  | note | INSPECTION/TEST METHOD: Verify
label | 3cb28eaa-0585-452e-9e8d-88f529c9db10 |  | note | RECORD OF CONFORMITY: Approved Work Procedure Report
label | 87939efb-87d5-4d86-845b-b877f1a8cba1 |  | note | HP*
label | 2859db9b-2a77-4606-8070-e6443f9104c4 |  | note | RESPONSIBILITY: FH Principals Rep
text | 7cf924b4-b16d-4ffd-93ef-04314b13c983 |  | textbox | Date Completed:
label | 4383c917-026d-4dc0-b706-92b44fa5ced6 |  | note | Hold point sign off reference: ACONEX: FHPL-TRANSMIT-000040
label | bff56100-01ea-4837-a290-0aaae38df0a8 |  | note | 27/5/19
checkpoint-status |  |  | checkpoint | 1.3 Material Classification
label | 4be6df74-5f89-4a0c-8dd2-b48ded848932 |  | note | FREQUENCY: Prior to works
label | 938aca4d-c75f-408e-920b-2bf141374eae |  | note | ACCEPTANCE CRITERIA: Proposed material source information and samples to be submitted to Principal’s Representative.
label | 86851991-017e-4053-a258-ee1f496a2321 |  | note | REFERENCE DOCUMENTS: Spec Cl. 4 VicRoads section 812
label | e38877a4-e4f8-4bf0-9fe1-b91c69e6dfd5 |  | note | INSPECTION/TEST METHOD: Verify
label | 62cb3eda-433e-4752-ad87-4e410a25c90d |  | note | RECORD OF CONFORMITY: Approved Rock Mix Design Report
label | 22dd4d1b-1756-4462-90d0-3ff00c925972 |  | note | HP
label | db2ae44c-593a-42b0-b869-e45ab79bb6cf |  | note | RESPONSIBILITY: FH Principals Rep
text | eff2904b-1517-47db-883b-78791b8c0583 |  | textbox | Date Completed:
label | 7035fb1f-2884-418f-96f2-6f2f104c7044 |  | note | Hold point sign off reference: ACONEX: FHPL-TRANSMIT-000055
label | a08d2abc-e8e9-45c3-9921-679874aa35e7 |  | note | 15/7/19
checkpoint-status |  |  | checkpoint | 1.4 Production Testing
label | a3b8f4da-aef6-4d74-90af-1cdc7ffacb30 |  | note | FREQUENCY: Prior to works
label | baa9a8d7-ec7f-4ec6-8b73-383d12782474 |  | note | ACCEPTANCE CRITERIA: Supply of information with respect to production testing.
label | efc967d1-897a-422a-b04f-c3db421c5375 |  | note | REFERENCE DOCUMENTS: Spec Cl. 4 VicRoads section 812
label | dd54fd1c-c15a-4f5a-b3db-8979e45071be |  | note | INSPECTION/TEST METHOD: Verify
label | 6139b6a2-0c99-4cb8-94b0-384b68944443 |  | note | RECORD OF CONFORMITY: Approved Production Testing Results
label | e7ef2d57-ed61-45fa-ae44-e6849c074cee |  | note | TP
label | bfa2537c-e35f-44ef-b28e-e749c8db7a70 |  | note | RESPONSIBILITY: FH Principals Rep
text | 9db9017d-3ee3-415e-85de-8a504cc819ee |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.5 Implementation of all measures & controls
label | 4f807599-1ae7-4e67-a886-decaf86ab7cd |  | note | FREQUENCY: Prior to works
label | d00456bb-d739-4b11-90f5-9a19d440da8a |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented including: PSP, EMP, TMP, SWMS and WP.
label | 580c6a6b-53eb-4a8a-8def-c889907a8d3b |  | note | REFERENCE DOCUMENTS: PSP,EMP, TMP, SWMS, WP
label | 0f4bd89c-d3c2-4d4f-b45b-b7ab8b51072d |  | note | INSPECTION/TEST METHOD: Visual inspection
label | cfd1757b-0686-48dc-898c-6a0d52107f09 |  | note | RECORD OF CONFORMITY: Site Inspection
label | 191f3952-6b94-44ab-ac12-221fb7e8b566 |  | note | HP*
label | 8b1ab947-fcc0-4e63-b2c3-53946726bb96 |  | note | RESPONSIBILITY: FH Engineer
text | c0fd15aa-c0f8-43db-a9f3-1845f9c7a6ff |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.6 Plant & Equipment
label | a2ada57d-8555-49b3-b58b-b57a147c39ec |  | note | FREQUENCY: Prior to works
label | cb29fc48-128f-4308-8113-61421365446c |  | note | ACCEPTANCE CRITERIA: Plant and Equipment used in the works are appropriate to achieve specification requirements.
label | aeb6618d-0bde-430f-8a86-e799fd46c5c1 |  | note | REFERENCE DOCUMENTS: Spec Cl. 4 & Cl. 5.6.2
label | f7bd3593-a62f-46e9-b8d7-4a184c6db49b |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 966124d8-d5e2-441b-b6cc-feca459f1d6b |  | note | RECORD OF CONFORMITY: Finalised ITP
label | b14cdb1f-75a6-43b6-84a8-24ef1e281e08 |  | note | HP*
label | cfa91361-31a1-4b76-827e-dd5365b1b8cd |  | note | RESPONSIBILITY: FH Engineer
text | 1af32e25-16c8-43d9-bc31-d521226d6508 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.7 Stockpile Material On Site
label | 1f31e735-9bbf-4e2e-be0c-b460c2bb4f01 |  | note | FREQUENCY: Prior to works
label | 9b30229c-7842-4229-84d6-d64fc95da1a3 |  | note | ACCEPTANCE CRITERIA: Class 1 and class 2 crushed rock has been stockpiled in locations approved by the Principal’s Representative.
label | 92e7cc65-47e3-41bd-91e8-3921af756c90 |  | note | REFERENCE DOCUMENTS: Stockpile Map
label | aa9b9e39-58a9-4206-bb74-660d11e1cd7d |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 24401b9f-237d-402e-94b5-b56323d1fcea |  | note | RECORD OF CONFORMITY: Materials receivable checklist (dockets)
label | 27ff98c4-560e-4ca5-841b-2c42d72e2d45 |  | note | AP
label | d30d6f61-9480-4c69-9e47-d1eb2b80abd6 |  | note | RESPONSIBILITY: FH Engineer
text | aacfad05-f563-410e-97f2-bf2d3649a9e3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 Commencement of construction of the base and subbase
label | b362c0ba-32a2-474c-84bd-e5030d6efba9 |  | note | FREQUENCY: Each lot
label | 1a77f21a-89e6-4c42-9453-baa41546dac6 |  | note | ACCEPTANCE CRITERIA: The underlying layer shall be clean of all foreign matter. All edges of previously placed material must be water conditioned prior to placement continuation.
label | 95f40634-8184-42b0-95e6-e47989654232 |  | note | REFERENCE DOCUMENTS: Spec Cl.4, Cl. 3.6 & VicRoads section 204
label | 6e72fd01-df31-40e9-97a6-c5e9034732f0 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | b3628d5d-7020-4f7f-8b55-ec3335648c69 |  | note | RECORD OF CONFORMITY: Site inspection
label | cb7acf6f-a925-430c-8ed8-f2a0bc85a5ac |  | note | HP*
label | 7e56274a-693d-44d9-a944-1355dc30f677 |  | note | RESPONSIBILITY: FH Engineer
text | 45ab3943-f01f-4c8f-a02a-eeb3e0c7fa0a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Placing Crushed Rock
label | 3669732a-2260-4ed2-8c2d-9a582419486f |  | note | FREQUENCY: Each lot
label | 061829d8-902b-4589-8bcf-b82a8fb6db13 |  | note | ACCEPTANCE CRITERIA: The maximum lot size for surface levelling is to be 4,000 m2 with a minimum quantity of 40 measurements per lot. Surface tolerances per layer is as follows;
label | 72dbecc6-f39a-43be-942b-1c45ac8140ac |  | note | Class 1 Crushed Rock: +0, -10mm
label | 9e487b7f-8aff-4c88-b6c9-f26b619f451f |  | note | Class 2 Crushed Rock: +0, -10mm
label | 451a176d-42a5-4d8a-801e-6afffcb1edc2 |  | note | Crushed Rock Working Platform: +0, -10mm
label | f98d5feb-a06b-42f4-beac-84cf37f78d83 |  | note | PT2 & PT3 Top Layer Shoulder and Blast Shoulder: +5, -5mm
label | b5861077-a2c3-477a-91f1-30c08629c925 |  | note | Pavement layer thickness tolerances as follows;
label | 90e9f5a8-f802-453f-912d-65912f2a7c77 |  | note | Class 1 rock (Base): -10mm. The average thickness over every 100m shall be no less than the specified thickness. Max thickness of any base layer shall not exceed 200mm and be no less than 80mm.
label | a3a59bda-6c7b-427d-ba4c-214b3004fefa |  | note | Class 2 rock (subbase): -15 mm. Max thickness of any subbase layer shall not exceed 150mm and be no less than 80mm.
label | 055d3988-9e70-4ad0-bbb3-9fa8ba951262 |  | note | The combined thickness of subbase and base course shall be no less than the specified thickness by more than 15mm.
label | b152a75b-6656-4a11-9853-42fb39afc15d |  | note | No point on the surface of any pavement layer shall vary by more than 8mm from a 3 m straight edge. Underlying layers are not disturbed during placing, compacting and trimming; Segregation and contamination of materials must not occur;
label | 8d41787c-6270-44dc-ad4a-e029fd868478 |  | note | The completed layer meets the specified density, thickness, surface level and surface shape requirements for that layer.
label | f10605b8-e3c2-45e4-9c8c-00003bc2c33b |  | note | REFERENCE DOCUMENTS: VicRoads section 304 & Spec Cl. 4
label | 406ee3d6-002a-4726-baa1-85aa4b63295f |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 867d9c1e-e26a-4ced-a747-c38706802ffd |  | note | RECORD OF CONFORMITY: Survey day and visual inspection
label | 065215ed-2a06-4d9f-ab6c-ce4e0cb3cb83 |  | note | HP*
label | 429d4238-e888-4bf6-83fd-d2ae526d6d92 |  | note | RESPONSIBILITY: FH Engineer
text | 1b1d21ae-607c-46cd-9a0d-081b9a7ee9bd |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Compaction and Post Compaction Testing
label | 1bc1b60b-20f6-4fc7-b51d-9f8fba8cd701 |  | note | FREQUENCY: Each lot
label | 68e8dcd6-bd5d-4a58-b720-37dd5a23b13a |  | note | ACCEPTANCE CRITERIA: Full compaction of each course shall be achieved in all areas including the interfaces between successively placed lanes and sections; Compaction is achieved whilst material is within desired moisture range.
label | 403d8c21-4e09-4396-9afe-3b5debaf3470 |  | note | The class 1 crushed rock shall of a minimum soaked CBR of 100% to VicRoads section 8.12 and is to be compacted to a characteristic Density Ratio ≥98% (modified compactive effort).
label | 6789f6bb-431a-4349-b8e3-7c2237249047 |  | note | Crushed Rock Working Platform to have a characteristic density ratio of not less than 98% modified compaction. Minimum of Eight coverages with the 27T Pneumatic Tyre Roller for the CRWP.
label | d94ab59f-b4f1-4bcb-be3d-8dafc3497f37 |  | note | The class 2 crushed rock shall have a minimum soaked CBR of 45% to VicRoads section 812 and is to be compacted to a characteristic Density Ratio ≥95%. (first layer of PT2 Shoulders).
label | 81e80f90-e865-4ea3-9b75-babac4411090 |  | note | The first lot of each pavement course shall be tested for post-compaction grading and PI. If the first lot of each pavement course satisfies the specified post compaction requirements, no further post-compaction testing will be required for that pavement course. Result requirements to conform to VicRoads section 304. Post-compaction testing frequency of 1 per 5 lots.
label | 2990fbc5-0913-40d3-b47d-a7ca12dddfde |  | note | REFERENCE DOCUMENTS: VicRoads section 304, Spec Cl. 4 & Spec Cl. 3.6.3
label | 4b487894-a648-40b7-982d-6c3ad06575f7 |  | note | INSPECTION/TEST METHOD: Testing
label | 1285bd94-99fe-4e5e-95c2-7a57debf3c20 |  | note | RECORD OF CONFORMITY: Test result register
label | be6a726d-bdd6-4b70-abb1-912fadc811b6 |  | note | TP
label | b1f0edee-b998-4590-9ea4-d53bb206707a |  | note | RESPONSIBILITY: FH Engineer
text | 927214c4-d65a-486c-a660-15d3c85f4ad3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Proof Rolling
label | 06a59ee0-3c13-44fe-b6f3-b27df0497ba1 |  | note | FREQUENCY: Each lot
label | 3aabdbe1-2aa5-47c7-b522-74a1ab52ab66 |  | note | ACCEPTANCE CRITERIA: Proof Roll will occur once compaction has been completed, as part of the final sequence of compaction.Proof Roll to be systematic and in a manner that covers the entire area.Vibrating Plant travel at speed less than 4km/h and less than 6 km/h for pneumatic rollers;Rollers operated as close as practicable to unsupported edges.Contractor shall provide for the Principal's Representative to be present during all test rolling. Proof rolling of the Crushed Rock Working Platform to be completed with a 27T Pneumatic Multi Tyre Roller.
label | 9b716e58-9866-44b0-b1e3-fa36b6b29b78 |  | note | Witness Point for Proof Rolling in Shoulders and Blast Shoulders either physically witnessed, or through GPS mapping system with 38T MWR of four passes.
label | 89f134b2-9692-40f3-b3d5-88c31159dc7f |  | note | For the CRWP, refer to relevant CMCR lot for HP release of Underlying Layer Inspection.
label | fffdaced-d28f-462f-9f83-9163fea826a4 |  | note | REFERENCE DOCUMENTS: VicRoads section 173&Spec cl 3.6.3
label | f77aae7d-37ff-429e-8af7-bfdecd420e7c |  | note | INSPECTION/TEST METHOD: Visual inspection and mapping data
label | c3db3b07-4aaf-45bb-94b8-91e2a419b291 |  | note | RECORD OF CONFORMITY: Visual inspection and mapping data
label | b7147519-fd81-4d21-9d3d-f4c577db1d8f |  | note | WP / HP*
label | b90bf87c-76e1-471a-9a24-1294a1cf0138 |  | note | RESPONSIBILITY: FH Principals Rep
text | 759cc975-9fe1-4533-9c85-32923906f970 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 Identification and treatment of unsuitable areas
label | af29adc2-18d4-4336-9d1a-a1f3ea3c0287 |  | note | FREQUENCY: Each lot
label | 6569825d-8d0a-4a76-a84e-4d779bddf7a6 |  | note | ACCEPTANCE CRITERIA: Should any area crushed rock be disturbed or become unstable during proof rolling, the Principal’s Representative should be advised immediately and proof rolling of the area ceased. Any areas of crushed rock layer that rut, yield or become unstable under the proof rolling must be investigated in the presence of the Principal’s Representative.
label | 456f562c-4a2f-40be-9db7-ab40bea282a2 |  | note | REFERENCE DOCUMENTS: Spec cl 3.6.3 & VicRoads Section 204
label | b459fef5-88cd-42c5-9c35-f48050155331 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | c0116202-deab-404c-91a3-83405576552b |  | note | RECORD OF CONFORMITY: Site Inspection
label | 8ba0d80e-e4e3-4617-bf91-5e6e29cc324b |  | note | HP
label | 524fbacb-0b56-43c8-b412-39f05d76ce85 |  | note | RESPONSIBILITY: FH Principals Rep
text | 04b5e797-7345-4443-b2fd-383333f29249 |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 2.6 Recycled concrete working platform
label | 700936c5-8292-4e11-b66b-f7323426e1f6 |  | note | FREQUENCY: Each lot
label | 4aa46d24-2162-4d28-a312-08315687e057 |  | note | ACCEPTANCE CRITERIA: The intent to adopt recycled concrete from existing pavements will require the development of an airport specific technical specification and will include grading and aggregate strength limits being agreed with the Principal’s Representative.
label | 7b6db2e5-39ec-4c3d-b89e-741d9f4a2b54 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002-D-Cl3.6.3
label | 9e25dd88-2118-4589-83d0-af0d9669279b |  | note | INSPECTION/TEST METHOD: Verify
label | fcc0da5c-c32a-40b4-a2bb-52d33f858be6 |  | note | RECORD OF CONFORMITY: This signed ITP
label | ee4feb36-75d6-4048-a7ac-06f2fb994085 |  | note | HP
label | 6d208461-860c-4ebe-aa85-d85acacab2e4 |  | note | RESPONSIBILITY: Project Engineer Principal’s Representative
text | 6202bbc2-f5e9-4e7d-9297-020c7138ca0b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | FULTON HOGAN FINAL INSPECTION - On behalf of Fulton Hogan, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 71394f8c-e2e9-4af3-8e6d-2edc9eaeeb2a |  | textbox | Name:
text | 0f201c84-eb5d-4982-8932-7f5cb359e545 |  | textbox | Position:
checklist-sectioned |  |  | checklist | Defect ID No: | itp |  |  |  | Yes | Defect Checklist | d3230a69-2ad5-485f-987b-1ba46ce642d0
checkpoint-group |  |  | section | Defect
checkpoint-status |  |  | checkpoint | Defect Identification
text | db5da556-675b-4df0-ad7f-d2c7c0b3bfd9 |  | textbox | Identified on (date):
text | 0a70099e-d1f2-4ebb-b36b-96bbbdfe3898 |  | textbox | Identified by:
text | 3b0f8245-5fb9-4182-8623-c53319a6b9c4 |  | textbox | Process:
text | a86e7d06-f260-46f9-9266-d33558a753d7 |  | textbox | Area:
text | 50108761-6e46-4082-9bf2-02b2173f17d1 |  | textbox | Location:
text | a23d1c29-4f5e-44ad-8674-ec7894d2677d |  | textbox | Client Reference (if any):
text | b5edf653-b0fc-45b1-a282-09d872466cdc |  | textbox | CAMS NO. (if applicable):
text | 362d4e34-f7a3-43ee-8598-8390f6529580 |  | textbox | Description
boolean | a88b9d8b-b875-471e-8d1d-821dd1496f2d |  | tickbox | Photo Attached
checkpoint-status |  |  | checkpoint | Defect Rectification
text | 03fc1ebf-22b7-400f-ab51-3485de58fb8e |  | textbox | Completion Date:
checkpoint-status |  |  | checkpoint | Defect rectification accepted and closed (signed off by FH & Client)
text | 3c5a0eec-16fb-4126-bf51-2e3e009018c4 |  | textbox | Date Completed
text | 0c6d088f-5cbe-42b6-a854-2acd301d733d |  | textbox | Fulton Hogan Representative
text | 1ae7aeb4-b3f9-4789-97cf-4a754a183473 |  | textbox | Client Representative
text | 73d30093-98ff-45a2-ba60-69ba941ef7ef |  | textbox | Date Signed off
holdpoint |  |  | signoff | Request Approval
checklist-sectioned |  |  | checklist | ITP 014 - Joint Sealing of Pavement joints | itp |  |  |  | Yes | ITP 014 - Joint Sealing of Pavement joints | e0f07fa6-8f47-4daf-a837-bf61b6635fcc
checkpoint-group |  |  | section | ITP 014 - Joint Sealing of Pavement joints
checkpoint-status |  |  | checkpoint | 1.1 Check for correct documentation
label | ea4fe5d7-27c6-4ab9-bbec-77566d71d40a |  | note | FREQUENCY: Prior to commencing works
label | 95e8a8a3-7fa9-4e68-a371-b3d12f1afa2d |  | note | ACCEPTANCE CRITERIA: Current revision of drawings, technical specifications and any other construction documentation is being utilised by Fulton Hogan and subcontractors obtained via Aconex
label | 84df1756-0e75-4907-a4b5-093292754040 |  | note | REFERENCE DOCUMENTS: Jacobs Technical Specifications & Drawings
label | 48c721b6-511b-4e37-a171-1d9ea5a7735b |  | note | INSPECTION/TEST METHOD: Verify
label | ebedd09a-719d-4279-b023-5fbac12df322 |  | note | RECORD OF CONFORMITY: This ITP signed
label | a25617a2-ade7-468c-8665-808f97795da2 |  | note | HP*
label | 2b690c26-eb61-4c3c-8739-bc8e53d2369b |  | note | RESPONSIBILITY: FH Engineer
text | 7b239fec-09d2-4e36-b32b-ef8992c5db79 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 Implementation of all measures and controls
label | cec339ce-1f85-4e6d-9e9c-01ba157d62f9 |  | note | FREQUENCY: Prior to commencing works
label | 26b5cdb4-c981-4463-b02d-2ee310f37038 |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented in accordance with PSP,EMP, TMP, JSEA, SWMS & WP
label | bf6384c9-eb48-42d9-900c-843d4d525a38 |  | note | REFERENCE DOCUMENTS: PSP, EMP,TMP, JSEA, SWMS, WP
label | 8c11ab06-a9f4-44ee-ac0f-d7077f05b241 |  | note | INSPECTION/TEST METHOD: Verify
label | 1bb0fff4-ec93-4c07-a241-27f03b5029ad |  | note | RECORD OF CONFORMITY: This ITP signed
label | afb75c18-cb49-46e9-9e43-29560ac1c345 |  | note | HP*
label | ecf18167-600b-4e04-8665-d5aaa08a26fd |  | note | RESPONSIBILITY: FH Engineer
text | 349c619d-53d8-452f-9f8d-51e8d5397605 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 Material Sample
label | 5857f071-d2ee-4e56-b5ac-04d27b179d21 |  | note | FREQUENCY: Prior to commencing Production and Construction Trial
label | 71c951ed-c965-406e-b0e7-560f5ce9f83f |  | note | ACCEPTANCE CRITERIA: Joint sealer shall be Dow Corning 888 silicone joint sealant or approved equivalent for concrete and concrete interfaces.
label | ded7a2d9-e1b3-484d-96d1-204b98da4e26 |  | note | ACCEPTANCE CRITERIA: Joint sealer shall be Dow Corning 890 silicone joint sealant or approved equivalent for concrete and asphalt interfaces.
label | 2d4adc39-aacf-4dcc-bc06-57d4c4da50fb |  | note | REFERENCE DOCUMENTS: 6.3.2
label | 838da3b0-93b5-4d1c-8702-86d612ceaffe |  | note | INSPECTION/TEST METHOD: Verify , Aconex Approval
label | 2502b2d2-d6ca-4fe7-b253-aa774e2233dd |  | note | RECORD OF CONFORMITY: Aconex Mail Number
label | d1a6f36a-9ec0-4d63-b630-bed4ebe2affe |  | note | HP
label | 4d6a071a-3585-4a28-9918-6fcfac9013b8 |  | note | RESPONSIBILITY: Principals Representative
label | 35afe892-d5b2-4b88-907c-08da3fb96dfa |  | note | CLIENT: Refer to Aconex: FHPL-TRANSMIT-000228 for materials sign off
label | 39c6def3-e328-49f6-86b4-083b0a023eda |  | note | Date Completed: (16/08/2019)
checkpoint-status |  |  | checkpoint | 2.1 Define area of works.
label | 5fac6023-8f76-4e00-9a07-1be611b69c21 |  | note | FREQUENCY: Prior to commencing works
label | 3ead6c80-67ec-4614-8ab0-d7ead7ccada7 |  | note | ACCEPTANCE CRITERIA: All joints shall conform to the details and shall be constructed in the locations shown on the Drawings.
label | 4e10be37-98ae-4557-8462-3707441e6342 |  | note | REFERENCE DOCUMENTS: 6.7.5.1 CI0200-CI0287
label | 465a9328-eba3-47de-8d3f-8a7a85858180 |  | note | INSPECTION/TEST METHOD: Verify
label | 3c5c7a9a-fa7b-4c3e-a40d-a90e407bb6af |  | note | RECORD OF CONFORMITY: This ITP signed
label | 33b79085-a405-4c79-834b-0b6ead9c6aa5 |  | note | IP
label | 0b9671e5-6f8d-4238-aa6a-ddc9ab84db7e |  | note | RESPONSIBILITY: FH Engineer
text | 12ab0e89-26e1-4210-a6d3-4970133c3066 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.1 PCC cure
label | be949adc-aa00-4b38-90b9-29363987b94b |  | note | FREQUENCY: Each Lot
label | 6bf39181-dc2c-4e8f-95e6-f713363ec357 |  | note | ACCEPTANCE CRITERIA: Check PCC pour lots for area of works to ensure concrete has been allowed to dry and cure. At least 7 days curing should be allowed prior to sealing.
label | e9207cda-f680-4763-b5f8-3dff1541c55d |  | note | REFERENCE DOCUMENTS: 6.7.5.7
label | f15efa66-e49e-4266-a294-08ef116ca26e |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 11ec4272-7e30-47ca-a8cc-25f35c02075e |  | note | RECORD OF CONFORMITY: This ITP signed
label | 0dbe2834-43e8-441f-9376-d07d4698062b |  | note | HP*
label | 9f640775-0834-4ce4-97ad-a32798682c11 |  | note | RESPONSIBILITY: FH Engineer
text | a60d1cd7-eb68-443b-9bb9-5689a2a604b7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Free from spoils
label | cdffabb5-7ec6-4565-a3dc-a15b924c64e0 |  | note | FREQUENCY: Each Lot
label | 5cea4abd-9498-48b1-8eea-8958146a93bb |  | note | ACCEPTANCE CRITERIA: Where more than two chips, spalls or tears in any 5m length occur – a hold point shall be installed and advice given to the Principles Representative of actions taken to rectify and how to reduce occurrence
label | b45fe059-b76e-4d6c-807e-609cdafd70c2 |  | note | REFERENCE DOCUMENTS: 6.7.5.5
label | 39069d71-7e7b-459b-9f57-3536cf9c68fd |  | note | INSPECTION/TEST METHOD: Visual inspection
label | f929fd6e-6fd6-4e53-b4cc-8ce29e09c9e1 |  | note | RECORD OF CONFORMITY: This ITP signed & CL014A
label | 6e631e88-42b3-427a-8419-476a8a1c80b6 |  | note | HP
label | 78b7df64-54fe-4519-8892-6225775dcd3f |  | note | RESPONSIBILITY: FH Engineer / Principals Representative (if required)
text | c718e4a7-a027-498c-9e8a-cca3234ca8b8 |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 3.3 Clean and dry Joints
label | 0c121d7d-3104-4c13-a99d-b2841b1531cf |  | note | FREQUENCY: Each Lot
label | 6814cf9f-31ba-44a5-86e4-aa2335863e45 |  | note | ACCEPTANCE CRITERIA: Joints clean, dry and free from dust – washed and air blown. Ensure chamfer completed on joint as per design drawing. Ensure joint is to correct size and depth. Any foreign debris removed offsite to avoid being blown into surrounding joints.
label | 2c714f41-aee2-49e6-bcf6-2daa286951c0 |  | note | REFERENCE DOCUMENTS: 6.7.5.7
label | cf25082e-649a-4ea9-9943-2185dad3d288 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 4ce0d307-ae09-4761-ae10-a3711b43cc61 |  | note | RECORD OF CONFORMITY: This ITP signed & CL014A
label | 71665588-b802-45e5-bc65-27a03ec2274d |  | note | WP
label | c7443825-6916-452b-b4c7-ab6f0bc2f0bc |  | note | RESPONSIBILITY: FH Engineer / Principals Representative
text | 5f9bdba0-4da9-47d6-b739-44749e087539 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 Joint Alignment
label | 140a544a-916b-4e14-8730-e1ddf2065128 |  | note | FREQUENCY: Each Lot
label | 5a5736f9-e33c-49b9-a1c4-50b6f822b11a |  | note | ACCEPTANCE CRITERIA: Joints shall be inspected for trueness of line. Joint alignment to be inspected with the 3.5m straight edge at a minimum of 1 in every 10 slabs. Joints shall not deviate more that 3mm in 3m. Results shall be recorded.
label | e2fb3dca-02f3-4dc9-8c84-697aec070cd8 |  | note | REFERENCE DOCUMENTS: 6.9.12
label | ee4d47f3-b3d9-4864-aa01-8e06055ba461 |  | note | INSPECTION/TEST METHOD: Visual Inspection & Straight Edge
label | f39712d6-c335-414d-a6fc-3619c5d8c13b |  | note | RECORD OF CONFORMITY: This ITP signed & CL014A
label | 37ffa152-651c-4465-a2e5-e2ce675a1592 |  | note | WP
label | 24ad945f-b38c-4f06-8f6e-e32259352a51 |  | note | RESPONSIBILITY: FH Engineer / Principals Representative
text | c54c97ba-0b98-4ee0-90a1-27daae7d1380 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.5 Install Backing Rod
label | e519586f-bec8-453d-89e4-1f3d21e29143 |  | note | FREQUENCY: Each Lot
label | fcb239b7-f09f-4a87-87e8-4a79a6c16696 |  | note | ACCEPTANCE CRITERIA: Inspect Backing Rod – ensure homogenous. Backing rod installed to depth as detailed by the drawings
label | 6e91d468-7f49-42e9-b254-7bb44a465c07 |  | note | REFERENCE DOCUMENTS: 6.7.5.7, CI-0282, CI0283
label | fc4c2e20-8d9d-4847-a288-e692c8ca5484 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 85669293-766a-45e9-9d1c-718b3acd924d |  | note | RECORD OF CONFORMITY: This ITP signed
label | f04a694d-54ba-4755-af6d-7e17f53dfe6e |  | note | HP*
label | 2572a784-925a-44ec-a7fb-c0ca688c13ea |  | note | RESPONSIBILITY: FH Engineer
text | 0efcd26a-40db-4334-a945-e5e06d353d75 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.6 Install sealant
label | 12429fb3-73e6-4d8b-8e76-33785c739bd8 |  | note | FREQUENCY: Each Lot
label | e1602ea1-6d91-4e45-b591-e13a50f56028 |  | note | ACCEPTANCE CRITERIA: Sealant tooled off to correct recess. Excess sealant removed from surface of concrete (DO NOT REUSE). Sealant to be installed by an experienced installer in strict accordance with the manufacturer’s recommendations
label | c409d01c-6b9d-4166-b8ad-991ecaee6800 |  | note | REFERENCE DOCUMENTS: CI-0283
label | 698d82c8-7d15-4bfd-a6fa-7690094997aa |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | d3255bdf-f403-47c0-a0e8-242673100468 |  | note | RECORD OF CONFORMITY: This ITP signed
label | f50aee30-b355-450e-b921-e4221ac3f59a |  | note | HP*
label | 5650a00c-c2bc-4d14-9207-f62153807d17 |  | note | RESPONSIBILITY: FH Engineer
text | d8b1f3f5-6b82-4712-8e6c-77e0dc4f732d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | FINAL INSPECTION: FULTON HOGAN
label | 79a3820b-c1c5-4526-be40-8fa893d35306 |  | note | This is to verify that the final inspection has been carried out in accordance with the Fulton Hogan’s Quality Procedures and Project Quality Strategy and the product is hereby certified to confirm with the contract specifications:
text | 7614e660-2491-4e21-a975-022c69bcc955 |  | textbox | Print Name:
text | 2ac9bfeb-abcf-4f3e-b67d-88366acf609d |  | textbox | Position:
text | f6a022d0-e404-491a-a39d-d5ce16f1f0dd |  | textbox | Date:
checklist-sectioned |  |  | checklist | ITP 003 - Stormwater Drainage | itp |  |  |  | Yes | ITP 003 - Stormwater Drainage | eb4c088f-fd1e-4d9f-aef4-00add70f8a6e
checkpoint-group |  |  | section | ITP 003 - Stormwater Drainage
checkpoint-status |  |  | checkpoint | 1.1 Check for correct documentation
label | 6130e9bf-8d46-4257-9da3-fe5f73fc6440 |  | note | FREQUENCY: Prior to commencing any activity
label | 4872b03c-b5ec-424c-a39b-edb3d2ffda8b |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | 8b389b88-0b1f-4713-83e5-18b33607aeb2 |  | note | ACCEPTANCE CRITERIA: using the correct and complete set of drawings
label | bd13f4f8-d642-4afd-b920-2cd5afc273ff |  | note | ACCEPTANCE CRITERIA: all drawings are the latest revision
label | 9685cd7f-3829-4a09-bb71-6e323581384c |  | note | REFERENCE DOCUMENTS: Drawings and Aconex Register
label | 600d370e-004c-4479-afb2-f164b319bd3a |  | note | INSPECTION/TEST METHOD: Review
label | 23b9d3e0-9925-498a-b2a7-c3eceba45c14 |  | note | RECORD OF CONFORMITY: Up to date drawing sets & ITP
label | 972049bc-a3ea-4cc5-9ad6-ef90cc7ebe2b |  | note | HP*
label | a1eb4028-e5b0-4b37-97ba-a1c142a128a4 |  | note | RESPONSIBILITY: Project Engineer
text | 8af579ba-fc11-4a10-a2db-39b71133d60a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 Implementation of all measures and controls
label | 493a60e9-64e2-40d2-a428-5ae0f3937f5c |  | note | FREQUENCY: Prior to commencing any activity
label | a9a5b88d-2a2e-4622-9627-e1025aaa63c2 |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: EMP, TMP, SWMS & WP
label | 22c1cecb-41dc-4ab9-911e-2bcce053554a |  | note | REFERENCE DOCUMENTS: EMP, TMP, JSEA, SWMS, WP
label | 9bfcebd8-48ae-41aa-8289-67f90aa13bba |  | note | INSPECTION/TEST METHOD: Review
label | 2e6769d8-9d3b-4fe9-9528-b46d5d8b6508 |  | note | RECORD OF CONFORMITY: Site and Office Inspection
label | b4be3670-7807-455b-a243-b94f9cca748d |  | note | HP*
label | 089f0003-fe41-4e39-826b-647594ea2116 |  | note | RESPONSIBILITY: Project Engineer/ Site Supervisor
text | 37585b09-fa13-4963-8e10-4cf3127e23c9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 Definition of the work area (survey)
label | 4b395744-2a9e-48ce-9f38-70fa3185a3ea |  | note | FREQUENCY: Prior to commencement of activity
label | fe3f1825-25d3-4ccd-ba06-d4be401fb1cc |  | note | ACCEPTANCE CRITERIA: Work area has been cleared and surveyed (marked on site). Limits of excavation clearly defined.
label | b650d6f4-5eed-4eb6-9352-b15298829d74 |  | note | ACCEPTANCE CRITERIA: Confirm position of all culverts with the Principal’s Representative.
label | ff2cb4c3-77fe-4df2-b670-657ee5463076 |  | note | REFERENCE DOCUMENTS: Drawings/CP14038- AIR-DET- PM-SP- 0002¦1
label | 820f8961-aa31-4974-ad77-e35d151b1e76 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | e54cd323-549d-4396-8330-0015f037f8e2 |  | note | RECORD OF CONFORMITY: Site Inspection
label | 9870cf32-b3dd-454d-a224-5e64678937a7 |  | note | HP*
label | 5d335cff-6e6a-493a-a157-4c9b6c6313b2 |  | note | RESPONSIBILITY: Surveyor/Site Supervisor
text | 59f76f13-ceee-48db-889b-27b1e759fff3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.4 Service Locations
label | b5b83ff3-af8d-4e22-aa61-dbe03090657b |  | note | FREQUENCY: Prior to commencement of activity
label | 8dab9e97-c070-4f93-947f-c1e813bb9394 |  | note | ACCEPTANCE CRITERIA: Locate all underground services and mark on the ground within the works, and 10m beyond the boundary of works where applicable.
label | bca99289-8f23-4438-b57f-5e213bd24c31 |  | note | ACCEPTANCE CRITERIA: Cables marked with paint lines.
label | 5fe9477c-c5c4-4ddd-9d60-4fa9f86b221a |  | note | ACCEPTANCE CRITERIA: Services located within the works area to be exposed using approved location methods, in the presence of the Principal’s Representative where required.
label | 34858799-113c-4807-8f0a-78bc8f875cec |  | note | ACCEPTANCE CRITERIA: Service Locations and Depths recorded by Surveyor where required.
label | e4c46b8e-417a-4b63-91b3-7ef8e2adfcef |  | note | ACCEPTANCE CRITERIA: Ensure no mechanical excavation within 3m of Fuel Lines.
label | fba1612f-5cdc-47bf-a212-eceb05737239 |  | note | REFERENCE DOCUMENTS: CP14038- AIR-DET- PM-SP- 0002¦1- cl.8.1.8
label | 02428e3c-5abf-4f82-b28e-c6d4815e922b |  | note | INSPECTION/TEST METHOD: Verify
label | f879506b-54ec-4844-bcc4-24821f3f092d |  | note | RECORD OF CONFORMITY: Survey Report of Service Locations and Depths
label | 547f4a79-cd53-492c-8fc3-34527e3a724f |  | note | IP / SCP
label | 57595405-a086-43d0-b115-a144c225488c |  | note | RESPONSIBILITY: Project Engineer/ Foreman/ Surveyor
text | c5b602dd-7061-4f3d-ad30-2a95a715af2a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.5 Excavation Permit
label | feb4ac3c-88c8-43ed-95b3-642a927c89c2 |  | note | FREQUENCY: Prior to commencement of activity
label | ae9087be-3556-49d0-982b-ea9430dee0f7 |  | note | ACCEPTANCE CRITERIA: Excavation Permit issued by APAM obtained prior to any excavation on site.
label | f7cd56a2-80ba-4dd1-8126-a30c38f13229 |  | note | REFERENCE DOCUMENTS: CP14038- AIR-DET- PM-SP- 0002¦1- cl.8.1.8/ Approved FH OH&S Plan
label | 4d8e6e84-566a-4511-8ee1-6f793fa360c9 |  | note | INSPECTION/TEST METHOD: Review
label | 9dd1938b-4ec0-4f75-91d6-81ee10a3d7e6 |  | note | RECORD OF CONFORMITY: Proof of permit & ITP signed
label | eb386e36-7cd8-49ae-8306-39cafabb4f5b |  | note | HP*
label | 5bc838f3-c2b6-44b3-9158-d41afbefeb1a |  | note | RESPONSIBILITY: Project Engineer
text | 7ac36f5c-377f-4582-b381-b31da8f6a241 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 Pipe Material
label | 3a6b0706-f681-4578-918e-4cf156beaefc |  | note | FREQUENCY: Prior to commencement of works & Receiving Inspection
label | 13660b1e-cb5b-4466-888b-bcf99b962af1 |  | note | ACCEPTANCE CRITERIA: Manufacturer QMS in accordance with ISO 9001.
label | 81fe5fcf-3795-4332-b404-050817fdd64e |  | note | ACCEPTANCE CRITERIA: Pipes comply with AS4058 and VicRoads Technical Specification.
label | 0dda421f-d835-46d6-baba-92bfd8f35ee5 |  | note | ACCEPTANCE CRITERIA: Spigot & socket with rubber rings joint (unless otherwise stated); rubber ring to comply with AS1646
label | 00b8970a-6803-4050-8960-bf9c506719c4 |  | note | ACCEPTANCE CRITERIA: Class 4 and correct size with no damage.
label | fcc13b0b-ed20-439e-9401-67d685e5b8fc |  | note | REFERENCE DOCUMENTS: CP14038- AIR-DET- PM-SP- 0002¦1-cl.8.1.3b
label | 83649bb5-4ee0-4c56-b652-2a64f074d377 |  | note | INSPECTION/TEST METHOD: Verify
label | 402ab8af-e7a8-4f25-a525-327934613101 |  | note | RECORD OF CONFORMITY: Delivery docket or Technical data sheet & visual inspection
label | 3b626ace-ce11-4411-9ea9-697542b31dac |  | note | HP*
label | c189548c-46a5-4c0c-a4f6-ef1956422b3d |  | note | RESPONSIBILITY: Project Engineer
text | f3db99da-ff52-40f5-b557-1db243e824d4 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Bedding Material
label | 5d27d1c5-62c0-44f6-baff-05b9ad919d4b |  | note | FREQUENCY: Prior to commencement
label | 3890f329-79cf-4f1e-bdf4-2c3fa6a39ccf |  | note | ACCEPTANCE CRITERIA: Bedding material shall be free from perishable matter & lumps and 100% of the material passing 19mm sieve and 5- 40% passing 0.075mm sieve.
label | 446c998e-aea6-4c78-b1c4-4fe06e16e194 |  | note | ACCEPTANCE CRITERIA: Plastic Index ( Max): 20
label | 2d90b8a9-ee89-4d80-8bdb-7072122f488b |  | note | REFERENCE DOCUMENTS: CP14038- AIR-DET- PM-SP- 0002¦1- cl.8.1.3c
label | 94a62bd4-10f0-47e3-a740-c7b0a56d9c01 |  | note | INSPECTION/TEST METHOD: Verify
label | 4115fddc-a253-46cf-b11c-0a2459bb670b |  | note | RECORD OF CONFORMITY: Conformance Record
label | b22ddcac-7f13-454b-a1c3-1497b6fe8868 |  | note | IP
label | 49332955-e26b-4002-906e-7c5690d66eba |  | note | RESPONSIBILITY: Project Engineer
text | 3a1c6f7b-de86-4723-847e-3220ca8064cf |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Encasement Material
label | a379f84e-53ea-4f80-92b2-25677cdf5c54 |  | note | FREQUENCY: Prior to commencement
label | 5099b6e0-2340-455c-8f9c-0e4b04f72aa4 |  | note | ACCEPTANCE CRITERIA: Encasement Material is 5Mpa lean mix concrete.
label | ebc50865-0512-4898-8590-89020115cb08 |  | note | REFERENCE DOCUMENTS: IFC drawing
label | b3730553-55f9-433a-b22a-bb418e6d403c |  | note | INSPECTION/TEST METHOD: Verify
label | f5372e47-f65e-46a1-a47f-da7ac597de37 |  | note | RECORD OF CONFORMITY: Delivery Docket or ITP signed
label | 4e419246-d940-4208-8522-30eeed373a09 |  | note | IP
label | 5b27d18a-af43-42e2-87cb-95dd544ec9d0 |  | note | RESPONSIBILITY: Project Engineer
text | 5a48c561-80f3-4808-ad23-6e9979c4f3ac |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Backfill Material
label | df58bdcc-91b8-499f-bc90-ef9f4138df3c |  | note | FREQUENCY: Prior to commencement
label | 71f04942-29bb-460b-84f0-9e9d163c328a |  | note | ACCEPTANCE CRITERIA: Backfill material shall be free from perishable matter and lumps.
label | 4b8a4d43-e008-4685-b80f-c565208e3c3e |  | note | ACCEPTANCE CRITERIA: Material used for selected backfill shall be class 2 FCR and 100% of the material passing 37.5mm sieve and 5-40% passing 0.075mm sieve
label | 1730e03b-0df6-4505-b3fc-b2be74679683 |  | note | ACCEPTANCE CRITERIA: Material used for ordinary backfill shall be the best excavated material available on site and 100% of the material passing 75.0mm and 40-100% passing 2.36mm sieve
label | f3223ec9-605b-4a07-b2b8-b905e6e37c53 |  | note | ACCEPTANCE CRITERIA: Plastic Index ( Max): 20
label | 29e12108-5ac4-4a44-a29c-edd694e550e7 |  | note | ACCEPTANCE CRITERIA: Material used under Pavement shall be 6% Cement stabilised sand to design subgrade level.
label | ffcdc6da-80d3-4980-b31b-ff74a095c283 |  | note | REFERENCE DOCUMENTS: IFC drawing
label | affb65d7-da3f-4013-aad3-30281a95f44b |  | note | INSPECTION/TEST METHOD: Delivery Docket
label | 79a30945-9a7d-47c9-858e-13a128129858 |  | note | RECORD OF CONFORMITY: Conformance Record for import material and Delivery Docket or ITP Signed for local material
label | 602a2e5e-7d48-4807-8e30-243b42a354ae |  | note | IP / TP
label | 213b1161-27b4-4ff1-a384-2cdfc51f560d |  | note | RESPONSIBILITY: Project Engineer
text | 64f7c28a-4c74-401a-986f-cca580d507a0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.1 Survey Set out
label | 9cb1e48b-72b9-43f2-b4b3-915984d2f2bd |  | note | FREQUENCY: Prior to construction and each lot
label | 1176832e-ef30-49a2-b692-04a4edfa6381 |  | note | ACCEPTANCE CRITERIA: Identify locations and levels of pipes and drainage structure.
label | 7a408224-e9db-4703-ad54-caf89b684b9e |  | note | ACCEPTANCE CRITERIA: Pit on kerbs (Offset): ±20mm
label | 59dd45b5-5581-4e2d-bd3f-4db9f4783d54 |  | note | ACCEPTANCE CRITERIA: Pit elsewhere (Offset): ±100mm
label | 38886020-3456-4701-8213-c373701cacc9 |  | note | ACCEPTANCE CRITERIA: Inverts: ±10mm
label | abe5571c-816a-4669-ba49-f187a6c43086 |  | note | ACCEPTANCE CRITERIA: Grade: ±10mm over 10m
label | e294086d-f865-456c-bb23-08dcbc191e43 |  | note | REFERENCE DOCUMENTS: CP14038- AIR-DET- PM-SP- 0002¦1- cl.8.1.4
label | 718cf182-4aea-41fc-8285-cd70fe0bc14d |  | note | INSPECTION/TEST METHOD: Survey
label | cccdb049-4cb0-4508-9cc8-e6ce4c777874 |  | note | RECORD OF CONFORMITY: ITP signed
label | df73be20-e698-4584-a92b-c37a67178a11 |  | note | IP
label | e5793a87-7059-4b32-9d3c-4846ed0a22dd |  | note | RESPONSIBILITY: Surveyor/ Project Engineer
text | a2e48c95-12e2-4abc-bdee-d5f24af741f0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Excavation for pipes
label | 0424818f-84c6-49a7-9b91-0dc7e3e0aceb |  | note | FREQUENCY: Each Lot
label | a26fe7ed-beef-4bfc-8209-9cdad15991c9 |  | note | ACCEPTANCE CRITERIA: In accordance with the drawings.
label | e624c5e7-3929-488d-ada1-125809071605 |  | note | ACCEPTANCE CRITERIA: Excavation depth shall include depth required to achieve specified bedding depth.
label | 44928d59-b024-48a4-b000-67a649c8f507 |  | note | ACCEPTANCE CRITERIA: Width of trench shall be outside of pipe diameter + min. 300mm and max. 600mm horizontal clearance to trench wall.
label | f1690466-e148-451f-9c6a-9e576b4bedab |  | note | ACCEPTANCE CRITERIA: Trench sides adequately shored or benched.
label | e93ab1e1-c688-4ea9-bd1f-d7b6ec6bd58d |  | note | ACCEPTANCE CRITERIA: The base of the trench shall be compacted to refusal using mechanical plant.
label | a941ffdb-9250-405b-ad37-6b915a27c9ba |  | note | ACCEPTANCE CRITERIA: Rock encountered in trench shall be removed to a depth of 75mm from bottom of pipe, any resulting depression to be filled with 20mm class 2 compacted crushed rock.
label | 8c38043f-0da5-4f6b-a776-6786e1b4ee8d |  | note | REFERENCE DOCUMENTS: CP14038- AIR-DET- PM-SP- 0002¦1- cl.8.1.8
label | 8c237f66-9e57-481f-a3a1-d8e6eef89189 |  | note | INSPECTION/TEST METHOD: Verify
label | f55f9450-bc6c-4685-b0b4-a4a62a275371 |  | note | RECORD OF CONFORMITY: ITP signed
label | 02d9437b-227b-46f7-aec2-a9669c3ceef8 |  | note | IP
label | 313fd3cc-9579-46b9-8a6d-031545dcd5e2 |  | note | RESPONSIBILITY: Project Engineer/ Foreman
text | c4af7924-f287-45d8-b797-38bf5e7882fa |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Stockpiling Material
label | 42a66c9b-0bd7-4241-b112-5e7893902ef7 |  | note | FREQUENCY: Each Lot
label | 435757f8-5df7-4c73-b8f8-b4b45f913268 |  | note | ACCEPTANCE CRITERIA: Material shall not be stockpiled or stored on any airside areas without consent of the Principal’s Representative.
label | 84b53691-8994-468f-9fb7-c3d94943a933 |  | note | REFERENCE DOCUMENTS: CP14038- AIR-DET- PM-SP- 0002¦1- cl.8.1.5
label | 6ebefdbe-6b64-49d5-bb92-fe5d373adefa |  | note | INSPECTION/TEST METHOD: Verify
label | 306f5ada-4ec4-40bc-a09e-843c3cdd9cf1 |  | note | RECORD OF CONFORMITY: ITP Signed
label | c697d346-23c3-4cdd-9c1e-41627b828a4d |  | note | AP
label | 0fa8e1eb-d5d6-4c43-925d-f94b5f5bb904 |  | note | RESPONSIBILITY: Project Engineer/ Foreman
text | 0d74fd88-a098-4131-8a45-d311d4f3a7d3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 Drainage During Works
label | 951b400c-9e49-442e-ac3e-31e8867df1d0 |  | note | FREQUENCY: Each Lot
label | e2acef59-fa60-40c7-82e8-7730447306b1 |  | note | ACCEPTANCE CRITERIA: Ensure no water is discharged inside taxiway or runway strips, or on aircraft movement areas.
label | 97d556d2-7e1a-41bc-95a9-4d875753955d |  | note | ACCEPTANCE CRITERIA: Provide safe discharge of seepage and stormwater and keep trenches and excavations dewatered during the process of construction
label | c5e016d4-8342-4259-a9f7-03d34fb325d3 |  | note | ACCEPTANCE CRITERIA: Ensure temporary flow diversion is in place prior to obstructing any waterway.
label | 487a6039-ab53-4d79-94ba-32ccfa77989a |  | note | ACCEPTANCE CRITERIA: Obtain written approval from Principal’s Representative prior to obstructing or diverting waterways
label | d0f9ca0f-f4ae-4297-95c7-b0e986fb055e |  | note | REFERENCE DOCUMENTS: CP14038- AID-DET- PM-SP- 0002¦1- cl. 8.1.6
label | 251fd570-4976-416d-88ec-64c679c16ea5 |  | note | INSPECTION/TEST METHOD: Inspect
label | 8e21a101-e6ec-4627-ad2a-b917805470a3 |  | note | RECORD OF CONFORMITY: ITP Signed
label | 484cf805-094e-40c7-bfb5-7a268dabd33d |  | note | AP
label | 888bc190-29d2-4d6c-bd37-45d7302ee410 |  | note | RESPONSIBILITY: Project Engineer/ Foreman
text | c9d92276-dc39-4495-b0a7-ed6620fb94cc |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.5 Bedding for pipes
label | 41862754-02fe-48bf-8020-a20f69801c2d |  | note | FREQUENCY: Each lot
label | 70cd7216-90e6-4933-91bd-e107b7637343 |  | note | ACCEPTANCE CRITERIA: Pipes to be laid on an evenly graded 20mm class 2 FCR as per specification and drainage detail drawing.
label | 1a47a56a-1c9b-4881-9d99-f3fff978da99 |  | note | ACCEPTANCE CRITERIA: Bedding material shall be placed across full width of trench or if non trench condition, to a width of 0.8m greater than diameter of culvert.
label | 0e4a523c-d2a3-4d4b-af9b-ed3ce4f82cd2 |  | note | ACCEPTANCE CRITERIA: Compacted bedding thickness depth shall be 100mm where D˂1500mm and 200mm where D≥1500mm.
label | c9b7e567-e2eb-4441-beb5-54932e660997 |  | note | ACCEPTANCE CRITERIA: When sections are in position, an additional layer shall be placed to 30% of the diameter
label | 1bce1993-96f0-45cb-9591-df7f99af5de6 |  | note | ACCEPTANCE CRITERIA: Compacted bedding to be shaped to accommodate the joint collar and the pipe to support each pipe along entire length.
label | 36b9df0d-5fcc-418b-8308-62c88bf09512 |  | note | REFERENCE DOCUMENTS: CP14038- AIR-DET- PM-SP- 0002¦1- cl.8.1.9
label | aaad193b-dc25-4746-8319-cefdbc4c930d |  | note | INSPECTION/TEST METHOD: Verify & Visual Inspection
label | e3908b6d-75ed-42ad-bb2c-0ff51e53b987 |  | note | RECORD OF CONFORMITY: Delivery Docket and ITP signed
label | defa7b0e-2543-4951-9a39-3eea64ecf40b |  | note | IP
label | 3e07c322-de86-455b-8abd-ece9c5997328 |  | note | RESPONSIBILITY: Project Engineer
text | 13d4232c-c266-4b76-85f1-f6cba8b82a2d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.6 Laying and Jointing of Pipes
label | 5ed21344-0213-4648-aab6-1efe4c31876f |  | note | FREQUENCY: Each lot
label | 86bb4d0e-3f84-4f9a-aabc-465ef13d4a5a |  | note | ACCEPTANCE CRITERIA: Gaps between installed pipe sections shall not be greater than the manufacturer’s recommendations.
label | 01553dbc-eeec-422e-960e-eed2fba5f45b |  | note | ACCEPTANCE CRITERIA: No laying of pipes in water and in unsuitable conditions.
label | 73d3db7f-3e34-45c1-b862-6b4aea37f397 |  | note | ACCEPTANCE CRITERIA: Ensure pipe is supported during laying, jointing and backfilling.
label | f1eb74ce-8dff-409b-ba56-b7b7ed07351f |  | note | ACCEPTANCE CRITERIA: Socket end of pipe shall be placed facing upstream and be fully entered
label | 39cd9fad-4028-4a55-b1c1-353ff14ba636 |  | note | ACCEPTANCE CRITERIA: Rubber rings shall be kept undisturbed, clean and free from dirt and other foreign material.
label | 6b2efa1e-531b-4762-9ed9-414231bb1a26 |  | note | ACCEPTANCE CRITERIA: Rubber rings to be assembled and prepared in accordance with the manufacture’s recommendations
label | b9b7f1eb-4d15-4972-ac72-f38837179521 |  | note | REFERENCE DOCUMENTS: CP14038- AIR-DET- PM-SP- 0002¦1- cl.8.1.9
label | 04605bb3-3b72-472f-ada2-dee8e5c9fdfa |  | note | INSPECTION/TEST METHOD: Inspect & Verify
label | 80357665-028f-460f-9cef-9b21360e9cf2 |  | note | RECORD OF CONFORMITY: ITP Signed
label | e29d96a7-c1fa-404b-80a4-ab2d10d1a699 |  | note | IP
label | 9bbbcdb0-71d7-48c7-9997-011d32e1c4d9 |  | note | RESPONSIBILITY: Project Engineer
text | 5c5a8ba4-f09e-40ae-b3e5-4b8a30d85f3f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.7 Multiple Rows of Pipe – Spacing & Material
label | c1958588-8b2e-477c-8d91-4820a4edc7e1 |  | note | FREQUENCY: Each Lot (where applicable)
label | 6c034019-0791-426b-8141-52e06ad25c3d |  | note | ACCEPTANCE CRITERIA: Spacing and encasement material for multiple rows of pipe shall be as per pipe protection detail in drawings.
label | 9273ed6e-bfb0-47d9-9470-15853f42cfe2 |  | note | ACCEPTANCE CRITERIA: Spacing for multiple row pipe shall be:
label | 68fdf379-df5d-46fa-a1ff-3daa4f4b987f |  | note | ACCEPTANCE CRITERIA: 0.3m spacing for pipes diameter less than 600mm.
label | c96abf92-62b4-41b9-85a7-f416c0bbfe1f |  | note | ACCEPTANCE CRITERIA: (Diameter/2) spacing for pipes diameter between 600mm to 1800mm
label | 59ae6722-ac91-476c-8853-6ba163bc9aae |  | note | ACCEPTANCE CRITERIA: 0.9m spacing for pipes diameter over 1800mm.
label | a4243d84-aa60-4c89-b3e6-76911bd54054 |  | note | ACCEPTANCE CRITERIA: The contact areas between the top and bottom sections shall be mortared.
label | 973e623c-19d8-452d-841e-e41d0227c674 |  | note | REFERENCE DOCUMENTS: CP14038- AIR-DET- PM-SP- 0002¦1- cl.8.1. 9 and IFC drawing
label | 09734afd-2df3-402e-b919-48be067ecd3c |  | note | INSPECTION/TEST METHOD: Verify
label | 231aa508-520f-407d-9662-1fee58a828f7 |  | note | RECORD OF CONFORMITY: ITP Signed
label | fcaafad7-ebb2-453a-9fef-ae8e8e70436b |  | note | IP
label | d3e587b6-db74-4cff-86d9-53bb9180fcb2 |  | note | RESPONSIBILITY: Project Engineer
text | 1d66ec81-17e7-4245-9683-caaa7020312d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.8 Cutting of Pipes
label | d56d63c3-0443-4e38-8a0e-b4a69a9b20db |  | note | FREQUENCY: Each lot (where applicable)
label | 52092aec-1a75-40f1-b21f-cb07ce8e20e3 |  | note | ACCEPTANCE CRITERIA: Where necessary to cut pipes to length or to create penetrations, pipes shall be cut using appropriate method and plant. Any exposed rebar to be coated with an approved epoxy.
label | 3fe433eb-072f-4d4e-ab73-b2cfe0909153 |  | note | REFERENCE DOCUMENTS: CP14038- AIR-DET- PM-SP- 0002¦1- cl.8.1.9
label | 9745fd1e-73a1-407d-9a22-534aee0f08f4 |  | note | INSPECTION/TEST METHOD: Verify
label | f7309eb8-caf9-48b0-bab9-bcfed4ed7366 |  | note | RECORD OF CONFORMITY: ITP Signed
label | 466c45dd-7aad-42df-a21a-e3e270c62980 |  | note | IP
label | a864319b-8f39-46be-8178-90cdfc03f74a |  | note | RESPONSIBILITY: Project Engineer
text | d8736f0a-f11b-4b2d-a07b-9665664aadc3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.9 Survey As-build pick up
label | a11c1b66-185a-40e2-b40f-452de4e8111e |  | note | FREQUENCY: Each lot (prior to backfill)
label | 33fd760e-8695-4ca8-bd59-22a03efc4d61 |  | note | ACCEPTANCE CRITERIA: Pipes shall be laid to the levels and alignment shown on the drawings with tolerances of :
label | f438539f-fa62-4dbe-9c7f-d5d693b8eea7 |  | note | ACCEPTANCE CRITERIA: a) ±20mm offset of entry pit ( required to match lines of kerb or barrier)
label | fe9cf038-3f77-43da-ad96-4ebbca415a61 |  | note | ACCEPTANCE CRITERIA:b)±100mm plan location of pits other than offsets to kerb lines or barrier
label | dad4997a-88ce-4698-ae03-8380f882bc21 |  | note | ACCEPTANCE CRITERIA: c)±10mm for invert level
label | 726e4044-a696-449f-a9b5-b36762262a4d |  | note | ACCEPTANCE CRITERIA:d)±10mm departure from design grade in 10m provided min grade not less than 1:250.
label | 4f004038-9189-49db-9211-0bca97f0a00f |  | note | REFERENCE DOCUMENTS: CP14038- AIR-DET- PM-SP- 0002¦1- cl.8.1.10 IFC drawings
label | d47ebf33-9fce-46d2-95d6-6754ee6eee4c |  | note | INSPECTION/TEST METHOD: Inspect and Verify
label | fccad616-6e18-4b40-97ca-415eaa0f1f25 |  | note | RECORD OF CONFORMITY: ITP Signed
label | 2b138330-f33a-4213-a163-828d1a401f23 |  | note | IP
label | 6ba0d86d-f3fb-41a5-8d95-a71f294cd492 |  | note | RESPONSIBILITY: Project Engineer/ Foreman
text | 7afb7c52-53e6-49ce-aa63-48147b8f33d3 |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 3.10 Backfilling of trenches
label | e33118bf-b35e-40b3-9191-86228191660a |  | note | FREQUENCY: Each Lot
label | 96321b89-dc5c-400c-a0e7-1e896ba70abd |  | note | ACCEPTANCE CRITERIA: Ensure floatation of the pipe does not occur at any stage, restrain if required.
label | 3a2b4063-2893-44b2-99b0-cdc5685ae6b7 |  | note | ACCEPTANCE CRITERIA: Backfill placed on both sides of pipe equally. Concrete backfill to be vibrated to fill all voids
label | e83e2dab-1739-4467-9559-345fb3c4bfc5 |  | note | ACCEPTANCE CRITERIA: Where non trenching conditions apply, selected backfill material shall be placed for the full width of the previously placed bedding material and to a height equal to the lower of 300mm above top of pipe or design subgrade level. Ordinary backfill consisting of the best available excavated material may be used to support selected backfill material
label | 11a27e61-2a9b-4dc9-9946-16733aee2948 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002¦1-cl.8.1.10 and IFC drawings
label | ffb6443b-f801-4f49-ac71-8014fda24e63 |  | note | INSPECTION/TEST METHOD: Inspect and Verify
label | 64d73a4a-472f-41d0-8606-90e75eac54b5 |  | note | RECORD OF CONFORMITY: ITP Signed
label | 8ba61d48-c06c-4c2e-a08f-9da916d020e0 |  | note | IP
label | 6d8fb04f-fd3e-48f3-84e7-7347aebea41f |  | note | RESPONSIBILITY: Project Engineer/ Foreman
text | f02bb4e5-80f2-4c25-bd1d-6405b4cfa685 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.11 Compaction
label | f7752758-fbbe-4026-a81a-19441f8b5893 |  | note | FREQUENCY: Each Lot
label | 2367bbb0-013b-4b10-b075-d55571516f9e |  | note | ACCEPTANCE CRITERIA: Bedding and backfill material shall be placed in layers not exceeding 200mm- uncompacted thickness for non-granular material and 150mm for granular material.
label | fdef3df2-5630-497b-ab60-835a1565bcc6 |  | note | ACCEPTANCE CRITERIA: Bedding shall be compacted to refusal using hand-held mechanical plant and tested for moisture ratio and density ratio of 97% on material passes 19mm after compaction. Backfill material with 40mm or less nominal size after compaction shall be compacted to min of 97% density ratio.
label | 58bfd90d-3c1f-4775-815e-afc26d908d4f |  | note | ACCEPTANCE CRITERIA: Backfill material greater than 40mm nominal size after compaction shall be compacted using grading, mixing, watering and rolling procedure
label | d6911db3-bb98-41c4-ac71-852d0ed53386 |  | note | ACCEPTANCE CRITERIA: Bedding and/or backfill material with swell greater than 2.5% shall be maintained at a mean moisture ratio of 92% between completion of rolling and placement of the overlying layer.
label | 7ab9d032-b528-4e1e-8bbe-60e8b2191661 |  | note | ACCEPTANCE CRITERIA: Minimum of 3 tests per lot.
label | a6d2a28d-ecec-4899-bd53-a8bd966209ad |  | note | ACCEPTANCE CRITERIA: A lot shall be each layer of bedding or backfill for each drainage line from pit to pit.
label | 47434c7a-63af-4e89-9fcc-23b4984a3979 |  | note | REFERENCE DOCUMENTS: CP14038- AIR-DET- PM-SP- 0002¦1- cl.8.1.11 & IFC drawing
label | 1e2fbc78-508d-41a5-95a7-dc60f51973da |  | note | INSPECTION/TEST METHOD: Inspect and Verify
label | b8fd423b-b804-4b5f-bb3b-4c6ac6d5c1a5 |  | note | RECORD OF CONFORMITY: ITP Signed
label | 77876cb2-ea43-4416-a70c-cb9e02736792 |  | note | IP
label | f7ec01b7-32b7-4e46-9243-6b02f132f4c8 |  | note | RESPONSIBILITY: Project Engineer/ Foreman
text | de2a0206-6437-4c17-812a-a9c86a508e56 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.12 Removal of existing pipes
label | a00adc65-b398-45cf-9659-22e20a5dfbca |  | note | FREQUENCY: Where required
label | a7e825b0-c570-4253-b8a2-413d0a31b8de |  | note | ACCEPTANCE CRITERIA: Where specified, existing pipes shall be removed from existing paved areas.
label | ef282d59-02cc-43b1-b0ab-e3749f7207ea |  | note | ACCEPTANCE CRITERIA: (i)Except where the pavement under which the pipes pass is to be abandoned, the trench shall be kept to the minimum width to allow removal of the pipe or laying a replacement.
label | 70fad522-438f-4e6d-848c-4a42e73c2217 |  | note | ACCEPTANCE CRITERIA: (ii)Where pipe has been removed and the excavation is not to be backfilled, the excavation shall be neatly trimmed to slope not steeper than 1:1.5 and the ends of the trench shaped to facilitate the smooth flow of water
label | fabe187f-0de8-49fe-81b3-cdd1b1175a63 |  | note | ACCEPTANCE CRITERIA: (iii)Where the trench is to be backfilled in layers not exceeding 300mm loose thickness and compacted to refusal using hand held equipment. The final surface shall be shaped to conform to the adjoining profile.
label | fc9775d2-16e0-4ad0-b381-3de707bf2e7f |  | note | REFERENCE DOCUMENTS: CP14038- AIR-DET- PM-SP- 0002¦1- cl.8.1.12
label | 6cbc043b-ac68-45ea-b9dc-e6f4052035bf |  | note | INSPECTION/TEST METHOD: Inspect and Verify
label | 6f45fb5a-d21b-49ce-9a80-981e38dc8b17 |  | note | RECORD OF CONFORMITY: ITP Signed
label | 641363e7-c5e0-4a7d-be1c-e6e738926d8a |  | note | IP
label | 8b348b83-a331-43b7-be80-41891638a94d |  | note | RESPONSIBILITY: Project Engineer/ Foreman
text | b8ff04a2-7161-4774-8c60-8f1ae07d2929 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.1 Inspection of pipes
label | a90ce693-93f7-4179-9fb9-962b2fd90628 |  | note | FREQUENCY: Prior to constructing pavement
label | 5501a6b0-91a5-4db0-865e-13ca0f586e20 |  | note | ACCEPTANCE CRITERIA: All drainage lines constructed beneath pavements shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers.
label | b2f9157d-62a6-40d1-b7e5-a6e0245410f0 |  | note | ACCEPTANCE CRITERIA: Complete CCTV inspection of all newly constructed drainage pipes by independent testing organisation. Results to be submitted to the Principal’s Representative.
label | a94f0fd6-9a3d-4dbe-a74b-4a580ce315dd |  | note | REFERENCE DOCUMENTS: CP14038- AIR-DET- PM-SP- 0002¦1- cl.8.1.13
label | a256b7f1-b777-46d4-b340-b0b030ddf287 |  | note | INSPECTION/TEST METHOD: Verify
label | d48b611d-ece9-453d-9899-fdf9e78dd326 |  | note | RECORD OF CONFORMITY: Aconex Correspondence
label | 9cfd740c-f9c7-4cbe-8406-28cdeb9d4022 |  | note | IP
label | 8c834fb6-66bc-477c-9323-3c4204da55b4 |  | note | RESPONSIBILITY: Project Engineer
text | ba21949c-cd9a-42aa-8ee2-20a58fbfac61 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Construction Traffic
label | dbeaa99a-02b9-47c8-981a-c680d9c75c71 |  | note | FREQUENCY: Prior to heavy plant or vehicle tracking over pipe
label | 74eae0ec-3be9-41a7-8a28-8f675762ff8c |  | note | ACCEPTANCE CRITERIA: Minimum compacted thickness of cover required for construction traffic to cross the culvert or pipe:
label | e3d48948-d549-40bf-954d-feefae8a5763 |  | note | ACCEPTANCE CRITERIA: up to 35 tonne of range axle or track loading required 0.4m cover
label | 23d04165-58da-473c-9eb5-12e7a81f1dcf |  | note | ACCEPTANCE CRITERIA: 35-50tonne of range axle or tack loading require 0.5m for D<1.2m or 0.4m for D<1.2m
label | 8b5ec2c2-ceac-4d2a-b468-2662ca89b73a |  | note | ACCEPTANCE CRITERIA: 50 tonne and above range of axle or tack loading require 0.7m cover
label | 69623a44-7887-409e-82c8-0cb88a56c7d1 |  | note | REFERENCE DOCUMENTS: CP14038- AIR-DET- PM-SP- 0002¦1- cl.8.1.7
label | 62eb7ef7-3926-479b-9b0f-6113530a8fc7 |  | note | INSPECTION/TEST METHOD: Verify
label | 356cf1cc-25b8-4d25-9ca7-8d52933f25fc |  | note | RECORD OF CONFORMITY: ITP signed
label | 3550decb-b3d6-475b-bc59-1214fae38044 |  | note | HP*
label | 7992f6e5-26e6-42d3-b9e6-ff2bb0f0602d |  | note | RESPONSIBILITY: Project Engineer
text | c015a9fb-7a06-4b52-be13-56005da99428 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Records
label | ea73014b-4ba6-42d6-8d60-395d24d3ede6 |  | note | FREQUENCY: After Practical Completion
label | c16658c3-17ed-4f20-973b-4e8f778f90bc |  | note | ACCEPTANCE CRITERIA: Levels and alignments recorded in as built report.
label | f8514cdb-73e8-4609-84ee-6eaa075c1c1e |  | note | INSPECTION/TEST METHOD: Review
label | 9fe7d387-ee90-4717-beab-e62a9a6c25e2 |  | note | RECORD OF CONFORMITY: Aconex Correspondence
label | 23d48304-78ac-4488-abee-b8d5bab09f27 |  | note | IP
label | c56e7330-c962-421a-965f-8775c66e7cc4 |  | note | RESPONSIBILITY: Project Engineer
text | 61a40f4e-dd0c-4b4b-95af-a6f1be06548a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspecion
label | a72fb632-5f50-4639-b19b-190ef7cc7d5c |  | note | On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract
text | e7f9af63-293d-4c9a-9ec7-0075071d155d |  | textbox | Print Name:
text | 6bdbd055-e480-46bf-99b2-84f201bfe0d0 |  | textbox | Position:
text | 4967110c-00d8-4232-9db6-32b228f9649b |  | textbox | Signature:
checklist-sectioned |  |  | checklist | ITP 012 - Electrical and Communications Conduits | itp |  |  |  | Yes | ITP 012 - Electrical and Communications Conduits | f00113d2-6713-481a-b054-e214eb583d95
checkpoint-group |  |  | section | ITP 012 - Electrical and Communications Conduits
checkpoint-status |  |  | checkpoint | 1.1 Check for Correct Documentation
label | f1a604f0-62db-4d03-8b0d-e5804a37e4dd |  | note | FREQUENCY: Prior to commencing activity
label | 49b1f436-ef00-4754-981a-dd2b5a1061c0 |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | 790e9fbd-dc1d-4c4e-b9d8-238429431136 |  | note | Using the correct and complete set of drawings
label | 3b1dd70d-1fd6-4b08-92ae-b0bca662795d |  | note | All drawings are the latest revision
label | e37e7a1e-b951-42fc-a946-7fac85e5ea5b |  | note | REFERENCE DOCUMENTS: Drawings /Aconex Register
label | 0aed7288-5472-421c-80fb-6a017b1fd098 |  | note | INSPECTION/TEST METHOD: Verify
label | 5dd490bc-5f92-4758-bef9-0497ddd3f723 |  | note | RECORD OF CONFORMITY: Drawings and drawing registers
label | 1139dc6a-253c-42aa-a976-9186d2965128 |  | note | HP*
label | 2d98d6f2-dbc3-491f-b0a6-6c6e0d44374d |  | note | RESPONSIBILITY: Project Engineer
text | a9c7b95a-625c-4245-a6df-4e3c7476dee2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 Implementation of all measures and controls
label | 49ce4ec6-449c-483a-b467-33031f70ec2b |  | note | FREQUENCY: Prior to commencing activity
label | 25a2d879-fac3-4c5c-9a2f-b57a69632fee |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls being implemented, that is PSP, EMP, TMP, SWMS & WP
label | c7fa8b0e-91e7-4a9c-bf24-d4d2e0e33ec5 |  | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | 3ce2f75b-ac8d-495d-8664-63be2f74deb9 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | e7293fbf-389b-4f28-a93b-e98c03a05c01 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 032866e8-c5d6-44e9-b587-099dfa1a1263 |  | note | HP*
label | 0e47a0a7-f009-438f-8d1c-89a4b7502c07 |  | note | RESPONSIBILITY: Project Engineer
text | 5a986103-1235-4a4d-b90b-cbeacf8e3d24 |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 1.3 Definition of the work Area (survey)
label | fb93c551-ff98-4821-888d-a762433a66e5 |  | note | FREQUENCY: Prior to commencing activity
label | dda72b47-bad3-47d4-8b73-5add816b7e80 |  | note | ACCEPTANCE CRITERIA: Work area has been cleared and surveyed (marked on site). Limits of excavation clearly defined.
label | 8dfb15b9-6fc4-4791-94a0-5ec3d820ba67 |  | note | REFERENCE DOCUMENTS: Drawings
label | f373af59-53cb-46d4-b2e6-d64b61709ac3 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 18e4ee62-6179-42cc-a545-ab9685c51f70 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 4276af60-817a-4ed4-b70a-672e951d9568 |  | note | HP*
label | 6e037930-a05f-4a8c-9a51-0e089ab9257e |  | note | RESPONSIBILITY: Project Engineer / Surveyor
text | ac5a0956-8c3c-47f6-9369-6d8458d69d9d |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 1.4 Check Conduit Compliance
label | 94595ad9-fb3b-4a75-bca4-16eff553ecb9 |  | note | FREQUENCY: Prior to commencing activity
label | 8560fba2-050c-4706-b20e-bf1e9bef7a70 |  | note | ACCEPTANCE CRITERIA: Ensure that uPVC conduits comply with AS 1477 or equivalent AS 2053. Shall be heavy duty, orange for electrical services and white for communication services.
label | 96c9c297-fc67-46c9-86f5-9f2918106fb9 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DETPM-SP0002C cl.9.1.4 & AS 1477, AS 2053
label | 37fb54f9-b874-49ae-8590-5697e1b61a53 |  | note | INSPECTION/TEST METHOD: Verify
label | 51560ef6-7e23-456b-9dc6-a0931bede7f5 |  | note | RECORD OF CONFORMITY: Manufacturer’s certificate of compliance This ITP signed
label | e0d64356-0198-4bea-9106-f261a791f1e8 |  | note | IP
label | 354a2ce6-84c0-4996-9375-9d177382c078 |  | note | RESPONSIBILITY: Project Engineer
text | 510708ea-43e8-4525-8804-6304e8bdc6d7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.5 Check Bedding Material Compliance
label | 13fb2b40-f553-43e6-9c0f-92b5802f76ee |  | note | FREQUENCY: Prior to commencing activity
label | 306813bf-93b6-4a9d-b610-20194803d101 |  | note | ACCEPTANCE CRITERIA: Ensure that conduit bedding material is nonplastic granitic sand complying with Table 9-6 and 9-7 under Cl. 9.3.1.11 of the Works Specification.
label | 1277b594-71b3-4033-aa20-68f714e36139 |  | note | REFERENCE DOCUMENTS: CP14038- AIR-DETPM-SP0002C cl. 9.3.1.11
label | 212dec1f-8794-4d31-b931-0a79436a7c25 |  | note | INSPECTION/TEST METHOD: Verify
label | 0090bdfb-fd0d-4fc5-82d7-98e6be0479cf |  | note | RECORD OF CONFORMITY: Quarry Test Report
label | bc6b4d6e-6dd0-4804-8733-d249fe18b133 |  | note | TP
label | 96f47f27-ac43-4080-8c97-46c9c74c139f |  | note | RESPONSIBILITY: Project Engineer
text | 65063fbd-949f-489e-95ce-3b41fdfa6700 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.6 Type A Backfill Compliance (within graded taxiway/runway strips)
label | 6edcb342-14fe-4bcc-ace5-2aa7a6b3b6e6 |  | note | FREQUENCY: Prior to commencing activity
label | d512e06a-cd99-4e6a-9d20-2e0d4409d914 |  | note | ACCEPTANCE CRITERIA: Ensure to use Fill Material Type A that is totally free of organic content, topsoil, deleterious and/or perishable matter such as bricks, concrete, glass, plastic, timber, steel, or steel by-products.
label | a476572c-560c-49ac-8268-b34c0071e7c2 |  | note | ACCEPTANCE CRITERIA: SMDD 98% CBR ≥ 6%
label | d8fbb8db-20e7-4752-8c96-0b9dd6c11ba9 |  | note | ACCEPTANCE CRITERIA: Swell ≤ 1.5% If swell is greater, material may be used upon approval by the Principal’s Representative
label | 6cd24bf0-ce46-46cd-b8ec-b2ef5e5e9328 |  | note | ACCEPTANCE CRITERIA: PSD maximum aggregate size < 75mm
label | e184960b-0a1c-4ed0-99a5-cfe7049401bf |  | note | ACCEPTANCE CRITERIA: PSD passing 0.075mm between 10-40%
label | 86f7b1e0-b3d4-4311-b3cb-784c055403c3 |  | note | ACCEPTANCE CRITERIA: PI (post compaction) ≥ 7%
label | 3a23936e-fea9-4fc4-b07a-a5490c4ac420 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002C cl. 3.5.2 VicRoads Standard Specification Section 204 cl. 204.04 (b)
label | bf0e39c3-efd3-4bf0-9d14-e1e2a563c810 |  | note | INSPECTION/TEST METHOD: Verify
label | 1c9d1451-3bd4-4e88-ae37-ff5175e3ea9b |  | note | RECORD OF CONFORMITY: Stockpile Test Report
label | 237400da-d96a-46f1-b71a-17d4b463fd21 |  | note | TP/AP
label | 67184358-8bf9-42f3-8d2d-38afd4c1cd67 |  | note | RESPONSIBILITY: Project Engineer / Principal’s Representative
text | db6bd357-1a4b-4451-b178-9dee87336a20 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.7 Type B Backfill Compliance (beyond graded taxiway/runway strips)
label | 50d87df2-a4c6-47bf-9408-ac753a0c9893 |  | note | FREQUENCY: Prior to commencing activity
label | e5614a3d-8037-4d7d-adde-ef0a22196f6e |  | note | ACCEPTANCE CRITERIA: - Ensure to use Fill Material Type B that is totally free of organic content, topsoil, deleterious and/or perishable matter such as bricks, concrete, glass, plastic, timber, steel, or steel by-products.
label | c4352d5b-de36-4a4f-b4a3-46155ecfd71e |  | note | ACCEPTANCE CRITERIA: - SMDD 95% CBR ≥ 2%
label | 11fb80fb-0b12-4a96-8008-605f4ce1c7ea |  | note | ACCEPTANCE CRITERIA: - Swell ≤ 2.5% If swell is greater, material may be used upon approval by the Principal’s Representative
label | dc1c0b8d-8d22-48d4-98cd-2b08e4504576 |  | note | ACCEPTANCE CRITERIA: PSD maximum aggregate size < 150mm
label | 93151cc0-c826-4a09-824a-374b1cb69a88 |  | note | REFERENCE DOCUMENTS: VicRoads Standard Specification Section 204 cl. 204.04 (c)
label | ace54de9-5ca8-46d4-8cfe-e35caa730fd9 |  | note | INSPECTION/TEST METHOD: Verify
label | 90323747-55cc-42c7-8e18-ba4582f8ebc6 |  | note | RECORD OF CONFORMITY: Stockpile Test Report
label | 8f3a541b-8b06-4878-a222-a047f131966d |  | note | TP/AP
label | 4011a08c-980f-47c5-9f84-37261b9c2317 |  | note | RESPONSIBILITY: Project Engineer / Principal’s Representative
text | df9ae97f-ee5d-4f8f-91fe-fef8d2d175b6 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.8 Check Concrete Mix Design Compliance
label | 742e8406-769e-4acc-be49-965a9b8e993f |  | note | FREQUENCY: Prior to commencing activity
label | 434f85a7-86e1-45ce-85ce-49e7caec7322 |  | note | ACCEPTANCE CRITERIA: The theoretical mix design and results of any preliminary trial or production mixes shall be submitted in a report to the Principal’s Representative for review not less than five (5) working days prior to pouring.
label | 9a9e3f6a-faee-497b-9bbb-eb030b7beefb |  | note | ACCEPTANCE CRITERIA: Concrete encasement shall be Class D Lean Mix 5MPa/20mm
label | c8f222d7-4589-4215-9af3-b9f84a8807e6 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002C cl. 12.3.3, cl. 12.3.4
label | c50c32b0-938a-457b-b149-4b1aaea45e22 |  | note | INSPECTION/TEST METHOD: Verify
label | c4abfc61-403c-4c86-8d40-395a5d252749 |  | note | RECORD OF CONFORMITY: Laboratory Test Report
label | bae37089-3d07-405c-9703-06ff76df8cbc |  | note | TP/AP
label | d8afc529-96f7-45d6-94b2-dfb8e2c537c7 |  | note | RESPONSIBILITY: Project Engineer / Principal’s Representative
text | d68f2e09-3d16-4458-8b84-ec7ff2b6d66e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.9 Locate and prove existing services
label | 2c543e5d-0a00-4727-ada5-2531fb6355b0 |  | note | FREQUENCY: Prior to commencing activity
label | cb590aa0-54ab-49ad-a8ff-4b5dbe09bcbd |  | note | ACCEPTANCE CRITERIA: Location of services to be found and marked on the ground within the works;
label | 246c9b46-0e24-4762-a852-5d579db6dea9 |  | note | ACCEPTANCE CRITERIA: Contractor to obtain excavation permit from APAM prior to any demolition works.
label | 92796d2e-160b-41f2-a932-20a547fee3de |  | note | ACCEPTANCE CRITERIA: Services located within the works area to be exposed/proven, recorded as survey data and also on a service plan which is to be attached to the Excavation Permit.
label | f4105b4d-2420-47e1-8d7f-dd0b1176f689 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP0002C cl.9.1.1
label | 97a5018a-8149-4005-a393-954d373e9cf0 |  | note | INSPECTION/TEST METHOD: Verify
label | cb914b13-7a61-4590-88ee-4c804d0f9db6 |  | note | RECORD OF CONFORMITY: Melbourne Airport Excavation Permit
label | bd43307f-60ae-4859-8129-1505abbb1f63 |  | note | HP*
label | 874df33a-5167-4384-856c-da1840a37f47 |  | note | RESPONSIBILITY: Project Engineer / Surveyor
text | 360be2b5-ed32-43e6-8906-43dc3cfa53ff |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.10 Check for upcoming inclement weather
label | 8427eca9-862d-4c01-87e3-1717e23ac5e4 |  | note | FREQUENCY: Prior to commencing activity
label | 15baf630-91d3-4b5b-a264-4ed98833e07c |  | note | ACCEPTANCE CRITERIA: If significant rainfall is forecasted (>5mm) with a high probability (>70%), trenches must be backfilled the day prior to the forecasted rainfall.
label | 7c1fdb99-2695-4642-abf6-892c456262db |  | note | REFERENCE DOCUMENTS: FH-PM-NCR141
label | 411dade8-9f8f-4507-a748-85db827a891b |  | note | INSPECTION/TEST METHOD: Verify
label | 8bd74273-be47-48fb-a878-bafc51ac50a9 |  | note | RECORD OF CONFORMITY: This ITP signed
label | 0ad9de03-950c-4ea4-8354-54f694482bf1 |  | note | IP
label | 7cbe01d9-ebd0-424a-9776-7d6d54cfe196 |  | note | RESPONSIBILITY: Project Engineer
text | 1846ba90-8c5f-40b0-9f57-d8aa83fe188b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 Excavate Trenches for Conduits
label | dedfcfcd-3903-48b6-b15b-da4e634d6355 |  | note | FREQUENCY: Each Lot
label | b1959801-3db2-40d4-9c17-49245a99c974 |  | note | ACCEPTANCE CRITERIA: Trenches for conduits shall be excavated to the width and depth required enabling construction of the conduits to the requirements specified on the drawings.
label | 7bf7ff4e-09ba-476e-9827-20e20ef72e57 |  | note | ACCEPTANCE CRITERIA: The level at the bottom of the trench shall not be above the required level at any point
label | 50e6e36e-e2e3-4d23-b42d-07165968dced |  | note | ACCEPTANCE CRITERIA: Any over excavation under pavements shall be restored using 5MPa lean mix concrete in conjunction with the embedment.
label | 93aefbe0-ae48-4ae6-ab4a-68d62cc5cd6b |  | note | REFERENCE DOCUMENTS: Drawings & CP14038-AIR-DETPM-SP0002C cl.9.3.1.6
label | c5ad5834-c598-4fda-90e7-a943507e9087 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 2cdca996-c510-4838-a008-6f00458fa9da |  | note | RECORD OF CONFORMITY: This ITP Signed
label | 7ad18c91-391e-4abd-8f73-10fc5b93d40a |  | note | IP
label | 71062e52-ca79-4962-9108-541f4cbbbe7f |  | note | RESPONSIBILITY: Project Engineer / Foreman
text | eed10968-f792-4277-a593-71a705cb07d0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Existing services crossing new conduits
label | 32e5b390-b8ac-4c25-9f04-72da56e1e98c |  | note | FREQUENCY: Each lot
label | 1da42a25-01c7-44d2-af23-f5498dfe15ee |  | note | ACCEPTANCE CRITERIA: Only approved methods of excavation that has been approved by the Principal’s Representative shall be used.
label | d8b42d00-8b34-465a-a458-33a06346cae5 |  | note | ACCEPTANCE CRITERIA: Location, level and configuration of existing service crossing to be recorded in as built documentation prior to backfill (including CAD model file)
label | 426d63b5-625a-4080-b210-bb207243dc78 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DETPM-SP0002C cl.9.3.1.7
label | 439cbe13-c27c-4f7b-959c-93a12ac74d10 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | e3b5d5cd-19db-4f39-99a0-95577a9894a3 |  | note | RECORD OF CONFORMITY: As-built Survey Report
label | 4ee87ab7-2077-49fe-9af0-5c0615970213 |  | note | SCP
label | 09d4fa37-4ec6-48e6-8005-e433e0056ff1 |  | note | RESPONSIBILITY: Project Engineer / Principal’s Representative / Surveyor
text | 6eadd117-9bd4-486a-bd84-c3ffb9b80a76 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Laying and Jointing of Conduits
label | be5ed50b-4035-489f-8db5-e2c3a7422c0a |  | note | FREQUENCY: Each lot
label | f779d305-72a2-42fe-812a-6bf34b34508c |  | note | ACCEPTANCE CRITERIA: All conduits shall be rigidly supported and positioned by concrete or plastic spacer blocks so that no displacement occurs during backfill.
label | 81597114-9dda-49fb-ae3c-a6b983b26430 |  | note | ACCEPTANCE CRITERIA: Where conduit ends are not open to a pit, UPVC end caps shall be temporarily fitted to each end
label | 5d52e896-1148-43f5-901a-e762bbfd72fa |  | note | ACCEPTANCE CRITERIA: Number of conduits and duct route to be confirmed for conformity with design.
label | 256d797f-1fe8-4b20-ae18-5ee1a2e79a5e |  | note | REFERENCE DOCUMENTS: CP14038- AIR-DETPM-SP0002C cl.9.3.1.8
label | 248899ed-a5e4-4df8-b876-7ff41045a0cb |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 047c4bb6-d280-4a29-93d2-5a2aefa13ea9 |  | note | RECORD OF CONFORMITY: This ITP Signed
label | de0f7b20-c33f-4045-b6ee-34e754e3b4bd |  | note | IP
label | a6f3d4ef-4b3a-4609-ac55-7658afb7b24c |  | note | RESPONSIBILITY: Project Engineer / Principal’s Representative
text | c3b51b37-41f2-48dd-9d41-430eb19295f2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Survey As-built
label | 0b3d0efc-38c1-4908-9397-8add28435764 |  | note | FREQUENCY: Prior to Backfilling Each Lot
label | fd3d13a4-1a26-4547-b11e-ac6f3b825dd6 |  | note | ACCEPTANCE CRITERIA: Surveyor to pick up completed conduit runs before backfill
label | fb35cc60-2836-454a-a783-c7144f2178c0 |  | note | REFERENCE DOCUMENTS: FH QMP Section 6.3
label | b38a9f6d-1ac3-4b83-a00b-a696c5869b71 |  | note | INSPECTION/TEST METHOD: Verify / Inspection
label | df9322ae-05ee-418d-a59c-45703a4ebebd |  | note | RECORD OF CONFORMITY: Survey Report
label | 3defc9fd-2dd6-4846-afdd-0938323750aa |  | note | SCP / IP
label | cf30b17f-bc1a-4435-bca7-caf9bd8ae4e5 |  | note | RESPONSIBILITY: Project Engineer / Surveyor
text | 55989734-daa7-4fa7-a3b2-2e09a9b8b2eb |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 Pre Pour Inspection
label | 5d39f2d3-11c2-47a3-81ef-9fe475fcdc30 |  | note | FREQUENCY: Prior to Backfilling Each Lot
label | 27afaa39-54e3-4ef7-837c-6016ace81ab9 |  | note | ACCEPTANCE CRITERIA: The Contractor must provide the Principal’s Representative notice of the Contractor’s intention to place concrete, within a Lot. This must include details of the date, time and location of the proposed work.
label | 53b1da10-30e0-4f51-aba4-17dd8e8b8ad0 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002 , Revision 2 , cl. 6.7.2.1
label | a14713ae-c8b7-43a6-a0f4-1ca2e20fe727 |  | note | INSPECTION/TEST METHOD: Inspection
label | 9c24b29e-c2e2-49a2-87ea-e441efb4e77f |  | note | RECORD OF CONFORMITY: This ITP Signed
label | 2d2dcb39-2e30-4d5f-8dbd-fdf59df54b74 |  | note | WP
label | 435d6860-3929-41ce-a57d-dc6c868a8aeb |  | note | RESPONSIBILITY: Principal’s Representative
text | d2335219-a4eb-490b-8e98-631095cc0aa5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.6 Duct Encasement Material
label | 407369e9-3023-418d-b71c-2b7979776a97 |  | note | FREQUENCY: Each lot
label | f3f288e8-86b2-4e62-8d5d-d809b64417c2 |  | note | ACCEPTANCE CRITERIA: Under Pavements: Conduits to be encased in 5MPa lean mix concrete as per drawings.
label | 018599ba-9cc2-4790-871d-bbd9797bce10 |  | note | ACCEPTANCE CRITERIA: Under Grass: Conduits to be encased in compacted sand bedding. The material shall be granitic sand, non-plastic and comply with properties specified in table 9-6 & 9-7 of the specification.
label | abf6efdf-f54d-4c15-b810-f6b253607fb1 |  | note | REFERENCE DOCUMENTS: CP14038- AIR-DETPM-SP0002C cl.9.3.1.9 & cl.9.3.1.11
label | 5c7812db-81c1-47ab-a584-5f4662f8bf77 |  | note | INSPECTION/TEST METHOD: Verify
label | aee7263a-e563-4205-856a-946e8cd5575b |  | note | RECORD OF CONFORMITY: Delivery Docket and This ITP Signed
label | 6313e0a8-432e-4142-9ee7-ca2adb87aba9 |  | note | IP
label | 8e7b923d-1922-47ab-8f1e-ca38fedb8b92 |  | note | RESPONSIBILITY: Project Engineer/ Foreman
text | e93cfd4d-dd60-43aa-8aeb-4255065760d7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.7 Backfilling Conduits in Grassed Areas
label | 1e306db9-5593-4a8f-8951-19f48a88dd6a |  | note | FREQUENCY: Each Lot
label | e021e3b8-68a8-46d2-b607-9eede2e06c8b |  | note | ACCEPTANCE CRITERIA: Selected excavated backfill with layers not exceeding 225mm compacted thickness.
label | f99ae161-5778-496e-9786-1b504b1d2da7 |  | note | Within Graded Taxiway/Runway Strip:
label | 3cd277ee-fdae-4559-9b7c-59ae34c76ffd |  | note | The standard of compaction to be achieved shall be a minimum dry density ratio of 98%SMDD. Testing shall meet the requirements of VicRoads Standard Specification Section 204 for a Fill Material Type A and shall occur at the frequency of 1 test per 500m3 or one day’s work, whichever is the lesser.
label | 85eb0b4e-0a67-4bfe-ab02-7f74a7f16f59 |  | note | Outside Graded Taxiway/Runway Strip:
label | 8a7f4378-9a5a-47a0-82ee-d6222d15f8be |  | note | The standard of compaction to be achieved shall be a minimum dry density ratio of 95%SMDD. Testing shall meet the requirements of VicRoads Standard Specification Section 204 for a Fill Material Type B and shall occur at the frequency of 1 test per 500m3 or one day’s work, whichever is the lesser.
label | e9e54210-7216-47cf-9dcd-038f298a0118 |  | note | Backfill shall be to the original or design level without subsidence and without cracking at junctions with existing surfaces.
label | 192e54d9-b276-49d3-917b-4ef8fb7606f4 |  | note | Testing shall occur within a week of backfilling trenches.
label | 1061770f-fc8f-4847-bd0d-8f09358f1f91 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DETPM-SP0002C cl. 9.3.1.14 & cl. 3.5.2
label | 5b6760e7-bac4-4a13-9c27-f8de28c04d3d |  | note | FH-PM-NCR141
label | d44b7b47-308f-4df4-9da9-06e422208324 |  | note | INSPECTION/TEST METHOD: Verify
label | 1afa40f7-ac23-4f1f-97e8-fea20068c094 |  | note | RECORD OF CONFORMITY: Test Report and This ITP Signed
label | 39b61441-79cf-498b-a9ab-262811910801 |  | note | TP/IP
label | 076a456b-9657-4ac7-8336-eade185256f5 |  | note | RESPONSIBILITY: Project Engineer/ Foreman
text | b7ab1b40-0c06-4f33-bbef-b07385ea950a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.8 Conduit Markers & Warning Tape
label | fb5caac0-c64c-453e-bb43-453d70e255a3 |  | note | FREQUENCY: Each Lot
label | 721c658f-10c3-4232-82ba-fe712d83166f |  | note | ACCEPTANCE CRITERIA: Pavement edge duct markers shall be installed at the edge of pavements immediately over the centreline of duct banks.
label | 3472ee21-55a2-4676-a2f8-41f814cbb86f |  | note | ACCEPTANCE CRITERIA: Warning tape shall be of polythene not less than 150mm wide and 0.1mm thick. They shall be orange/white in colour and bear “CAUTION ELECTRIC /COMMUNICATION BELOW” or similar repeatedly in black letter not less than 30mm high.
label | e77e5616-58a9-42e0-92da-ba3ee2b3c2e0 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DETPM-SP0002C cl.9.3.2
label | 787ffe84-288b-4345-88ca-6eaa80ca0fcf |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 8a300d42-51ac-4d36-92a0-e4f4f98555c8 |  | note | RECORD OF CONFORMITY: This ITP Signed
label | cb4dabca-5457-4f5d-951c-e4dbdb2e6bda |  | note | IP
label | b8205616-3f53-49c7-bec3-f7163164db8d |  | note | RESPONSIBILITY: Project Engineer / Foreman
text | b1fe70eb-1eb0-48d3-9104-3d85c46dcf09 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.9 Conduit Draw Chord
label | 84b9ee61-3165-4ad9-a00d-58be73c62cfe |  | note | FREQUENCY: Each Lot
label | 1a035798-3e3d-4a65-868e-196ddd5eba39 |  | note | ACCEPTANCE CRITERIA: Each duct way in each duct bank shall be fitted with a single unjointed length of draw cord of a length equal to the length of the duct plus 4m. The draw cord shall be polypropylene rope and be 6mm in diameter, blue in colour. The ends of the rope shall be coiled at the bottom of each pit or wound around a stake.
label | b9724820-47a3-4007-bb19-c4f4d121057b |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DETPM-SP0002C cl.9.3.1.13
label | 7798b28b-0749-4f15-b816-57f4e4ac6357 |  | note | INSPECTION/TEST METHOD: Visual
label | 8f936437-20a4-4f4a-81d2-c8f012ee2d89 |  | note | RECORD OF CONFORMITY: This ITP Signed
label | d76c1c91-c9e1-4076-a094-2d47b1d5359a |  | note | IP
label | ada4445b-c496-4121-87c6-522ae48047d6 |  | note | RESPONSIBILITY: Project Engineer / Foreman
text | 7e164d5e-8a43-4a41-a829-378b28dbc7ef |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.11 Checking Duct Banks
label | 8428fe98-1fdf-408f-b3b7-eb47ce1c58be |  | note | FREQUENCY: Each Lot
label | 7927cd0b-46a8-4c2a-8327-3c81185748c0 |  | note | ACCEPTANCE CRITERIA: After stripping of end forms following installation, the duct bank shall be checked by passing a mandrel (not less than 300 mm long and having a diameter of not more than 6 mm less than the diameter of the conduit) through each way.
label | 620ccce9-a0cd-423a-8652-a843659cac5c |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002C cl.9.3.1.12
label | 77971585-9bcc-4c0e-af32-52c488530af6 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 764f18fc-36a9-4936-a0a1-d55adb1e59de |  | note | RECORD OF CONFORMITY: This ITP signed
label | 2b23f9f5-7f59-4323-942d-7196182c176b |  | note | HP
label | b5d2554e-6b2a-462b-8ce3-71f6ed0ec697 |  | note | RESPONSIBILITY: Project Engineer / Principal’s Representative
text | 5299d15e-74c8-4754-a0a2-849b6c3da19d |  | textbox | Date Completed:
holdpoint |  |  | signoff | Hold Point
checkpoint-status |  |  | checkpoint | FULTON HOGAN FINAL INSPECTION - The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications
text | 460b8c88-5b13-4607-b9fc-07a4a0b73514 |  | textbox | Print Name:
text | 6a80032f-a878-4a2b-a0d3-482ad3f36128 |  | textbox | Position:
text | 44b0d64c-eaca-45a7-921a-d4c3fe2ee9ec |  | textbox | Signature:
checklist-sectioned |  |  | checklist | ITP 023 - Pit Raising & Modification | itp |  |  |  | Yes | ITP 023 - Pit Raising & Modification | f7e8a711-ac8c-4239-b7e6-b5f8e52638c6
checkpoint-group |  |  | section | ITP 023 - Pit Raising & Modification
checkpoint-status |  |  | checkpoint | 1.1 The current revision drawings are being used including subcontractors copy
label | cdae945b-097d-47f5-9562-4da5e508b839 |  | note | FREQUENCY: Prior to commencing works
label | 3b3f8dab-67ba-482b-a65d-268e09d2f123 |  | note | ACCEPTANCE CRITERIA: Current revision drawing is being used including the subcontractors copy. Current revision to be obtained via Aconex.
label | 19f46279-1466-49b4-8685-e1eed6a8b6c2 |  | note | REFERENCE DOCUMENTS: Drawing & drawing registers
label | ef765091-5f20-4c71-88ea-2f021cb15596 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | af906c5a-f0db-4f0c-bae4-629e0e98305e |  | note | RECORD OF CONFORMITY: Up to date drawings and this ITP signed
label | 03bafce7-b684-4d97-a4c2-f773aa5fc27a |  | note | HP*
label | 34c0dd60-280a-425a-9b34-5d9e5efe0d37 |  | note | RESPONSIBILITY: FH Engineer
text | 78594110-d88f-4565-8bc7-8956964f06fc |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 Setting out for miscellaneous structures
label | 9bbccc20-c2f9-4424-b2d9-00cbc1063940 |  | note | FREQUENCY: Prior to start
label | 32cd7bcd-aabe-4b58-b8ea-f2645d906bc2 |  | note | ACCEPTANCE CRITERIA: Conformance with Jacobs for Construction Drawings and pipe penetrations in the correct locations.
label | c68aced1-a7dd-4f79-9be5-f1695b2a81e4 |  | note | REFERENCE DOCUMENTS: WP023
label | 43bcf14b-e4bf-4b71-b02e-c3ed2acf579e |  | note | INSPECTION/TEST METHOD: Verify
label | 5c96bfaf-5a65-44c9-85ca-6583282c44e6 |  | note | SCP
label | 9d07d014-056b-4c32-bf4c-a85153c99e2b |  | note | RESPONSIBILITY: FH Engineer/Surveyor
text | 934702fa-987a-4d98-b6a0-99bcdeb1baf1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 Materials & Source Approval
label | 09a25a99-08ac-46a1-b502-fcf2d28bbd1e |  | note | FREQUENCY: Pre commencement
label | 92df1172-6eb2-443e-af26-0a3187d851ff |  | note | ACCEPTANCE CRITERIA: Details submitted to Superintendent regarding: • Ready mixed concrete supplier; and • Test Certificates demonstrating compliance of the reinforcement with the requirements of AS 3600 • Concrete mix shall be submitted to the superintendent for approval. • The theoretical mix design shall be submitted to the Principal’s Representative for review not less than 5 working days prior to pouring • Concrete for pits shall be specified in drawings, typically it will be as follows: o 40 MPa/80mm Slump/20mm Agg
label | e12b9bde-b160-4a37-a025-103527369a00 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002-D-8.2.1
label | 50c16962-9ea0-420c-aa5e-16295acf3239 |  | note | INSPECTION/TEST METHOD: Verify
label | 703e1cb8-3e3e-423f-bbdd-c6c2d299027e |  | note | HP*
label | cd969f4f-320c-436d-8f6a-865de04ad194 |  | note | RESPONSIBILITY: FH Engineer & Jacobs
text | 930e0f67-e41a-4e95-9e96-361ccb2d107c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Materials & Source
label | 478a795a-2459-43c7-9270-7ac4fcea8b11 |  | note | FREQUENCY: Each delivery
label | d4dd498d-aaf5-4490-ad84-f139d665040d |  | note | ACCEPTANCE CRITERIA: Pit covers, grates, lids and lintels shall be as specified on drawings and installed as per manufacture’s recommendations.
label | 66bb4f43-b526-4e1f-96b0-14e0c3767769 |  | note | REFERENCE DOCUMENTS: WP 023 CP14038- AIR-DET-PM-SP-0002-D-8.2.3C
label | 8af34702-a5c8-44ed-a284-7af6304b847b |  | note | INSPECTION/TEST METHOD: Verify
label | a7c17e61-3770-4e74-8292-8f269f5be28f |  | note | IP
label | 8aaa414e-19f2-45ab-9539-fbe0af5b52b1 |  | note | RESPONSIBILITY: FH Engineer
text | 76d3e434-1af1-45c2-bde8-7d0cbfad492d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Acceptance Covers/Frames/Grates
label | 1b0e4a22-2811-41fc-ac16-1406eb57d508 |  | note | FREQUENCY: Prior to start
label | 153b5ef2-0283-43b4-bd57-e9ac992bf5cc |  | note | ACCEPTANCE CRITERIA: All Pit covers shall conform to Class G- Airside standards.
label | 5731cf03-15fd-48b6-b9d8-e60f7aca99d7 |  | note | REFERENCE DOCUMENTS: AS3996500.3 CP14038-AIR-DET-PM-SP-0002-D-8.2.1
label | 90cf0ad6-008f-4c3e-8974-0c850def42c2 |  | note | INSPECTION/TEST METHOD: Verify
label | c67d6011-a34b-47d9-b574-2995d37a5b89 |  | note | HP*
label | bc20c834-a258-48ad-bebd-8b15d9302020 |  | note | RESPONSIBILITY: FH Engineer
text | 40608748-6a89-4374-86dc-d663596f904f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Reinforcement
label | 9539c831-1756-4172-bea5-1a989952e670 |  | note | FREQUENCY: Each lot
label | 2ab496c0-20a1-4dba-ad69-ec9b1807269f |  | note | ACCEPTANCE CRITERIA: Reinforcement shall be grade 500N hot rolled deformed bars unless noted otherwise on drawings. Hold Point Test Certificate demonstrating that reinforcement will comply with AS 3600 requirements constitutes a Hold Point.
label | 3628e0e8-95aa-4d3e-af0c-b3eb2ea0ad3b |  | note | REFERENCE DOCUMENTS: AS/NZS 4671 CP14038-AIR-DET-PM-SP-0002-D-12.3.7 WP 023 VicRoads 611.03
label | 95e6b884-2c2d-4a17-be48-4dde465ef6e6 |  | note | INSPECTION/TEST METHOD: Verify
label | b8f6f644-3165-492e-a294-b3de416dfec3 |  | note | HP*
label | c933ac2f-bb02-4f42-9da0-6d4bb2100acf |  | note | RESPONSIBILITY: FH Engineer
text | d5927174-7067-4e4d-8855-69d05aa9f75d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.1 Excavate Pits
label | ba6ead84-b247-4147-88c1-15b18c8542ee |  | note | FREQUENCY: Each lot
label | cc233e7a-87d1-428c-a047-1e9b235b21f9 |  | note | ACCEPTANCE CRITERIA: Excavation depths where required will be as per specified on drawings as per survey set out
label | ed53e779-5196-4da2-9c92-a8ee0471121e |  | note | REFERENCE DOCUMENTS: CP14038-AIR-SCH-CI-RP-0004 Rev B CP14038-AIR-DET-PM-SP-0002-D-12.4.1 CP14038-AIR-DET-PM-SP-0002-D-8.2.4 WP 023
label | a52351f8-992b-4308-b95b-1f19b7903e15 |  | note | INSPECTION/TEST METHOD: Verify
label | e649fbf6-40ba-46da-99cd-2dcfb2597ec4 |  | note | IP
label | ccff7144-a11c-49c3-9add-df4175b85378 |  | note | RESPONSIBILITY: FH Engineer
text | 6a7eef78-de10-4ded-898c-49901f7d8c51 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Scabble Pits
label | 0759f703-8e9b-4a3d-a4c9-2f0f697fec07 |  | note | FREQUENCY: Each lot
label | 4c4f27db-762c-4e16-a182-ffe4c5c26e2c |  | note | ACCEPTANCE CRITERIA: Existing wall to be broken back to 100mm minimum below existing concrete level Surface of walls to be modified shall be scabbled and aggregate exposed. Ensure surface is clean and dry prior to concrete pour.
label | 74bbeafa-240b-4748-85eb-c8daaf67838d |  | note | REFERENCE DOCUMENTS: WP023
label | c99907e4-9a4d-47a2-a66d-0fe7e7027fb1 |  | note | INSPECTION/TEST METHOD: Verify
label | 56d79445-9891-402b-a06b-1fe864738419 |  | note | IP
label | 26099522-47b6-43a8-a251-b32e717f842b |  | note | RESPONSIBILITY: FH Engineer
text | b5c708b8-8412-4fed-9976-95124a260665 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 Formwork
label | 023917af-81ba-4e91-a036-6159297ab3b8 |  | note | FREQUENCY: Each lot
label | 7bc1ac6c-a181-4174-9401-e974a5386670 |  | note | ACCEPTANCE CRITERIA: Formwork / Reverse Forms shall conform to shapes, lines, levels and dimensions of the concrete shown or indicated on the Drawings. Forms shall be chamfered, bevelled or filleted at external corners, typically having a 20mm
label | 90a1be8e-c2d5-433d-a20d-5a2b686d5820 |  | note | REFERENCE DOCUMENTS: WP023
label | 45735e58-0d5a-417a-bee1-0b5d32a84f77 |  | note | INSPECTION/TEST METHOD: Verify
label | 7701ef2d-348d-442b-b36f-3cc6309fce11 |  | note | IP
label | 1d1252a1-c6ff-475a-aa67-5d87b54ee51a |  | note | RESPONSIBILITY: FH Engineer/Surveyor
text | 7afa46e7-c468-49d3-950c-6848499b798c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.1 Reinforcement Installation
label | 8f6b3994-7a8c-43ac-b2da-e79153734b1b |  | note | FREQUENCY: Prior to concrete pour
label | 5b0204c8-c7df-43f0-a63a-f1b059f829b3 |  | note | ACCEPTANCE CRITERIA: Holes are to be drilled into the exposed concrete as per the positions and spacing’s specified in the drawings. Reinforcement to be epoxied or tied into position as per drawings Pre-pour checklist
label | 40bce742-593e-44a0-8d43-7ccd04e5ea86 |  | note | REFERENCE DOCUMENTS: WP 023 CL006A
label | dd47ed54-e1e5-4e25-8ca5-cf1a3054b061 |  | note | INSPECTION/TEST METHOD: Inspection
label | d5111987-ff8c-469b-9cbb-ed9f8a1da10e |  | note | IP/HP*
label | 388d7a93-6de5-4e60-975e-948d82ba8cb5 |  | note | RESPONSIBILITY: FH Engineer
text | 6a9792fc-14eb-455b-b26d-52bc1e67d465 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.1 Pre-Pour Inspection
label | bb5b550a-6601-4436-8f11-9a5eafe86849 |  | note | FREQUENCY: Prior to concrete pour
label | 93175bef-20a3-469e-a3cb-909d9620efe6 |  | note | ACCEPTANCE CRITERIA: Superintendent to perform final Pre-pour inspection. Fulton Hogan to notify Superintendent 24 hours in advance to pour concrete to enable the formwork and reinforcement to be inspected and approved. For cast in lids, check correct level and cover. For grouted in lids, refer to ITP027
label | b47f2974-1309-4bc4-b439-9ffd9cd31066 |  | note | REFERENCE DOCUMENTS: WP 023 CP14038-AIR-DET-PM-SP-00002-C-12.4.8 CL006A
label | 9d0deb51-e7a8-48e0-ae21-06d3091033c0 |  | note | INSPECTION/TEST METHOD: Inspection
label | 0341704c-a366-485e-b9a1-8645295a21fe |  | note | AP
label | bafd3ac8-9969-4e08-9848-b170e7957014 |  | note | RESPONSIBILITY: FH Engineer/Superintendent
text | d4e85cae-c896-4663-b45e-ae810d79f3ac |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Pour In-Situ Pits
label | ad0d2521-0c29-4a65-915a-d482f50d7b51 |  | note | FREQUENCY: Each lot
label | ef675d94-6fe5-4571-9e97-7cb018fe0b50 |  | note | ACCEPTANCE CRITERIA: Concrete shall be placed within 90mins from batching. All concrete supplied for concrete structures shall be subject to project control testing in accordance with AS 1379.
label | 627fffc1-75c5-4b59-a41e-6ee13349c5a4 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002-C-12.4.14 WP 023 Concrete Pour Record Sheet Field Test Docket/Delivery Docket
label | 9a649c11-113d-4ed9-90e3-c6f391f5381a |  | note | INSPECTION/TEST METHOD: Record
label | d4c2bc6e-867b-4a6a-89fe-1d30245e56fd |  | note | HP*
label | 5d8c3a7c-ce09-4e97-b330-70bd706647f3 |  | note | RESPONSIBILITY: FH Engineer
text | b6d80803-68a5-4a19-a9c1-3b1c0433767b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Concrete Testing
label | 495f1e4b-4b29-4187-be95-3dd978b6346e |  | note | FREQUENCY: Each lot
label | 0bf48059-5425-4d74-a296-b707305b6854 |  | note | ACCEPTANCE CRITERIA: Pit - Each pour 1 slump & 3 cylinders to be cast per lot.
label | dab3e295-59af-4f9c-9db4-ccf89cb8e523 |  | note | REFERENCE DOCUMENTS: WP023 CP14038-AIR-DET-PM-SP-0002-C-12.4.14 CL006B Drawings
label | b7b3dff0-3e4b-4e7b-afa9-697282bc1d7c |  | note | INSPECTION/TEST METHOD: Record
label | a9d7edbc-9a3d-40f2-b555-75d01565eef5 |  | note | TP
label | 68777e98-bd19-40b4-af68-86eaf3f5e549 |  | note | RESPONSIBILITY: FH Engineer
text | ac1b3eb4-33d1-4e12-89cd-0079198a1b64 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Concrete Traceability
label | 44204b6d-233c-4d74-b67d-083d46621f41 |  | note | FREQUENCY: Each lot
label | 0204f92a-8009-4201-8198-368ed9037c19 |  | note | ACCEPTANCE CRITERIA: All concrete delivery information to be recorded on CL 006B – Concrete Pour record sheet.
label | aff6e762-e3c8-483b-bfbb-d082c6284afa |  | note | REFERENCE DOCUMENTS: WP 023 CL006B
label | 25c41b45-2369-41ce-a92d-8c064b8d23b1 |  | note | INSPECTION/TEST METHOD: Record
label | c83ea3fb-fe96-4d18-8233-d3eb6069677e |  | note | IP
label | a5819b62-caf3-4243-ad2e-a8a39fc8419c |  | note | RESPONSIBILITY: FH Engineer
text | 974656ed-c229-4cb3-8c13-03fb8b2133c2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Finishing & Cutting
label | e1c1adfb-f791-4e81-8ce3-edb01127539c |  | note | FREQUENCY: Each lot
label | b1715bbc-7bf0-410d-b764-9d081cab67f2 |  | note | ACCEPTANCE CRITERIA: Concrete to be vibrated to ensure compaction and air voids removed. Screed finish to top surface of concrete Concrete shall be moist cured or coated by an approved membrane curing compound for a period not less than seven days unless approved by the Superintendent.
label | c3d9ee76-e366-4028-b417-d27ec1bf15ef |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002-C-12.4.11-12.4.12 CP14038-AIR-DET-PM-SP-0002-D-8.2.9
label | 938b7429-ad7d-4e10-bbdb-851b93aee5f4 |  | note | INSPECTION/TEST METHOD: Verify
label | f1f9bcf0-faac-4e17-bb57-fea6e2589f92 |  | note | IP
label | 5189eab0-f299-414e-978a-296a3d30fd8b |  | note | RESPONSIBILITY: FH Engineer
text | a0c84123-7119-4e77-9004-a3c2be84c791 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Pit Lid Frame & Covers
label | 5fbf0ab3-a101-4450-9ad8-7ec07415a874 |  | note | FREQUENCY: Each lot
label | a45772c3-74a2-4c7b-bdb9-980ef238d83b |  | note | ACCEPTANCE CRITERIA: Frames for pit covers shall typically be cast into the top of the pit, however may also be grouted in as approved and as per the locations instructed by the superintendent. For grouted in lids, refer to ITP027
label | 8bf04b5c-5f91-4beb-91b1-4c055824e0a6 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002-C-8.2.10 WP 023
label | 578c87b9-7e13-45c0-8b99-fdc1d2c50ccb |  | note | INSPECTION/TEST METHOD: Verify
label | 42299ae2-a2d8-483c-b3da-69aa125e387a |  | note | IP
label | 852038cf-be4e-4e02-9344-99b106cb6e9c |  | note | RESPONSIBILITY: FH Engineer
text | be23733b-3e2c-4cbf-bad7-76414044f856 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 8.1 Removal of Formwork
label | 5efdda8b-23c9-4159-bb88-c214b6c0a9a1 |  | note | FREQUENCY: Each lot
label | d3c9086e-539d-4f1a-9a5f-76fa72dd4e79 |  | note | ACCEPTANCE CRITERIA: Forms shall remain and be maintained firmly in place until the concrete has attained the necessary strength to support its own weight. Refer at attached table 12-4 Form Removal Information
label | eb5416a6-310a-4a78-a917-43e379e92d67 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002-C-12.4.5
label | 28138a02-3ec4-4cb7-91ca-a192dc05e714 |  | note | INSPECTION/TEST METHOD: Verify
label | b099a4dc-7bc5-4f98-97c1-3b6242a4a42d |  | note | IP
label | d78a68b5-bfb3-47de-8c1f-cd4871da7888 |  | note | RESPONSIBILITY: FH Engineer
text | 7fff09f2-ba1e-4216-b613-cee221b31762 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 8.2 Finishing & Cutting
label | e36fb465-a740-40c0-b75c-b8ca014995de |  | note | FREQUENCY: Each concrete pour
label | 6477f6dd-47e6-4985-8113-77965dc81fb2 |  | note | ACCEPTANCE CRITERIA: Check finish behind formwork. Defects such as honeycombing or cracking to be recorded and repaired as per Superintendent’s direction Post Pour Checklist.
label | 67fa0910-74af-4954-92b5-8db0790ce8eb |  | note | REFERENCE DOCUMENTS: WP023/CL006C
label | 6b8c56ed-e6e5-42cd-a83c-deceac722f39 |  | note | INSPECTION/TEST METHOD: Verify
label | 6541e1ba-a28f-41be-bb62-0d78caa5a36f |  | note | IP
label | 8e2652d0-f16e-4dec-b469-5573fa79276f |  | note | RESPONSIBILITY: FH Engineer
text | 1aa0fb7f-2251-4bff-b1f2-8b12f6800ae6 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 8.4 Quality Report/Concrete Test Results
label | cdb896bf-c58e-490d-8f9e-4049827781ec |  | note | FREQUENCY: Each lot
label | 6590b67c-8444-41a0-acfe-b5f45b3c3eb2 |  | note | ACCEPTANCE CRITERIA: All quality control and concrete test results obtained and attached to ITP. All quality control and concrete test results submitted on Aconex Check all results compliant as per specifications
label | e61946e2-4872-42d8-991e-da1aee1eb173 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002-C-12.4.14
label | d34d1787-316c-4898-8374-a61767ea497e |  | note | INSPECTION/TEST METHOD: Verify
label | 1fd1b17f-6d9d-4888-b166-25e9888b4e0d |  | note | TP
label | 314e85ec-4cca-4780-b97a-1ba6b3dd5f5c |  | note | RESPONSIBILITY: FH Engineer
text | 5c0d0227-1024-4e66-8d09-ee9749fa750e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | FULTON HOGAN FINAL INSPECTION - "On behalf of Fulton Hogan, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract".
text | d76272d5-cd42-4ffc-9453-85ba5013d40f |  | textbox | Name:
text | b5330a11-1f62-4c3e-b3ab-9b44ef70e39d |  | textbox | Position:
checklist-sectioned |  |  | checklist | ITP 013B - Aeronautical Ground Lighting (AGL) – AGL Cabling Works | itp |  |  |  | Yes | ITP 013B - Aeronautical Ground Lighting (AGL) | fa74d09d-cf66-495d-96fe-115761b8fbd0
checkpoint-group |  |  | section | ITP 013B - Aeronautical Ground Lighting (AGL) – AGL Cabling Works
checkpoint-status |  |  | checkpoint | 1.1 Check for correct documentation
label | 4e61c311-8ea3-488b-87dd-54cd56471e4b |  | note | FREQUENCY: Prior to commencing any activity
label | fe7fae9b-6d53-4c41-9232-10fec9a11007 |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the latest and complete set of drawings
label | 0c99b9ea-a2dc-474e-b64c-7837b52a4fc5 |  | note | REFERENCE DOCUMENTS: IFC Drawings
label | 9f96d6d2-c0bb-4014-a8f7-01796fa1b9e1 |  | note | INSPECTION/TEST METHOD: Verify
label | 57c66114-8d81-4a6d-baaa-fd704da504fe |  | note | RECORD OF CONFORMITY: Drawings
label | 0da9efe3-2147-41c8-b5a1-884523ddae89 |  | note | IP
label | 9039c139-ea67-4942-94ef-86dc1d40025c |  | note | RESPONSIBILITY: Project Engineer
text | ed7f0bbc-3d6a-45e4-8f47-3fe63146efdf |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 Implementation of all measures and controls
label | 6ad4ed81-898f-4ef8-8744-c5fb9c2d6d18 |  | note | FREQUENCY: Prior to commencing any activities
label | 4ff831f4-c4e7-4355-8636-f57bd7b0b95d |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is PSP, EMP, TMP, SWMS & WP.
label | 598c6d86-2355-487f-8a94-d840ce201fd4 |  | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | 71c54676-bbdb-4c39-8391-d24336e8118a |  | note | INSPECTION/TEST METHOD: Verify
label | 548ed198-0c9f-46d6-9e74-680b69256924 |  | note | RECORD OF CONFORMITY: Site and Office Inspection
label | cd90bd3d-a9c7-45b6-8db6-01649314a395 |  | note | HP*
label | 3e455119-8c02-4983-806b-5f69b843aa92 |  | note | RESPONSIBILITY: Project Engineer / Site Supervisor
text | e9698c73-c42e-4d50-b3ed-e09970273b26 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 Existing Service Location
label | dc12e205-7468-43ef-8465-5c7a4fd3b498 |  | note | FREQUENCY: Prior to Start
label | 38e7ee56-f911-4120-b86b-744f1eb7173b |  | note | ACCEPTANCE CRITERIA: Prior to installing any fittings, location of all existing services to be identified and marked onsite.
label | d8fcee9c-09e8-4d38-8358-2ffc4f926b16 |  | note | REFERENCE DOCUMENTS: SWMS
label | d686d359-167c-4069-825a-cebfa9daabfb |  | note | INSPECTION/TEST METHOD: Verify
label | d4247ca7-9744-418b-8dd5-7e59995314b6 |  | note | RECORD OF CONFORMITY: APAM Excavation Permit
label | 80ff9f4b-4c1b-471e-aacf-42eb36b23d88 |  | note | HP*
label | 74414d8e-efdc-487c-9425-6893e5ea84ca |  | note | RESPONSIBILITY: Project Engineer/ Site Supervisor
text | a8aa46b4-8cac-40d3-9a67-75d3ad58bffe |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.4 Trial AGL Joint
label | e4769835-fa38-4d80-9e89-8c34846d50e1 |  | note | FREQUENCY: Prior to Start
label | a26dca60-2dd3-4736-a8cb-107175c9f717 |  | note | ACCEPTANCE CRITERIA: Prior to commencement of AGL cabling works, the works contractor is to demonstrate proficiency in making airfield joints to the satisfaction of the Airfield Maintenance team.
label | 819bebe0-2258-4b45-951e-fdc924cf1fd5 |  | note | The accepted joint shall be the benchmark for all further joints and is to be submitted to the Principal’s Representative.
label | f53667e4-8256-468d-9677-f08d241b645c |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002C cl 10.1.3
label | 7215db05-6890-4bbd-9415-bdab8b1e456e |  | note | INSPECTION/TEST METHOD: Verify
label | 97f379bb-08f7-4e9f-8d8d-41d634cd6e75 |  | note | RECORD OF CONFORMITY: This ITP Signed / Aconex
label | 56d12581-8b9d-432b-b580-7cbd22563071 |  | note | AP
label | 92e84b4c-f0d2-4358-a71e-f65116dbd39b |  | note | RESPONSIBILITY: Project Engineer / Principal’s Representative
text | 8295ae88-83c3-489a-9d1f-90d8c60156f3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.5 Cable Route
label | fe060a3d-65ba-46ce-8930-bace27f40b7b |  | note | FREQUENCY: Each Lot
label | 73f79110-07bd-4dd3-8722-41fd1c45ac3a |  | note | ACCEPTANCE CRITERIA: Cabling route installed as per path shown in construction drawings.
label | 89cca9f0-eb0a-4b23-973e-441efaaf7913 |  | note | See relevant lot from ITP 012 – Electrical and Communications Conduits for cable route.
label | 5a770f4e-21b9-4c7d-8e0d-bb14314f55a3 |  | note | Under new pavements, secondary cables shall be installed in straight duct in un-jointed runs between seating pot and the pit.
label | c618f366-5f7d-463a-8b87-e3e952601a0d |  | note | REFERENCE DOCUMENTS: ITP012 – Electrical and Communications Conduits
label | f4e9b807-fc08-4181-b029-985be95f99f1 |  | note | INSPECTION/TEST METHOD: Verify
label | 870e58eb-8d37-4c2d-95c2-333e2387a495 |  | note | RECORD OF CONFORMITY: ITP012
label | 882c2471-372a-4c3c-a203-fda175260b6f |  | note | HP*
label | 732c13f6-93d3-4b25-988c-37ccbc6e0312 |  | note | RESPONSIBILITY: Project Engineer
text | eaf59536-b427-431f-aa5a-0a003763f417 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 Primary Cable
label | 89f7a915-2e46-4a1e-8551-ff72fcd7bf89 |  | note | FREQUENCY: Prior to Start
label | 76ea6d6e-6932-4a9a-9477-22be80a7eac9 |  | note | ACCEPTANCE CRITERIA: New Primary cabling shall comply with the requirements of the FAA advisory circular 150/5345-7 and ICAO Aerodrome design manual part 5.
label | e1780008-8b19-45b4-afc8-0307f38ba38d |  | note | - 6mm2 cable with polyethylene jacket and copper tape screen
label | aad62fe9-b3ec-4fc0-9614-d99239452fda |  | note | - Rated for 5000V
label | 5aa87e4d-49d8-431a-98f4-4cc94e361078 |  | note | - 7 Strands
label | 97791c25-a349-42bd-9540-03b91ef7c3af |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002C cl 10.4.2
label | 621a83d6-7e6e-4312-b10a-22fa61062482 |  | note | INSPECTION/TEST METHOD: Aconex
label | dd425005-6bc5-43d2-8653-297b184a8ab7 |  | note | RECORD OF CONFORMITY: Datasheet
label | 18143305-92af-45ba-ae04-acc90c58e4e7 |  | note | HP*
label | c6c38701-7dc5-4e0b-bfe7-8c561bee6b5e |  | note | RESPONSIBILITY: Project Engineer
text | 53393ab6-19f9-4f19-8528-3c12bc703489 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Secondary Cable
label | dd26650c-2d0b-42d5-9f0e-978e79e5937e |  | note | FREQUENCY: Prior to Start
label | 101ffdaa-cc15-4169-9faa-4d9f3d21a174 |  | note | ACCEPTANCE CRITERIA: New Secondary cabling shall comply with the requirements of the Department of Transport YSVE4005 issue 2, V5-2842 and ICAO Aerodrome Design Manual Part 5
label | b52da861-7026-448d-9804-72e3d1d08f5e |  | note | - 6mm2 Cable with black nylon jacket.
label | 8eede04a-f8ba-402b-b88f-56b80324475c |  | note | - Rated for 600V
label | ee34cde9-2e24-4db8-8d1f-dd2fb731408f |  | note | - 56 strands
label | 6567a05d-6028-4a61-8f6d-3145c2e87eac |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002C cl10.4.4
label | a4562a42-13a5-4972-8b3c-1fd4a8e2bc42 |  | note | INSPECTION/TEST METHOD: Aconex
label | 199af5cb-d148-4d60-b440-d5a93f32dcba |  | note | RECORD OF CONFORMITY: Datasheet
label | ac1e068f-d966-463e-add4-d93024435729 |  | note | HP*
label | 92da07e1-280a-4064-ab8d-6a916498816f |  | note | RESPONSIBILITY: Project Engineer
text | 05da7f54-a081-4624-b0bd-d16f4d984299 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Cable Connectors
label | c82d0aec-d0f8-42c0-94e4-cca37aa659c0 |  | note | FREQUENCY: Prior to Start
label | 2ffa6594-8a9d-4c23-9266-bac8cd45a196 |  | note | ACCEPTANCE CRITERIA: All cables will be jointed using heat shrink cable joint kit & Must comply with the requirements of FAA advisory circular AC 159/5354-7D (L-824)
label | c601036e-3c47-477e-ae03-22e32f53b806 |  | note | Primary plug and socket connections to be:
label | 52060525-4727-4ae6-9043-e2e28a46d9c7 |  | note | - Plugs to be L-823 Class B type 1 Style 3
label | 8ea97be9-9046-4348-ab3e-7eb497304de5 |  | note | - Sockets to be L-823 Class B Type Style 10
label | 40cfd381-331e-458d-b8b5-7943749a9d81 |  | note | Secondary plug and socket connections to be:
label | 3fb1b201-20a3-46a2-806a-b4d18807d412 |  | note | - Plugs to be KDC503 style 1 with fly leads
label | 853471dc-f2e1-480d-8774-59e0fe1d5da0 |  | note | - Sockets to be KDC503R style 7 with fly leads
label | 91f93fed-7c7f-4593-bcfe-2f6cd217910b |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002C cl10.4.2
label | ffe3d699-b957-4860-9c24-3e07a5f0c7c6 |  | note | INSPECTION/TEST METHOD: Aconex
label | fc353ffc-edb0-4683-a504-ff370935e365 |  | note | RECORD OF CONFORMITY: Datasheet
label | 743c6e85-9fcf-4a39-a2b4-9e26033e8caf |  | note | HP*
label | 09d22c4b-3faf-4094-be1d-8c8614afcf3e |  | note | RESPONSIBILITY: Project Engineer
text | 97ad1f18-4965-4d23-9708-30eea6faf95b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 CCR
label | a55e6440-a988-4064-8aab-aa6990e43499 |  | note | FREQUENCY: Prior to Start
label | 0b33052f-e2d0-43ae-ba94-decbbf35b98e |  | note | ACCEPTANCE CRITERIA: All CCR’s to be 7.5kVA and be from the ADB Safegate SafeCCR Range.
label | 1cbcbe23-dee0-47f1-bd31-51c4f31f7501 |  | note | CCR’s shall have the following installed
label | 85623ee9-adbc-4686-a816-8062a4b27a61 |  | note | - Inbuilt two circuit selector for two circuits
label | 068c80f5-49bf-48d4-894f-0120cb1bd367 |  | note | - Earthing fault monitoring
label | 5842bd27-8b36-4710-8cd9-f9aab76b2c20 |  | note | - Surge Arrestor
label | de75a5c4-adfb-41e6-a9e6-75d97fa4ff0a |  | note | - Wheels
label | ccd06c72-0810-4d40-9ec4-a0a34c54315e |  | note | - In Built series cut out switch
label | 2ce7fa68-0e72-48d8-a3ef-69f4f2da7294 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002C cl.10.4.1
label | c65c5ca0-d30b-4c76-a0af-a9126523d8bb |  | note | INSPECTION/TEST METHOD: Aconex
label | dcb2996a-25bf-4576-8544-de41f30cf7c5 |  | note | RECORD OF CONFORMITY: Datasheet
label | 2ff8c18b-0ce2-4c2f-830a-8f41abc76f9c |  | note | HP*
label | 6969d397-7cc8-48dc-ad45-07846d3b00f7 |  | note | RESPONSIBILITY: Project Engineer
text | c0c0b92a-227f-432f-90d4-6cde4b7d11b5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 Series Isolation Transformers
label | a16742d9-f631-44f9-829f-d5b649c2b769 |  | note | FREQUENCY: Prior to Start
label | 065496b4-ac07-4800-a271-39a3ba46aa8b |  | note | ACCEPTANCE CRITERIA: New Fittings shall be from the EFLA KR600 (with earthing) range
label | df7f4ed5-7675-4c6e-a0c2-70f4ae933e56 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002C cl.10.4.6
label | e7d54660-2c2a-4d69-b056-896b74a3deaa |  | note | INSPECTION/TEST METHOD: Aconex
label | 188168a7-49b1-4840-90e3-ca23487cac7f |  | note | RECORD OF CONFORMITY: Datasheet
label | c3256494-fb2a-47fe-8a8f-0a24ac636900 |  | note | HP*
label | 55c85994-7d59-4c0a-adf9-ee5e7b8ce0e3 |  | note | RESPONSIBILITY: Project Engineer
text | c21edf17-7604-4d70-a198-948b6b224abb |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.1 Primary Cabling Connections
label | ae52a51b-c1cf-4e25-8411-ad763e7b6884 |  | note | FREQUENCY: Each Lot
label | c1031847-81c7-42cc-8471-27218e333de9 |  | note | Primary cables to be terminated at series transformers with plugs and receptacles to mate with the transformer leads.
label | d2179f14-cfc8-49ec-8bfe-fd89f0f7456e |  | note | Plug/receptacle connection to be wrapped with 2 layers of self-bonding tape to keep the connection clean.
label | cf43af33-0cc4-4d7c-8fee-b267a16976e1 |  | note | ACCEPTANCE CRITERIA: Screens of the primary cable must be bonded using crimped on cable lugs bolted together.
label | 11794faf-914f-4cc8-90f1-7497de1749e6 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002C cl 10.4.3
label | 3beda2a5-04cb-46c8-aab5-8b5cdf58db34 |  | note | INSPECTION/TEST METHOD: Verify
label | b3d3feaf-fb15-42fa-a12f-483bdb52e6b0 |  | note | RECORD OF CONFORMITY: This ITP Signed
label | 1de383c5-9f64-4825-83f1-05704405a4db |  | note | IP
label | d2feed05-4550-46e7-908f-b4f1de602741 |  | note | RESPONSIBILITY: Project Engineer / Site Supervisor
text | c73158cb-77e4-4938-9b46-34b006178543 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Secondary Cabling connections
label | db36b6f5-8a5c-4755-aae8-9d1c35f8b997 |  | note | FREQUENCY: Each Lot
label | b5143609-8b6b-4b7a-a192-65653d6eee8d |  | note | ACCEPTANCE CRITERIA: Secondary cabling is to be installed in unjointed lengths between SIT pits and seating pots.
label | 64950c2c-c327-4540-aaf2-273994f25979 |  | note | New secondary cabling to be terminated in a secondary receptacle in the light base and in a secondary plug in the pit.
label | 16d2126d-23c2-483b-b0b5-278bd0f07087 |  | note | Connection to a secondary plug in base and series isolation transformer in the pit
label | 51f68280-645e-431e-b8a2-5c841c948d77 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002c cl 10.5.2, 10.4.4
label | ac683b3a-a9dc-4a80-bb02-0b8920981262 |  | note | INSPECTION/TEST METHOD: Verify
label | 8222dd14-79ff-4766-b005-6eb3694df0bd |  | note | RECORD OF CONFORMITY: This ITP Signed
label | 310c77b1-b1c5-4829-a638-999df24235d0 |  | note | IP
label | 48139dd6-e26a-4ded-8f5e-bff5206e6166 |  | note | RESPONSIBILITY: Project Engineer/ Site Supervisor
text | d5cefd0a-202a-4736-8d18-5de73d9edaca |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Max Conduit Capacity
label | 8d059092-11cc-435a-a039-940bd9d076c4 |  | note | FREQUENCY: Each Lot
label | 920fcfe4-0041-459c-889b-1332a735fb8f |  | note | ACCEPTANCE CRITERIA: Must distribute cabling to maximise free space in conduits.
label | 8dbfb7ab-707d-4c6c-a63e-e9c1e359df5c |  | note | Primary Conduits
label | 606a3679-4a98-48e6-956b-f2e4c056410f |  | note | - Max 6 circuits or 12 cores per 100mm diameter conduit
label | 76c1cae1-3729-44f6-8db8-6fdd0bdfbd5d |  | note | - 6 circuits of 12 cores per 125mm diameter under bore
label | fe6e8654-37b5-4f84-a0d3-75e21d2632e5 |  | note | - 6 circuits of 12 cores per 75mm diameter sub duct
label | a0d251dc-e0eb-48ac-bd02-233c2b6886e0 |  | note | Secondary Conduits
label | a9600268-1943-456c-92c7-27b56f06b745 |  | note | - Six secondary circuits per 63mm diameter conduit
label | 87ca3388-926c-4cb7-9d3d-7bf0de4fa889 |  | note | - Three plug/receptacle sets per light base.
label | 171c613b-ce22-41c5-96ca-e7f5affb29d4 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002c cl10.5.1
label | e01f80de-86e1-40f7-93d9-02135aa095c6 |  | note | INSPECTION/TEST METHOD: Verify
label | e8e96f5d-7ad1-468c-ba8c-7940ea6c7bab |  | note | RECORD OF CONFORMITY: This ITP Signed
label | c3985174-df79-4a0d-9ca7-d38f9f57229d |  | note | IP
label | b1bdfb45-b00e-497f-b12c-6a117f3ccad2 |  | note | RESPONSIBILITY: Project Engineer / Site Supervisor
text | f1cba262-11bc-40e7-bd93-737257c33ff5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.1 Split Ducting of Existing cabling
label | 4ec61512-cf8f-43c9-bbdc-e3a2a79650a9 |  | note | FREQUENCY: Each Lot
label | 13769c2c-ea5f-46c9-9ff2-b788dcb3eca9 |  | note | ACCEPTANCE CRITERIA: Any existing cabling encountered in the path of new cabling under new pavements which are required to remain, where noted shall be protected by split ducting and surrounded as shown in drawings
label | 1f7ac593-d80e-46f6-b0cc-4b9ffdef9369 |  | note | REFERENCE DOCUMENTS: CP13038-AIR-DET-PM-SP-0002c cl. 10.2.9
label | a92123a7-e6af-46d9-b5fc-f2e96c91b17a |  | note | INSPECTION/TEST METHOD: Verify
label | 77873186-e7c3-48ff-af31-2e8f6f2c26f3 |  | note | RECORD OF CONFORMITY: This ITP Signed
label | 5d5e7557-67ec-4ac5-8be2-d841668a1a46 |  | note | IP
label | 15506d11-3dd6-463a-a6d1-a511e013ef8f |  | note | RESPONSIBILITY: Project Engineer / Site Supervisor
text | 11551225-12e2-47b2-8586-61707926a81b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Slack
label | 8f97eaa7-85ca-41b6-bfab-2d14150b52f2 |  | note | FREQUENCY: Each Lot
label | 03749e99-66b0-40ca-9687-bba2a6a1c92b |  | note | ACCEPTANCE CRITERIA: Primary Cabling – Must provide 1500mm slack at any point of connection and within pits.
label | f96c0e3f-605a-4acf-9627-144232d2846a |  | note | Secondary Cabling
label | a5c73fab-4ed2-4db4-8743-8ea9a58975a9 |  | note | - Must provide 1200mm for cabling connecting to a series transformer within a primary pit
label | d2be9e3d-a4d4-41e6-875d-750676afeb7b |  | note | - Must provide 1000mm for cabling connecting to a series transformers within a secondary pit
label | ad0193c4-0009-4965-9b4c-2030ed6ce90b |  | note | - 300mm for each end of secondary cabling connecting to a plug/receptacle within shallow base.
label | a1836997-2b4e-4038-a6bc-cac5761be201 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002c cl.10.5.1 & 2
label | 72474730-1faf-4fc5-84d3-7e247c97e320 |  | note | INSPECTION/TEST METHOD: Verify
label | 7951984b-cb4d-488d-b589-a79a03534722 |  | note | RECORD OF CONFORMITY: This ITP Signed – ADBSG Primary Cable Checklist
label | efa12b9e-2043-41f7-a53e-da9c7efed2a8 |  | note | IP
label | 1f777ce1-be72-4a6f-bc05-6412a00d2607 |  | note | RESPONSIBILITY: Project Engineer / Site Supervisor
text | d48d2bb5-cc28-49c5-9815-226bf842da0d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 SIT Pit Earthing Rod
label | fdb01b32-6aca-4ae8-803c-79a70d15d437 |  | note | FREQUENCY: Each Lot
label | 1b56bdc9-ca86-471f-8bc7-01e0bccdb35d |  | note | ACCEPTANCE CRITERIA: New 1500mm x 20mm diameter stainless steel earthing rod shall be installed internal to each sit pit.
label | 43fbd49c-4751-4cd0-b775-d5f43c5720c5 |  | note | All extraneous metal work and each transformer shall be connected to the AGL Earth
label | d25f997b-5c50-427e-b35c-320c80641463 |  | note | Bonding cable within each pit to be single core 6mm2 copper PVC (green/yellow) circuit protective conductor as a minimum.
label | 1b3c9050-f733-4fde-a9ea-264e6f69e448 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002c cl. 10.4.7
label | baffc95b-bb36-4d82-80f5-2f4f06ec4d9c |  | note | INSPECTION/TEST METHOD: Verify
label | d551773b-52de-418f-939c-91bd4d8d3ea5 |  | note | RECORD OF CONFORMITY: This ITP Signed – ADBSG Cable Joint / Pit-fit Out Checklist
label | 341a1fb0-dce9-42e2-96aa-e5536ea2aa46 |  | note | IP
label | 56d8b6b8-82ba-4040-8a61-334f7142f732 |  | note | RESPONSIBILITY: Project Engineer / Site Supervisor
text | e4e10a91-04f4-4c1c-9b22-d0bcfd1f8776 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 CCR Loading
label | 2cf9f04d-8024-4801-883a-21983deff6a6 |  | note | FREQUENCY: Each Lot
label | 369d816f-46dc-4fbd-a2aa-7f13000096b2 |  | note | ACCEPTANCE CRITERIA: Ensure CCR units are installed in positions shown on drawings and achieve no greater loading than 1000V with the new AGL fitting installations.
label | dd72a056-0b47-45b2-898a-4280ecd0b077 |  | note | CCR’s to be fed from the distribution board local to its installation.
label | 14c36c1e-792c-4ce2-9a02-e7f476497d4d |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002C cl.10.4.1
label | 70a093f2-8376-41cf-a351-50dc43c1ac91 |  | note | INSPECTION/TEST METHOD: Verify
label | 5582fa23-f314-4544-ad88-08a68122cd18 |  | note | RECORD OF CONFORMITY: This ITP Signed
label | e9f66a97-9c38-4d07-96c3-a0464c407a73 |  | note | IP
label | dd3eece9-a9f5-4d93-853f-665411a98d12 |  | note | RESPONSIBILITY: Project Engineer
text | 80e2764f-2d15-401f-b881-d0e42ef1094a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 Identification of configuration
label | df743f5c-5712-4291-a88f-cc3b88123bd3 |  | note | FREQUENCY: Each Lot
label | 0eaf7350-7bce-4955-b8d2-3f48a3b5683e |  | note | ACCEPTANCE CRITERIA: Every cable end shall be provided with a means of identification showing the designation, number and cross-sectional area of cores and rated voltage of the cable.
label | fcdc56d0-859e-404a-957e-a839584572b6 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002C cl. 9.3.2
label | 94fc3833-bf9d-4e37-9f78-8466a7ce2ea6 |  | note | INSPECTION/TEST METHOD: Visual
label | f20fc987-22a9-429a-b79c-946843a560a0 |  | note | RECORD OF CONFORMITY: This ITP signed – ADBSG Cable Joint / Pit-fit Out Checklist
label | ac5af1ce-3152-4b75-9a2c-100520003be7 |  | note | IP
label | 3fcb6e05-8bce-470b-8ed2-0c1aac366247 |  | note | RESPONSIBILITY: Project Engineer
text | b6c9bc43-dfd6-4a76-85a5-3c9c86def4f3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.1 As-built Documentation
label | f0166186-0119-4874-8658-b8240ab57bf3 |  | note | FREQUENCY: Prior to practical Completion
label | 9e0ffb8f-ff68-41e8-9b0a-368c3b0c5876 |  | note | ACCEPTANCE CRITERIA: Submission of as built report showing cabling route submitted to the Principal’s Representative prior to practical completion.
label | 8d569131-a534-4c26-b683-dbcdc38d48ae |  | note | REFERENCE DOCUMENTS: WP013
label | d61ffa51-013d-4c36-813c-5e4dfff79ab1 |  | note | INSPECTION/TEST METHOD: Verify
label | 4101c38f-070a-4cf2-b43f-6bf03b14fef9 |  | note | RECORD OF CONFORMITY: Aconex
label | 1dbcea0a-16ea-46e9-b851-922d706cdca6 |  | note | SCP
label | 3dfdf02d-a51f-4769-8ac5-65b9b39d9eba |  | note | RESPONSIBILITY: Project Engineer
text | b82ee551-b9e1-4531-9018-82084e5ab5d1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 0828f41b-046d-4466-ae66-0be9447e0420 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 064b047d-67ce-4307-ab68-988523f96a35 |  | textbox | Print Name:
text | 5ebeecdc-199d-4f2d-8d58-b4ebb36ab0ce |  | textbox | Position:
text | 6bfab066-9b7d-4f42-894c-c33a8cae98fd |  | textbox | Date:
checklist-sectioned |  |  | checklist | ITP 004 - Subsurface Drainage | itp |  |  |  | Yes | ITP 004 - Subsurface Drainage | fe653109-13fe-49b6-9a0e-2e38bf16e884
checkpoint-group |  |  | section | ITP 004 - Subsurface Drainage
checkpoint-status |  |  | checkpoint | 1.1 Check for correct documentation
label | bd4e941d-66bd-4969-8538-e49169241040 |  | note | FREQUENCY: Prior to commencing any activity
label | e2656779-e0ee-4ab8-b14a-9641ac4ac44a |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision
label | 75c9e951-3454-474b-b087-60943b4f34ec |  | note | REFERENCE DOCUMENTS: Drawings and drawing registers
label | fc176349-27be-4bc2-bac3-5476f151e279 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 9baa0b51-9dc0-41eb-b162-5c69bb4c34ad |  | note | RECORD OF CONFORMITY: Up to date drawing sets and this ITP signed
label | 2eae3b6d-fd2a-4b9a-9dca-957cef514048 |  | note | HP*
label | de0f9607-5a27-4f51-97c1-7ca56142241c |  | note | RESPONSIBILITY: Project Engineer
text | 01a5f11b-95db-4a77-88b7-1c8b78903669 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 Implementation of all measures & controls
label | 688d6fb0-8cfc-4c4a-8cf0-fab9dd56be65 |  | note | FREQUENCY: Prior to commencing any activity
label | 174d94d7-44fc-41d5-a0e3-abd15f822bb9 |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | b1168f0e-160f-4016-b7b4-6ab6e427866e |  | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, SWMS, WP
label | 64d25ee3-499f-40b6-8349-f6907a4d4013 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | d35134cf-f7f5-4412-997e-94980c639433 |  | note | RECORD OF CONFORMITY: Site and Office Inspection
label | d82f4828-ce1e-47c4-b586-b4b38b75931e |  | note | HP*
label | e77797fe-da82-4d04-9ba8-72769eaab2a4 |  | note | RESPONSIBILITY: Project Engineer/ Site Supervisor
text | ca2ff0e0-9997-4364-a2f1-337a444303e2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 Definition of the work areas
label | 9ddfa591-cba9-412b-ae1a-989679b704c9 |  | note | FREQUENCY: Before commencement of activity
label | 3682a63a-9d7d-406e-9cd2-f584b104c2d2 |  | note | ACCEPTANCE CRITERIA: Work area has been cleared and surveyed (marked on site). Limits of excavation clearly defined.
label | a272cb95-7b74-4f41-8089-1e8dc7d03ce1 |  | note | REFERENCE DOCUMENTS: Drawings
label | d37b90d8-391a-4648-a8f8-8dc47683eba5 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 5d5e6f81-208f-4500-a0f3-c30bf5d3ea33 |  | note | RECORD OF CONFORMITY: Site Inspection
label | a1dba410-d7ae-4b65-9274-0248fb5b4eea |  | note | HP*
label | 00acaa72-e439-4e52-baff-9983f692d5ee |  | note | RESPONSIBILITY: Foreman
text | 5bd9aa4e-8bd8-42d2-b8fc-e5d2eca0e909 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.4 Service Locations
label | 637e1c7b-f83d-405c-a8f2-379b81d3457c |  | note | FREQUENCY: Prior to start
label | d7d0fa7e-89af-47e8-b069-0d363eda7eb4 |  | note | ACCEPTANCE CRITERIA: The location of services are to be found and marked on the ground within the works, and 10m beyond the boundary of works where applicable. - Services located within the works area to be exposed using approved location methods, in the presence of an Airport Rep. where required. Service Locations and Depths recorded by surveyor where required - Ensure no mechanical excavation within 3m of Fuel Lines
label | 3674aa5d-f17e-4a9c-926e-129bc50e401c |  | note | REFERENCE DOCUMENTS: Service drawings (Excavation permit) Spec cL8.1.8
label | 1d53fd9b-bff8-4233-bb70-da008d5265c6 |  | note | INSPECTION/TEST METHOD: Verify
label | e36df011-1cbe-4e17-8f32-1c09384d0a62 |  | note | RECORD OF CONFORMITY: Survey Report of Service Locations and Depths
label | ef2e85b4-8d9e-4fdb-9e72-7fbbaa0976ce |  | note | IP/SCP
label | c3fb3daa-151d-4613-bbaf-b5829ba5b8b0 |  | note | RESPONSIBILITY: Project Engineer / Foreman / Surveyor
text | 73a44f29-560a-4aaa-bba8-eaf16686e3b0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 Subsurface Drainage Pipes
label | e2a3ee7c-3fd5-445e-8511-6d6bf0a8cdf4 |  | note | FREQUENCY: Prior to start
label | bceb714e-99f6-415b-ad05-a7e7fa64fba4 |  | note | ACCEPTANCE CRITERIA: Subsoil Pipe material to be 160mm SN20 corrugated AGI pipe with Filter sock
label | 63590969-e33b-4808-8e6e-a88c22712bce |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002C cl.8.3.1
label | ff852da2-1136-49ca-b525-62970966862b |  | note | INSPECTION/TEST METHOD: Verify
label | dd8d5e51-b757-41b3-ab58-b53dc3d174c3 |  | note | RECORD OF CONFORMITY: Visual Inspection & Delivery Docket
label | 11601768-448a-4fc9-992d-d5572f1de148 |  | note | IP
label | 6463a87e-a40d-4f90-88a6-3cdd07c64529 |  | note | RESPONSIBILITY: Project Engineer
text | af7f52aa-b244-49a8-8a38-2e712a5644c4 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Bedding & Backfill Material
label | 390d4e64-77f9-41ea-b141-9e6e9e909133 |  | note | FREQUENCY: Each lot
label | b8d14a23-d458-44e7-8eeb-bd745f41223d |  | note | ACCEPTANCE CRITERIA: Under Grassed V Drains: 5% cement 40mm no Fines Concrete (5MPa) Under Pavements: Granular filter material VicRoads A3 material or equivalent
label | 5a0a8130-300f-4ab3-83c5-57c60fe7b260 |  | note | REFERENCE DOCUMENTS: Drawings Spec cl.8.1.9 and cl.8.1.10
label | 366441c7-b88b-4817-933a-a5552353a9e8 |  | note | INSPECTION/TEST METHOD: Verify
label | 56447f2b-1e3c-445d-9e15-7a4abe02839c |  | note | RECORD OF CONFORMITY: Visual Inspection & Delivery Docket
label | 6fb8052e-5385-413c-a082-ce6283d5884c |  | note | IP
label | c14312ec-3815-4678-823d-51fcdad6301f |  | note | RESPONSIBILITY: Project Engineer
text | 246ed6d0-0874-4384-8660-e1e6953681c1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.1 Pipe Depth
label | 7e2ee7f7-9a37-4e72-8b85-9eb3ef783625 |  | note | FREQUENCY: Each lot
label | a876e87c-c232-42c8-9dff-7ca1ee28dc9d |  | note | ACCEPTANCE CRITERIA: Subsoil pipe must be installed at a minimum depth measured to the crown of the pipe satisfying: • At least 100mm between top of pipe and design subgrade line • At least 100mm below average gradient of the bottom of footings. • At least 450mm below the finished surface of unpaved ground.
label | 9322aca8-ee3c-4f64-9e14-9bc43b0dae64 |  | note | REFERENCE DOCUMENTS: CP14038- AIR-DET- PM-SP- 0002C cl.8.3.1 cl.8.3.2
label | d76379ec-2b0a-4a7b-95c4-68af857bf6a2 |  | note | INSPECTION/TEST METHOD: Verify
label | d3404941-5a87-4159-96d9-26fbf9aeca9c |  | note | RECORD OF CONFORMITY: Site inspection and This ITP Signed
label | c4cc538d-808a-41b2-94f5-a91c29339eb8 |  | note | IP
label | f591834e-31d5-4bf4-8222-6b595450ed23 |  | note | RESPONSIBILITY: Project Engineer / Foreman.
text | 7f23bb83-41ce-4fb7-a04a-4d5dc48cc4a2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Trench Excavation
label | 025979b0-9ee0-49ce-8718-ecf9f09e8532 |  | note | FREQUENCY: Each lot
label | 8f223903-956b-44e9-9662-b7d6e769c8fb |  | note | ACCEPTANCE CRITERIA: Trench Excavation to allow for minimum pipe bedding and backfill depths to achieve the minimum depths specified in item 3.1
label | f2fef493-cec5-4c1b-83a5-f748eaf8189a |  | note | Trench width: Under Pavements: In accordance to the dimensions outlined in the drawings
label | 88ae9a5f-d424-4686-b79a-03b2c6cc82b8 |  | note | Under Grassed V Drains: In accordance to the dimensions outlined in the drawings
label | fc266507-25fe-4c6a-92f4-52c80589d93b |  | note | Trench walls to be adequately shored.
label | f6e71f3d-c667-467d-a312-9aface015fa0 |  | note | Excavation material from trench shall not be stockpiled adjacent to trench without approval from superintendent
label | e2435142-c659-40df-8652-6fa2eae7c953 |  | note | REFERENCE DOCUMENTS: Drawings Spec cl.8.8.8
label | c0931bef-a227-4ccf-8f03-b52e2a47900a |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | e2542fda-91a3-4890-82ee-c7387a145aab |  | note | RECORD OF CONFORMITY: This ITP Signed
label | f4cdf1c9-d994-40ed-8af6-3e6904f805a6 |  | note | IP
label | 48fc48b9-4b0c-4998-8d86-5a6191d715fe |  | note | RESPONSIBILITY: Project Engineer / Foreman.
text | 826b11c6-e904-4f02-8bf0-332c6cfc5523 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Bedding & Backfill of Pipes
label | c3e32914-61a3-47cf-886c-3880666f6575 |  | note | FREQUENCY: Each lot
label | eabb5d92-51fc-4556-9905-4e8ed7ed1c96 |  | note | ACCEPTANCE CRITERIA: Under Grass V Drains: In accordance to the dimensions outlined in the drawings
label | 4d4d3614-2f32-4caa-af64-1468e11b8316 |  | note | Under Pavements: In accordance to the dimensions outlined in the drawings
label | c2284170-37a3-404b-b8de-32b221b936c8 |  | note | A bedding of filter material between 25mm – 50mm thickness.
label | e8661bf1-5d25-4bd0-a06b-0cb9afa09260 |  | note | Bedding to be tamped and screeded or graded to level.
label | 224a103c-23c4-4d49-aaa4-ffa5631268dd |  | note | Filter material shall be placed moist and compacted with minimum disturbance to pipes and in layers no greater than 300mm uncompacted.
label | 951cf549-42c5-4728-ad68-96fd1649e15d |  | note | REFERENCE DOCUMENTS: Drawings & CP14038-AIR-DET-PM-SP-0002C cl.8.3.2 cl.8.1.9 cl.8.1.10 cl.8.1.11
label | 5dd2be99-ff60-404c-b30a-7565a9abf0d8 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | ac38b3fe-3f8b-4244-a1ba-4d7a21262162 |  | note | RECORD OF CONFORMITY: This ITP Signed
label | f49511aa-1852-439a-95ce-d26976255221 |  | note | IP
label | 8ab3b3b3-6e59-4d0d-a87b-c1b4e97bdfe1 |  | note | RESPONSIBILITY: Project Engineer / Foreman.
text | 0fc5f7a6-ce4f-4b52-8652-33c3dbc33352 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 Laying & Jointing of Pipes
label | ae92b62a-f68f-4864-a0d0-39c8617fee77 |  | note | FREQUENCY: Each lot
label | 68c634d0-be29-4425-928c-7a71fc38cd50 |  | note | ACCEPTANCE CRITERIA: Pipes laid at the depths and lines indicated on drawings with the following tolerances: • +/- 25mm vertical alignment • +/- 50mm horizontal alignment Changes in grade shall not be abrupt or exceed 10mm in any 3m length. Minimum grade of 1:250 to outlet. Pipe to be laid centrally in trench and held firmly in place with slots in the lower half of the pipe. Preformed Pipe joints and fittings may be used.
label | 17fbbe19-9f0e-4a0b-9639-a3f1d0c61f95 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002C cl.8.3.1 cl.8.3.2 & Drawings
label | ff1dfa46-6fb7-470a-b400-b3f7c6fdb239 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 49f0016a-fddb-4dbe-9396-22f8b922d716 |  | note | RECORD OF CONFORMITY: As built documentation & This ITP Signed
label | 40ad4ca2-5a70-4840-a862-2f8644d4753e |  | note | IP
label | 5dc2f5ce-f5a2-430a-b16a-97fac9ab8eef |  | note | RESPONSIBILITY: Project Engineer
text | d645f711-f21e-47cb-ba58-5e869c9015f2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.5 Compaction of Material (160mm subsoil)
label | 3b331eb2-88a5-4e98-a1d1-5ae37658a5b3 |  | note | FREQUENCY: Each lot
label | 5c795539-9bc2-4d20-9d6c-7b43e57ca2b4 |  | note | ACCEPTANCE CRITERIA: Trench to be compacted with the use of a plate compactor for every 300mm layer of backfill material.
label | 96b74fe0-7fdb-46ff-be7e-bcc0311716a8 |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002C cl.8.3.2
label | e997497f-eb65-4ee9-a1bd-471f8e0c8d4f |  | note | INSPECTION/TEST METHOD: Verify
label | f128cc14-6113-4d15-bdaf-d8b55ce3c513 |  | note | RECORD OF CONFORMITY: Aconex Correspondence
label | 3b342a7f-afab-4ddd-848f-efe3804ca91b |  | note | AP
label | 1a112ccc-3e3f-46ef-a068-52d332020e91 |  | note | RESPONSIBILITY: Project Engineer
text | dd5db80e-24bb-45af-b5a7-d8b508de4428 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Check Type A/B Backfill compliance (50mm subsoil)
label | e236c7ab-f164-4a2f-ac8c-a85956a644d8 |  | note | FREQUENCY: Check Type A/B Backfill compliance (50mm subsoil) Prior to commencing activity
label | 666d8481-1541-4754-9930-18286697c883 |  | note | ACCEPTANCE CRITERIA: For grassed areas outside the taxiway or runway strip, Fill material complying with VicRoads Section 204 Type B shall be used.
label | fcdb8c13-37fe-4ba3-9852-44bcc2b29033 |  | note | Ensure to use Fill Material Type B that is totally free of organic content, topsoil, deleterious and/or perishable matter such as bricks, concrete, glass, plastic, timber, steel, or steel by-products.
label | d49b9dd5-978f-43a8-9179-9555773f93ff |  | note | SMDD 95% CBR ≥ 5%
label | 3fddecbc-ff20-4c46-9d38-6675607d23cb |  | note | Swell ≤ 2.5%
label | 33358423-63ab-4ba5-945e-917dc778237e |  | note | PSD maximum aggregate size < 75mm
label | 958eb449-c03e-46f1-9a75-dc6886f2d789 |  | note | PSD passing 0.075mm between 15- 30%
label | 49796769-9641-4aea-b3dc-22503429bf70 |  | note | PI (post compaction) ≥ 7%
label | 1243779e-aa40-4b4a-9be9-32c954a0f5c6 |  | note | For grassed areas within the taxiway or runway strip, fill material complying with either Appendix R Clause 3.5.2 or VicRoads Section 204 Type A shall be used.
label | 641d3947-9894-4c6d-9e1b-bf52965a620f |  | note | Ensure to use Fill Material Type A that is totally free of organic content, topsoil, deleterious and/or perishable matter such as bricks, concrete, glass, plastic, timber, steel, or steel by-products.
label | ea19e12d-33a6-4726-a898-b44b43e5f468 |  | note | SMDD 95% CBR ≥ 5%
label | 973cafa2-e315-4d00-9f03-e7a271ccd860 |  | note | Swell ≤ 1.5%
label | fea0f958-b2fc-47a5-9b5d-b597d26aed27 |  | note | PSD maximum aggregate size < 75mm
label | e327a285-d62c-40fe-ac5c-6e22306be7ac |  | note | PSD passing 0.075mm between 15- 30%
label | a9d38964-af58-41a0-b811-bf0a5f6c8d52 |  | note | PI (post compaction) ≥ 7%
label | f7ff95e4-8966-43e7-b9a5-ed8d2835ebac |  | note | REFERENCE DOCUMENTS: CP14038- AIR-DET-PM- SP-0002C cl. 3.5.2 VicRoads Standard Specification Section 204
label | 0fb6ffde-4f3f-470f-b8c7-bc829f76bfe8 |  | note | INSPECTION/TEST METHOD: Verify
label | 8aeb9a46-0419-429a-ac62-a276ef77926d |  | note | RECORD OF CONFORMITY: Stockpile Test Report
label | 25528918-9ee8-4741-84dc-0477f86251ce |  | note | TP/AP
label | 692a1a42-54dd-4424-8b2a-63dc1d34d9e0 |  | note | RESPONSIBILITY: Project Engineer / Principal’s Representative
text | a637389c-67af-4993-87fb-0acb341ae628 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.6 Compaction of backfill material (50mm collector in grassed areas)
label | 87fcf487-bb8b-4c4f-9c6d-e0668b77da61 |  | note | FREQUENCY: Each lot
label | 6c9427b8-8f07-4367-819b-33b4941b7fa2 |  | note | ACCEPTANCE CRITERIA: Selected excavated backfill with layers not exceeding 225mm compacted thickness.
label | 12ce43ab-92ec-4653-8ff0-133526e50fb0 |  | note | The standard of compaction to be achieved shall be a minimum dry density ratio of 95%SMDD. Testing shall meet the requirements of VicRoads Standard Specification Section 204 for a Fill Material Type A/B and shall occur at the frequency of 1 test per 500m3 or one day’s work, whichever is the lesser.
label | 18efd245-f76f-42b3-bcc6-0e6cd345bb09 |  | note | Backfill shall be to the original or design level without subsidence and without cracking at junctions with existing surfaces.
label | 7ee4d96d-1905-4c80-9796-e5bd4b4c8224 |  | note | REFERENCE DOCUMENTS: CP14038- AIR-DET-PM- SP-0002C cl. 9.3.1.14 & cl. 3.5.2
label | 033e002a-3996-4cb3-96be-16de0441d9b2 |  | note | INSPECTION/TEST METHOD: Verify
label | ef49807f-2ed4-48e4-9f5e-d6bc32333f62 |  | note | RECORD OF CONFORMITY: Test Report and This ITP Signed
label | cd732ddd-128c-41e7-b7b1-82204016a7fe |  | note | TP/IP
label | f1dfe90e-33e3-4d15-826c-88223b8f0f6f |  | note | RESPONSIBILITY: Project Engineer/ Foreman
text | 80cc9adb-fa93-4843-bace-dffccb0e6ff6 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.7 Testing (A3 filter material)
label | 932ebe4d-98c9-4932-8dea-2103fbbc8459 |  | note | FREQUENCY: Each lot
label | 547289fe-9f5f-4003-a1d4-5bae946eb8d7 |  | note | ACCEPTANCE CRITERIA: Testing of filter material to be undertaken at the following frequencies; Grading – One test per production day Unsound rock content – One test per production day Sand equivalent – One test per production month PH – One test per production month All tests to conform to standards stipulated in VicRoads section 702.
label | 5a95d102-7528-487c-9cdc-bd64d782f552 |  | note | REFERENCE DOCUMENTS: Vic roads section 702. Table 702.131
label | d78b53f9-59e5-43d6-84ae-834913e07819 |  | note | INSPECTION/TEST METHOD: Test results
label | 474c3dbd-9ac8-4db2-a223-7a102f0c73ce |  | note | TP
label | f0ff3b2b-569d-412e-b049-0e571ceb5976 |  | note | RESPONSIBILITY: Site Engineer
text | f31a55a0-959b-4a04-b42d-2c6ad77b9d03 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.8 Subsoil Access Point & Inspection Point
label | 6df5f0d1-59b6-4c4f-a569-ccbfea381d1a |  | note | FREQUENCY: Each lot
label | 79762feb-1f82-4c27-81d9-2dfea01796c4 |  | note | ACCEPTANCE CRITERIA: Subsoil outlet point to be located at a drainage pit, pipe end wall or outlet in a fill batter or drain. All subsoil drain outlets shall be fitted with pest proof flap.
label | a9a551e9-8ee5-4c48-9c07-d3756c0b8c34 |  | note | REFERENCE DOCUMENTS: CP14038- AIR-DET- PM-SP- 0002C cl.8.3.1
label | ae759085-d231-49e4-879e-096fd506f288 |  | note | INSPECTION/TEST METHOD: Verify
label | 4e32e812-4890-4a8b-98c8-b765156babd0 |  | note | RECORD OF CONFORMITY: This ITP Signed
label | d180e9d8-75b0-4d31-bf5a-33c81c3d78df |  | note | IP
label | b699df64-8740-42f7-ae63-b62603f95c07 |  | note | RESPONSIBILITY: Project Engineer
text | 1d3110ce-bd95-4ebe-a543-3f8f3ee4ffea |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.9 Subsoil Access Point & Inspection Point
label | cb232e65-5915-4d98-9f14-0c5501f48dd0 |  | note | FREQUENCY: Each lot
label | 54deea92-685f-4041-a97d-2db658528158 |  | note | ACCEPTANCE CRITERIA: Subsoil pipes shall have access points at the beginning and end of the drainage run and have inspection openings at intervals of maximum 100m along the run.
label | 82822dda-82d0-4320-bb2e-880053dd36c8 |  | note | Where stormwater drainage pits are used as access points, the invert at the beginning of each run shall be above the top of the pit outlet, and the invert at the end of each run shall be not less than 100mm above the invert of the pit outlet.
label | a8ea951a-dc89-4ce0-b0fa-079f734545eb |  | note | REFERENCE DOCUMENTS: CP14038- AIR-DET- PM-SP-0002C cl.8.3.3
label | dd1ce919-6ae9-4e92-9de5-6c97d8acc9db |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | d975a043-9025-42d7-b079-ce8231913dd8 |  | note | RECORD OF CONFORMITY: This ITP Signed / As built report
label | 981aaa03-f441-43e3-941c-22aebb7a632b |  | note | IP
label | 22f48fcd-e114-47ae-8ae3-20606af4aa90 |  | note | RESPONSIBILITY: Project Engineer
text | c76594f8-7334-4e5d-9dcf-63ee4bcecfbd |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.10 Flush out Risers
label | b4ee2e2c-a679-4e4f-88bc-98b60f002dda |  | note | FREQUENCY: As applicable
label | 22da4f83-3338-4a0a-8283-26dde0dd6f96 |  | note | ACCEPTANCE CRITERIA: To be the same diameter as the subsoil pipe and be installed in locations indicated on the drawings.
label | bc8c3358-10ee-4bbe-bf1a-c23d1bbd737a |  | note | REFERENCE DOCUMENTS: Drawings
label | d3a211c9-554d-4550-8b29-4f74f8815872 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 67fd933f-a6d5-4ea1-bbb5-a56e3ae06444 |  | note | RECORD OF. CONFORMITY: This ITP Signed
label | c200f93d-b4e9-428b-885e-0b6fb4492607 |  | note | IP
label | a640761a-cfcf-4f8c-9619-0cbdb823fecb |  | note | RESPONSIBILITY: Project Engineer
checkpoint-status |  |  | checkpoint | 4.1 Flushing Test
label | 3153b758-a550-404b-8433-50ea3958c405 |  | note | FREQUENCY: Each lot
label | 6b94d287-f872-4be9-8b32-cd941ba68359 |  | note | ACCEPTANCE CRITERIA: A flushing test shall be carried out on each subsurface drainage line after completion of subsurface drains, flushers and outlets. Each drain shall be flushed with sufficient water to remove material that has entered the pipes during construction and to ensure that the drainage line is free from obstruction. The test shall be witnessed by the superintendent
label | 5f3abbe9-f7a2-4be7-be00-1cd31dc0c40a |  | note | REFERENCE DOCUMENTS: CP14038-AIR-DET-PM-SP-0002C cl.8.3.2 cl.8.3.3
label | 843bca56-5dfa-4a0f-ab08-53c61d33e82b |  | note | INSPECTION/TEST METHOD: Inspection
label | 022f8dde-2579-42b2-bf8a-0da29792f026 |  | note | RECORD OF CONFORMITY: This ITP Signed
label | 72565256-fbc1-4752-83d2-c04cfb8d04da |  | note | IP
label | 7212113f-1820-4ded-9e04-cb7d8016d460 |  | note | RESPONSIBILITY: Project Engineer / Principles Representative
text | 167a0673-6a5c-4910-9c50-644ade1c2199 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Records
label | 1a3aea96-e11a-4412-b0a7-14b0a0116bab |  | note | FREQUENCY: After practical completion
label | 1bf12174-6e22-49f1-8f04-e3c51ffc02b4 |  | note | ACCEPTANCE CRITERIA: Levels and alignment recorded in as built documentation and provided to superintendent
label | 4056d592-22f7-4c26-bdf0-afc615b6dce1 |  | note | REFERENCE DOCUMENTS: As built data
label | b75d41fa-8429-4a2b-b317-18fbab4ece64 |  | note | INSPECTION/TEST METHOD: Inspection
label | 063e920b-d321-4573-a807-63931fc58756 |  | note | RECORD OF CONFORMITY: Aconex Correspondence
label | 5fc23a45-6920-4ee9-ae00-faa278e74da4 |  | note | IP
label | 67452c39-45ff-4c8d-a4e2-d96ef7eb387a |  | note | RESPONSIBILITY: Project Engineer
text | e11b9d4a-74ce-46ed-84c4-f05462fb0cc7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | FULTON HOGAN FINAL INSPECTION - "On behalf of Fulton Hogan, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract".
text | f4a75cef-9367-4390-ad09-3a9b7aaaf53a |  | textbox | Name:
text | a1688507-07c7-439c-b0e2-0ae3ddda4e61 |  | textbox | Position: