## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP001 - Demolition of Existing Infrastructure | itp |  |  |  |  | ITP001 - Demolition of Existing Infrastructure - Rev A
section | 1.0 - Preliminary Activities
checkpoint | 1.1 - Check for correct documentation
label | Frequency - Prior to works
label | Acceptance Criteria - Ensure that all employees and subcontractors are:
label | ○ Using the correct and complete set of drawings.
label | ○ All drawings are the latest revision
label | Reference Documents - Aconex
label | Inspection/Test Method - Visual inspection
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 1.2 - Demolition Work Plan
label | Frequency - 2-weeks prior to start of works
label | Acceptance Criteria - Prepared and submit Demolition Work Plan in accordance with AS 2601 to Contract Administrator two weeks prior to start of works.
label | Reference Documents - Spec cl. 8.4 AS2601 WMS-001
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP
label | Responsibility - Project/Site Engineer, Principal’s Representat ive
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Dilapidation Report
label | Frequency - Prior to works
label | Acceptance Criteria - A dilapidation report is to be completed and submitted prior to works on site. Dilapidation report to include photos and recordings of the condition of the pavement prior to demolition works.
label | Reference Documents - Dilapidation Report
label | Inspection/Test Method - Visual inspection & Verify
label | Record of conformity - Aconex & This ITP signed
label | HP*
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 1.4 - Existing Service Identification & Protection
label | Frequency - Prior to works
label | Acceptance Criteria - Area to be demolished has current BYD plans, service scanned, and existing services has been proved. Services have been identified and protected prior to demolition.
label | Reference Documents - Spec cl. 8.5.1 Drawings, BYDA, Survey Maps
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Surveyor, Project/Site Engineer
date | Date Completed:
checkpoint | 1.5 - Execution of Demolition works
label | Frequency - 2-weeks prior to start of works
label | Acceptance Criteria - If working within the existing vicinity of AGL services, Fulton Hogan to give APAM a two-week written notice to work in the vicinity of existing AGL cables and transformers, to provide notice for APAM to assist in isolating services.
label | Reference Documents - Spec cl. 8.5.1
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 1.6 - Implementation of all measures and controls
label | Frequency - Prior to works
label | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, ECP, TMP, SWMS and WP
label | Reference Documents - PSP, EMP, TMP, SWMS, WP
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 1.7 - Testing of Demolition Materials
label | Frequency - Prior to works
label | Acceptance Criteria - Ensure PFAS testing has been completed. The results of the testing will be used to determine the appropriate disposal or re-use of the demolished materials.
label | Reference Documents - Spec cl. 8.5.5
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 1.8 - Excavation Permits
label | Frequency - Prior to works
label | Acceptance Criteria - Prior to works, check that excavation permit has been gathered from APAM prior to any demolition works. Internal Fulton Hogan permit has been issues to excavation works and plant operators.
label | Reference Documents - APAM Excavation permit, FH Permit, Go- Cards
label | Inspection/Test Method - Verify
label | Record of conformity - Excavation Permit
label | HP*
label | Responsibility - Project/Site Engineer
date | Date Completed:
section | 2.0 - Demolition of Existing Pavement Works
checkpoint | 2.1 - Definition of a works area (survey)
label | Frequency - Each Lot
label | Acceptance Criteria - Work area has been cleaned and surveyed (marked on site). Limits of demolition are clearly marked.
label | Reference Documents - Drawings
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project/Site Engineer Surveyor
date | Date Completed:
checkpoint | 2.2 - Temporary Supports
label | Frequency - Each Lot
label | Acceptance Criteria - Check demolition will not affect any structural or service supports, if so, temporary supports will be provided until it is no longer required.
label | Reference Documents - Spec cl. 8.5.3
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project/Site Engineer Superintendent, Foreman
date | Date Completed:
checkpoint | 2.3 - Disposal of Material
label | Frequency - Each Lot
label | Acceptance Criteria - Demolished clean concrete material will be taken to Vic Civils at Gate 8, for concrete recycling. Contaminated or PFAS material are to be taken to Gate 11 to be stockpiled into their dedicated category and contaminant. Any discovered contaminated material found on site, that are not already known, will be notified to the client immediately.
label | Reference Documents - Spec cl. 8.5.5
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project/Site Engineer Foreman
date | Date Completed:
checkpoint | 2.4 - Asbestos Materials
label | Frequency - Each Lot
label | Acceptance Criteria - If asbestos material is identified, works are to be stopped until test is conducted to verify the asbestos. If asbestos is confirmed, licensed subcontractors are to remove and dispose the asbestos out of site.
label | Reference Documents - Spec cl. 8.5.6
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project/Site Engineer Foreman
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Print Name:
text | Position:
date | Work Completed On:
date | Date: