## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP003 - Stripping Top Soil and Bulk Excavation | itp |  |  |  |  | ITP003 - Stripping Top Soil and Bulk Excavation - Rev A
section | 1.0 - Preliminary Activities
checkpoint | 1.1 - Check for correct documentation
label | Frequency - Prior to works
label | Acceptance Criteria - Ensure that all employees and subcontractors are:
label | ○ Using the correct and complete set of drawings.
label | ○ All drawings are the latest revision
label | Reference Documents - Aconex
label | Inspection/Test Method - Visual inspection
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency - Prior to works
label | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS and WP.
label | Reference Documents - PSP, EMP, TMP, SWMS, WP
label | Inspection/Test Method - Visual inspection
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 1.3 - Survey
label | Frequency - Prior to works
label | Acceptance Criteria - Area has been surveyed, highlighting any areas where excavations should not occur (e.g. exclusion zone).
label | Reference Documents - PSP, EMP, TMP, SWMS, WP
label | Inspection/Test Method - Visual inspection
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project/Site Engineer Surveyor
date | Date Completed:
checkpoint | 1.4 - APAM permits
label | Frequency - Prior to works
label | Acceptance Criteria - Excavation permit issued. If working near HV electrical, an Electricity supply Isolation form and cabling permit has been issued from Melbourne Airport.
label | Reference Documents - Excavation permit
label | Inspection/Test Method - Approved permits
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 1.5 - Fulton Hogan Permits
label | Frequency - Prior to works
label | Acceptance Criteria - Fulton Hogan Excavation permit issued to plant operators prior to excavation works. Native Grass heatmap issued and boundary of working area has been set out.
label | Reference Documents - Excavation permit
label | Inspection/Test Method - Approved permits
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 1.8 - Plant and Equipment
label | Frequency - Prior to works
label | Acceptance Criteria - Plant and Equipment used in the works are appropriate to achieve specifications requirements. All plant inducted and inspected as per Fulton Hogan’s plant safety guidelines.
label | Reference Documents - WMS - 003
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project/Site Engineer
date | Date Completed:
section | 2.0 - Stripping / Bulk Excavation
checkpoint | 2.1 - Site Preparation
label | Frequency - Each lot
label | Acceptance Criteria - All excavation and filling will be free draining to low points clear of the Works. Sufficient pumps, well-points or other equipment for work area de-watered during the works shall be provided where required. Existing drainage lines and water mains found to be traversing the site must be removed as shown on drawings. Contractor must provide temporary pollution control devices or ponds in existing drainage systems and receiving waters.
label | Reference Documents - ZULU- BECA-001- DWG-00001 to ZULU- BECA-005- DWG-01119
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This signed ITP
label | IP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 2.2 - Dust & FOD control
label | Frequency - Each Lot
label | Acceptance Criteria - Prevention of dust during earthworks and subgrade preparation. Sweeper onsite at all times to manage dust / FOD.
label | Reference Documents - Site ECP
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This signed ITP
label | IP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 2.3 - Stripping Top Soil
label | Frequency - Each Lot
label | Acceptance Criteria - Prior to bulk excavation, site shall be stripped of all topsoil and organic matter as shown on the drawings. Spoil to be taken to Gate 11.
label | Reference Documents - WMS - 003
label | Inspection/Test Method - Inspection Point
label | Record of conformity - This signed ITP
label | IP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 2.4 - Excavation
label | Frequency - Each Lot
label | Acceptance Criteria - Bulk out subgrade to 100mm of subgrade. If rain is imminent, ensure subgrade is left 100mm high prior to trimming.
label | ○ Rocks Under <800mm can be taken as mixed fill to Gate 11
label | ○ Rocks >800mm to be sorted and taken to Vic Civil
label | Reference Documents - WMS – 003 Spec 001 - Cl8.5.3
label | Inspection/Test Method - Inspection Point
label | Record of conformity - This signed ITP
label | IP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 2.5 - Batters & Temporary Support
label | Frequency - Each Lot
label | Acceptance Criteria - All batters to be kept at 1:1. If not, temporary support will need to be designed, engineer and approved for use.
label | Reference Documents - WMS – 003 Spec 001 - Cl8.5.3
label | Inspection/Test Method - Inspection Point
label | Record of conformity - This signed ITP
label | IP / HP* (if required)
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 2.6 - Excavation – Detailed Trim
label | Frequency - Each Lot
label | Acceptance Criteria - Detail trim Subgrade with excavator / dozer
label | Reference Documents - WMS - 003
label | Inspection/Test Method - Inspection Point
label | Record of conformity - This signed ITP
label | IP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 2.6 - Contaminated Materials (if found)
label | Frequency - Each Lot
label | Acceptance Criteria - If contaminated or hazardous materials are found, immediate notice is to be given to the Principal’s Representative. These include the following;
label | ○ Asbestos or material containing asbestos;
label | ○ Flammable or explosive liquids or gases;
label | ○ Toxic, infective or contaminated materials;
label | ○ Radiation or radioactive materials;
label | ○ Noxious or explosive chemicals; and
label | ○ Tanks or other containers which have been used for storage of explosive, toxic, infective or contaminated substances.
label | ○ High levels of PFAS
label | – Agreed removal location to be confirmed with Principles Representative.
label | Reference Documents - WMS - 003
label | Inspection/Test Method - Inspection Point
label | Record of conformity - This signed ITP
label | HP*
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Print Name:
text | Position:
date | Work Completed On:
date | Date: