## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP004 - Select Fill Placement | itp |  |  |  |  | ITP004 - Select Fill Placement - Rev A
section | 1.0 - Preliminary Activities
checkpoint | 1.1 - Check for correct documentation
label | Frequency - Prior to works
label | Acceptance Criteria - Ensure that all employees and subcontractors are:
label | ○ Using the correct and complete set of drawings.
label | ○ All drawings are the latest revision
label | Reference Documents - Aconex
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency - Prior to works
label | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS and WP.
label | Reference Documents - PSP, EMP, TMP, SWMS, WP
label | Inspection/Test Method - Visual inspection
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 1.3 - Survey
label | Frequency - Prior to works
label | Acceptance Criteria - Area has been surveyed, highlighting any areas where excavations should not occur (e.g. exclusion zone).
label | Reference Documents - PSP, EMP, TMP, SWMS, WP
label | Inspection/Test Method - Visual inspection
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project/Site Engineer Surveyor
date | Date Completed:
checkpoint | 1.4 - Select Fill Material Source (Under Pavements, Imported)
label | Frequency - Prior to works
label | Acceptance Criteria - Material to meet the following the properties:
label | – – – – – – – – –
label | Wet strength ¦¦ Not less than 125 kN wet/dry strength variation less than 40%
label | – – – – – – – – –
label | Linear Shrinkage ¦¦ < 6%
label | Organic Matter Content ¦¦ < 0.2%
label | Maximum Particle Size ¦¦ 75 mm
label | % Passing 0.075 mm sieve ¦¦ 0-12%
label | Soaked CBR ¦¦ > 20%
label | CBR swell % ¦¦ ≤ 1.5%
label | Permeability < 5 x 10-9 m/s
label | – – – – – – – – –
label | Gradings:
label | ○ Production testing of supplied select fill will be: 1 per 1,000t for first 5000t, increase to 1 per 2000t following conforming 5000t of conforming results
label | – – – – – – – – –
label | AS1152 Sieve Size (mm) ¦¦ Percentage of mass passing sieve size
label | – – – – – – – – –
label | 75.0 ¦¦ 100 to 100
label | 37.5 ¦¦ 67 to 100
label | 26.5 ¦¦ 54 to 100
label | 19.0 ¦¦ 44 to 85
label | 9.5 ¦¦ 31 to 65
label | 4.75 ¦¦ 21 to 50
label | 2.36 ¦¦ 13 to 38
label | 1.18 ¦¦ 9 to 30
label | 0.425 ¦¦ 4 to 23
label | 0.075 ¦¦ 0 to 12
label | – – – – – – – – –
label | Reference Documents - Spec 002 – Cl 2.5 Cl2.7.5
label | Inspection/Test Method - Test Report
label | Record of conformity - This ITP signed
label | HP
label | Responsibility - Project/Site Engineer Principles Rep
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Select Fill Material Source (Other Locations, Site Won)
label | Frequency - Prior to works
label | Acceptance Criteria - Site won or imported material to be chosen based on the assessment that the material is generally free from clay pockets, and rocks that are fractured and/or weathered.
label | Reference Documents - Spec 002 – Cl 2.6.2
label | Inspection/Test Method - Test Report
label | Record of conformity - This ITP signed
label | HP
label | Responsibility - Project/Site Engineer Principles Rep
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Submission of Select Fill Methodology Plan
label | Frequency - 14-days Prior to works
label | Acceptance Criteria - Principal Contractor to submit a Select Fill Methodology addressing the criteria listed in Spec cl. 2.3.1. Hold Point to be released by Principal’s Representative after acceptance of Select Fill Methodology.
label | Reference Documents - Spec cl. 2.3.2
label | Inspection/Test Method - Select Fill methodology & verify
label | Record of conformity - Select Fill methodolog y & this ITP signed
label | HP
label | Responsibility - Project/Site Engineer Principal’s Rep
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.6 - Starting Works
label | Frequency - Prior to works
label | Acceptance Criteria - Principles Representative to approve works starting in each Separable Portion
label | Reference Documents - Spec cl. 2.3.1
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP
label | Responsibility - Project/Site Engineer, Principal’s Rep
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.7 - Preparation of Underlying Surface Layer
label | Frequency - Each lot
label | Acceptance Criteria - All excavation and filling are free draining to low points clear of the working area. Sufficient pumps, well-points, or other equipment for work area are de-watered as required.
label | Reference Documents - Spec cl. 2.8.2 ITP003
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project/Site Engineer Foreman
date | Date Completed:
checkpoint | 1.8 - Cut Floor Level
label | Frequency - Prior to works
label | Acceptance Criteria - Cut floor to be inspected for suitability - compacted, firm and dry
label | Reference Documents - WMS003 cl 3.3.3
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project/Site Engineer Foreman
date | Date Completed:
section | 2.0 - Select Fill Works – Imported Material - Under Pavements
checkpoint | 2.1 - Select Fill Placement
label | Frequency - Each Lot
label | Acceptance Criteria - Each Lot of fill must:
label | ○ Not be greater than 200mm in thickness
label | ○ Material is to maintain within 1% of the optimum moisture content during all steps of placement, compaction, and finishing
label | ○ Placement of material to commence at the crown or the highest side of the pavement, with each lane spread adjacent to the previously placed lane
label | ○ Material to not be contaminated by foreign materials and other contaminants
label | Reference Documents - Spec cl. 2.8.4
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project/Site Engineer Foreman
date | Date Completed:
checkpoint | 2.2 - Proof Rolling & Compaction
label | Frequency - Each Lot
label | Acceptance Criteria - Each layer of select fill under pavements is to be inspected with the Principles Representative.
label | ○ A medium size vibrating roller (or larger) is to be used for all proof rolls.
label | ○ At least 5m of longitudinal Select Fill and 500mm of lateral overlap of proof rolling between adjacent areas is needed.
label | ○ At least one working days’ notice is to be provided to schedule the presence of the Principles Representative.
label | ○ Maximum allowable rutting of 25mm.
label | ○ No heaving to be observed.
label | Reference Documents - Spec cl. 2.10
label | Inspection/Test Method - Visual Inspection & Verify
label | Record of conformity - This ITP signed
label | WP, HP, HP
label | Responsibility - Project/Site Engineer Principal's Rep
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Final Trimming and Surface Finishing
label | Frequency - Per lot (final layer only)
label | Acceptance Criteria - Final layer of Select Fill surface to the required level, grade, and shape with a tolerance of +0mm and -25mm. Intermediate layers of select fill do not require a Survey Conformance Report
label | Reference Documents - Spec cl 2.11 WMS003 – cl3.4.5
label | Inspection/Test Method - SCP
label | Record of conformity - This ITP signed
label | HP
label | Responsibility - Surveyor, Project/Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3.0 - Select Fill Works – Site Won Material – Other Areas (Not Under Pavements)
checkpoint | 3.1 - Select Fill Placement
label | Frequency - Each Lot
label | Acceptance Criteria - Each Lot of fill must:
label | ○ Not be greater than 200mm in thickness.
label | ○ If required, material to be lightly watered to aid in compaction.
label | ○ Placement to start on the high side.
label | ○ Material to not be contaminated by foreign materials and other contaminants.
label | Reference Documents - Spec cl. 2.8.4
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project/Site Engineer Foreman
date | Date Completed:
checkpoint | 3.2 - Proof Rolling & Compaction
label | Frequency - Each Lot – intermediate layers
label | Acceptance Criteria - Intermediate Layers
label | ○ Each intermediate layer will be visually inspected for conformance to the specification following compaction.
label | ○ No rutting greater than 25mm observed
label | Reference Documents - WMS003 – cl3.4.4.1
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project/Site Engineer Foreman
date | Date Completed:
checkpoint | 3.2 - Proof Rolling & Compaction
label | Frequency - Each Lot (final layer only)
label | Acceptance Criteria - Final layer
label | ○ Principles Representative to be invited to visually inspect final layer of Select Fill not under pavements.
label | ○ At least 5m of longitudinal Select Fill and 500mm of lateral overlap of proof rolling between adjacent areas is needed.
label | ○ If requested, Proof rolling is carried out in the presence of the Principles Representative
label | ○ If requested, at least one working days’ notice is to be provided to schedule the presence of the Contract Administrator.
label | ○ Maximum allowable rutting is 25mm.
label | ○ No heaving to be observed.
label | Reference Documents - Spec cl. 2.10 WMS003 – cl3.4.4.1
label | Inspection/Test Method - Visual Inspection & Verify
label | Record of conformity - This ITP signed
label | WP, HP, HP
label | Responsibility - Project/Site Engineer Principal's Rep
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 4.0 - Testing & Acceptance
checkpoint | 4.1 - Classification and Testing (imported material, under pavements only)
label | Frequency - Each Lot
label | Acceptance Criteria - Imported Material Under Pavements
label | – Dry Density as per AS1289.5.3.1
label | ○ 4 test per lot to achieve average
label | ○ Minimum average standard dry density ratio of no less than 98.0%.
label | ○ No single standard dry density ratio test result being less than 97.0%.
label | Reference Documents - Spec cl. 2.9 AS1289 5.3.1, AS1289 5.4.1, AS1289 5.8.1, Spec tab. 2-3
label | Inspection/Test Method - Verify
label | Record of conformity - Test results & This ITP signed
label | HP
label | Responsibility - Project/Site Engineer, Principles Rep Foreman
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Lot Acceptance
label | Frequency - Each Lot
label | Acceptance Criteria - Principles Representative to review acceptance of lot according to table 2-3. Acceptance of lot will not hold up placing succeeding layer of subbase.
label | Reference Documents - Spec Table 2-3 Cl2.12
label | Inspection/Test Method - Verify
label | Record of conformity - Test results & This ITP signed
label | HP
label | Responsibility - Project/Site Engineer, Principles Rep
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
label | On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Print Name:
text | Position:
date | Work Completed On:
date | Date: