## Table 1
Inspection and Test Plan Reviewed and Approved by Customer | Project Structure Specification C0702 Rev. 01 IFC structure DWG | Inspection and Test plan shall be submitted to the Engineer for review and approval before fabrication is commenced | IFCDWGs | PM/PE
Inspection bearings upon receipt at site | Project Structure Specification C0702 Rev. 01 IFC structure DWG | The material receipt at site need to be visually inspected for quantity and make sure no damage occurred during transport | IFCDWG | PM/PE
Remove the connecting balustrade panels between Span 6 and concrete ramp | Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC struclure DWG | Conecting balustrade panels between Span 6 and concrele ramp to be removed |  | Site Supervisor
Positioning the hudraulic jack(s) | Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC structure DWG | Place the hydraulic jack on concrete underneath the main girder once the jack is in the correct location, raise it until it touch the girder (protected surtace) but do not take any weight |  | Site Supervisor
Loosen the uplift restrain! | Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC slructure DWG | Tl1e uplift restraint bolts need to be loosen to allow the bridge end lo be lifted |  | Site Supervisor
Loosen bolts holding the top of the bearing | Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC structure DWG | Bolts holding the top of tl1e bearing need to be loosen |  | Site Supervisor
Packer to be placed between the concrete ramp and the end girders of Span 6 | Replacing and installing permanent bearing Project Stn,clure Specification C0702 Rev. 01 IFC structure DWG | Packer 10 be placed between the concrete ramp and the end girders ol Span 6 to minimize any possible lateral movement |  | Site Supervisor
Jack up the Bridge | Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC structure DWG | Jack up the bridge structure with Jack no more than 5mm gap for removal the Bearing, so that wall panels between Span 5 and 6 are not displaced |  | Site Supervisor
Packer to be placed underneath of girder | Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC structure OWG | Packer to be placed underneath of girder to eliminate suspended load risk |  | Site Supervisor
Remove the temporary bearing top plates | Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC structure DWG | Unscrew the bolts and remove temporary top plates make sure bolting surtaces and threads are clean and free of debris |  | Site Supervisor
Remove the temporary bearing bottom plates | Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC structure DWG | Unscrew the bolts from cast in base plate to remove temporary bottom plates make sure bolting surtaces and threads are clean and free of debris |  | Site Supervisor
Install Permanent bearing bottom plates | Replacing and installing permanen1 bearing Project Structllfe Specification C0702 Rev. 01 IFC structure DWG | Fil the bolt loosly in base plate and bottom girder flange | IFCDrawing | Site Supervisor
Install Permanent bearing top plates | Roplacing ond installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC structure DWG | Fil the bolt loosly in top plates | IFC Drawing | Site Supervisor
Lower the Jack | Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC structure DWG | Lower the Jack until it is no longer taking any weight Once the span has been lowered off the Jack, Remove temporary restraints on the bearings. Remove 1he Jack |  | Site Supervisor
Tightening the permanent bearing Bolts and remove keeper plate | Replacing and installing permanent bearing Standard operation procedure for steel structure bolt tightening SHEQ-01-02-0038 | All Bolts need to be tightened as per Standard operation procedure for steel structure bolt tightening SHEQ-01-02-0038 | Bolt inspection report | Site Supervisor
Visual Inspection | Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC structure DWG AS/NZS 1554.1:2014 Category SP | Visual and Dimensional inspections comple1ed by PFS Project Manager to verify the structural integrity and functionality of the replaced bearings | IFCDWGs | Site Supervisor
Tightening the uplift restraint | Standard operation procedure for steel structure bolt tightening SHEQ-01-02-0038 | Restraint Bolls need to be tightened as per Standard operation procedure for steel structure bolt tightening SHE0-01-02-0038 ensure the 2mm gap between keeper plate and girder ,;,ebb is sustained | Bolt inspection report | Site project Manager
Re-install the connecting balustrade panels between Span 6 and concrete ramp | Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC structure DWG | Conecling balustrade panels between Span 6 and concrete ramp to be re-installed. |  | Sile Supervisor
Compile, review and submit documentation | Project Structure Specification C07 Rev. 01 IFC structure DWG | Documentation and reports to support installation of steel structure items compiled into PFS Manufactures Data Report | PFS Manufactures Data Report | Site project Manager