## Table 1
Inspection and Test Plan Reviewed and Approved by Customer | IFC OWGs | Inspection and Test plan shall be submitted to the Engineer for review and approval before fabrication is commenced. | ITP-002-39028- Span 2 Rev C | Project Manager/ Engineer
Identify paint spec & colour | Specification for coating steelwork on highway structure IFC structure DWG | Coating Specification: Zinc metal thermal Spray TSZ150S and Sealer coat Paint Specification - Anti Graffiti paint system Structure Colour - Resene Armadillo 2GR10 | Painting Project Commencement Meeting Minutes | Project Manager/ Engineer
Preparing Test panels | Specification for coating steelwork on highway structure NZTA S9 | Testing panels (250 mm x 250 mm) showing Blasted surface profile and the metal spray (unsealed and sealed) to be provided along with material certificate, manufacturer's data sheet, brand of sealer, equipment type and set up parameter, name of operator who prepared panel. after satisfactory testing of the sample panel, none of the above items shall be changed. | Inspection report by Paint inspector
Confirmation on protective coatings preparation by painting contractor | Project Structure Specification CO? Rev. 01 AS/NZS 5131 Clause 9.8.4 | The surface needs to be in comply with P3 Treatment based on AS/NZS 5131 clause 9.8.4 Removal of all burrs, fins and weld defect, weld spatter, weld slags and dressing of any weld to removed sharp edges/ spatter, undercut, visible porosity. All sharp edges are ground to a smooth 2 mm radius. | Project Manager/ Engineer
Surface Preparation | Specification for coating steelwork on highway structure NZTA S9 AS/NZS 5131 | Any surface contamination shall be removed in accordance with NACE No. 2/ SSPC-SP 10 (AS 1627.1). Abrasive blast to SSPC-SP 10 (AS 1627.4 Sa 2 1/2) Surface profile shall be within 40 µm to 75µm surface preparation shall not be Carried out in following condition: a) when surface temperature are less than 3C above dew point b) when the relative humidity of the air is above 85% c) in condition of poor visibility with light below 200 Ix | ITP signed to verify blasting completed to Class 2½ finish Contractor paint inspection report
Zinc metal thermal spray (85/15 Zn/Al) | TSZ150S | The coating should be uniform in thickness without excessive drips, sags, porosity or inconsistencies. Thickness measurement need to be performed and thickness to be in range of 150 micron ±20% | Contractor paint inspection report
Coat #1 - Sealer Coat -Penguard Universal | Specification for coating steelwork on highway structure NZTA S9 | A mist coat of Penguard Universal (low viscosity epoxy sealer) to be applied within 2.5 hours after application of thermal metal spray Penguard Universal applied to minimum 50 µm OFT The coating shall be free from breaks in the coating, runs, sags, wrinkles, fat edge, .dust or sand, irregular coated patches, dry spray, brush mark, blisters and pin holes | Contractor paint inspection report
Coat #2 - Penguard Universal | Specification for coating steelwork on highway stnicture NZTA S9 | Recoating interval needs to be considered based on paint data sheet and ambient temperature Penguard Universal applied to minimum 150 µm OFT. The coating shall be free from breaks in the coating, runs, sags, wrinkles, fat edge, dust or sand, irregular coated patches, dry spray, brush mark, blisters and pin holes | Contractor paint inspection report
Coat #3 - Hardtop Optima | Specification for coating steelwork on highway structure NZTA S9 | Recoating interval needs to be considered based on paint data sheet and ambient temperature Hardtop Optima applied to minimum 75 µm OFT. Structure Colour - Resene Armadillo 2GR10 The coating shall be free from break in the coating, runs, sags, wrinkles, fat edge, dust or sand, irregular coated patct,es, dry spray, brush mark, blisters and pin holes | Coating application record by Coating contractor Coating inspection report by Inspector
Specification for coating |  | Adhesion test shall be performed on plate sample determined by
Adhesion test on plate sample steelwork on highway the X-cut tape test using method A of ASTM 03359 Coating application record by Coating which painted along with steel structure stnicture NZTA S9 The acceptance criteria is 4A contractor ASTM 03359 (Approve adhesive tape is 3M No. 810 scotch Magic Tape Coating inspection report by Inspector transparent pressure sensitive paint)
> Visual Inspection of steel structure Specification for coating > Items covered by ITP visually inspected, any defects to be Coaling application record by Coating steelwork on highway remediated before transporting from protective coating facility. contractor > Approved for Transport to PFS structure NZTA S9 > Coating reports reviewed. Coating inspection report by Inspector
Project Manager/ Engineer