## Sheet1
1 | Inspection and Test Plan Reviewed and Approved by Customer | Project Structure Specification C0702 Rev. 01 IFC structure DWG | Inspection and Test plan shall be submitted to the Engineer for review and approval before fabrication is commenced | IFCDWGs | PM/PE | 1 - Inspection and Test Plan Reviewed and Approved by Customer | Specification Standard - Project Structure Specification C0702 Rev. 01 IFC structure DWG | Acceptance Criteria - Inspection and Test plan shall be submitted to the Engineer for review and approval before fabrication is commenced | Certify Doc / Ref - IFCDWGs | PFS Engineering - PM/PE | C - | 1 - Inspection and Test Plan Reviewed and Approved by Customer
2 | Inspection bearings upon receipt at site | Project Structure Specification C0702 Rev. 01 IFC structure DWG | The material receipt at site need to be visually inspected for quantity and make sure no damage occurred during transport | IFCDWG | PM/PE | 2 - Inspection bearings upon receipt at site | Specification Standard - Project Structure Specification C0702 Rev. 01 IFC structure DWG | Acceptance Criteria - The material receipt at site need to be visually inspected for quantity and make sure no damage occurred during transport | Certify Doc / Ref - IFCDWG | PFS Engineering - PM/PE | C - | Specification Standard - Project Structure Specification C0702 Rev. 01 IFC structure DWG
3 | Remove the connecting balustrade panels between Span 6 and concrete ramp | Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC struclure DWG | Conecting balustrade panels between Span 6 and concrele ramp to be removed |  | Site Supervisor | 3 - Remove the connecting balustrade panels between Span 6 and concrete ramp | Specification Standard - Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC struclure DWG | Acceptance Criteria - Conecting balustrade panels between Span 6 and concrele ramp to be removed | Certify Doc / Ref - | PFS Engineering - Site Supervisor | C - | Acceptance Criteria - Inspection and Test plan shall be submitted to the Engineer for review and approval before fabrication is commenced
4 | Positioning the hudraulic jack(s) | Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC structure DWG | Place the hydraulic jack on concrete underneath the main girder once the jack is in the correct location, raise it until it touch the girder (protected surtace) but do not take any weight |  | Site Supervisor | 4 - Positioning the hudraulic jack(s) | Specification Standard - Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC structure DWG | Acceptance Criteria - Place the hydraulic jack on concrete underneath the main girder once the jack is in the correct location, raise it until it touch the girder (protected surtace) but do not take any weight | Certify Doc / Ref - | PFS Engineering - Site Supervisor | C - | Certify Doc / Ref - IFCDWGs
5 | Loosen the uplift restrain! | Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC slructure DWG | Tl1e uplift restraint bolts need to be loosen to allow the bridge end lo be lifted |  | Site Supervisor | 5 - Loosen the uplift restrain! | Specification Standard - Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC slructure DWG | Acceptance Criteria - Tl1e uplift restraint bolts need to be loosen to allow the bridge end lo be lifted | Certify Doc / Ref - | PFS Engineering - Site Supervisor | C - | PFS Engineering - PM/PE
6 | Loosen bolts holding the top of the bearing | Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC structure DWG | Bolts holding the top of tl1e bearing need to be loosen |  | Site Supervisor | 6 - Loosen bolts holding the top of the bearing | Specification Standard - Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC structure DWG | Acceptance Criteria - Bolts holding the top of tl1e bearing need to be loosen | Certify Doc / Ref - | PFS Engineering - Site Supervisor | C - | C -
7 | Packer to be placed between the concrete ramp and the end girders of Span 6 | Replacing and installing permanent bearing Project Stn,clure Specification C0702 Rev. 01 IFC structure DWG | Packer 10 be placed between the concrete ramp and the end girders ol Span 6 to minimize any possible lateral movement |  | Site Supervisor | 7 - Packer to be placed between the concrete ramp and the end girders of Span 6 | Specification Standard - Replacing and installing permanent bearing Project Stn,clure Specification C0702 Rev. 01 IFC structure DWG | Acceptance Criteria - Packer 10 be placed between the concrete ramp and the end girders ol Span 6 to minimize any possible lateral movement | Certify Doc / Ref - | PFS Engineering - Site Supervisor | C - | 2 - Inspection bearings upon receipt at site
8 | Jack up the Bridge | Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC structure DWG | Jack up the bridge structure with Jack no more than 5mm gap for removal the Bearing, so that wall panels between Span 5 and 6 are not displaced |  | Site Supervisor | 8 - Jack up the Bridge | Specification Standard - Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC structure DWG | Acceptance Criteria - Jack up the bridge structure with Jack no more than 5mm gap for removal the Bearing, so that wall panels between Span 5 and 6 are not displaced | Certify Doc / Ref - | PFS Engineering - Site Supervisor | C - | Specification Standard - Project Structure Specification C0702 Rev. 01 IFC structure DWG
9 | Packer to be placed underneath of girder | Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC structure OWG | Packer to be placed underneath of girder to eliminate suspended load risk |  | Site Supervisor | 9 - Packer to be placed underneath of girder | Specification Standard - Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC structure OWG | Acceptance Criteria - Packer to be placed underneath of girder to eliminate suspended load risk | Certify Doc / Ref - | PFS Engineering - Site Supervisor | C - | Acceptance Criteria - The material receipt at site need to be visually inspected for quantity and make sure no damage occurred during transport
10 | Remove the temporary bearing top plates | Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC structure DWG | Unscrew the bolts and remove temporary top plates make sure bolting surtaces and threads are clean and free of debris |  | Site Supervisor | 10 - Remove the temporary bearing top plates | Specification Standard - Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC structure DWG | Acceptance Criteria - Unscrew the bolts and remove temporary top plates make sure bolting surtaces and threads are clean and free of debris | Certify Doc / Ref - | PFS Engineering - Site Supervisor | C - | Certify Doc / Ref - IFCDWG
11 | Remove the temporary bearing bottom plates | Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC structure DWG | Unscrew the bolts from cast in base plate to remove temporary bottom plates make sure bolting surtaces and threads are clean and free of debris |  | Site Supervisor | 11 - Remove the temporary bearing bottom plates | Specification Standard - Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC structure DWG | Acceptance Criteria - Unscrew the bolts from cast in base plate to remove temporary bottom plates make sure bolting surtaces and threads are clean and free of debris | Certify Doc / Ref - | PFS Engineering - Site Supervisor | C - | PFS Engineering - PM/PE
12 | Install Permanent bearing bottom plates | Replacing and installing permanen1 bearing Project Structllfe Specification C0702 Rev. 01 IFC structure DWG | Fil the bolt loosly in base plate and bottom girder flange | IFCDrawing | Site Supervisor | 12 - Install Permanent bearing bottom plates | Specification Standard - Replacing and installing permanen1 bearing Project Structllfe Specification C0702 Rev. 01 IFC structure DWG | Acceptance Criteria - Fil the bolt loosly in base plate and bottom girder flange | Certify Doc / Ref - IFCDrawing | PFS Engineering - Site Supervisor | C - | C -
13 | Install Permanent bearing top plates | Roplacing ond installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC structure DWG | Fil the bolt loosly in top plates | IFC Drawing | Site Supervisor | 13 - Install Permanent bearing top plates | Specification Standard - Roplacing ond installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC structure DWG | Acceptance Criteria - Fil the bolt loosly in top plates | Certify Doc / Ref - IFC Drawing | PFS Engineering - Site Supervisor | C - | 3 - Remove the connecting balustrade panels between Span 6 and concrete ramp
14 | Lower the Jack | Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC structure DWG | Lower the Jack until it is no longer taking any weight Once the span has been lowered off the Jack, Remove temporary restraints on the bearings. Remove 1he Jack |  | Site Supervisor | 14 - Lower the Jack | Specification Standard - Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC structure DWG | Acceptance Criteria - Lower the Jack until it is no longer taking any weight Once the span has been lowered off the Jack, Remove temporary restraints on the bearings. Remove 1he Jack | Certify Doc / Ref - | PFS Engineering - Site Supervisor | C - | Specification Standard - Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC struclure DWG
15 | Tightening the permanent bearing Bolts and remove keeper plate | Replacing and installing permanent bearing Standard operation procedure for steel structure bolt tightening SHEQ-01-02-0038 | All Bolts need to be tightened as per Standard operation procedure for steel structure bolt tightening SHEQ-01-02-0038 | Bolt inspection report | Site Supervisor | 15 - Tightening the permanent bearing Bolts and remove keeper plate | Specification Standard - Replacing and installing permanent bearing Standard operation procedure for steel structure bolt tightening SHEQ-01-02-0038 | Acceptance Criteria - All Bolts need to be tightened as per Standard operation procedure for steel structure bolt tightening SHEQ-01-02-0038 | Certify Doc / Ref - Bolt inspection report | PFS Engineering - Site Supervisor | C - | Acceptance Criteria - Conecting balustrade panels between Span 6 and concrele ramp to be removed
16 | Visual Inspection | Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC structure DWG AS/NZS 1554.1:2014 Category SP | Visual and Dimensional inspections comple1ed by PFS Project Manager to verify the structural integrity and functionality of the replaced bearings | IFCDWGs | Site Supervisor | 16 - Visual Inspection | Specification Standard - Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC structure DWG AS/NZS 1554.1:2014 Category SP | Acceptance Criteria - Visual and Dimensional inspections comple1ed by PFS Project Manager to verify the structural integrity and functionality of the replaced bearings | Certify Doc / Ref - IFCDWGs | PFS Engineering - Site Supervisor | C - | Certify Doc / Ref -
17 | Tightening the uplift restraint | Standard operation procedure for steel structure bolt tightening SHEQ-01-02-0038 | Restraint Bolls need to be tightened as per Standard operation procedure for steel structure bolt tightening SHE0-01-02-0038 ensure the 2mm gap between keeper plate and girder ,;,ebb is sustained | Bolt inspection report | Site project Manager | 17 - Tightening the uplift restraint | Specification Standard - Standard operation procedure for steel structure bolt tightening SHEQ-01-02-0038 | Acceptance Criteria - Restraint Bolls need to be tightened as per Standard operation procedure for steel structure bolt tightening SHE0-01-02-0038 ensure the 2mm gap between keeper plate and girder ,;,ebb is sustained | Certify Doc / Ref - Bolt inspection report | PFS Engineering - Site project Manager | C - | PFS Engineering - Site Supervisor
18 | Re-install the connecting balustrade panels between Span 6 and concrete ramp | Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC structure DWG | Conecling balustrade panels between Span 6 and concrete ramp to be re-installed. |  | Sile Supervisor | 18 - Re-install the connecting balustrade panels between Span 6 and concrete ramp | Specification Standard - Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC structure DWG | Acceptance Criteria - Conecling balustrade panels between Span 6 and concrete ramp to be re-installed. | Certify Doc / Ref - | PFS Engineering - Sile Supervisor | C - | C -
19 | Compile, review and submit documentation | Project Structure Specification C07 Rev. 01 IFC structure DWG | Documentation and reports to support installation of steel structure items compiled into PFS Manufactures Data Report | PFS Manufactures Data Report | Site project Manager | 19 - Compile, review and submit documentation | Specification Standard - Project Structure Specification C07 Rev. 01 IFC structure DWG | Acceptance Criteria - Documentation and reports to support installation of steel structure items compiled into PFS Manufactures Data Report | Certify Doc / Ref - PFS Manufactures Data Report | PFS Engineering - Site project Manager | C - | 4 - Positioning the hudraulic jack(s)
Specification Standard - Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC structure DWG
Acceptance Criteria - Place the hydraulic jack on concrete underneath the main girder once the jack is in the correct location, raise it until it touch the girder (protected surtace) but do not take any weight
Certify Doc / Ref -
PFS Engineering - Site Supervisor
C -
5 - Loosen the uplift restrain!
Specification Standard - Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC slructure DWG
Acceptance Criteria - Tl1e uplift restraint bolts need to be loosen to allow the bridge end lo be lifted
Certify Doc / Ref -
PFS Engineering - Site Supervisor
C -
6 - Loosen bolts holding the top of the bearing
Specification Standard - Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC structure DWG
Acceptance Criteria - Bolts holding the top of tl1e bearing need to be loosen
Certify Doc / Ref -
PFS Engineering - Site Supervisor
C -
7 - Packer to be placed between the concrete ramp and the end girders of Span 6
Specification Standard - Replacing and installing permanent bearing Project Stn,clure Specification C0702 Rev. 01 IFC structure DWG
Acceptance Criteria - Packer 10 be placed between the concrete ramp and the end girders ol Span 6 to minimize any possible lateral movement
Certify Doc / Ref -
PFS Engineering - Site Supervisor
C -
8 - Jack up the Bridge
Specification Standard - Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC structure DWG
Acceptance Criteria - Jack up the bridge structure with Jack no more than 5mm gap for removal the Bearing, so that wall panels between Span 5 and 6 are not displaced
Certify Doc / Ref -
PFS Engineering - Site Supervisor
C -
9 - Packer to be placed underneath of girder
Specification Standard - Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC structure OWG
Acceptance Criteria - Packer to be placed underneath of girder to eliminate suspended load risk
Certify Doc / Ref -
PFS Engineering - Site Supervisor
C -
10 - Remove the temporary bearing top plates
Specification Standard - Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC structure DWG
Acceptance Criteria - Unscrew the bolts and remove temporary top plates make sure bolting surtaces and threads are clean and free of debris
Certify Doc / Ref -
PFS Engineering - Site Supervisor
C -
11 - Remove the temporary bearing bottom plates
Specification Standard - Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC structure DWG
Acceptance Criteria - Unscrew the bolts from cast in base plate to remove temporary bottom plates make sure bolting surtaces and threads are clean and free of debris
Certify Doc / Ref -
PFS Engineering - Site Supervisor
C -
12 - Install Permanent bearing bottom plates
Specification Standard - Replacing and installing permanen1 bearing Project Structllfe Specification C0702 Rev. 01 IFC structure DWG
Acceptance Criteria - Fil the bolt loosly in base plate and bottom girder flange
Certify Doc / Ref - IFCDrawing
PFS Engineering - Site Supervisor
C -
13 - Install Permanent bearing top plates
Specification Standard - Roplacing ond installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC structure DWG
Acceptance Criteria - Fil the bolt loosly in top plates
Certify Doc / Ref - IFC Drawing
PFS Engineering - Site Supervisor
C -
14 - Lower the Jack
Specification Standard - Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC structure DWG
Acceptance Criteria - Lower the Jack until it is no longer taking any weight Once the span has been lowered off the Jack, Remove temporary restraints on the bearings. Remove 1he Jack
Certify Doc / Ref -
PFS Engineering - Site Supervisor
C -
15 - Tightening the permanent bearing Bolts and remove keeper plate
Specification Standard - Replacing and installing permanent bearing Standard operation procedure for steel structure bolt tightening SHEQ-01-02-0038
Acceptance Criteria - All Bolts need to be tightened as per Standard operation procedure for steel structure bolt tightening SHEQ-01-02-0038
Certify Doc / Ref - Bolt inspection report
PFS Engineering - Site Supervisor
C -
16 - Visual Inspection
Specification Standard - Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC structure DWG AS/NZS 1554.1:2014 Category SP
Acceptance Criteria - Visual and Dimensional inspections comple1ed by PFS Project Manager to verify the structural integrity and functionality of the replaced bearings
Certify Doc / Ref - IFCDWGs
PFS Engineering - Site Supervisor
C -
17 - Tightening the uplift restraint
Specification Standard - Standard operation procedure for steel structure bolt tightening SHEQ-01-02-0038
Acceptance Criteria - Restraint Bolls need to be tightened as per Standard operation procedure for steel structure bolt tightening SHE0-01-02-0038 ensure the 2mm gap between keeper plate and girder ,;,ebb is sustained
Certify Doc / Ref - Bolt inspection report
PFS Engineering - Site project Manager
C -
18 - Re-install the connecting balustrade panels between Span 6 and concrete ramp
Specification Standard - Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC structure DWG
Acceptance Criteria - Conecling balustrade panels between Span 6 and concrete ramp to be re-installed.
Certify Doc / Ref -
PFS Engineering - Sile Supervisor
C -
19 - Compile, review and submit documentation
Specification Standard - Project Structure Specification C07 Rev. 01 IFC structure DWG
Acceptance Criteria - Documentation and reports to support installation of steel structure items compiled into PFS Manufactures Data Report
Certify Doc / Ref - PFS Manufactures Data Report
PFS Engineering - Site project Manager
C -