## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DN1212-ITP-004-39028.VO07 Bearing Replacement | itp |  |  |  |  | DN1212-ITP-004-39028.VO07 Bearing Replacement RevA
section | ENGINEERING
checkpoint | 1 - Inspection and Test Plan Reviewed and Approved by Customer
label | Specification Standard - Project Structure Specification C0702 Rev. 01 IFC structure DWG
label | Acceptance Criteria - Inspection and Test plan shall be submitted to the Engineer for review and approval before fabrication is commenced
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - PM/PE
label | C - S
label | Downer - Downer
label | C - H
holdpoint | AUTHORITY HOLDPOINT
section | GOOD RECEIPT ON SITE
checkpoint | 2 - Inspection bearings upon receipt at site
label | Specification Standard - Project Structure Specification C0702 Rev. 01 IFC structure DWG
label | Acceptance Criteria - The material receipt at site need to be visually inspected for quantity and make sure no damage occurred during transport
label | Certify Doc / Ref - IFC DWG
label | PFS Engineering - PM/PE
label | C - V
label | Downer - Downer
label | C - R
section | INSTALLATION OF PERMANENT BEARING
checkpoint | 3 - Remove the connecting balustrade panels between Span 6 and concrete ramp
label | Specification Standard - Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC struclure DWG
label | Acceptance Criteria - Connecting balustrade panels between Span 6 and concrele ramp to be removed
label | PFS Engineering - Site Supervisor
label | C - V
checkpoint | 4 - Positioning the hydraulic jack(s)
label | Specification Standard - Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC structure DWG
label | Acceptance Criteria - Place the hydraulic jack on concrete underneath the main girder once the jack is in the correct location, raise it until it touch the girder (protected surtace) but do not take any weight
label | PFS Engineering - Site Supervisor
label | C - V
checkpoint | 5 - Loosen the uplift restraint
label | Specification Standard - Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC structure DWG
label | Acceptance Criteria - the uplift restraint bolts need to be loosen to allow the bridge end lo be lifted
label | PFS Engineering - Site Supervisor
label | C - V
checkpoint | 6 - Loosen bolts holding the top of the bearing
label | Specification Standard - Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC structure DWG
label | Acceptance Criteria - Bolts holding the top of the bearing need to be loosen
label | PFS Engineering - Site Supervisor
label | C - V
checkpoint | 7 - Packer to be placed between the concrete ramp and the end girders of Span 6
label | Specification Standard - Replacing and installing permanent bearing Project Stn,clure Specification C0702 Rev. 01 IFC structure DWG
label | Acceptance Criteria - Packer to be placed between the concrete ramp and the end girders of Span 6 to minimize any possible lateral movement
label | PFS Engineering - Site Supervisor
label | C - V
checkpoint | 8 - Jack up the Bridge
label | Specification Standard - Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC structure DWG
label | Acceptance Criteria - Jack up the bridge structure with Jack no more than 5mm gap for removal the Bearing, so that wall panels between Span 5 and 6 are not displaced
label | PFS Engineering - Site Supervisor
label | C - V, D
checkpoint | 9 - Packer to be placed underneath of girder
label | Specification Standard - Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC structure DWG
label | Acceptance Criteria - Packer to be placed underneath of girder to eliminate suspended load risk
label | PFS Engineering - Site Supervisor
label | C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Remove the temporary bearing top plates
label | Specification Standard - Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC structure DWG
label | Acceptance Criteria - Unscrew the bolts and remove temporary top plates make sure bolting surtaces and threads are clean and free of debris
label | PFS Engineering - Site Supervisor
label | C - V
checkpoint | 11 - Remove the temporary bearing bottom plates
label | Specification Standard - Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC structure DWG
label | Acceptance Criteria - Unscrew the bolts from cast in base plate to remove temporary bottom plates make sure bolting surtaces and threads are clean and free of debris
label | PFS Engineering - Site Supervisor
label | C - V
checkpoint | 12 - Install Permanent bearing bottom plates
label | Specification Standard - Replacing and installing permanen1 bearing Project Structure Specification C0702 Rev. 01 IFC structure DWG
label | Acceptance Criteria - Fit the bolt loosely in base plate and bottom girder flange
label | Certify Doc / Ref - IFC Drawing
label | PFS Engineering - Site Supervisor
label | C - V
checkpoint | 13 - Install Permanent bearing top plates
label | Specification Standard - Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC structure DWG
label | Acceptance Criteria - Fit the bolt loosely in top plates
label | Certify Doc / Ref - IFC Drawing
label | PFS Engineering - Site Supervisor
label | C - V
checkpoint | 14 - Lower the Jack
label | Specification Standard - Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC structure DWG
label | Acceptance Criteria - Lower the Jack until it is no longer taking any weight
label | ○ Once the span has been lowered off the Jack, Remove temporary restraints on the bearings. Remove the Jack
label | PFS Engineering - Site Supervisor
label | C - V
checkpoint | 15 - Tightening the permanent bearing Bolts and remove keeper plate
label | Specification Standard - Replacing and installing permanent bearing Standard operation procedure for steel structure bolt tightening SHEQ-01-02-0038
label | Acceptance Criteria - All Bolts need to be tightened as per Standard operation procedure for steel structure bolt tightening SHEQ-01-02-0038
label | Certify Doc / Ref - Bolt inspection report
label | PFS Engineering - Site Supervisor
label | C - V
checkpoint | 16 - Visual Inspection
label | Specification Standard - Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC structure DWG AS/NZS 1554.1:2014 Category SP
label | Acceptance Criteria - Visual and Dimensional inspections comple1ed by PFS Project Manager to verify the structural integrity and functionality of the replaced bearings
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - Site Supervisor
label | C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 17 - Tightening the uplift restraint
label | Specification Standard - Standard operation procedure for steel structure bolt tightening SHEQ-01-02-0038
label | Acceptance Criteria - Restraint Bolls need to be tightened as per Standard operation procedure for steel structure bolt tightening SHEQ-01-02-0038
label | ○ Ensure the 2mm gap between keeper plate and girder webb is sustained
label | Certify Doc / Ref - Bolt inspection report
label | PFS Engineering - Site project Manager
label | C - V
checkpoint | 18 - Re-install the connecting balustrade panels between Span 6 and concrete ramp
label | Specification Standard - Replacing and installing permanent bearing Project Structure Specification C0702 Rev. 01 IFC structure DWG
label | Acceptance Criteria - Connecting balustrade panels between Span 6 and concrete ramp to be re-installed.
label | PFS Engineering - Sile Supervisor
label | C - V
section | QUALITY REVIEW
checkpoint | 19 - Compile, review and submit documentation
label | Specification Standard - Project Structure Specification C07 Rev. 01 IFC structure DWG
label | Acceptance Criteria - Documentation and reports to support installation of steel structure items compiled into PFS Manufactures Data Report
label | Certify Doc / Ref - PFS Manufactures Data Report
label | PFS Engineering - Site project Manager
label | C - S
label | Downer - Downer
label | C - RA
section | FINAL ITP CLOSE-OUT
checkpoint-no-status | ITP APPROVAL PROCESS
textbox | Approved by [Engineer/Client] - Name:
textbox | Issued for Construction - Name:
date | Date:
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | DN1212-ITP-001-39028 Shop Fabrication Span 2 | itp |  |  |  |  | DN1212-ITP-001-39028 Shop Fabrication Span 2 RevD
section | ENGINEERING
checkpoint | 1 - Inspection and Test Plan Reviewed and Approved by Customer
label | Specification Standard - Project Structure Specification C07 Rev. 01 IFC structure DWG
label | Acceptance Criteria - Inspection and Test plan shall be submitted to the Engineer for review and approval before fabrication is commenced.
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - PM/PE
label | C - S
label | Downer - Downer
label | C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Shop Drawing approval
label | Specification Standard - Project Structure Specification C07 Rev. 01 IFC structure DWG
label | Acceptance Criteria - Shop Drawing shall be submitted to Engineer for review along with Shop Drawing Check form
label | Certify Doc / Ref - Shop Drawing Check form
label | PFS Engineering - PM/PE
label | C - S
label | Downer - Downer
label | C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Submit Inspection personel competencies
label | Specification Standard - Project Structure Specification C07 Rev. 01
label | Acceptance Criteria - Inspection personnel (Independent inspectors) qualification and certificate shall be submitted to the Engineer for review and approval according to C0701.2.4
label | Certify Doc / Ref - NDT qualification
label | PFS Engineering - PM/PE
label | C - S
label | Downer - Downer
label | C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Welding Procedures - Structural
label | Specification Standard - AS/NZS 1554.1 :2014 Category SP
label | Acceptance Criteria - Details of the welding procedures to be used including details of the equipment and consumables before any welding is carried out. No welder shall carry out work for which he is not certified.
label | Certify Doc / Ref - Welding Procedures HERNCSWIP Stamp
label | PFS Engineering - PM/PE
label | C - S
label | Subcontracted scope - SQA
label | C - RA
checkpoint | 5 - Welder Qualifications - Structural
label | Specification Standard - AS/NZS 1554.1 :2014, ISO 9606-1 :2017
label | Acceptance Criteria - A list of proposed welders and their welding certificates to be provided prior to any welding being carried out.
label | ○ No welder shall carry out work for which he is not certified.
label | Certify Doc / Ref - WQT by Authorised Person (Welding Supervisor)
label | PFS Engineering - PM/PE
label | C - S
label | Subcontracted scope - SQA
label | C - RA
checkpoint | 6 - Submit the required documents to Client for review
label | Specification Standard - Project Structure Specification C07 Rev. 01
label | Acceptance Criteria - Following shall be submitted to the Engineer for review before fabrication is commenced:
label | 1 - Quality Management Plan
label | 2 - IMS Manual
label | 3 - SFC Certificate
label | 4 - ISO 9001 Certificate
label | Certify Doc / Ref - Quality certificates Quality Plan
label | PFS Engineering - PM/PE
label | C - S
label | Downer - Downer
label | C - R
section | PROCUREMENT
checkpoint | 7 - Procurement of materials in line with IFC drawings and Technical Specification
label | Specification Standard - Project Structure Specification C07 Rev.01 IFC structure DWG
label | Acceptance Criteria - Materials match that specified in Project IFC drawings and Technical Specification.
label | ○ Structural steel Material shall be sourced from suppliers certified by ACRS
label | ○ Material test certificates shall report all element required by AS/NZS relevant standard, plus total boron content
label | ○ (Manufacturer certificates shall from ILAC MRA laboratories)
label | Certify Doc / Ref - Supplier Material Certificate
label | PFS Engineering - PM/PE
label | C - RA / S
label | Downer - Downer
label | C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Procurement of Welding consumable to match Weld procedure and parent materials.
label | Specification Standard - AS/NZS 1554.1
label | Acceptance Criteria - Welding consumables and gas match what is specified on the appropriate welding procedures.
label | Certify Doc / Ref - Supplier Material Certificate PFS Welding Procedures
label | PFS Engineering - PM/PE
label | C - RA
checkpoint | 9 - Material inspection upon receiving (By supplier/sub-contractor/ Free issue material)
label | Specification Standard - Project Structure Specification C07 Rev. 01 IFC structure DWG
label | Acceptance Criteria - All material shall be inspected against IFC drawing to make sure material grades, type, thickness, size are in compliance with IFC DWGs.
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - Team Leader
label | C - H
holdpoint | AUTHORITY HOLDPOINT
section | STEEL STRUCTURE FABRICATION
checkpoint | 10 - Manufacturing Work Pack Issued to Production Manager
label | Specification Standard - Project Structure Specification C07 Rev.01 IFC structure DWG
label | Acceptance Criteria - Job barcodes, Inspection & Test Plan's, IFC Fabrication Drawings, Reference Drawings/Info, Welding Procedures, weld map, welding log info, traceability sheet
label | PFS Engineering - Production Manager
label | C - RA
checkpoint | 11 - Cutting the structural steel
label | Specification Standard - Project Structure Specification C07 Rev. 01 IFC structure DWG SHEQ-01-02-0039
label | Acceptance Criteria - Dimensional survey of fabricated item's against IFC drawings.
label | ○ Measured dimensions shall be within Functional Tolerances class 2 as per AS/NZS 5131 Table F2.1 to F2.10
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - Team Leader
label | C - D
checkpoint | 12 - Holing
label | Specification Standard - Project Structure Specification C07 Rev. 01 IFC structure DWG SHEQ-01-02-0040
label | Acceptance Criteria - Dimensional survey of fabricated item's against IFC drawings.
label | ○ Measured dimensions shall be within Functional Tolerances class 2 as per AS/NZS 5131 Table F2.1 to F2.10
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - Team Leader
label | C - D
checkpoint | 13 - Identification and traceability for main items
label | Specification Standard - Project Structure Specification C07 Rev. 01 IFC structure DWG AS/NZS 5131
label | Acceptance Criteria - Lot traceability shall be provided for main structural members, connections between main structural members and major plate components. Tracibility as per AS/NZS 5131:Amd 1 :2020 5.2.3 (ii) for minor components including cleats, connecting brackets and the like.
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - PM/PE
label | C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14 - Manufacture of steel structure Tack welded only
label | Specification Standard - IFC DWGs
label | Acceptance Criteria - Manufacture completed as per IFC Fabrication drawings. All tack welding shall be performed in accordance with PFS weld procedure.
label | ○ Welding consumables, process & any applicable pre/post heat requirements shall comply with approved welding procedure's.
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - Team Leader
label | C - D
checkpoint | 15 - Pre Weld Dimensional Check (Tack Check)
label | Specification Standard - IFC Drawings
label | Acceptance Criteria - Dimensional survey of fabricated items against IFC drawings.
label | ○ Measured dimensions shall be within stated tolerances unless noted otherwise.
label | ○ Project specification clause C0702.1.3
label | ○ Functional Tolerances shall be class 2 as per AS/NZS 5131 Table F2.1 to F2.10
label | ○ Inspections recorded in line with SHEQ-01-02-0035 Product lnspection Procedure
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - Team Leader
label | C - D
checkpoint | 16 - Welding
label | Specification Standard - AS/NZS 1554.1, AS/NZS 9606.1
label | Acceptance Criteria - All welding shall be performed in accordance with PFS weld procedures
label | ○ Welding consumables, process & any applicable pre/post heat requirements shall comply with approved welding procedure's. Welder ID, weld date & consumable batch are recorded on traceability register.
label | Certify Doc / Ref - Welding Procedure and Welder Qualification
label | PFS Engineering - Team Leader
label | C - V
checkpoint | 17 - Post Weld Dimensional Check
label | Specification Standard - IFC DWGs
label | Acceptance Criteria - Dimensional survey of fabricated items against IFC drawings.
label | ○ Measured dimensions shall be within stated tolerances unless noted otherwise.
label | ○ Project specification clause C0702.1.3
label | ○ Functional Tolerances shall be class 2 as per AS/NZS 5131 Table F2.1 to F2.10
label | ○ Inspections recorded in line with SHEQ-01-02-0035 Product lnsnection Procedure
label | Certify Doc / Ref - IFC DWGs & Workshop Pack.
label | PFS Engineering - Team Leader
label | C - D
checkpoint | 18 - Weld Visual Scanning (PFS Internal Check)
label | Specification Standard - IFC Drawing
label | Acceptance Criteria - 100% of all welds shall be subject to visual scanning
label | Certify Doc / Ref - PFS NDT Register
label | PFS Engineering - Team Leader
label | C - V
checkpoint | 19 - NDT inspection
label | Specification Standard - Project Structure Specification C07 Rev. 01
label | Acceptance Criteria - NOE shall include as a minimum:
label | ○ 100% Visual Scanning, 100% Visual examination, 100% UT examination of all butt weld, 10% MT examination for fillet weld
label | ○ The Welding Compliance Inspector shall complete all inspections including any additional inspection, tests and reports necessary due to any welding or welding related workmanship defects.
label | Certify Doc / Ref - Stamped NDT report
label | PFS Engineering - PM/PE
label | C - RA
label | Subcontracted scope - NDT subcontractor
label | C - S
checkpoint | 20 - Protective Coatings Preparation
label | Specification Standard - Project Structure Specification C07 Rev. 01
label | Acceptance Criteria - Removal of all weld spatter and dressing of any weld to removed sharp edges/ spatter.
label | ○ All sharp edges are ground to a smooth 2 mm radius.
label | Certify Doc / Ref - N/A
label | PFS Engineering - Team Leader
label | C - V
checkpoint | 21 - Fabrication NCR (if any)
label | Specification Standard - Project Structure Specification C07 Rev. 01
label | Acceptance Criteria - All Non-conformities reported in PFS NCR system during manufacturing of steel structure need to be submitted to Client for approval
label | PFS Engineering - PM/PE
label | C - S
label | Downer - Downer
label | C - RA
section | SHOP ASSEMBLY - PANELS, HANDRAILS AND BALUSTRADES
checkpoint | 22 - Inspection the free issue pannel uppon receipt at PFS work shop
label | Specification Standard - Panel DWGs
label | Acceptance Criteria - Check panel to make sure the quantity and/or dimension are based on approved DWGs.
label | Certify Doc / Ref - Panel DWGs
label | PFS Engineering - Team Leader
label | C - V
checkpoint | 23 - Panels Pre-assembly
label | Specification Standard - Project Structure Specification C07 Rev. 01 IFC structure DWG
label | Acceptance Criteria - After painting, Client supplied pannels for decking and balastrades to be assembled.
label | ○ Handrails need to be assembled in the shop
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - Team Leader
label | C - V / D
checkpoint | 24 - Dimension check
label | Specification Standard - IFC DWG
label | Acceptance Criteria - Compliance with IFC DWGs
label | PFS Engineering - Team Leader
label | C - D
checkpoint | 25 - Visual inspection of Fasteners (Free issue)
label | Specification Standard - IFC Drawing
label | Acceptance Criteria - All fasteners (bolts, nuts, washers) are to be in complied with the Porject requirement (Grade, Size and Length)
label | Certify Doc / Ref - IFC Drawing
label | PFS Engineering - Team Leader
label | C - V
checkpoint | 26 - Snug lightening of conposite component fixings
label | Specification Standard - Standard operation procedure for steel structure bolt tightening SHEQ-01-02-0038
label | Acceptance Criteria - 100% of fixings securing composite material to structure are to be inspected for snug tight condition and marked with coloured paint pen to confirm fixing condtion has been checked and verified.
label | PFS Engineering - Team Leader
label | C - V
checkpoint | 27 - Final Inspection
label | Specification Standard - IFC Drawings, AS/NZS 1554.1:2014 Category SP
label | Acceptance Criteria - Visual and Dimensional inspections completed by PFS Project Manager to confirm manufactured items have been manufactured to acceptable standard & tolerance and approved to progress to protective coatings.
label | ○ Confirmation that dimensional inspections have been completed in line with SHEQ-01-02-0035 Product Inspection Procedure
label | ○ Confirmation that required quantity and type's of NOE has been completed and any identified defects have been remediated.
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - PM/PE
label | C - RA
section | QUALITY REVIEW
checkpoint | 28 - Compile, review and submit documentation
label | Specification Standard - Project Structure Specification C07 Rev.01 IFC structure DWG
label | Acceptance Criteria - Documentation, Certificates and reports to support manufacture of steel structure and subcontracted items compiled into PFS Manufactures Data Report
label | Certify Doc / Ref - PF'S Manufactures Data Report
label | PFS Engineering - PM/PE
label | C - RA
label | Downer - Downer
label | C - RA
section | FINAL ITP CLOSE-OUT
checkpoint-no-status | ITP APPROVAL PROCESS
textbox | Approved by [Engineer/Client] - Name:
textbox | Issued for Construction - Name:
date | Date:
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | DN1212-ITP-001-39028 Lighting and Conduit Span 2 | itp |  |  |  |  | DN1212-ITP-001-39028 Lighting and Conduit Span 2 RevA
section | ENGINEERING
checkpoint | 1 - Inspection and Test Plan Reviewed and Approved by Customer
label | Specification Standard - Project Structure Specification C07 Rev. 01 IFC structure DWG
label | Acceptance Criteria - Inspection and Test plan shall be submitted to the Engineer for review and approval before fabrication is commenced.
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - PM/PE
label | C - S
label | Downer - Downer
label | C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Shop Drawing approval
label | Specification Standard - Project Structure Specification C07 Rev. 01 IFC structure DWG
label | Acceptance Criteria - Shop Drawing shall be submitted to Engineer for review along with Shop Drawing Check form
label | Certify Doc / Ref - Shop Drawing Check form
label | PFS Engineering - PM/PE
label | C - S
label | Downer - Downer
label | C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Welding Procedures - Structural
label | Specification Standard - AS/NZS 1554.1:2014 Category SP
label | Acceptance Criteria - Details of the welding procedures to be used including details of the equipment and consumables before any welding is carried out. No welder shall carry out work for which he is not certified.
label | Certify Doc / Ref - Welding Procedures HERA/CSWIP Stamp
label | PFS Engineering - PM/PE
label | C - S
label | Subcontracted scope - SQA
label | C - RA
checkpoint | 4 - Welder Qualifications - Structural
label | Specification Standard - AS/NZS 1554.1:2014, ISO 9606-1:2017
label | Acceptance Criteria - A list of proposed welders and their welding certificates to be provided prior to any welding being carried out.
label | ○ No welder shall carry out work for which he is not certified.
label | Certify Doc / Ref - WOT by Authorised Person (Welding Supervisor)
label | PFS Engineering - PM/PE
label | C - S
label | Subcontracted scope - SQA
label | C - RA
section | PROCUREMENT
checkpoint | 5 - Procurement of materials in line with IFC drawings and Technical Specification
label | Specification Standard - Project Structure Specification C07 Rev. 01 IFC structure DWG
label | Acceptance Criteria - Materials match that specified in Project IFC drawings and Technical Specification.
label | ○ Structural steel Material shall be sourced from suppliers certified by ACRS
label | ○ Material test certificates shall report all element required by
label | ○ AS/NZS relevant standard, plus total boron content (Manufacturer certificates shall from ILAC MRA laboratories)
label | Certify Doc / Ref - Supplier Material Certificate
label | PFS Engineering - PM/PE
label | C - RA / S
label | Downer - Downer
label | C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Procurement of Welding consumable to match Weld procedure and parent materials.
label | Specification Standard - AS/NZS 1554.1
label | Acceptance Criteria - Welding consumables and gas match what is specified on the appropriate welding procedures.
label | Certify Doc / Ref - Supplier Material Certificate PFS Welding Procedures
label | PFS Engineering - PM/PE
label | C - RA
checkpoint | 7 - Material inspection upon receiving
label | Specification Standard - Project Structure Specification C07 Rev. 01 IFC structure DWG
label | Acceptance Criteria - All material shall be inspected against IFC drawing to make sure material grades, type, thickness, size are in compliance with IFC DWGs.
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - Team Leader
label | C - H
holdpoint | AUTHORITY HOLDPOINT
section | STEEL STRUCTURE FABRICATION
checkpoint | 8 - Manufacturing Work Pack Issued to Production Manager
label | Specification Standard - Project Structure Specification C07 Rev. 01 IFC structure DWG
label | Acceptance Criteria - Job barcodes, Inspection & Test Plan's, IFC Fabrication Drawings, Reference Drawings/Info, Welding Procedures, weld map, welding log info. traceability sheet
label | PFS Engineering - Production Manager
label | C - RA
checkpoint | 9 - Identification and traceability for main items
label | Specification Standard - Project Structure Specification C07 Rev. 01 IFC structure DWG AS/NZS 5131
label | Acceptance Criteria - Lot traceability shall be provided for main structural members. connections between main structural members and major plate components. Tracibility as per AS/NZS 5131:Amd 1:2020 5.2.3 (ii) for minor components including cleats, connecting brackets and the like.
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - PM/PE
label | C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Manufacture of steel structure Tack welded only
label | Specification Standard - IFC DWGs
label | Acceptance Criteria - Manufacture completed as per IFC Fabrication drawings. All tack welding shall be performed in accordance with PFS weld procedure.
label | ○ Welding consumables. process & any applicable pre/post heat requirements shall comply with approved welding procedure's.
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - Team Leader
label | C - D
checkpoint | 11 - Pre Weld Dimensional Check (Tack Check)
label | Specification Standard - IFC Drawings
label | Acceptance Criteria - Dimensional survey of fabricated items against IFC drawings.
label | ○ Measured dimensions shall be within stated tolerances unless noted otherwise.
label | ○ Project specification clause C0702.1.3 Functional Tolerances shall be class 2 as per AS/NZS 5131 Table F2.1 to F2.10
label | ○ Inspections recorded in line will1 SHEQ-01-02-0035 Product lnspection Procedure
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - Team Leader
label | C - D
checkpoint | 12 - Welding
label | Specification Standard - AS/NZS 1554.1, AS/NZS 9606.1
label | Acceptance Criteria - All welding shall be pertorrned in accordance with PFS weld procedures
label | ○ Welding consumables, process & any applicable pre/post heat requirements shall comply with approved welding procedure's. Welder ID. weld date & consumable batch are recorded on traceability register.
label | Certify Doc / Ref - Welding Procedure and Welder Qualification
label | PFS Engineering - Team Leader
label | C - V
checkpoint | 13 - Post Weld Dimensional Check
label | Specification Standard - IFC DWGs
label | Acceptance Criteria - Dimensional survey of fabricated items against IFC drawings.
label | ○ Measured dimensions shall be within stated tolerances unless noted otherwise.
label | ○ Project specification clause C0702.1.3 Functional Tolerances shall be class 2 as per AS/NZS 5131, Table F2.1 to F2.10
label | ○ Inspections recorded in line with SHEQ-01-02-0035 Product lnsnection Procedure
label | Certify Doc / Ref - IFC DWGs & Workshop Pack.
label | PFS Engineering - Team Leader
label | C - D
checkpoint | 14 - Weld Visual Scanning (PFS Internal Check)
label | Specification Standard - IFC Drawing
label | Acceptance Criteria - 100% of all welds shall be subject to visual scanning
label | Certify Doc / Ref - PFS NOT Register
label | PFS Engineering - Team Leader
label | C - V
checkpoint | 15 - NDT inspection
label | Specification Standard - Project Structure Specification C07 Rev. 01
label | Acceptance Criteria - NOE shall include as a minimum:
label | ○ 100% Visual Scanning, 100% Visual examination
label | ○ The Welding Compliance Inspector shall complete all inspections including any additional inspection, tests and reports necessary due to any welding or welding related workmanship defects.
label | Certify Doc / Ref - Stamped NDT report
label | PFS Engineering - PM/PE
label | C - RA
label | Subcontracted scope - NDT subcontractor
label | C - S
checkpoint | 16 - Prolective Coatings Preparation
label | Specification Standard - Project Structure Specification C07 Rev. 01
label | Acceptance Criteria - Removal of all weld spatter and dressing of any weld to removed sharp edges / spatter.
label | ○ All sharp edges are ground to a smooth 2 mm radius.
label | Certify Doc / Ref - N/A
label | PFS Engineering - Team Leader
label | C - V
checkpoint | 17 - Fabrication NCR (if any)
label | Specification Standard - Project Structure Specification C07 Rev. 01
label | Acceptance Criteria - All Non-conformities reported in PFS NCR system during manufacturing of steel structure need to be submitted to Client for approval
label | PFS Engineering - PM/PE
label | C - S
label | Downer - Downer
label | C - RA
section | ASSEMBLY - LIGHTNING AND CONDUIT BRACKET
checkpoint | 18 - Lighting and conduit bracket - assembly
label | Specification Standard - Project Structure Specification C07 Rev. 01 IFC structure DWG
label | Acceptance Criteria - After coating, the bracketes to be assembled on GRP material
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - Team Leader
label | C - V / D
checkpoint | 19 - Holing
label | Specification Standard - Project Structure Specification C07 Rev. 01 IFC structure DWG SHEQ-01-02-0040
label | Acceptance Criteria - Manual holing shall be performed on GRP material.
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - Team Leader
label | C - D
checkpoint | 20 - Dimension check
label | Specification Standard - IFC DWG
label | Acceptance Criteria - Compliance with IFC DWGs
label | PFS Engineering - Team Leader
label | C - D
checkpoint | 21 - Visual inspection of Fasteners
label | Specification Standard - lFC Drawing
label | Acceptance Criteria - All fasteners (bolts, nuts, washers) are to be in complied with the Project requirement (Grade, Size and Length)
label | Certify Doc / Ref - IFC Drawing
label | PFS Engineering - Team Leader
label | C - V
checkpoint | 22 - Snug tightening of fastener to fasten the brackets to the GRP material
label | Specification Standard - Standard operation procedure for steel structure boll lightening SHEQ-01-02-0038
label | Acceptance Criteria - 100% of fixings securing brackets to be inspected for snug light condition and marked with coloured paint pen to confirm fixing condtion has been checked and verified.
label | PFS Engineering - Team Leader
label | C - V
checkpoint | 23 - Assembly of the angles between brackets
label | Specification Standard - Project Structure Specification C07 Rev. 01 IFC structure DWG
label | Acceptance Criteria - The angles to be assembled between bracket with fasteners
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - Team Leader
label | C - V / D
checkpoint | 24 - Snug tightening of fastener to fasten angles to the brackets
label | Specification Standard - Project Structure Specification C07 Rev. 01 IFC structure DWG
label | Acceptance Criteria - The angles to be assembled between bracket with fasteners
label | ○ Lock tight applied to bolts
label | ○ Hand tight for expansion joins
label | PFS Engineering - Team Leader
label | C - V
checkpoint | 25 - Final Inspection
label | Specification Standard - IFC Drawings, AS/NZS 1554.1:2014 Category SP
label | Acceptance Criteria - Visual and Dimensional inspections completed by PFS Project Manager to confirm manufactured items have been manufactured to acceptable standard & tolerance and approved to progress to protective coatings.
label | ○ Confirmation that dimensional inspections have been completed in line with SHEQ-01-02-0035 Product Inspection Procedure
label | ○ Confirmation that required quantity and type's of NOE has been completed and any identified defects have been remediated.
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - PM/PE
label | C - RA
section | QUALITY REVIEW
checkpoint | 26 - Compile, review and submit documentation
label | Specification Standard - Project Structure Specification C07 Rev. 01 IFC structure DWG
label | Acceptance Criteria - Documentation, Certificates and reports to support manufacture of steel structure and subcontracted items compiled into PFS Manufactures Data Report
label | Certify Doc / Ref - PFS Manufactures Data Report
label | PFS Engineering - PM/PE
label | C - RA
label | Downer - Downer
label | C - RA
section | FINAL ITP CLOSE-OUT
checkpoint-no-status | ITP APPROVAL PROCESS
textbox | Approved by [Engineer/Client] - Name:
textbox | Issued for Construction - Name:
date | Date:
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | DN1212-ITP-002-39028 Surface Protection Span 2 | itp |  |  |  |  | DN1212-ITP-002-39028 Surface Protection Span 2 RevC
section | SURFACE PROTECTION
checkpoint | 1 - Inspection and Test Plan Reviewed and Approved by Customer
label | Specification Standard - IFC DWGs
label | Acceptance Criteria - Inspection and Test plan shall be submitted to the Engineer for review and approval before fabrication is commenced.
label | Certify Doc / Ref - ITP-002-39028- Span 2 Rev C
label | PFS Engineering - Project Manager/Engineer
label | C - S
label | Coating inspector - Lumen
label | C - RA
label | Downer - Downer
label | C - RA
checkpoint | 2 - Identify paint spec & colour
label | Specification Standard - Specification for coating steelwork on highway structure IFC structure DWG
label | Acceptance Criteria - Coating Specification: Zinc metal thermal Spray TSZ150S and Sealer coat
label | ○ Paint Specification - Anti Graffiti paint system
label | ○ Structure Colour - Resene Armadillo 2GR10
label | Certify Doc / Ref - Painting Project Commencement Meeting Minutes
label | PFS Engineering - Project Manager/Engineer
label | C - S
label | Downer - Downer
label | C - RA
checkpoint | 3 - Preparing Test panels
label | Specification Standard - Specification for coating steelwork on highway structure NZTA S9
label | Acceptance Criteria - Testing panels (250 mm x 250 mm) showing Blasted surface profile and the metal spray (unsealed and sealed) to be provided along with material certificate, manufacturer's data sheet, brand of sealer, equipment type and set up parameter, name of operator who prepared panel. After satisfactory testing of the sample panel, none of the above items shall be changed.
label | Certify Doc / Ref - Inspection report by Paint inspector
label | Paint contractor - Fleet image/Linkup
label | C - H
label | Coating inspector - Lumen
label | C - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Confirmation on protective coatings preparation by painting contractor
label | Specification Standard - Project Structure Specification C07 Rev. 01 AS/NZS 5131 Clause 9.8.4
label | Acceptance Criteria - The surface needs to be in comply with P3 Treatment based on AS/NZS 5131 clause 9.8.4
label | ○ Removal of all burrs, fins and weld defect, weld spatter, wold slags and dressing of any weld to removed sharp edges / spatter, undercut, visible porosity.
label | ○ All sharp edges are ground to a smooth 2 mm radius.
label | PFS Engineering - Project Manager/Engineer
label | C - H
label | Paint contractor - Fleet image/Linkup
label | C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Surface Preparation
label | Specification Standard - Specification for coating steelwork on highway structure NZTA S9 AS/NZS 5131
label | Acceptance Criteria - Any surface contamination shall be removed in accordance with NACE No. 2/ SSPC-SP 10 (AS 1627.1). Abrasive blast to SSPC-SP 10 (AS 1627.4 Sa 2 1/2)
label | ○ Surface profile shall be within 40 µm to 75µm
label | ○ Surface preparation shall not be Carried out in following condition:
label | a) when surface temperature arc less than 3C above dew point
label | b) when the relative humidity of the air is above 85%
label | c) in condition of poor visibility with light below 200 Ix
label | Certify Doc / Ref - ITP signed to verify blasting completed to Class 2½ finish. Contractor paint inspection report.
label | Paint contractor - Fleet image/Linkup
label | C - H
label | Coating inspector - Lumen
label | C - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Zinc metal thermal spray (85/15 Zn/Al)
label | Specification Standard - TSZ150S
label | Acceptance Criteria - The coating should be uniform in thickness without excessive drips, sags, porosity or inconsistencies.
label | ○ Thickness measurement need to be performed and thickness to be in range of 150 micron ±20%
label | Certify Doc / Ref - Contractor paint inspection report
label | Paint contractor - Fleet image/Linkup
label | C - H
label | Coating inspector - Lumen
label | C - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Coat #1 - Sealer Coat - Penguard Universal
label | Specification Standard - Specification for coating steelwork on highway structure NZTA S9
label | Acceptance Criteria - A mist coat of Penguard Universal (low viscosity epoxy sealer) to be applied within 2.5 hours after application of thermal metal spray
label | ○ Penguard Universal applied to minimum 50 µm DFT
label | ○ The coating shall be free from breaks in the coating, runs, sags, wrinkles, fat edge, dust or sand, irregular coated patches, dry spray, brush mark, blisters and pin holes
label | Certify Doc / Ref - Contractor paint inspection report
label | Paint contractor - Fleet image/Linkup
label | C - H
label | Coating inspector - Lumen
label | C - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Coat #2 - Penguard Universal
label | Specification Standard - Specification for coating steelwork on highway structure NZTA S9
label | Acceptance Criteria - Recoating interval needs lo be considered based on paint data sheet and ambient temperature
label | ○ Penguard Universal applied to minimum 150 µm DFT.
label | ○ The coating shall be free from breaks in the coating, runs, sags, wrinkles, fat edge, dust or sand, irregular coated patches, dry spray, brush mark, blisters and pin holes
label | Certify Doc / Ref - Contractor paint inspection report
label | Paint contractor - Fleet image/Linkup
label | C - H
label | Coating inspector - Lumen
label | C - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Coat #3 - Hardtop Optima
label | Specification Standard - Specification for coating steelwork on highway structure NZTA S9
label | Acceptance Criteria - Recoating interval needs to be considered based on paint data sheet and ambient temperature
label | ○ Hardtop Optima applied to minimum 75 µm DFT.
label | ○ Structure Colour - Resene Armadillo 2GR 10
label | ○ The coating shall be free from break in the coating, runs, sags, wrinkles, fa ledge, dust or sand, irregular coated patches, dry spray, brush mark, blisters and pin holes
label | Certify Doc / Ref - Coating application record by Coating contractor. Coating inspection report by Inspector.
label | Paint contractor - Fleet image/Linkup
label | C - H
label | Coating inspector - Lumen
label | C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Adhesion test on plate sample which painted along with steel structure
label | Specification Standard - Specification for coating steelwork on highway structure NZTA S9 ASTM D3359
label | Acceptance Criteria - Adhesion test shall be performed on plate sample determined by the X-cut tape test using method A of ASTM D3359
label | ○ The acceptance criteria is 4A (Approve adhesive tape is 3M No. 810 scotch Magic Tape transparent pressure sensitive paint)
label | Certify Doc / Ref - Coating application record by Coating contractor. Coating inspection report by Inspector.
label | Paint contractor - Fleet image/Linkup
label | C - H
label | Coating inspector - Lumen
label | C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 - Visual Inspection of steel structure, Approved for Transport to PFS
label | Specification Standard - Specification for coating steelwork on highway structure NZTA S9
label | Acceptance Criteria - Items covered by ITP visually inspected, any defects to be remediated before transrorting from protective coating facility.
label | ○ Coating reports reviewed.
label | Certify Doc / Ref - Coating application record by Coating contractor. Coating inspection report by Inspector.
label | PFS Engineering - Project Manager/Engineer
label | C - RA
section | FINAL ITP CLOSE-OUT
checkpoint-no-status | ITP APPROVAL PROCESS
textbox | Approved by [Engineer/Client] - Name:
textbox | Issued for Construction - Name:
date | Date:
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature