## ITP Cover Page
Traffic Signs Installation Inspection and Test Plan
Project: Tauriko Enabling Project
Number and Revision: DN1210 - 023- 01 - Rev 0
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Tauriko Enabling Project |  |  |  |  | ITP Number: |  |  |  | 023- 01
Project Number: |  |  | DN1210 |  |  |  |  | ITP Status: |  |  |  | Draft
ITP Description: |  |  | Traffic Signs and Barriers |  |  |  |  | Revision: |  | 1000 |  | 0
Contract Number: |  |  | 8287 |  |  |  |  | Drawing Sets: |  |  |  | WSP-DR-RSA 0001,0002, 0003,0101,0102,0103,0104,0105
Customer: |  |  | Waka Kotahi |  |  |  |  | Specification: |  |  |  | Project Specification Section 26, NZTA M23, P24
Quality Specified: |  |  | ISO 9001:2015
Review / Update History | [10 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  |  | Activity Key |  |  | Responsibilities Key
0 | Draft for Approval |  |  | Cordelia Girdler-Brown | [6 empty] | A | Action |  | ENG | Engineer / Engineer's Rep
[11 empty] | B | Report by Breach |  | CR | Customer Rep
[11 empty] | C | Check |  | PD | Project Director
[11 empty] | D | Dimension Inspection |  | PM | Project Manager
[11 empty] | E | Examine |  | OP | Operations Manager
[11 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[11 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[11 empty] | I | Inspection |  | PE | Project Engineer
[11 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[11 empty] | O | Operation |  | QE | Quality Engineer
[11 empty] | R | Review |  | SUP | Superintendent / Supervisor
[11 empty] | S | Subcontractor |  | SV | Surveyor
[11 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[11 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  |  | Name: |  | Signature: |  |  | Date:
Downer PM |  | CHRIS BENSON | [5 empty] | Downer PM |  |  | CHRIS BENSON
Downer QM |  | CORDELIA GIRDLER-BROWN |  |  |  |  | 25/03/2025 | Downer QM |  |  | CORDELIA GIRDLER-BROWN
Client (If Applicable) | [7 empty] | Client (If Applicable)

## ITP Master Body (Sign)
Traffic Signs Installation Inspection and Test Plan
Project: Tauriko Enabling Project
Number and revision DN1210 - 023 - 01 Rev 0
Item No. | Inspection and Test Point | Detail | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Testing Quantity Required (based from schedule qtys) | Verification Activity |  | Downer Conformance of Compliance Signoff
[7 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details | ENGINEERS COMMENTS - Date: | DOWNER RESPONSE - Date:
SECTION 3 – PRE-CONSTRUCTION - MATERIAL, PERSONEL & THIRD PARTY APPROVALS
3.1 | Underground Services | Pothole all services prior to commencement of trenching. Suitably protect the existing services from construction damage. | All underground services marked on site before pot holing or excavation | PS23.5.3 b) | Survey Data/Site Photos | Pre Excavation | H | PE/SE
3.2 | Sign manufacture | Ensure sign products and systems are listed in NZ transport agency's accepted products and systems table in Appendix F of P24 | Listed in Apendix F of P24: specification for permanent traffic signs | PS26.3.2 | Appendix F | Prior to installation | HP | ENG
3.3 | Sign Retroreflective sheeting | All signs be reflectorised with Class 1W sheeting, and must be turned about 5 degree away from the driver's line of sight. | Visual Inspection: Manufactrur's confirmance | PS26.3.3 | Photo/Visual Inspection | Prior to Construction and after installation | HP | ENG
3.4 | Delivery of Materials | Ensure materials are delivered as per project schedule and specifications | Materials delivered in good condition, without damage to anything | Section 26.3.4 (Project Specification PS) | Photo/Visual Inspection | 100% of material deliveries | I | SE, QE, SUP
SECTION 4 – CONSTRUCTION ACTIVITY - W-Section GuardRail Installation/Sign Installation
4.1 | Set out of Traffic Signs | Set out to be done as per IFC drawings/design Specification, if there is no model and position for sign post to mount on grond: seek Engineer's consent follow the installation schedule as per WSP-DR-RSA 0326 | Visual Inspection: checks for appropriate position for sign to install | PS23.11.8.a) vi | Photo/Visual Inspection | Each installation | HP | ENG
4.2 | Installation of small traffic signs | Sign installation follow standard method as indicated in specification and drawings | Visual Inspection: checks for appropriate position for sign to install | PS23.11.8.a) vi | Photo/Visual Inspection/Checksheet | Each installation | I | SE
4.3 | Installation of large signs with face area more than 4.7m2 Specific design | The foundation for post need to be 3500 deep with 750mm dia | Foundation as per design and drawing | WSP-DR-RSA 0336 | Photo/Visual Inspection/Checksheet | Each installation | HP | ENG
4.4 | Installation of large signs with face area more than 4.7m2 Specific design | The foundation for post need to be 3500 deep with 750mm dia, 75mm cover all over: 12YD16 longitubinal bars with YR12@200mm spiral. The concrete to have minimum 30MPa | Foundation REO as per dwg 0336: | WSP-DR-RSA 0337 | Pre Pour inspection/photo/ Concrete Docket | Each installation | HP | ENG
4.5 | Installation of large signs withface area more than 4.7m2 Specific design | The Foundation post pour inspection | Engineers Approval | WSP-DR-RSA 0338 | Post Pour inspection/photo | Each installation | HP | ENG
4.6 | Installation of Retroreflective sheeting | All signs be reflectorised with Class 1W sheeting, and must be turned about 5 degree away from the driver's line of sight. The chevron boards beed to be turned about 10 degrees away as per section 1.10 from MOTSAM part 1 | Visual Inspection | PS26.3.3 | Photo/Visual Inspection | Prior to Construction and after installation | I | SE
4.7 | Foundation Embedment depths for signage posts | The depths provided in the schedule do not include the topsoil, total depth below surface of the signs shall be the embedment depths plus the topsoil depth | Visual Inspection: checks for specified embedment depth | PS26.3.4 g, III | Photo/Visual Inspection/Checksheet | Each installation | I | SE
SECTION 5 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
5.1 | Final Inspection and approval of installed signs | Conduct final inspection and audit of all installations | Visual Inspection | PS26.3 | Final inspection reports, Compliance Sticker from the installer | 100% of installations | R, HP | ENG
5.2 | As built and records of installed signage | As built and record of installed barriers | Survey/Records | PS | As built records | 100% of installations | SV | Surveyor

## ITP Cover Page
Barriers Installation Inspection and Test Plan
Project: Tauriko Enabling Project
Number and Revision: DN1210 - 023-02 - Rev 0
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Tauriko Enabling Project |  |  |  |  | ITP Number: |  |  |  | 023-02
Project Number: |  |  | DN1210 |  |  |  |  | ITP Status: |  |  |  | Draft
ITP Description: |  |  | Barriers installation |  |  |  |  | Revision: |  | 1000 |  | 0
Contract Number: |  |  | 8287 |  |  |  |  | Drawing Sets: |  |  |  | WSP-DR-RSA 0001,0002, 0003,0101,0102,0103,0104,0105
Customer: |  |  | Waka Kotahi |  |  |  |  | Specification: |  |  |  | Project Specification Section 26, NZTA M23, P24
Quality Specified: |  |  | ISO 9001:2015
Review / Update History | [10 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  |  | Activity Key |  |  | Responsibilities Key
0 | Draft for Approval |  |  | Cordelia Girdler-Brown | [6 empty] | A | Action |  | ENG | Engineer / Engineer's Rep
[11 empty] | B | Report by Breach |  | CR | Customer Rep
[11 empty] | C | Check |  | PD | Project Director
[11 empty] | D | Dimension Inspection |  | PM | Project Manager
[11 empty] | E | Examine |  | OP | Operations Manager
[11 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[11 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[11 empty] | I | Inspection |  | PE | Project Engineer
[11 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[11 empty] | O | Operation |  | QE | Quality Engineer
[11 empty] | R | Review |  | SUP | Superintendent / Supervisor
[11 empty] | S | Subcontractor |  | SV | Surveyor
[11 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[11 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  |  | Name: |  | Signature: |  |  | Date:
Downer PM |  | CHRIS BENSON | [5 empty] | Downer PM |  |  | CHRIS BENSON
Downer QM |  | CORDELIA GIRDLER-BROWN |  |  |  |  | 25/03/2025 | Downer QM |  |  | CORDELIA GIRDLER-BROWN
Client (If Applicable) | [7 empty] | Client (If Applicable)

## ITP Master Body (Barrier)
Barriers Installation Inspection and Test Plan
Project: Tauriko Enabling Project
Number and revision DN1210 - 023 -02 Rev 0
Item No. | Inspection and Test Point | Detail | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Testing Quantity Required (based from schedule qtys) | Verification Activity |  | Downer Conformance of Compliance Signoff
[7 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details | ENGINEERS COMMENTS - Date: | DOWNER RESPONSE - Date:
SECTION 3 – PRE-CONSTRUCTION - MATERIAL, PERSONEL & THIRD PARTY APPROVALS
3.1 | Underground Services | Set out new and existing services and identify clashes with design | All underground services marked on site before pot holing or excavation | PS23.5.3 b) | Survey Data/Site Photos | Pre Excavation | H | PE/SE
3.2 | Materials for W-Section Gurad Rail | Confirm that the W-Section barrier meets the specification and NZTA M23 specification | All the materials meets the specification requirements and Engineers Approval | PS 26.5.3 | Material data sheet and Engineers Approval | Prior to Installation | HP | ENG
3.3 | Road Safety hardware system performance | The minimum performance level for permanent road safety hardware systems installed on SH for side is MASH TL-3 | All the materials meets the specification requirements and Engineers Approval | PS26.5.4 | Material data sheet and engineers approval | Prior to Construction | HP | ENG
3.4 | Delivery of Materials | Ensure materials are delivered as per project schedule and specifications | Materials delivered in good condition, within specified timelines | Section 26.3.4 (Project Specification PS) | Delivery receipts, inspection records | 100% of material deliveries | I | SE, QE, SUP
SECTION 4 – CONSTRUCTION ACTIVITY - W-Section GuardRail Installation/Sign Installation
4.1 | Set out of W-section barrier | Set out to be done as per IFC drawings/design Specification | Visual Inspection:and verification as per latest dwg | PS26.5.2 | Photo/Visual Inspection/Checksheet | Each Barrier Installation | HP | ENG
4.2 | Set out of Entry and Exit Terminals | Set out to be done as per IFC drawings/design Specification | Visual Inspection:and verification as per latest dwg | PS26.5.3 | Photo/Visual Inspection/Checksheet | Each Barrier Installation | HP | ENG
4.3 | Installation of W-Section barrier as per AS/NZS 3845 | Set out to be done as per IFC drawings/design Specification, and installation to be done by competence person | Visual Inspection: checks for appropriate Installation following standards | AS/NZS 3845 | Photo/Visual Inspection/Checksheet | Each Barrier Installation | V | SE
4.4 | End Terminal and Thrie beam installed as per AS/NZS 3845, M23 and Project specs | Set out to be done as per IFC drawings/design Specification, and installation to be done by competence person | Visual Inspection: checks for appropriate Installation following standards and QA checklist from suppiler | AS/NZS 3845 | Photo/Visual Inspection/Checksheet | Each Barrier Installation | V | SE
4.5 | Lapping of Rail in direction of Traffic | Lapping of W-Section barrier to be lapped in the direction of traffic | Visual Inspection | NZTA M23 | Photo/Visual Inspection/Checksheet | Each Barrier Installation | M | SE
SECTION 5 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
5.1 | Final Inspection and designer's approval of installed barriers | Conduct final inspection and audit of all installations | Visual Inspection: | Section 26.5.4 Vi (5) (Project Specification PS) | Final inspection reports, approval of installed bariers with tolerance -0mm, +20mm | 100% of installations | HP | ENG
5.2 | As built Records | As built and record of installed barriers | Survey/Records | Project Specification | As built records | 100% of signals and ITS installations | SV | Surveyor