## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DN1210-023-01 ITP Traffic signs Installation | itp |  |  |  |  | DN1210-023-01 ITP Traffic signs Installation Rev 0
section | SECTION 3 – PRE-CONSTRUCTION - MATERIAL, PERSONEL & THIRD PARTY APPROVALS
checkpoint | 3.1 - Underground Services
label | Detail - Pothole all services prior to commencement of trenching. Suitably protect the existing services from construction damage.
label | Acceptance / Conformance Criteria - All underground services marked on site before pot holing or excavation
label | Standard / Specification - PS23.5.3 b)
label | Verifying Document - Survey Data/Site Photos
label | Testing Quantity Required (based from schedule qtys) - Pre Excavation
label | Verification Activity: Activity - H
label | Verification Activity: By - PE/SE
checkpoint | 3.2 - Sign manufacture
label | Detail - Ensure sign products and systems are listed in NZ transport agency's accepted products and systems table in Appendix F of P24
label | Acceptance / Conformance Criteria - Listed in Apendix F of P24: specification for permanent traffic signs
label | Standard / Specification - PS26.3.2
label | Verifying Document - Appendix F
label | Testing Quantity Required (based from schedule qtys) - Prior to installation
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Sign Retroreflective sheeting
label | Detail - All signs be reflectorised with Class 1W sheeting, and must be turned about 5 degree away from the driver's line of sight.
label | Acceptance / Conformance Criteria - Visual Inspection: Manufactrur's confirmance
label | Standard / Specification - PS26.3.3
label | Verifying Document - Photo/Visual Inspection
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction and after installation
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Delivery of Materials
label | Detail - Ensure materials are delivered as per project schedule and specifications
label | Acceptance / Conformance Criteria - Materials delivered in good condition, without damage to anything
label | Standard / Specification - Section 26.3.4 (Project Specification PS)
label | Verifying Document - Photo/Visual Inspection
label | Testing Quantity Required (based from schedule qtys) - 100% of material deliveries
label | Verification Activity: Activity - I
label | Verification Activity: By - SE, QE, SUP
section | SECTION 4 – CONSTRUCTION ACTIVITY - W-Section GuardRail Installation/Sign Installation
checkpoint | 4.1 - Set out of Traffic Signs
label | Detail - Set out to be done as per IFC drawings/design Specification, if there is no model and position for sign post to mount on grond: seek Engineer's consent follow the installation schedule as per WSP-DR-RSA 0326
label | Acceptance / Conformance Criteria - Visual Inspection: checks for appropriate position for sign to install
label | Standard / Specification - PS23.11.8.a) vi
label | Verifying Document - Photo/Visual Inspection
label | Testing Quantity Required (based from schedule qtys) - Each installation
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Installation of small traffic signs
label | Detail - Sign installation follow standard method as indicated in specification and drawings
label | Acceptance / Conformance Criteria - Visual Inspection: checks for appropriate position for sign to install
label | Standard / Specification - PS23.11.8.a) vi
label | Verifying Document - Photo/Visual Inspection/Checksheet
label | Testing Quantity Required (based from schedule qtys) - Each installation
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.3 - Installation of large signs with face area more than 4.7m2 Specific design
label | Detail - The foundation for post need to be 3500 deep with 750mm dia
label | Acceptance / Conformance Criteria - Foundation as per design and drawing
label | Standard / Specification - WSP-DR-RSA 0336
label | Verifying Document - Photo/Visual Inspection/Checksheet
label | Testing Quantity Required (based from schedule qtys) - Each installation
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.4 - Installation of large signs with face area more than 4.7m2 Specific design
label | Detail - The foundation for post need to be 3500 deep with 750mm dia, 75mm cover all over: 12YD16 longitubinal bars with YR12@200mm spiral.
label | ○ The concrete to have minimum 30MPa
label | Acceptance / Conformance Criteria - Foundation REO as per dwg 0336:
label | Standard / Specification - WSP-DR-RSA 0337
label | Verifying Document - Pre Pour inspection/photo/ Concrete Docket
label | Testing Quantity Required (based from schedule qtys) - Each installation
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.5 - Installation of large signs withface area more than 4.7m2 Specific design
label | Detail - The Foundation post pour inspection
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - WSP-DR-RSA 0338
label | Verifying Document - Post Pour inspection/photo
label | Testing Quantity Required (based from schedule qtys) - Each installation
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.6 - Installation of Retroreflective sheeting
label | Detail - All signs be reflectorised with Class 1W sheeting, and must be turned about 5 degree away from the driver's line of sight. The chevron boards beed to be turned about 10 degrees away as per section 1.10 from MOTSAM part 1
label | Acceptance / Conformance Criteria - Visual Inspection
label | Standard / Specification - PS26.3.3
label | Verifying Document - Photo/Visual Inspection
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction and after installation
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.7 - Foundation Embedment depths for signage posts
label | Detail - The depths provided in the schedule do not include the topsoil, total depth below surface of the signs shall be the embedment depths plus the topsoil depth
label | Acceptance / Conformance Criteria - Visual Inspection: checks for specified embedment depth
label | Standard / Specification - PS26.3.4 g, III
label | Verifying Document - Photo/Visual Inspection/Checksheet
label | Testing Quantity Required (based from schedule qtys) - Each installation
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 5 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint | 5.1 - Final Inspection and approval of installed signs
label | Detail - Conduct final inspection and audit of all installations
label | Acceptance / Conformance Criteria - Visual Inspection
label | Standard / Specification - PS26.3
label | Verifying Document - Final inspection reports, Compliance Sticker from the installer
label | Testing Quantity Required (based from schedule qtys) - 100% of installations
label | Verification Activity: Activity - R, HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.2 - As built and records of installed signage
label | Detail - As built and record of installed barriers
label | Acceptance / Conformance Criteria - Survey/Records
label | Standard / Specification - PS
label | Verifying Document - As built records
label | Testing Quantity Required (based from schedule qtys) - 100% of installations
label | Verification Activity: Activity - SV
label | Verification Activity: By - Surveyor
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | DN1210-023-02 ITP Barriers Installation | itp |  |  |  |  | DN1210-023-02 ITP Barriers Installation Rev 0
section | SECTION 3 – PRE-CONSTRUCTION - MATERIAL, PERSONEL & THIRD PARTY APPROVALS
checkpoint | 3.1 - Underground Services
label | Detail - Set out new and existing services and identify clashes with design
label | Acceptance / Conformance Criteria - All underground services marked on site before pot holing or excavation
label | Standard / Specification - PS23.5.3 b)
label | Verifying Document - Survey Data/Site Photos
label | Testing Quantity Required (based from schedule qtys) - Pre Excavation
label | Verification Activity: Activity - H
label | Verification Activity: By - PE/SE
checkpoint | 3.2 - Materials for W-Section Gurad Rail
label | Detail - Confirm that the W-Section barrier meets the specification and NZTA M23 specification
label | Acceptance / Conformance Criteria - All the materials meets the specification requirements and Engineers Approval
label | Standard / Specification - PS 26.5.3
label | Verifying Document - Material data sheet and Engineers Approval
label | Testing Quantity Required (based from schedule qtys) - Prior to Installation
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Road Safety hardware system performance
label | Detail - The minimum performance level for permanent road safety hardware systems installed on SH for side is MASH TL-3
label | Acceptance / Conformance Criteria - All the materials meets the specification requirements and Engineers Approval
label | Standard / Specification - PS26.5.4
label | Verifying Document - Material data sheet and engineers approval
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Delivery of Materials
label | Detail - Ensure materials are delivered as per project schedule and specifications
label | Acceptance / Conformance Criteria - Materials delivered in good condition, within specified timelines
label | Standard / Specification - Section 26.3.4 (Project Specification PS)
label | Verifying Document - Delivery receipts, inspection records
label | Testing Quantity Required (based from schedule qtys) - 100% of material deliveries
label | Verification Activity: Activity - I
label | Verification Activity: By - SE, QE, SUP
section | SECTION 4 – CONSTRUCTION ACTIVITY - W-Section GuardRail Installation/Sign Installation
checkpoint | 4.1 - Set out of W-section barrier
label | Detail - Set out to be done as per IFC drawings/design Specification
label | Acceptance / Conformance Criteria - Visual Inspection:and verification as per latest dwg
label | Standard / Specification - PS26.5.2
label | Verifying Document - Photo/Visual Inspection/Checksheet
label | Testing Quantity Required (based from schedule qtys) - Each Barrier Installation
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Set out of Entry and Exit Terminals
label | Detail - Set out to be done as per IFC drawings/design Specification
label | Acceptance / Conformance Criteria - Visual Inspection:and verification as per latest dwg
label | Standard / Specification - PS26.5.3
label | Verifying Document - Photo/Visual Inspection/Checksheet
label | Testing Quantity Required (based from schedule qtys) - Each Barrier Installation
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 - Installation of W-Section barrier as per AS/NZS 3845
label | Detail - Set out to be done as per IFC drawings/design Specification, and installation to be done by competence person
label | Acceptance / Conformance Criteria - Visual Inspection: checks for appropriate Installation following standards
label | Standard / Specification - AS/NZS 3845
label | Verifying Document - Photo/Visual Inspection/Checksheet
label | Testing Quantity Required (based from schedule qtys) - Each Barrier Installation
label | Verification Activity: Activity - V
label | Verification Activity: By - SE
checkpoint | 4.4 - End Terminal and Thrie beam installed as per AS/NZS 3845, M23 and Project specs
label | Detail - Set out to be done as per IFC drawings/design Specification, and installation to be done by competence person
label | Acceptance / Conformance Criteria - Visual Inspection: checks for appropriate Installation following standards and QA checklist from suppiler
label | Standard / Specification - AS/NZS 3845
label | Verifying Document - Photo/Visual Inspection/Checksheet
label | Testing Quantity Required (based from schedule qtys) - Each Barrier Installation
label | Verification Activity: Activity - V
label | Verification Activity: By - SE
checkpoint | 4.5 - Lapping of Rail in direction of Traffic
label | Detail - Lapping of W-Section barrier to be lapped in the direction of traffic
label | Acceptance / Conformance Criteria - Visual Inspection
label | Standard / Specification - NZTA M23
label | Verifying Document - Photo/Visual Inspection/Checksheet
label | Testing Quantity Required (based from schedule qtys) - Each Barrier Installation
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
section | SECTION 5 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint | 5.1 - Final Inspection and designer's approval of installed barriers
label | Detail - Conduct final inspection and audit of all installations
label | Acceptance / Conformance Criteria - Visual Inspection:
label | Standard / Specification - Section 26.5.4 Vi (5) (Project Specification PS)
label | Verifying Document - Final inspection reports, approval of installed bariers with tolerance -0mm, +20mm
label | Testing Quantity Required (based from schedule qtys) - 100% of installations
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.2 - As built Records
label | Detail - As built and record of installed barriers
label | Acceptance / Conformance Criteria - Survey/Records
label | Standard / Specification - Project Specification
label | Verifying Document - As built records
label | Testing Quantity Required (based from schedule qtys) - 100% of signals and ITS installations
label | Verification Activity: Activity - SV
label | Verification Activity: By - Surveyor
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature