## Enabling Works
ITP
Site Location |  |  | Opaheke/Chapel St
Enabling Works - Footpath, Kerb and channel, Vehicle Crossing, Pram Crossing
Number | ACTIVITY DESCRIPTION | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQUENCY | ACCEPTANCE CRITERIA | Hold Point | Records | Onsite Responsibility
Site Set Out
1 | Site Set out | Surveyor | Surveyor | Everysite | Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criterea is acceptable. | Mandatory HOLD POINT | Onsite records/photos | Site Engineer
Kerb & Channel
2 | Kerb & Channel | QA Documentation | TDM Technical Standards - KC0001 | Everysite | Kerb & Channel to be precast hand-laid. Kerbing laid on 300mm min Gap 65 subbase in roads with CIV > 25. (Subgrade CBR>5). Concrete 20MPa @28 Days | Inprocess Inspection | Scalar Test Sheet Clegg Test Sheet Concrete Plant Docket | Site Engineer
3 | Channel Level | Visual inspection | TDM Technical Standards - KC0001 | Everysite | Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match new road level. Channel grade to follow long-sections provided in IFC set. All tie in levels are to be agreed with MSQA engineer on site. Expansion saw cut to be done by using concrete tool or using concrete saw on the following shift. | Mandatory HOLD POINT | Visual inspection | Site Engineer
Footpath
4 | Concrete Footpaths | QA Documentation / Pre-pour inspection | TDM Technical Standards - FP0001 | 10m Intervals | Subgrade - (CBR > 3) Basecourse Gap40- 100mm min. thickness Clegg CIV > 12 Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 black oxide with broom finish. Expansion saw cut to be done by using concrete tool or using concrete saw on the following shift. | Mandatory HOLD POINT | Scalar Test Sheet Clegg Test Sheet Concrete Plant Docket | Site Engineer
5 | Fall Gradients | QA Documentation / Pre-pour inspection | TDM Technical Standards - FP0001 | Everysite | Cross falll = 2% preferred (Min 1% and Max 3%) | Mandatory HOLD POINT | Photos of smart level | Site Engineer
Pram Crossing
6 | Tactiles | QA Documentation / Visual | TDM Technical Standards - FP0010 | Every PX | Tactile Pavers set out position to be agreed with MSQA Warning and Directional TGSI tiles should have 100mm concrete haunching underneath | Inprocess Inspection | Photos Concrete Plant Docket | Site Engineer
|  | QA Documentation / Visual | AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY | Every PX | Edge of warning indicators to set back minimum 300mm and maximum 1000mm from the face of the kerb | Inprocess Inspection | Photos | Site Engineer
|  | QA Documentation / Visual | AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY | Every PX | TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete paver slab type B in footpath and pedestrian crossing.Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing. | Inprocess Inspection | Materials Dockets | Site Engineer
7 | Pram Crossing | QA Documentation / Pre-pour inspection | TDM Technical Standards - FP006 | Each Crossing | Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing. Tactiles Directional & warning - 60mm thick; 600mm flares;width as per design; Slope no greater than 1:12 where practicably possible Clegg CIV > 12 20MPA concrete Expansion saw cut to be done by using concrete tool or using concrete saw on the following shift. | Mandatory HOLD POINT | Photos Photos of smart level Clegg Test Sheet Concrete Plant Docket | Site Engineer
Vehicle Crossing
8 | Vehicle Crossing | QA Documentation / Pre-pour inspection | TDM Technical Standards - VX0103 | Each VX | Subgrade -(CBR > 3) Base course - 100mm min. thickness GAP40 Clegg CIV > 12 Surfacing - Concrete 150mm and 20 MPa @ 28 days. 4kg/m3 black oxide Broom Finish The grade of vehicle crossings must be maintained at 2-3% to match the crossfall for the footpath area over the crossing. Vehicle Crossing Ramp 900mm wide at max 15% with total 40mm lip (20mm chamfer, 20mm vertical) above channel invert. Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level. Expansion saw cut to be done by using concrete tool or using concrete saw on the following shift. | Mandatory HOLD POINT | Photos Photos of smart level Scalar Test Sheet Clegg Test Sheet Concrete Plant Docket | Site Engineer
Refuge Island centre footpath
9 | Refuge Island centre footpath | QA Documentation / Pre-pour inspection | TDM Technical Standards - FP0001 | Each location | Subgrade - (CBR > 3) Basecourse ATAP40 - 100mm min. thickness Clegg CIV > 12 Surfacing - Concrete 150mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish. Expansion saw cut to be done by using concrete tool or using concrete saw on the following shift. | Mandatory HOLD POINT | Photos Scalar Test Sheet Clegg Test Sheet Concrete Plant Docket | Site Engineer
10 | Fall Gradients | QA Documentation / Pre-pour inspection | TDM Technical Standards - FP0001 | Everysite | Fall Gradients to follow shape of the final asphalt surfacing. The grade may need to be adjusted to ensure no ponding within the footpath area. | Mandatory HOLD POINT | Visual inspection | Site Engineer
Grass Berm
11 | Grass Berms | Visual | ATCOP Section 12 Footpaths and Pedestrian Facilities | 10m Intervals | 100mm thick layer of compacted approved quality topsoil, free of weeds and stones. | Inprocess Inspection | Photos | Site Engineer
Asbuilts
12 | As built information | RAMM DATA SHEET |  | Every Site | As built drawings and Ramm Sheets Completed | In Process Inspection | Asbuilt records | Supervisor and Engineer
13 | RAMM DATA | RAMM DATA SHEET |  | Every Site | RAMM SHEET | In Process Inspection | RAMM Sheet | Site Engineer & PM
ITP APPROVAL
Prepared By |  | Ajithkumar Ayyanar | Initial | AA |  | Date: | 2025-04-10
Approving Delegate |  |  | Initial |  |  | Date:

## Stormwater Drainage
|  |  |  | ITP - Opaheke/Chapel St |  |  | Approved |  | Signature
|  |  |  | Contract Name: | Opaheke/Chapel St intersection |  | FH Engineer |  | Ajithkumar Ayyanar
|  |  |  | Procedure: | Stormwater Drainage |  | FH Quality Manager |  | Daeyoung Jeong
Inspection & Test Plan / Checklist
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) | Conformance Criteria | Records | FH Initials | Design Engineer Initials (Grey if not required) | Date(s)
1 | Permits & Services | H | Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space) | Prior to any construction commencing | Document Review | Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority | Permit attached or permit number noted. | Site Engineer
|  | H | Locate and mark out all existing services | Prior to any construction commencing |  | B4u dig procedure - follow utility protocols and GPR Report | B4u dig plans & GPR report attached | Site Engineer
|  | H | Consents/Arborist report for trenching near Tree location | Working under tree drip line and working in the tree root zone | Consent Review | The Consents condition or Arborist instruction onsite to be followed | TOA, Consents and arborist instruction and Site photos | Site Engineer
2 | Pre-Construction Sign Offs | H | Sub-Contract and Supplier Agreements | Prior to commencement. | Document Review | Sub-Contract and Supplier Agreements to be agreed and signed | Subcontract and Supplier Agreements | Site Engineer
3 | Design | H | Design is approved and Drawings are of the latest revision. | Prior to commencement. | Document Review | Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT if not issued to IFC. | Drawing Register. | Site Engineer | Engineers Rep.
4 | Survey Setout | H | Setout Pipe Alignment and Service Locations with inlet & outlet points and inverts as required to construct to design | Prior to commencement. | Survey | As per IFC Drawings and design AutoCAD file. | Survey Receipt. | Site Engineer
5 | Pipe and Manhole Material Compliance | H | Cesspit, Manhole and Pipe shall comply with relevant AT/TDM/AC Standards | Prior to commencement. | Document Review, Visual Inspection | Pipe shall be Check for freshly formed pipes and return if required 1).Class 4 RCRRJ pipes AS/NZS 4058 or PVC SN16 Pipe(alternative material) 2). All Concrete RCRRJ pipes to be fitted with Rubber rings 3). Pipes shall have product certification (ISO Type 5) to AS/NZS 4058 Prefabricated concrete Manhole, Standard Catchpit and Street catchpit be in accordance with TDM Standards | Manufacturers Data Sheets, Delivery Dockets | Site Engineer
6 | Locate Existing Services by Hand Digging / Hydro Vac | H | Ensure all services conflicting with the line of trench have been exposed by hand digging. | Prior to commencement. | Potholing / Survey | All conflicts have been located. New services and / or conflicts to be advised to Project Manager. As-built all services. | As-built Drawings. Doc. Review | Site Engineer
7 | Trenching & Excavation | H | Excavation methodology | Daily | Prestart review | The excavation, benching and shoring requirements shall be in accordance with WorkSafe Excavation safety guidelines (2016) | Prestart RCP
|  | M | Trench Profile - Width | Daily / as trenching takes place. Different depth methodology | Visual Inspection, Excavation methodology | Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing | Construction Photos | Site Engineer
|  | W | Trench Profile - Depth | Daily / as trenching takes place. | Visual Inspection, Measurement | Trench depth varies according to long section and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings | FH Drainage Line Record / Construction Photos | Site Engineer
|  | M | Trench Base | Every 10m | Scalar testing | Trench base capacity to be tested using scala testing. Not less than 3 blows per 150mm for CBR 3.5 and 200mm for CBR 2. | Test reports / Construction Photos | Site Engineer
8 | Bedding for Concrete Pipe Laying & Manhole & Cesspit | W | Placing and compaction of Bedding Material. | Inspected continuously during placing and compaction of Bedding Material. | Visual Inspection | Bedding & Pipe surround material to be GAP7 or GAP 20 or alternate material that complies with AS/NZS 3725 | FH Drainage Line Record / Construction Photos | Site Engineer
9 | Pipe Position Tolerance | M |  | At any point of pipe |  | Position tolerance for pipe laying at any point along the length of the installation shall be within ±10 mm from the specified design. | FH Drainage Line Record, Survey Data. | Site Engineer
10 | Trench Backfill - Placing & Compacting | M | Placing and compacting of Trench Backfill Material | Throughout Trench Backfilling operation. | Visual Inspection | Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm ATAP40 for subbase/basecourse. | Construction Photos | Site Engineer
Subsoil Construction
11 | Subsoil Material Compliance | H | Ensure Subsoil Drainage pipe complies with TDM RD010 | Upon delivery to site | Ensure delivery docket matches materials delivered | 110mm diameter Drain flow TNZ F/2 Grade pipe - filter sock | Delivery docket | Site Engineer
|  | H | Ensure Material for Bedding, Side support and backfill F2 filter sand drainage aggregate |  | Visual inspection | Ensure clean drainage aggregate - F2 Sand | Delivery docket | Site Engineer
12 | Trenching | H | Inspect trench profile and ensure it is 0.300m wide and 375mm below subgrade | 10m intervals | Visual inspection and measurement | Record levels of base of trench on dip sheet. | Photo / subsoil log | Site Engineer
|  | H | Ensure the trench is cut in a manner than will ensure that the pipes will be laid true to the depths, grades and lines shown on the drawings. | 10m intervals | Visual inspection and measurement | Ensure trench line and levels match the design drawings | Photo / subsoil log | Site Engineer
13 | Bedding, pipe installation and Backfill. | W | Ensure 50/100mm (KC or Road) thick F2 Drainage aggregate bedding is placed in base of trench. | 10m intervals | Visual inspection | Record levels of top of bedding on dip sheet | Photo / subsoil log | Site Engineer
|  | W | Ensure Subsoil Pipe is laid on the Bedding in the centre of the trench | 10m intervals | Visual inspection | Consistency with Subsoil Details | Photos | Site Engineer
|  | W | Backfill by tipping AP20 as bedding & ATAP40 as pavement structure into the trench | - | Visual inspection | Ensure good coverage | Photos | Site Engineer
14 | Catchpit Connection | W | Ensure minimum entry point 150mm above soffit of outlet stormwater pipe | As required | Visual inspection | Consistency with Subsoil Details | Photo | Site Engineer
|  | W | Perforate Catchpit and epoxy grout pipe from inside to completely seal connection. | As required | Visual inspection | Consistency with Subsoil Details | Photos | Site Engineer
15 | As-Built Drawings | W | Red pen marked-up As-Builts of every 'Issued for Construction' | Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure. | Drawings / Visual Inspection | As Built and GIS Data | Redline As-Built Drawings, scanned as .pdf files. | Site Engineer | Engineers Rep.
Comments:
|  |  | Denny Jeong |  | Signature: | Denny Jeong |  | Date: | 2025-04-10
QA checked By Quality Manager:
[5 empty] | Signature: |  |  | Date:
Accepted By Engineers Rep:

## Traffic Islands
ITP -Opaheke/Chapel St
Site Location |  |  | Opaheke/Chapel St
Traffic Islands
Number | ACTIVITY DESCRIPTION | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQUENCY | ACCEPTANCE CRITERIA | Hold Point | Records | Onsite Responsibility
Materials
1 | Mountable Kerb | QA FORM | TDM Technical Standards - IS0001 | Each Island | Kerb to be laid using precast hand-laid (Stick-on with epoxy mortar on structral AC20) | Inprocess Inspection | Photos. | Site Engineer
Construction
2 | Survey Setout | Survey | Setout Kerb Alignment required to construct as per design | Prior to commencement. | Survey | As per Construction Drawings | Survey Receipt. | Site Engineer
3 | Concrete Infill | QA Documentation | TDM Technical Standards - IS0001 & IS0002 | Each Site | 180mm depth of 20MPa broom finish unreinforced Concrete with 6 kg/m3 Red oxide. Expansion saw cut to be done by using concrete tool or using concrete saw on the following shift. | Inprocess Inspection | Photos Concrete dockets | Site Engineer
Asbuilts
4 | As built information | Drawings |  | Every Site | As built drawings | In Process Inspection | Asbuilt records | Supervisor and Engineer
5 | RAMM DATA | RAMM DATA SHEET |  | Every Site | RAMM SHEET | In Process Inspection | Asbuilt records | Supervisor and Engineer
ITP APPROVAL
Prepared By |  | Ajithkumar Ayyanar | Initial | AA |  | Date: | 2025-04-10
Approving Delegate |  |  | Initial |  |  | Date:

## Signage
ITP - Opaheke/Chapel St
Site Location |  |  | Opaheke/Chapel St
Signage
Number | ACTIVITY DESCRIPTION | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQUENCY | ACCEPTANCE CRITERIA | Hold Point | Records | Onsite Responsibility
Site Set Out
1 | Site Set out | Surveyor | Surveyor | Everysite | Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable. Alternatively like for like | Mandatory HOLD POINT | Photos | Site Engineer
Materials
2 | Signs | QA Documentation | TDM Technical Standards | Every site | All signs to be in good condition. Signs to have good reflection and visibility. NO scratches or markings. All signs to match with construction drawings provided by designers. Any custom-made signs, approval of a proof design copy is required prior to manufacturing of the sign. | Inprocess Inspection | Dockets/Photos | Site Engineer
3 | Pole, Impact recovery post and Ground Socket | QA Documentation | TDM Technical Standards | Every site | Check for underground service before installtion. All poles and post to be in good conditon with end caps. | Inprocess Inspection | Dockets/Photos | Site Engineer
Construction
4 | Ground Socket | QA Documentation | TDM Technical Standards | Each Socket | The dug out hole to be 300mm wide and 600mm deep. 20Mpa concrete with 50mm cover at bottom to be used for installing socket. The sockets to have 50mm reveal at top and smooth finish of concrete around the socket. | Inprocess Inspection | Dockets/Photos with tape measurement | Site Engineer
5 | Pole and Impact recovery post | QA Documentation | TDM Technical Standards | Each Post or pole | All poles to inserted into the socket after the concrete curing. And, the screw or pins to be used to prevent the pole rotation. The impact recovery post installed on the island infill surface after curing period by drilling and using Dyna bolts. The bolts are tightned sufficent to prevent rotation | Inprocess Inspection | Dockets/Photos | Site Engineer
6 | Signs | QA Documentation | TDM Technical Standards | Each Sign | All the sign to be fixed to the pole or post with ARC brackets and tightened adequately. Ensure good visibility to road users & secured to prevent rotation around pole/post. Ensure sufficient offset from road & pedestrians/cyclists - as practicable as per existing environment/surroundings | Inprocess Inspection | Dockets/Photos | Site Engineer
Asbuilts
7 | As built information | RAMM DATA SHEET |  | Every Site | As built drawings and Ramm Sheets Completed | In Process Inspection | Asbuilt records | Supervisor and Engineer
ITP APPROVAL
Prepared By |  | Ajithkumar Ayyanar | Initial | AA |  | Date: | 2025-04-10
Approving Delegate |  |  | Initial |  |  | Date:

## Pavement
Opaheke & Chapel Street (PAVEMENT ITP)
Project Name: Opaheke/Chapel Street | [5 empty] | Design Report . | Bartley Pavement Design
ITP Prepared By: Ajithkumar Ayyanar |  |  |  | Date: | 2025-05-08 | Peer Review By: | Denny Jeong
No. | ACTIVITY DESCRIPTION | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQUENCY | ACCEPTANCE CRITERIA | TYPE | RECORDS (Responsibility) | ONSITE RESPONSIBILITY | CONTRACT MANAGER SIGNOFF
Type C - 155mm of AC on 150mm concrete subbase (total 305mm new pavement) Type W (Widening) - 155mm of AC on 150mm concrete subbase on 195mm ATAP65 (total 500mm new pavement)
Excavation/Milling - Widening Area, Concrete and Structural AC
1 | Identification and location of shallow services | Measure depth of cover to utility services | Trained contractor staff | Two measures per service (each side of the road) | Services sufficently deep to avoid damage. Otherwise consider relocation or concrete cap | Mandatory HOLD POINT Designer Signoff Required | Marked up sheet | Site Engineer | Designer Signoff
2 | Milling / Cut to Waste Type C = 305mm Type W = 500mm | Survey As-built / Stringline | Survey As-built / Stringline | 10m each lane | +0 / -20mm to design level | Mandatory HOLD POINT Designer Signoff Required | Survey As-built / Stringline sheet | Site Engineer | Designer Signoff
3 | Existing subgrade / subbase | No unacceptable subgrade materials after excavation | Visual Inspection | Sitewide | Free of detritius and loose material If exposed subgrade, to place geotextile cloth prior to concrete subbase | Inprocess Inspection | Photos | Site Engineer | Designer Signoff
Contingency Undercut Areas
5 | Type W = Contingency weak / soft spot | Scalar Testing | Scalar Testing on existing subgrade | 5m grid | Ensure exposed subgrade CBR ≥ 2. If CBR between 2 and 1 undercut 300mm and replace with ATAP65 If CBR < 1 - designer to review and advise | Mandatory HOLD POINT Designer Signoff Required | Test Results | Site Engineer | Designer Signoff
5 | Type C = Contingency weak / soft spot | Scalar Testing Proof Roll | Scalar Testing on exposed subgrade Proof-rolling on existing granular subbase Clegg testing on existing granular subbase | 5m grid | If CBR < 2 or visual movement under proof roll - undercut 50mm and replace with 20MPA concrete subbase If CBR <1 - undercut 200mm and replace with milling aggregates. CIV>25 for existing granular or milling aggregates. | Mandatory HOLD POINT Designer Signoff Required | Test Results / Visual | Site Engineer | Designer Signoff
6 | All Areas Contingency Weak / Soft Spot | Survey As-built / Stringline | Survey As-built / Stringline | 10m each lane | +0 / -20mm No trafficking of the excavated subgrade | Mandatory HOLD POINT Designer Signoff Required | Survey As-built / Stringline sheet | Site Engineer | Designer Signoff
7 | Existing subgrade / subbase | No unacceptable subgrade materials after excavation | Visual Inspection | NA | Free of detritius and loose material If exposed subgrade, to place geotextile cloth prior to concrete subbase | Inprocess Inspection | Photos | Site Engineer | Designer Signoff
Subbase
8 | AT AP65 = Pavement Type W | No non-compliant results | Material test results. The material requirements of AT AP65 are to be in accordance with Auckland Transport Series 0800 | Once | Construction layer shall be Compliance with TNZ B/2 | Mandatory HOLD POINT Designer Signoff Required | Testing Results | Site Engineer
9 |  | Compaction Testing | Clegg Testing - where there are plant restrictions. NZTA B/2 testing requirements need to be satisfied where there are no such plant restrictions. | 5m grids | CIV > 35. to be compacted in 150mm layers for the Plant Restricted areas. For NZTA B/2, unbound granular subbase shall be undertaken in 150 to 200mm lifts. | Mandatory HOLD POINT Designer Signoff Required | Testing Results | Site Engineer | Designer Signoff
10 |  | Survey As-built / Stringline | Survey As-built / Stringline | 10m each lane | +0 / -20mm No trafficking of the excavated subgrade | Mandatory HOLD POINT Designer Signoff Required | Survey As-built / Stringline sheet | Site Engineer | Designer Signoff
11 |  | Surface finish | Visual Inspection | All area | Free of detritius and loose material | Mandatory HOLD POINT Designer Signoff Required | Photos | Site Engineer
12 | Concrete Subbase = Pavement Type W & C | Strength and slump | Concrete dockets & Lab Testing | each pour | Strength = 20MPa Slump = 130mm pump mix Pump mix being used hence cannot specify slump. Shape of the concrete to be closely monitored due to fluidity nature of pump mix on graded surface | Inprocess Inspection | Concrete Dockets Slump Testing Report Cylinder Testing Report | Site Engineer
13 |  | Levels / thickness | Dip from stringline or survey as-built to top of subbase (Surveyor to provide set-out information prior to concrete pour) | 10m each lane | +0 / -20mm Target thickness = 150mm Soft spots = 200mm thick | Mandatory HOLD POINT Designer Signoff Required | Stringline Sheet | Site Engineer | Designer Signoff
14 |  | Rough trowel or U5 Broom surface finish | Visual Inspection | All area | Rough surface verified over 100% of surface area No significant cracks verified over 100% of the surface area. Remedial for +3mm cracks = Apply bitac tape. | Inprocess Inspection | Production Recurs | Site Engineer
15 |  | Curing Process | 24 hours of moist curing (apply coconut mat or similar & wet with water) | All area | 24 hours of moist curing (apply coconut mat or similar & apply water to wet it) | Inprocess Inspection | Photos | Site Engineer
Sealing & Hatelit XP Grid
15 | Type W & Type C | Blinding/CAT60 | Visual Inspection | each lot | ON CONCRETE SUBBASE Hand spray heavy tack coat emulsion (residual bitumen 0.6L/m2) Blinding sufficient to protect emsulsion from construction movement Manufacturer's guidelines for Hatelit XP installation and subsequent bitumen application on the concrete subbase in accordance with Hatelit XP installation guidelines. | Inprocess Testing | Photos | Site Engineer
17 | Hatelit XP Grid | Photos | Visual Inspection | each lot | Type W &C = required over concrete subbase Extend 500mm into existing pavement (with <20mm asphalt blinding) | Inprocess Testing | Photos | Site Engineer
18 | AC20 | Mix Design | Sign-off by Designer | Prior to starting | Sign-off by Designer | Mandatory HOLD POINT Designer Signoff Required | Mix Design Report | Site Engineer | Designer Signoff
19 | AC20 | Check weather reports | Check weather reports | Daily | No fog, rain or wet surface. Base temp ≥ 7o C | Inprocess Testing | AC check sheet | Site Engineer
20 | AC20 | Ensure previous layer is broomed clean | Visual | Prior to starting | Free of detritius and loose material | Inprocess Testing | AC check sheet | Site Engineer
21 | AC20 | Production tests | Grading, binder content, max density, temp | As per M/10 | NZTA M/10 | Inprocess Testing | Lab test | Site Engineer
22 | AC20 | Surface finish inspection | Visual inspection by the Engineer | Each lot | Uniform texture, no roller marks, no bleeding, cracking or shoving, no crushing of the aggregate. | Inprocess Testing | Inspection sheet | Site Engineer
23 | AC20 | Density testing | NDM | Every 10m each lane staggerd | Air voids to meet NZTA M/10:2020 | Inprocess Testing | Inspection sheet | Site Engineer | Auckland Transport Signoff
25 | AC20 | Survey As-built / Stringline | Survey As-built / Stringline | 10m each lane | +10 / -10mm Thickness no less than 100mm | Inprocess Testing | Survey As-built / Stringline sheet | Site Engineer
26 | AC20 | Density testing | Cores air voids | Location to be jointly agreed with the Engineer on-site and be outside of wheelpath | Air voids to meet NZTA M/10:2020 Cores shall be cut from the pavement at a rate of one core for every 300 m² with a minimum of eight cores representing each lot. 3 joint cores where possible/practicable | Mandatory HOLD POINT Auckland Transport Signoff Required | RFI response | Site Engineer | Auckland Transport Signoff
27 | AC20 | Thickness | Cores depth | Location to be jointly agreed with the Engineer on-site and be outside of wheelpath | Thickness no less than 100mm | Mandatory HOLD POINT Auckland Transport Signoff Required | Core test report | Site Engineer | Auckland Transport Signoff
Asphalt Surfacing - 55mm AC14 (PG64V)
28 | AC14 | Mix Design | Sign-off by Designer | Prior to starting | Sign-off by Designer | Mandatory HOLD POINT Designer Signoff Required | Mix Design Report | Site Engineer | Designer Signoff
29 | Shape of road | 3m straight edge | NZTA M/10 spec | At joints and any other areas of concern | Irregularities < 5mm under straight edge | Inprocess Inspection | Check sheet | Site Engineer
30 | Temperature Limitations | Temperature | Contract Spec / M10 Spec | Every Site | Asphalt not to be paved when foggy or raining, or placed on a wet surface or when temperature is below the base temperature limitations of 10 Degree | Inprocess Inspection | Asphalt QA | Site Engineer
31 | Surface Preparation | Visual | NZTA M/10 spec | Every Site | Swept clean; all necessary measures to prevent ponding prior to any surfacing | Inprocess Inspection | Visual | Site Engineer
32 | Asphalt Production Tests for AC14 | Production Tests | Grading, binder content, max density, temp | As per M/10 | NZTA M/10 | Laboratory Testing | IANZ Lab | Site Engineer
Site Engineer
Site Engineer
Site Engineer
33 | AC14 - Layer thickness - 55mm compacted depth | Insitu | Contract Spec / NZTA M10 Spec | Continuous | 55 mm minimum and 60 mm maximum compacted depth Final asphalt level to be 5mm proud of lip of channel | Mandatory HOLD POINT Auckland Transport Signoff Required | Asphalt QA | Site Engineer | Auckland Transport Signoff
34 | AC14 | Density testing | NDM | Every 10m each lane staggerd | NZTA M/10 | Mandatory HOLD POINT Auckland Transport Signoff Required | RFI response | Site Engineer | Auckland Transport Signoff
Reinstatement
35 | Reinstatement of Linemarking and RRPM's & Apply Joint sealing | Visual | Visual inspection | Every site | Visual inspection | Inprocess Inspection | Photos | Site Engineer
As-builts
36 | As-built information | Documentation | As-built drawings and ramm sheets completed |  | As-built records | Inprocess Inspection |  | Site Engineer | Auckland Transport Signoff
37 | RAMM DATA | Documentation | RAMM Sheet |  | RAMM Sheet | Inprocess Inspection |  | Site Engineer | Auckland Transport Signoff
APPROVALS
Approved by Project Engineer : |  | Ajithkumar Ayyanar |  | Signature: AK |  | Date: | 2025-05-08
Approved by Contract Manager : |  | Daeyoung Jeong |  | Signature: DJ |  | Date: | 2025-05-08
Approved by Client Rep : |  |  |  | Signature: |  | Date:

## Roundabout
ITP - Opaheke/Chapel St
Roundabout and Apron
Number | ACTIVITY DESCRIPTION | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQUENCY | ACCEPTANCE CRITERIA | Hold Point | Records | Onsite Responsibility
Survey - Set Out
1 | Survey Setout | Survey | Setout for Roundabout and Apron as per the drawings issued for construction | Prior to commencement. | Survey | Inprocess Inspection | Survey Set-out on site | Site Engineer
Roundabout construction
2.1 | Kerb | QA Documentation | Type 2B Mountable Kerb as per TDM Technical Standards - KC0001 | Circumfrence centre island | Kerb to be laid using precast hand-laid directly on polythene sheet on concrete subbase. Laid 100mm high from finish level of apron. Concrete 20MPa @28 Days | Inprocess Inspection | Clegg Sheet, photos. Concrete Plant Docket | Site Engineer
2.2 | Infill | QA Documentation | As per Drawings | Roundabout infill | 180mm depth of 20MPa broom finish reinforced(1 row of 663 Mesh with 60mm cover) Concrete with 6 kg/m3 Red oxide. Expansion saw cut to be done by using concrete tool or using concrete saw on the following shift. | Inprocess Inspection | FH concrete QA sheet. Concrete delivery Dockets kept as record | Site Engineer
Apron Construction
3.1 | Concrete Apron | QA Documentation | As per Drawings | Apron Infill | 205mm thick 40MPa Concrete, reinforced with 25kg/m3 Dramix 4D6560BG steel fibre. 4kg/m3 Black oxide-Broom finish,on 0.25mm polythene layer, on concrete subbase Total reveal from road level = 50mm Chamfer - 25mm Upstand - 25mm Expansion saw cut to be done by using concrete tool or using concrete saw 24 hours after the pour, 50mm deep. Saw-cut spacing/pattern to be as per Eliga Design Drawings. (5m spacing outer circle, 3m spacing inner circle) | Mandatory HOLD POINT | FH concrete QA sheet. Concrete delivery Dockets kept as record | Site Engineer
#VALUE!
Asbuilts
4.1 | As built information | Drawings |  | Every Site | As built drawings | In Process Inspection | Asbuilt records | Supervisor and Engineer
4.2 | RAMM DATA | RAMM DATA SHEET |  | Every Site | RAMM SHEET | In Process Inspection | Asbuilt records | Supervisor and Engineer
ITP APPROVAL
Prepared By |  | Ajithkumar Ayyanar | Initial | AA |  | Date: | 2025-05-08
Approving Delegate |  |  | Initial |  |  | Date: