## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Roundabout | itp |  |  |  |  | ITP - Opaheke/Chapel St - Roundabout
section | Survey - Set Out
checkpoint | 1 - Survey Setout
label | VERIFICATION ACTIVITY: Survey
label | METHODS OR REFERENCE: Setout for Roundabout and Apron as per the drawings issued for construction
label | FREQUENCY: Prior to commencement.
label | ACCEPTANCE CRITERIA: Survey
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Survey Set-out on site
label | ONSITE RESPONSIBILITY: Site Engineer
section | Roundabout construction
checkpoint | 2.1 - Kerb
label | VERIFICATION ACTIVITY: QA Documentation
label | METHODS OR REFERENCE: Type 2B Mountable Kerb as per TDM Technical Standards - KC0001
label | FREQUENCY: Circumfrence centre island
label | ACCEPTANCE CRITERIA: Kerb to be laid using precast hand-laid directly on polythene sheet on concrete subbase. Laid 100mm high from finish level of apron. Concrete 20MPa @28 Days
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Clegg Sheet, photos. Concrete Plant Docket
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 2.2 - Infill
label | VERIFICATION ACTIVITY: QA Documentation
label | METHODS OR REFERENCE: As per Drawings
label | FREQUENCY: Roundabout infill
label | ACCEPTANCE CRITERIA: 180mm depth of 20MPa broom finish reinforced(1 row of 663 Mesh with 60mm cover) Concrete with 6 kg/m3 Red oxide.
label | ○ Expansion saw cut to be done by using concrete tool or using concrete saw on the following shift.
label | HOLD POINT: Inprocess Inspection
label | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
label | ONSITE RESPONSIBILITY: Site Engineer
section | Apron Construction
checkpoint | 3.1 - Concrete Apron
label | VERIFICATION ACTIVITY: QA Documentation
label | METHODS OR REFERENCE: As per Drawings
label | FREQUENCY: Apron Infill
label | ACCEPTANCE CRITERIA: 205mm thick 40MPa Concrete, reinforced with 25kg/m3 Dramix 4D6560BG steel fibre. 4kg/m3 Black oxide-Broom finish,on 0.25mm polythene layer, on concrete subbase
label | ○ Total reveal from road level = 50mm
label | ○ Chamfer - 25mm
label | ○ Upstand - 25mm
label | ○ Expansion saw cut to be done by using concrete tool or using concrete saw 24 hours after the pour, 50mm deep. Saw-cut spacing/pattern to be as per Eliga Design Drawings. (5m spacing outer circle, 3m spacing inner circle)
label | HOLD POINT: Mandatory HOLD POINT
label | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
label | ONSITE RESPONSIBILITY: Site Engineer
holdpoint | AUTHORITY HOLDPOINT
section | Asbuilts
checkpoint | 4.1 - As built information
label | VERIFICATION ACTIVITY: Drawings
label | METHODS OR REFERENCE:
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: As built drawings
label | HOLD POINT: In Process Inspection
label | RECORDS: Asbuilt records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
checkpoint | 4.2 - RAMM DATA
label | VERIFICATION ACTIVITY: RAMM DATA SHEET
label | METHODS OR REFERENCE:
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: RAMM SHEET
label | HOLD POINT: In Process Inspection
label | RECORDS: Asbuilt records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
section | APPROVALS
checkpoint | ITP Approval
label | Prepared By: Ajithkumar Ayyanar
textbox | Approving Delegate: