## Master List Templates
Id | Type | Name | Values | Prompting Name
86ae3961-60d5-45f1-932f-d3e37caaebb8 | checklist | ITP006 - EC - Embankment Construction - Rev0 | itp | ITP006 - EC - Embankment Construction
13b0701b-437d-4439-8589-e352aa4d6a77 | section | Inspection and Test Plan Details
f8e1fda0-37f2-4f14-9b63-6f39648a3f6a | checkpoint | 01 - Lot Identification
2d96dbf8-4f30-58b1-815e-a071a9bc0309 | note | Work By - Contractor
36696be1-f395-597e-b498-6eee8d38cc40 | note | Standard / Spec - Clause 3.5 of OPS- TETW-CS-SPE-001 IFC Rev 0
c55d72e4-5b6c-5270-874b-60c28b9f48be | note | Criteria - Location of Works identified in accordance with project technical specification
15b5283f-f48b-5a6a-bd64-a589b1e40b17 | note | Frequency - 1/Lot
9ff5af48-147c-5aec-a4f5-10858abb8b59 | note | Record - ITP Verification Checklist / Lot Map
3d30033f-2363-5065-b134-400e8f55762c | note | Contractor: Resp - RSA
5ec84754-cc14-5a42-a8f1-46c6a29195e5 | note | Contractor: Type - Check
c0f12560-9579-550e-85b2-47bb4dbd9668 | note | Client: Resp - Senex
ed915557-5d6e-5886-840d-5c1b90b14564 | note | Client: Type - Check
b32dbc0f-bf42-453a-9eeb-65f313b37f15 | checkpoint | 02 - Lot Identification – Lot Plan
56803441-113a-5671-b36e-9f746b84823e | note | Work By - Contractor
4d430989-0ff9-551a-9578-07935b45256f | note | Standard / Spec - Clause 3.5 of OPS- TETW-CS-SPE-001 IFC Rev 0
5ddd7d35-5d07-57cf-be14-3d5ca7e64bad | note | Criteria - Lot Plan submitted to the Superintendent 5 days prior to the commencement of the Work (if required)
523170be-e24b-5ddb-adb9-96736f53c960 | note | Frequency - Prior to commencement
30dd0259-c1e9-5e9b-aa46-404149951d18 | note | Record - ITP Verification Checklist / Lot Plan
86d70440-12ad-5979-8c77-e353758273e9 | note | Contractor: Resp - RSA
8ed29f3f-58d6-5479-bd39-6d8c1f7537e6 | note | Contractor: Type - Hold Point
8a689619-fe4e-5a03-ab20-65efc1d0f017 | note | Client: Resp - Senex
fd0734df-6ad9-57e3-84db-e6d92927f312 | note | Client: Type - Hold Point
7c444921-baa6-437a-b82e-9da65e716e63 | signoff | HOLD POINT
5396f34d-8efc-4d6e-97b8-641a59752120 | checkpoint | 03 - Underlying Lot Conforms
0a83394b-e86b-5704-93bb-08b44b4fce8a | note | Work By - Contractor
fac80fa7-9a95-5ade-8219-df34de37cd23 | note | Standard / Spec - Clause 9.6 of OPS- TETW-CS-SPE-001 IFC Rev 0
44badee9-1d7c-5f35-b1f4-a8960ea6f1c7 | note | Criteria - The Superintendent shall inspect the results of the testing of each layer in each lot of material for conformance with the Specification.
fba09278-967a-538c-a01a-f00361aaf933 | note | Frequency - 1/Lot
419ecc15-bced-5063-97bf-b66f68300de5 | note | Record - ITP Verification Checklist / Lot Map
a87f1507-1ba4-5594-ba88-a5bac673f9fa | note | Contractor: Resp - RSA
d6ddf9c4-3cd6-57a2-a7e6-da4921eaae63 | note | Contractor: Type - Hold Point
78cf7ae4-c879-5b8f-985f-b50609e2abdf | note | Client: Resp - Senex
3aa2062d-ac6f-537a-a3a8-66bf02db35e4 | note | Client: Type - Hold Point
051b6aa3-d1c0-4983-989b-b4953ffda876 | signoff | HOLD POINT
8576ce32-5e55-4c23-928e-dcbd90595d34 | checkpoint | 04 - Placement of General Fill – Outer Zone and Inner Zone
8ba1a045-a2c1-5856-a832-b72e870efa68 | note | Work By - Contractor
4fcee5b6-0357-5eba-8034-ab73a7b70798 | note | Standard / Spec - Clause 9.4 of OPS- TETW-CS-SPE-001 IFC Rev 0, Clause 9.6 of OPS- TETW-CS-SPE-001 IFC Rev 0
09b6b0bc-487a-5e9b-82e9-bc6152570c4b | note | Criteria - Outer Zone and Inner zone earth fill to be placed, moisture conditioned and compacted generally in layers not exceeding 300mm thickness in line with RSA construction methodology.
e3da42e6-dc39-5602-87da-bf9e93ef5ac8 | note | ○ Any existing surfaces to be lightly scarified and moisture conditioned prior to placement of subsequent layer to provide sufficient bond and prevent lamination.
0de455a3-9eae-524a-9989-95650d22f86b | note | ○ Overfill to outer edges of embankment to allow for trim back to design surface
3ee59b50-a41b-5c35-8fb2-542b906a93f5 | note | ○ Completed under Level 2 Testing
e143fa1f-076e-5a42-8b33-cd5ef118dd47 | note | Frequency - Each Lot
3ee9334e-efd4-5787-919a-5f48fd96ef56 | note | Record - ITP Verification Checklist / Lot Map
3fdd6701-73ce-5a1f-a55f-b97bf27fe676 | note | Contractor: Resp - RSA
57cdfb22-157c-5cdc-a9c0-30dbfdd5ab93 | note | Contractor: Type - Check
970144f1-03ef-5a9c-bd8a-4767cbf9abdd | note | Client: Resp - Senex
17816d18-b5f1-5973-aa67-ce007013c896 | note | Client: Type - Witness Point
c0c3680a-710b-4c04-bd6c-0ab5b663e806 | checkpoint | 05 - Placement of Select Fill (if required)
de02f8f1-cf4d-55d1-a9ec-de270cf90eba | note | Work By - Contractor
94118cc9-0c5b-5d8c-b453-40e8a07d3cb0 | note | Standard / Spec - Clause 9.4 of OPS- TETW-CS-SPE-001 IFC Rev 0, Clause 9.6 of OPS- TETW-CS-SPE-001 IFC Rev 0
5728a1a9-2b4d-5eea-8611-51da7bc34109 | note | Criteria - Select Fill shall comprise clay-rich soils sourced from the excavation of the dam and onsite borrow areas that conform to the geotechnical properties specified in Table 8 of OPS-TETW-CS-SPE-001 IFC Rev 0
e1357788-b3ac-5caf-8bf0-a688cc9f2003 | note | ○ Select fill to be placed, moisture conditioned and compacted generally in layers not exceeding 300mm thickness.
a19f3098-d5ed-5efc-85e1-8716ba270ebc | note | ○ The final surface shall be prepared with a smooth drum roller to create a smooth surface immediately prior to the deployment of the geomembrane material
847e5261-6c6f-539b-be48-87e4cb543f70 | note | ○ Finished surface to be free of all stones or other objects with potential to puncture liner.
ad45f216-b2a2-54ac-acb2-600be26d5a02 | note | ○ Completed under Level 2 Testing
218bb607-4d86-5ac8-bbc2-caa6add808dd | note | Frequency - 1 / Lot
3cbb926b-588f-5217-b398-8918527b37c0 | note | Record - ITP Verification Checklist / Lot Map
c297ebcf-5ae4-500b-947f-98064b8837f8 | note | Contractor: Resp - RSA
2b65c637-b850-5140-89b4-f17d4e2980bd | note | Contractor: Type - Check
3654b183-420e-58b1-89d5-9033bd4408bb | note | Client: Resp - Senex
d11fc013-e2a4-5872-81f5-b585d69c737a | note | Client: Type - Witness Point
83277ca0-c5a9-41c3-ad26-d38093f91174 | checkpoint | 06 - Testing – Outler Layer Density and Moisture
ff6d8179-c182-5671-b5bb-a2c35b2c9da1 | note | Work By - Contractor
36f07909-181a-5ab8-b9bf-7c4d045ed5db | note | Standard / Spec - Table 10 & 11 of OPS-TETW-CS- SPE-001 IFC Rev 0
34bc7774-2d6e-5383-897f-de1bb6a6b007 | note | Criteria - Testing in line with Table 10 & 11 of OPS-TETW-CS-SPE-001 IFC Rev 0 (See below)
5d90cb6e-6f92-5d61-a0cf-6ba7a83188c9 | note | Frequency - 1 / 500m3
3ab4b78e-f882-5b8e-a83b-86b5264a0d3c | note | Record - ITP Verification Checklist / Report
e7187b55-4eaf-5e61-8569-b93fd5af556e | note | Contractor: Resp - RSA
1d10818d-8c94-56d7-898c-5cdcaf2c34d9 | note | Contractor: Type - Check
ca1094c1-2080-5523-9ebf-3fb8cfd6c42c | note | Client: Resp - Senex
8527d499-f472-50de-98cc-3087c0a1fb2a | note | Client: Type - Witness Point
fcf5e1e1-146f-4ffc-9926-51c076c6e80e | checkpoint | 07 - Testing – Outler Layer Material Quality
82a59712-4e7c-5b5f-a9ab-16c11a434210 | note | Work By - Contractor
5d7dc1c9-3d40-5947-abe0-ab4d21317d5f | note | Standard / Spec - Table 6 and 11 of OPS-TETW-CS- SPE-001 IFC Rev 0
1cb2743f-8e15-5f45-b983-2a02cf55edfa | note | Criteria - Testing in line with Table 11 of OPS- TETW-CS-SPE-001 IFC Rev 0 material for Outer Zone Conforming to properties provided in Table 6 (See below)
d56416db-108b-50a8-9acf-d73929738d1c | note | Frequency - See Criteria
38490ca5-a55d-5389-be78-b34104defdf0 | note | Record - ITP Verification Checklist / Report
bfce86a0-a50d-5dd7-807a-97c9bf8ed4a5 | note | Contractor: Resp - RSA
6d19f863-dab6-5762-b02a-1be8b2a2fcf4 | note | Contractor: Type - Check
56c69313-4f04-53a7-b0bd-989238014a53 | note | Client: Resp - Senex
335e4ef7-92b6-539f-a8d3-7f20c4becf09 | note | Client: Type - Witness Point
0c5137cd-626a-4cc5-bf89-3018505ad269 | checkpoint | 08 - Testing – Inner Layer Density and Moisture
91f1185a-5f03-568f-96c8-fef9df0712ca | note | Work By - Contractor
b19c1c8e-7974-5812-bb14-44b52bbf5403 | note | Standard / Spec - Table 10 & 11 of OPS-TETW-CS- SPE-001 IFC Rev 0
74b68c8c-c84e-5a9e-80fc-9c373cd7ea76 | note | Criteria - Testing in line with Table 10 & 11 of OPS-TETW-CS-SPE-001 IFC Rev 0 (See below)
dc7a18ce-ef23-54f8-8f19-8db501654510 | note | Frequency - 1 / 500m3
faa6b0e1-fa73-5cd2-8151-4826739883a4 | note | Record - ITP Verification Checklist / Report
1620a0f5-841a-5883-8b50-46c6fdc337f8 | note | Contractor: Resp - RSA
7beb19b0-8618-5216-8ef3-1ba82a544fa4 | note | Contractor: Type - Check
d7412273-6770-5841-acbd-4a2b4f611d29 | note | Client: Resp - Senex
39d8a134-5c08-5138-b07e-be26fde8752f | note | Client: Type - Witness Point
93e47e23-951f-47e4-b8e2-6c9188af0431 | checkpoint | 09 - Testing – Inner Layer Material Quality
c15d2f19-2e05-5429-895d-8d791399ff67 | note | Work By - Contractor
e3eea868-4926-5bde-9898-227ceac83b93 | note | Standard / Spec - Table 7 and 11 of OPS-TETW-CS- SPE-001 IFC Rev 0
ce81274e-2502-5918-8855-ef2ecde2c695 | note | Criteria - Testing in line with Table 11 of OPS- TETW-CS-SPE-001 IFC Rev 0 material for Inner Zone Conforming to properties provided in Table 7 (See below)
c6685d8b-22e3-55e6-93ee-0163fab2471e | note | Frequency - See Criteria
797e5c43-797d-53d2-82f8-f1d07f8c0d61 | note | Record - ITP Verification Checklist / Report
b164d12c-76dd-57c1-984e-74fa91cea3fa | note | Contractor: Resp - RSA
413b1e6f-4247-5f8b-b66d-af67e04ec0d2 | note | Contractor: Type - Check
320d6364-dd71-53b2-978a-52a96ca4ee03 | note | Client: Resp - Senex
892581f5-804b-536c-8833-f8bc6bb15879 | note | Client: Type - Witness Point
8eb47570-cf7a-4016-86a2-ac89642aea3a | checkpoint | 10 - Testing – Select Fill Density and Moisture
b2d38b55-0001-5687-9fa7-d1a9ab6b0088 | note | Work By - Contractor
385e5cd7-528b-5247-9b42-7059c359cc50 | note | Standard / Spec - Table 10 & 11 of OPS-TETW-CS- SPE-001 IFC Rev 0
1eb88e6a-a032-5a81-8d12-ab399599727f | note | Criteria - Testing in line with Table 10 & 11 of OPS-TETW-CS-SPE-001 IFC Rev 0 (See below)
1acf80db-ab35-5a77-a89e-25a651f2c360 | note | Frequency - 1 / 500m3
5acf81cf-cfb3-55da-a33a-eff8a4c337bc | note | Record - ITP Verification Checklist / Report
82152375-9425-5636-8053-a65605de645b | note | Contractor: Resp - RSA
3212cfe2-3a37-5c37-936d-e61ccfa7737d | note | Contractor: Type - Check
e8535253-97c8-5a67-b72e-ff2e2795a1f8 | note | Client: Resp - Senex
7514de69-4a84-5bd1-b3e8-e36e568ac1e9 | note | Client: Type - Witness Point
8cf70ad0-ba18-4291-ae53-68c8d161cb41 | checkpoint | 11 - Testing – Select Fill Material Quality
07dc1dd6-0a02-56be-a48c-1b58e86c5e0c | note | Work By - Contractor
bdadaf8a-ba2a-5d5d-9400-99ccef7e2fba | note | Standard / Spec - Table 7 and 11 of OPS-TETW-CS- SPE-001 IFC Rev 0
5f600a08-cdc4-5633-b784-0a93e4b9c7e8 | note | Criteria - Testing in line with Table 11 of OPS- TETW-CS-SPE-001 IFC Rev 0 material for Inner Zone Conforming to properties provided in Table 8 (See below)
5235e562-bc49-5052-a9d8-8a5a60c5c494 | note | Frequency - See Criteria
197ec230-26f4-5067-b0ea-6d48d5aa0725 | note | Record - ITP Verification Checklist / Report
f25668f1-d389-536b-9b3d-408ef2275aef | note | Contractor: Resp - RSA
5436c51c-6fc9-54a6-9981-c11fe8a2e5e5 | note | Contractor: Type - Check
028f0485-d030-5639-8e03-21749228af11 | note | Client: Resp - Senex
2b089aed-158a-5ed5-8dca-ec85dce15ae2 | note | Client: Type - Witness Point
1ad5445f-dd2b-4a2c-a7a3-618017ace181 | checkpoint | 12 - Rework / Repairs to fill (if required)
a880af30-af1c-5c70-8ca4-46959305577a | note | Work By - Contractor
643dbef4-6a05-5c3f-a27c-5fac202ab2d3 | note | Standard / Spec - Clause 9.4 of OPS- TETW-CS-SPE-001 IFC Rev 0
bd84bd46-e9cf-5c48-b400-4abd1fb3f0c9 | note | Criteria - The Superintendent shall approve the extent of all repairs to damage, eroded, cracked or otherwise non-conforming materials and also the finish product of the repairs.
747550ab-e4ea-58ae-8496-5e3110c760f2 | note | ○ If the moisture content is within plus or minus 1% of the range, the Contractor may scarify that layer or area and add moisture, or work the clay to dry out as appropriate, re-compact, and present for retesting.
f8468fe8-9c47-5a82-994e-795602f84a35 | note | ○ If the moisture content is drier than 1% of the specified range, the layer shall be removed and reworked to a satisfactory condition before it is reused.
be3cf073-57d3-5ba7-a6b5-689485d9e87a | note | ○ If the dry density ratio is within 3% of the specified requirement additional compaction using a roller may be performed to increase the density and the layer, then presented for re-testing.
48f6aa7d-fde8-5070-a7a9-e21a6830a2ed | note | ○ If the dry density ratio is more than 3% below the specified requirement, the layer shall be removed and be replaced to achieve specification.
b4bf948d-160d-5dc2-b38b-72ef3e0a171b | note | ○ Retesting (if required) in line with requirements of the Zone being repaired.
c815c0fe-b174-5fa7-ae82-9f685fbe6a69 | note | Frequency - As required
70093ae5-7cc2-53da-8509-e7caa9050615 | note | Record - ITP Verification Checklist / Lot Map
6904bd0a-88a8-5eb4-a093-e94f8eb83ca4 | note | Contractor: Resp - RSA
f7222743-5b86-57d6-ba37-bdbb61384796 | note | Contractor: Type - Hold Point
97226475-a5d0-56bc-bdb9-b6190998ab0a | note | Client: Resp - Senex
2abc2bf1-f69d-5833-8480-813fea910bbd | note | Client: Type - Hold Point
e0165a58-08cc-416c-b82a-3f76b3ceef25 | signoff | HOLD POINT
f318ea0c-be0e-4c66-99ec-caf1e282e9d9 | checkpoint | 13 - Survey – Progress
fab901f6-b9f3-5ca6-bff6-9bbefa2281b9 | note | Work By - Contractor
1c8c0d5a-a095-5c5f-8a07-cc6ba10e738a | note | Standard / Spec - Clause 3.6 of OPS- TETW-CS-SPE-001 IFC Rev 0
15cf62a6-b21b-5c13-bdfd-5cdaa81b8402 | note | Criteria - The Contractor shall submit to the Superintendent 25%, 50% and 75% embankment fill placement completion surveys within 48 hours days of each milestone achievement.
ab1d14ef-5043-5d19-b969-def7fc6b097d | note | Frequency - 25%, 50%, 75%
db34ea0b-bb6c-5d24-8324-21ddbac9a958 | note | Record - Survey
99cd1498-e62d-55d5-8cab-7a4c7f3c2cc6 | note | Contractor: Resp - RSA
4775b183-5f35-56ea-aee7-dc7acf694c32 | note | Contractor: Type - Check
9b14a90e-7185-5a6c-ac35-cc0a558889b9 | note | Client: Resp - Senex
7bafec6e-5a47-5c46-95b4-521fb3dd8c49 | note | Client: Type - Hold Point
d2286d55-02f8-4776-8cb4-b563cb2477f7 | signoff | HOLD POINT
781e3580-5153-4a98-b686-b7d88ac21d1c | checkpoint | 13 - As-constructed Survey
ff13b901-028a-5943-a6b5-d738171d5584 | note | Work By - Contractor
09e072db-b5bb-538a-8cc8-f6beb251ba94 | note | Standard / Spec - Clause 3.4 of OPS- TETW-CS-SPE-001 IFC Rev 0, Clause 20.2.4 of OPS-TETW-CS- SPE-001 IFC Rev 0
0df5c2ba-711b-5528-a710-74df68edc044 | note | Criteria - After all work, or parts of work requiring survey acceptance has been completed, a final survey of all elements of the work shall be performed and submitted to the CQA Engineer for review and acceptance.
007f52d5-469a-56c4-b427-750f96a73305 | note | Tolerances:
e84cf095-b07c-565c-8323-bcb66f51c217 | note | — Embankment Crest
549fa817-082a-5f2d-a12d-f94bd5b3b290 | note | ○ -0 / +200mm
de50c36c-1301-5a8a-acfd-a2d422e600a2 | note | — Liner Subgrade
ec4325bf-99a7-52e1-891b-471344290e94 | note | ○ -20 / +50mm
1cd2eeab-c4e7-5ea8-a988-fc5f2e5907da | note | — Final Liner Subgrade Grader
9c5cfd0e-e26d-5170-9549-133beeafb70d | note | ○ Within 1/20th specified grade
345805ae-cec2-543b-9666-06628aafaef6 | note | — Emergency Spillway (invert)
a3e3c94a-2c97-53a0-8719-468f556c36e2 | note | ○ -20 / +20mm
c457717c-013d-5b1b-87f2-38013a733d1b | note | — Extraction Pipework
5141e39e-72cb-59c5-8147-4a2f1afb9766 | note | ○ ±50mm
13cfda93-ae90-5946-9b33-ccf8681375e7 | note | Frequency - 1/Lot
960067b8-37f3-50f4-a576-75344ece6720 | note | Record - Survey
7774c2ed-c775-57a4-9e7f-a54514696cfc | note | Contractor: Resp - RSA
26bf3980-ae47-5bbf-bc26-3e627cae4d75 | note | Contractor: Type - Hold Point
33b944ad-1803-598d-999b-af4f535fbbf2 | note | Client: Resp - Senex
3a585093-5beb-563c-807e-23c3ba53f6ea | note | Client: Type - Hold Point
e719a76d-f178-4537-9fc4-0bbbc17f2692 | signoff | HOLD POINT
b8bc743e-da4a-494c-9b64-057d4565ecb2 | checkpoint | Built in accordance with this document:
6df4b410-d793-5b1e-8f33-23a007977c7f | date | Date
bce0c0f6-fc0f-4baa-9abd-83a26a092bd3 | signoff | Signed
fb7d262f-3c1e-4767-b67e-79e0531b45b7 | checkpoint | Test results received. Lot conforms to Specification:
642b7ac2-f173-552e-8efa-5d2e7b4e63c9 | date | Date
1fe97b86-e7f0-40c1-8665-19032be111cd | signoff | Signed
6824d8e7-41a9-4dca-bef7-b072ac9b82c0 | checklist | RSA.WP28.FIC - ACCESS TRACK - Rev2.0 | itp | RSA.WP28.FIC - ACCESS TRACK
69387c76-6a81-4cd5-b6a1-5fb8b21f99b2 | section | FIELD INSPECTION CHECKLIST ACCESS TRACK
022fd95d-5237-41be-947f-5d65485e7d37 | checkpoint | CH and FDM clearance
ecd64d70-71b0-4c45-b19d-ef348573705d | signoff | HOLD POINT
fa656ecc-8a11-4fd3-8b48-e85d2de166a8 | checkpoint | Identify extent of work area, clearance boundaries and any required surveying works
9cd406a0-7916-4cf2-84aa-1cd3ef7f23f8 | checkpoint | Measure access road dimensions as per IFC
39d8127c-4df2-42da-8a43-20634c7914c7 | checkpoint | Clear & Grub
62d483f9-9717-459b-8507-3c390f3b7ae2 | checkpoint | Form track profile
9d0dbe2b-ba18-4b5d-9190-d8dc61793978 | checkpoint | Construct erosion and sediment controls
db5541c9-66d7-4b26-be35-507e91222438 | checkpoint | Construct water way barriers crossings
8ef879d7-2257-4f9d-8429-40efeb51cab3 | checkpoint | Gravel cap access track (if applicable)
d5e14f03-a3cf-4b9e-8d46-0b9588da4993 | checkpoint | As Built Completed
e5960946-98c8-450c-9374-3a9adb1efd53 | checkpoint | RSA QA Inspection
29102593-1758-4123-b5b7-25627eede0c1 | signoff | HOLD POINT
81ac979c-6389-4763-b9a5-182d12096eed | checklist | RSA.WP28.FIC - FENCING & GRIDS - Rev2.0 | itp | RSA.WP28.FIC - FENCING & GRIDS
fe3b6b3a-395c-4e1f-8cd6-8457c3d37cfd | section | FIELD INSPECTION CHECKLIST FENCING & GRIDS
c5e2fbfd-517c-47a7-8dd3-585197f53867 | checkpoint | CH & FDM Clearance
1d86cd3c-1c45-4588-b040-928cd6bc756d | signoff | HOLD POINT
91f45ff0-2a78-47a0-b18c-cc897ff200b9 | checkpoint | Identify Work Area, boundaries of Fencing
e43dae43-2af4-4f3f-a2ab-44e7d07ffb44 | checkpoint | Inspect fencing materials
83ff1169-bd15-4472-afda-be13ec4fa6fc | checkpoint | Installation of fencing
c399b626-d3e9-432e-bcb7-a2cef7acefed | checkpoint | Concrete for base of fencing
9050c22d-0cdb-4f8d-9d98-38e9efb6d067 | checkpoint | Fence posts caps
ec952728-95a9-4d3d-a797-3adfa2b5b196 | checkpoint | Welding
b242b80f-c61d-43c0-8377-a8fa2db5acbb | checkpoint | Welds Galvanized Painting
15c7992f-55d2-4ca0-84bb-369113072faa | checkpoint | Gate Chain and Carabiner clips
b187d229-1ef3-4c62-b0a7-f8af9f2b6f85 | checkpoint | Box Out Grid Footings and Prep Site
41b71f21-327e-4afc-98df-9bb78afd6bcc | checkpoint | Inspect grid materials
9a7e08f6-af83-4ec6-bee7-06a88c9d9d64 | checkpoint | Compaction for Grid base
1d1e0818-68eb-45c6-a7b3-bac784e6d73b | checkpoint | Concrete Abutment / Install Base Slab (if required)
0465663b-a0b6-4e62-8519-809113177a84 | checkpoint | Position and Install Grid
25579f57-9e69-48df-ba45-9be41f42cdda | checkpoint | Install and Compact Gravel Ramps
95318c65-425c-4f30-a7bf-e01cabbed195 | checkpoint | Attach Fence to Box Assembly
99485ed6-e7ff-4695-afb1-f454172a9332 | checkpoint | RSA QA inspection
6f4cfae8-0531-44f8-814c-049e6334ab2a | signoff | HOLD POINT
a2f28301-ad52-4600-adf7-85ceaf790734 | checklist | RSA.WP28.FIC - LEASE PADS - Rev2.0 | itp | RSA.WP28.FIC - LEASE PADS
f51fedc0-fa6b-44cd-8b0c-d780ffaae9f9 | section | FIELD INSPECTION CHECKLIST LEASE PADS
cb8b0a99-5fd0-425a-873d-86dc491fb502 | checkpoint | CH and FDM clearance
1e094529-19b3-411a-991b-ac1018ed126a | signoff | HOLD POINT
f6a6b65f-46f3-4688-ab37-57a92dfdcbaf | checkpoint | Identify work area, boundaries and survey requirement
8f18f6f6-44ad-42d2-92a1-800791b3005d | checkpoint | Clear & Grub Topsoil and stack timber
072d34b6-613b-42ce-ab8e-f599f3531cfc | checkpoint | Lease Entry Construction
ed51c11b-1006-4c98-afed-520a9534beee | checkpoint | Lease construction
a2365bd3-d844-4786-83a5-b0ac4ce0e38a | checkpoint | Compaction of layers in 300mm layers
bac5b8eb-e813-4801-b37f-1ea055a7e56a | checkpoint | Proof roll
4417cd67-86a5-4a89-864a-b89288a0154a | checkpoint | Verification of cross falls/laser set ups
d46dac32-34bb-4c41-8565-14db0cbb69cb | checkpoint | Final Trim
3b5097b0-2749-47cb-b951-529fd87b3445 | signoff | HOLD POINT
11e7a05b-3b5e-4256-b29f-fe3bdebdc116 | checkpoint | DCP Testing
09866dc9-38ea-445d-b786-c575f4420528 | signoff | WITNESS POINT
a14f9901-271b-47fa-9a7a-69026aa125c9 | checkpoint | Gravel Cap (as required)
b26012a9-9c09-4e9e-9c05-edecfd3751de | checkpoint | Install ESC
5ad1a4c9-4620-4f50-8b61-85c29a8338ca | checkpoint | Cellar Installation
7bd2a227-6be0-425a-9790-f512d0f7cc09 | checkpoint | Conductor Installation – Record plumb
366fb9b2-36ce-410c-b910-bf5811ebfcd2 | checkpoint | Conductor cemented in place
54f716c1-ada9-41ef-88aa-52dfd809f0ca | checkpoint | 4 x cattle panels to be installed
2e30158d-48d1-403f-8c98-fe7eb452d3db | checkpoint | Well signage and Pipeline entry mark completed
be858ad0-ac49-4b59-b219-f5d25fe7793e | checkpoint | As Built Completed
df28eb7c-e3c4-48ba-87b1-76f9672bb41e | checkpoint | RSA supervisor inspection
8bedfbdd-7ac2-42bd-9c27-ec20351f38ec | signoff | HOLD POINT
cf576cdc-3ae5-41af-bd9b-2d78c5d476d2 | checklist | RSA.WP28.FIC - PRELIMINARY - Rev2.0 | itp | RSA.WP28.FIC - PRELIMINARY
113ae58b-3e03-4a2d-941d-8b9bceb8d1a9 | section | FIELD INSPECTION CHECKLIST LEASE PADS
93e363bd-3c35-4235-9930-675bbefbd32d | checkpoint | Access documentation of relevant ATW, LARs/PTA, Cultural Heritage, Clearance Request
e9bc2d2f-7b2e-432f-aaa8-91b07b26a2cf | signoff | HOLD POINT
25c23025-b9a2-4229-9c53-72be2794cffb | checkpoint | Mobilisation of Machinery & Fit for Purpose inspection
141eb26d-6031-4789-9d7f-2588c2ddf3d1 | signoff | HOLD POINT
0fd53f78-656e-40d9-aed1-433c179fa64f | checkpoint | Gravel Compliance
db9e68e9-2210-4718-b706-26a3fef98fa7 | checklist | RSA.WP28.ITP | itp | RSA.WP28.ITP
3b25b908-a6c8-48de-bf4b-65181a189d03 | section | 1 - Preliminary
850f0d2d-e837-45e1-957a-2c0c2bea1604 | checkpoint | 1.1 - Access Documentation
71c2652f-7ab6-5b8e-afd5-0999f1ee4481 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Relevant ATW
97ae41d2-6732-56ca-9fb9-64ea2941a8d4 | note | ○ LARS / PTA
6a0359e9-cc47-5927-a9b2-ed9b4a787f82 | note | ○ Cultural Heritage Clearance Request (Works Notice)
d604ac57-73cc-5b5f-afb5-440d174be5f0 | note | Frequency - Prior to Start
a800cf7d-c606-50ae-bacc-65efa86b9387 | note | Test Method - Review
7ff3cadf-d9f2-57b3-9200-a0a6909f0805 | note | Acceptance Criteria - All documents in place and correct.
0150894b-d52f-5631-843d-2ee874db1a54 | note | Verifying Documents - LARS / PTA
75400374-4aef-59a7-9fd6-d101805f10b0 | note | ○ Landholder Notification
588b7862-2838-583b-a2aa-f3eb6a7f436c | note | ○ Weed Washdown Cert.
122e8c07-037c-5d44-9453-3f33288412e8 | note | ○ Species and Fauna Management
3d6d9a8f-a1d6-5ee0-aae3-5ed7ff8a237e | note | ○ Cultural Heritage Induction Attendance Register
a1557186-6986-583d-a255-dee2bc65ba71 | note | ○ Cultural Heritage Clearance Report / Form
d8dd3f3b-5552-5f65-bc70-2b66681032fd | note | Responsibility: RSA - H
9a85cf4c-a1e4-584a-8f63-bf382649b517 | note | Responsibility: Senex - H
6714bc34-c61a-4e96-88cc-4323e4cde7a5 | signoff | HOLD POINT
19b16ff4-7eef-4840-a386-028e5d20bc96 | checkpoint | 1.2 - Mobilise Machinery & Fit For Purpose (FFP) Inspection
381c782b-00ca-5ca8-9c5c-4382d4c9d6bf | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Permit To Access (PTA), Land Access Rules (LARs), and Construction Management Plan (CMP)
065bd560-768b-5cb9-841d-a84d4043fa81 | note | Frequency - Prior to Start
18f47546-90e5-54e6-af8e-d3c69fcdfa8a | note | Test Method - Review
eae80768-863c-5915-beb3-671f35b3d196 | note | Acceptance Criteria - Valid Weed Hygiene Certification for all vehicles and plant.
211967ee-ba0d-541b-9ee4-03158a196dd9 | note | Verifying Documents - Weed Declaration Certificate.
e12e18f0-78ca-51f0-89c9-a93ce4c77fff | note | ○ Appenate FFP Form
8c4945ca-d2cf-5cf6-8a42-87bae3f60b96 | note | Responsibility: RSA - H
4dd3db65-480c-5365-9730-f2b736ccec03 | note | Responsibility: Senex - W
a6fba66c-3e3c-4f01-9799-288ac753c774 | signoff | HOLD POINT
8229142c-0706-4362-9241-0bd14005ecc6 | checkpoint | 1.3 - Gravel Compliance
385afd1d-df84-575e-af4f-af410405c9fc | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specifications OPS-QLDS-CI-SPE-002: Section 6
c76360b0-71ba-5e28-8c3b-538f04689c68 | note | Frequency - Each Quarry
e2bc2527-6b8a-5ab2-810b-f252894cae43 | note | Test Method - Lab Testing
ed741200-ce4a-5f2b-9775-8b07097075b0 | note | Acceptance Criteria - Grading C
2e089bff-de73-5253-91c0-d9b81a026d66 | note | Verifying Documents - NATA Test Report
bb87964a-eb52-58e6-b550-0871125d05a3 | note | Responsibility: RSA - R
9af022e6-a69e-5ac8-8524-c5679a55f3f0 | note | Responsibility: Senex - W
9a667e0f-dc3b-424b-83b1-8497bcd09dbb | section | 2 - Access Tracks
a3291f52-3917-4123-8864-3e08c9e1a4dc | checkpoint | 2.1 - RSA QA inspection
42cb65bf-b111-5a54-9e12-d023367d0056 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specifications OPS-QLDS-CI-SPE-002: Section 7.1.2
a5fb43a7-60e2-59a2-80fd-7de67421d4d0 | note | Frequency - Each Track
f0e6481a-cf1b-569d-9463-a83cd1da767b | note | Test Method - Visual Inspection
9121480d-2407-559a-8bf1-b9c9f13ddd01 | note | Acceptance Criteria - RSA Supervisor to inspect and accept the works are complete.
32c2b27f-7e05-59f6-bcc3-17253cec4dee | note | Verifying Documents - Access Track FIC
22ce588f-7126-50c2-a198-7dfb5d8d4ada | note | Responsibility: RSA - H
346b5b1d-0537-5430-a530-106858ac772d | note | Responsibility: Senex - N/A
b2cc6697-593d-4085-9e7e-1956e09bf93d | signoff | HOLD POINT
f479ab23-723e-4f5e-819a-15ef56e38d9e | checkpoint | 2.2 - Client Signoff
4219a84c-6515-54e9-807a-b7eaf042211b | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specifications OPS-QLDS-CI-SPE-002: Section 7.1.2
aa1e469f-600a-50f3-a12e-d67ea71254c7 | note | Frequency - Each Track
7bacc9ff-be70-5434-9243-1d327a5c1360 | note | Test Method - Visual Inspection
27ce9cd6-7a35-5aff-adfc-4fa7f95b1d6d | note | Acceptance Criteria - Senex Civil Supervisor to inspect and approve access road is fit for purpose prior to machinery being demobilised.
662a3ebc-87f1-5885-a949-fe8da499983d | note | Verifying Documents - Access Track FIC
6a7fb81d-d50b-5272-9319-b6206065559f | note | Responsibility: RSA - N/A
9cd8c4d0-ca51-5faf-bf9a-d14173d90998 | note | Responsibility: Senex - H
48512afa-dd59-43da-bd3d-2b72143fd68a | signoff | HOLD POINT
0f3e0f6b-895d-48d6-9211-041617e0cb24 | section | 3 - In Field, Property Fencing and Grid (Fencing)
6338b478-60e3-4d55-9bd2-e1ca0fa199a8 | checkpoint | 3.1 - RSA QA inspection
56315118-5a29-5e84-9bd2-88ef1f7c930d | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-003 REV 0: Section 4
9eee845a-5b64-5c36-8f4d-d3f5a3fa2d30 | note | Frequency - Each Grid
28d75ef2-bf0a-51f2-97d2-caec73f52535 | note | Test Method - Visual Inspection
709f73e5-5ed6-5bfa-8f9c-0754c64a268f | note | Acceptance Criteria - RSA Supervisor to inspect and accept the works are complete.
eae51c37-ff80-5163-8230-41d1557a0c2b | note | Verifying Documents - Grid &Fence Installation FIC
b596122e-8d39-5884-9a03-f1a684141ed7 | note | Responsibility: RSA - H
ee404a61-27a2-5ef5-8b4e-521351410070 | note | Responsibility: Senex - N/A
73b830a9-79f6-4513-960f-e638094163fb | signoff | HOLD POINT
a16c5e69-7d9e-43bd-b97c-01bbbe101c85 | checkpoint | 3.2 - Client Signoff
6a7cf3e6-3ed5-5c55-8705-dc44201f45e8 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-003 REV 0: Section 4
13d3f1b0-c976-5230-b04a-ed0f42cc97aa | note | Frequency - Each Grid
f21911c7-8756-5f97-bb7a-bb894e684879 | note | Test Method - Visual Inspection
5f43cbe5-5342-5944-b9b2-e4319ba05cc1 | note | Acceptance Criteria - Senex Civil Supervisor to inspect and approve Grid is fit for purpose prior to machinery being demobilised.
a33a9079-484e-5a64-bd18-766210d3da69 | note | Verifying Documents - Grid &Fence Installation FIC
ac71f739-5a26-5541-a671-d593c1b00c23 | note | Responsibility: RSA - N/A
3e74f123-d7fc-5b78-a196-3be2f982dd2b | note | Responsibility: Senex - H
8aaf4bb8-1163-4b9b-bae2-183bded972b4 | signoff | HOLD POINT
0f33aece-7d30-4cd1-b16f-902899fdc216 | section | 4 - Lease Pads
d0aa8a66-adb2-4dd7-9eba-be0da54aeef1 | checkpoint | 4.1 - RSA Supervispr inspection
4ee7d60d-e2c5-59f0-8e3b-05c4ca55c924 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - SENEX-QLDS-DR-SPE-001 & OPS-QLDS-CI-SPE-002
00575f72-aa66-5277-8117-554ee62e5478 | note | Frequency - Each Pad
f5f49b26-7082-5a7a-b866-42e9036127f8 | note | Test Method - Visual Inspection
d24190e2-c105-531d-b793-bb998067e882 | note | Acceptance Criteria - RSA Supervisor to inspect and accept the works are complete.
4f395cd1-bfb3-5d4c-befc-daf2a66a69c0 | note | Verifying Documents - Lease Pad FIC
756f6fdc-b986-53af-8bb1-d3ecea6f6ad4 | note | Responsibility: RSA - H
cdd81c8b-ced8-5dd7-b1c0-d50eb79d9493 | note | Responsibility: Senex - N/A
2b320a1c-8a4b-4c86-bbc6-b9667ad8fd31 | signoff | HOLD POINT
0c74c43e-afea-40e4-8428-5e1f82948ea1 | checkpoint | 4.2 - Client Signoff
88adf751-88f7-5499-a75a-2e36121818e2 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - SENEX-QLDS-DR-SPE-001 &OPS-QLDS-CI-SPE-002
faa9f5ef-0a27-50d6-8cc9-215865a2dacc | note | Frequency - Each Pad
1a19e18e-9b90-5df5-a56a-7deac1e079ea | note | Test Method - Visual Inspection
54502229-c3d2-5db9-8c46-4e8887db476f | note | Acceptance Criteria - Senex Civil Supervisor to inspect and approve Grid is fit for purpose prior to machinery being demobilised.
945a166e-e965-5f6b-a45e-79ff36c32594 | note | Verifying Documents - Lease Pad FIC
2505f2c3-85cf-54a4-9d71-58b8af01ee35 | note | Responsibility: RSA - N/A
9e8deef2-a7a5-520b-b5f8-be931d629273 | note | Responsibility: Senex - H
3c4a1e69-50c3-46aa-b2e6-419eb29659ac | signoff | HOLD POINT
2f0e9f06-b599-40c2-a349-b81952e15585 | section | Reference Documents
cd4bac6c-b1fe-408a-9f3c-40a6ca6ee8b2 | checkpoint-no-value | Reference Documents:
3ee55128-e638-55c7-9e0a-edd08bd54646 | note | SENEX-QLDS-EN-PRC-003 rev 1 (Queensland Erosion and Sediment Control Procedure)
f5931ffb-1737-5e76-ba25-8703364e0121 | note | OPS-QLDS-CI-SPE-003 REV 0 (Fencing, Grids and Gateways Civil Specification)
bbfb6c57-357c-50a4-a756-77ed7aac2e62 | note | OPS-QLDS-CI-SPE-002 Rev 0 (Lease Pads, Hardstands, Access Roads Civil Specification)
7df7496a-a078-50fd-8964-3bf189030bfb | note | OPS-QLDS-CN-GDL-002 (Survey Peg Identification Guide)
1cc94b81-18d8-5fc7-af30-e21707fbd93e | note | SENEX-QLDS-CI-GDL-001 Rev D (Whoa-Boy Construction Guidelines)
1871146a-0de5-5b5d-bd4f-3e2b4a5af22c | note | SENEX-QLDS-DR-SPE-001 Rev 4 (Conductor and Cellar Installation Specification)
e0800e5c-727d-5637-8ad4-114f4d2cce0d | note | OPS-QLDS-CN-GDL-002 (Survey Peg Identification Guide)
587ac5ea-06b4-57ce-8c29-1d7eb5192a15 | note | OPS-QLDS-CI-GAR-001 Rev 1A (Well Lease Layout Standard Drill Rig Civil General Arrangement)
7ec76482-c08a-457a-a805-27986355c9d2 | section | To be completed upon completion of all work activities
cf62cb0b-e4c6-4298-b0e1-4d0e8730e64f | checkpoint | This is to confirm that the above ITP has been completely signed off. All necessary inspections have been completed, the verifying documents have been provided, and the works conform to the contract specification
5f584e7a-a84f-53b7-909c-18ae703aa8c5 | note | Completed By:
8ad45b02-c269-529a-bcc1-de4a886cdb7f | textbox | Contractor Representative - Name:
32a5bead-bd3e-5e5a-825c-2b50efd28c74 | textbox | Contractor Representative - Position:
179cf659-e8c0-5fdc-adf7-3575bd95f808 | textbox | Senex Construction Representative - Name:
2b59d25d-8fe3-5658-9beb-6456c0232a50 | textbox | Senex Construction Representative - Position:
b559f123-c776-59b3-9f83-bccacbc9cc0f | note | Approved By:
282912a7-00bb-5ab8-9f41-44fcb38d7107 | textbox | Client Representative - Name:
5c80d40c-d465-54ca-b9d0-8291c6abb015 | textbox | Client Representative - Position:
db995536-f190-5a12-a959-de32801538fd | date | Date:
96a60e51-6445-4c84-b9e5-dceb1db5722f | signoff | Add Signature