## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | RSA.WP17.REHAB.ITP | itp |  |  |  |  | RSA.WP17.REHAB.ITP
section | 1 - Preliminary
checkpoint | 1.1 - Access Documentation
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Client PTA / LARS Relevant Construction Work Pack
label | Frequency - Prior to Start
label | Test Method - Review
label | Acceptance Criteria - All documents in place and correct.
label | Verifying Documents - Client PTA / LARS Relevant Construction Work Pack
label | Responsibility: RSA - H
holdpoint | HOLD POINT
checkpoint | 1.2 - Mobilise Machinery & Fit For Purpose (FFP) Inspection
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Permit To Access (PTA), Land Access Rules (LARs), and Construction Management Plan (CMP)
label | Frequency - Prior to Start
label | Test Method - Review
label | Acceptance Criteria - Valid Weed Hygiene Certification for all vehicles and plant.
label | Verifying Documents - Weed Declaration Certificate. Appenate FFP Form
label | Responsibility: RSA - H
holdpoint | HOLD POINT
section | 2 - Lease Rehab
checkpoint | 2.1 - Confirm set out workover rig area has been implemented by the Client
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Client Procedure OPS-QLDS-CI-GAR-005
label | Frequency - Each Lease Pad
label | Test Method - Visual Inspection
label | Acceptance Criteria - As per Client Procedure
label | Verifying Documents - Lease Rehab FIC
label | Responsibility: RSA - M
checkpoint | 2.2 - Confirm pipeline entry location (GIS)
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Client Procedure OPS-QLDS-CI-GAR-005
label | Frequency - Each Lease Pad
label | Test Method - Visual Inspection
label | Acceptance Criteria - As per Client Procedure
label | Verifying Documents - Lease Rehab FIC
label | Responsibility: RSA - M
checkpoint | 2.3 - ESC in working order (Ensure no sediment is past the containment point)
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Client Procedure SENEX-QLDS-EN-PRC-003
label | Frequency - Each Lease Pad
label | Test Method - Visual Inspection
label | Acceptance Criteria - As per Client Procedure
label | Verifying Documents - Lease Rehab FIC
label | Responsibility: RSA - M
checkpoint | 2.4 - Install table drain and/or clean out (If required)
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Client IFC Well Pad Cut Fill Lease Pad Layout Drawing
label | Frequency - Each Lease Pad
label | Test Method - Visual Inspection
label | Acceptance Criteria - Client IFC Well Pad Cut Fill Lease Pad Layout Drawing
label | Verifying Documents - Lease Rehab FIC
label | Responsibility: RSA - M
checkpoint | 2.5 - Clean out shot rock sump & tidy up (if required)
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Client Procedure OPS-QLDS-CI-SPE-002
label | Frequency - Each Lease Pad
label | Test Method - Visual Inspection
label | Acceptance Criteria - Rock shall be no smaller than 150 millimetres and no greater than 300 millimetres and free of course to fine-grained material
label | Verifying Documents - Lease Rehab FIC
label | Responsibility: RSA - M
checkpoint | 2.6 - Amelioration (Gypsum / Lime) (If required)
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Client IFC Well Pad Cut Fill Lease Pad Layout Drawing
label | Frequency - Each Lease Pad
label | Test Method - Visual Inspection
label | Acceptance Criteria - As per Client Procedure
label | Verifying Documents - Lease Rehab FIC
label | Responsibility: RSA - M
checkpoint | 2.7 - Rip Sub Soil Areas
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Client Procedure SENEX-QLDS-EN-PRC-002
label | Frequency - Each Lease Pad
label | Test Method - Visual Inspection
label | Acceptance Criteria - As per Client Procedure
label | Verifying Documents - Lease Rehab FIC
label | Responsibility: RSA - M
checkpoint | 2.8 - Reclaim topsoil from batters and topsoil stock pile where available
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Client Procedure SENEX-QLDS-EN-PRC-002
label | Frequency - Each Lease Pad
label | Test Method - Visual Inspection
label | Acceptance Criteria - As per Client Procedure
label | Verifying Documents - Lease Rehab FIC
label | Responsibility: RSA - M
checkpoint | 2.9 - Transport and Spread Topsoil
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Client Procedure SENEX-QLDS-EN-PRC-002
label | Frequency - Each Lease Pad
label | Test Method - Visual Inspection
label | Acceptance Criteria - Respread topsoil (should be a minimum depth of 150mm uncompacted, if material available). Ensure topsoil and subsoil are not mixed
label | Verifying Documents - Lease Rehab FIC
label | Responsibility: RSA - M
checkpoint | 2.10 - Fertiliser, Seed & Scarify
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Client Procedure SENEX-QLDS-EN-PRC-002 Client LARS
label | Frequency - Each Lease Pad
label | Test Method - Visual Inspection
label | Acceptance Criteria - As per Client Procedure
label | ○ Seed mix uses native or pasture grasses and does not contain pest species.
label | ○ Seed mix meets landholder requirements.
label | Verifying Documents - Lease Rehab FIC
label | Responsibility: RSA - M
checkpoint | 2.11 - Confirm As Con Map has been completed & received
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Client Marked Drawing
label | Frequency - Each Lease Pad
label | Test Method - Documentation
label | Acceptance Criteria - As Con Maps
label | Verifying Documents - Lease Rehab FIC
label | Responsibility: RSA - M
checkpoint | 2.12 - RSA QA inspection
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specifications
label | Frequency - Each Lease Pad
label | Test Method - Visual Inspection
label | Acceptance Criteria - RSA Supervisor to inspect and accept the works are complete.
label | Verifying Documents - Lease Rehab FIC
label | Responsibility: RSA - H
holdpoint | HOLD POINT
section | Reference Documents
checkpoint-no-value | Reference Documents:
label | SENEX-QLDS-EN-PRC-003 rev 1 (Queensland Erosion and Sediment Control Procedure)
label | OPS-QLDS-CI-SPE-002 Rev 0 (Lease Pads, Hardstands, Access Roads Civil Specification)
label | SENEX-QLDS-EN-PRC-002 Rev 0 (QLD Reinstatement and Rehabilitation Procedure)
label | OPS-QLDS-CI-GAR-001 Rev 1A (Well Lease Layout Standard Drill Rig Civil General Arrangement)
section | To be completed upon completion of all work activities
checkpoint | This is to confirm that the above ITP has been completely signed off. All necessary inspections have been completed, the verifying documents have been provided, and the works conform to the contract specification
label | Completed By:
textbox | Contractor Representative - Name:
textbox | Contractor Representative - Position:
textbox | Senex Construction Representative - Name:
textbox | Senex Construction Representative - Position:
label | Approved By:
textbox | Client Representative - Name:
textbox | Client Representative - Position:
date | Date:
holdpoint | Add Signature
checklist | RSA.WP17.REHAB.FIC | itp |  |  |  |  | RSA.WP17.REHAB.FIC
section | FIELD INSPECTION CHECKLIST ACCESS TRACK
checkpoint | Confirm set out workover rig area has been implemented by the Client
checkpoint | Confirm pipeline entry location (GIS)
checkpoint | ESC in working order (Ensure no sediment is past the containment point)
checkpoint | Install table drain and/or clean out (If required)
checkpoint | Clean out shot rock sump & tidy up (if required)
checkpoint | Amelioration (Gypsum / Lime) (If required)
checkpoint | Rip Sub Soil Areas
checkpoint | Reclaim topsoil from batters and topsoil stockpile where available
checkpoint | Transport and Spread Topsoil
checkpoint | Fertiliser, Seed & Scarify
checkpoint | Confirm As Con has been completed & received
checkpoint | RSA QA Inspection
holdpoint | HOLD POINT