## Sheet1
2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [31 empty] | MRTS92 Traffic Signal and Road Lighting Footings | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | MRTS92 Traffic Signal and Road Lighting Footings
[8 empty] | Mt Cotton and Coorang | [16 empty] | Doval Project No. |  |  |  |  | 25 002 |  |  |  | Inspection and Test Plan
[25 empty] | Client Project No. |  |  |  |  | 89511RDW2
[8 empty] | Lot Number |  |  |  | Description |  |  |  | Conduits, Pits and Footings | [13 empty] | Date Opened
[30 empty] | Date Started |  |  |  | 36 |  |  |  | MRTS92 Traffic Signal and Road Lighting Footings
Location | [14 empty] | Control Line | [6 empty] | Chainage |  |  |  |  | - |  |  | Date Finished
No. |  | Activity Description | [12 empty] | Acceptance Criteria & Frequency (Project Specific) | [7 empty] | Check Item |  |  |  | Inspection | [11 empty] | NCR |  | Related Lot #
[23 empty] | Reference |  |  |  | SS/QA |  |  |  | Client/Rep |  |  |  | Date
1 |  | Pre-Construction
1.1 |  | Construction procedure submitted to the Client. | [12 empty] | Check & Verify | [7 empty] | Check Item
MRTS91 Cl.5.2
1.2 |  | Asbestos presence assessment | [12 empty] | Check & Verify | [7 empty] | Check Item
MRTS91 Cl 6.1
1.3 |  | Material certifications submitted to the Client. | [12 empty] | Check & Verify | [7 empty] | Check Item
MRTS91 Cl.7.1
1.4 |  | Drawing versions correct. | [12 empty] | Check & Verify | [7 empty] | Check Item
IFC
1.1
1.2
1.1
1.2
1.1
1.2
1.1
1.2
1.1
1.2
1.1
1.2
1.1
1.2
1.1
1.2
1.1
1.2
1.1
1.2
1.1
1.2
1.1
1.2
1.1
1.5 |  | Certificate of Supply (Authority to Construct) received | [12 empty] | Check & Verify | [7 empty] | Check Item
WCS34
1.6 |  | Form 15 for footing design completed | [12 empty] | Check & Verify | [7 empty] | Check Item
Clause 2.4.2 MUTCD
1.7 |  | Conduit, pit, footing and slab location and finished level surveyed and SI approved. | [12 empty] | Check & Verify | [7 empty] | Hold Point
Clause 2.4.3 MUTCD
2 |  | Conduit Installation
2.1 |  | Bottom of trench compacted to form a firm uniform surface free from loose material. | [12 empty] | Check & Verify | [7 empty] | Witness Point
MRTS91 Cl.9.1
2.2 |  | Boring/Jacking Contractor and equipment approved by the SI and works are carried out by experienced operators. | [12 empty] | Check & Verify | [7 empty] | Hold Point
MRTS91 Cl.8.7
2.3 |  | Conduit installation approved by Superintendent and conduit will properly drain, contains no blockages and is not lower than pits that they are connected to. | [12 empty] | Check & Verify | [7 empty] | Check Item
MRTS91 Cl.9.1
2.4 |  | Conduits in roadway backfill: TMR/GCCC/Energex - lean mix BCC – Unbound Pavement or Lean Mix to match existing permeability Passing Test Result: TMR - 95% RDD | [12 empty] | Check & Verify | [7 empty] | Check Item
MRTS91 Cl.13.2
2.5 |  | Conduits in footpath backfilled with insitu material, else MRS11.05 Type 2 material where insitu cannot be compacted. Passing Test Result: TMR - 90% RDD | [12 empty] | Check & Verify | [7 empty] | Check Item
MRTS91 Cl.13.2
2.6 |  | Conduit and conduit fittings proved by drawing a mandrel of following size: TMR – 95% of ID and 95% of ID in length Energex:- 6mm less than ID and 100mm in length | [12 empty] | Check & Verify | [7 empty] | Hold Point
MRTS91 Cl 9.1
2.7 |  | Any joints made in the draw rope shall be capable of resisting the same tensile load as the draw rope without such a joint. The joint shall not appreciably increase the diameter of the rope. | [12 empty] | Check & Verify | [7 empty] | Witness Point
MRTS91 Cl 9.13
2.8 |  | Vermin proofing of conduits with unspecified sealing system. | [12 empty] | Check & Verify | [7 empty] | Check Item
MRTS91 Cl 10.9
3 |  | Pit Installation
3.1 |  | Soil under pit compacted to 95% RDD | [12 empty] | Check & Verify | [7 empty] | Witness Point
MRTS91 Cl.10.4
3.2 |  | Compact bedding material to density index 60. | [12 empty] | Check & Verify | [7 empty] | Check Item
MRTS91 Cl.10.4
3.3 |  | Lowest open end of conduits installed in poles and other field equipment enclosures shall be at least 50 mm higher than the surrounding finished surface level | [12 empty] | Check & Verify | [7 empty] | Witness Point
MRTS91 Cl.10.10
4 |  | Footing and slab Installation
4.1 |  | Depth, base and sidewalls of footing’s and slab’s confirmed for each location | [12 empty] | Verify & Hold Point | [7 empty] | Hold Point
4.2 |  | Ragbolt/reinforcement assembly inspected prior to concrete pour. Concrete poured in accordance with MRTS70. Concrete inspected to ensure correct vibration, monitor placing time and check that material is placed to avoid segregation. Check surface finish. | [12 empty] | Check & Verify | [7 empty] | Check Item
MRTS92 Cl.8.3.7 MRTS70
4.3 |  | Concrete tested for slump and compressive strength by NATA laboratory | [12 empty] | Check & Verify | [7 empty] | Check Item
MRTS70
4.4 |  | Form 16 provided to client verifying footing construction completed in accordance with drawings | [12 empty] | Check & Verify | [7 empty] | Check Item
Project Specific
5 |  | Energex Concrete Insitu Pits
5.1 |  | Form 15 provided by Pit Designer | [12 empty] | Check & Verify | [7 empty] | Check Item
5.2 |  | Form 16 provided to client verifying pit construction completed in accordance with drawing | [12 empty] | Check & Verify | [7 empty] | Check Item
6 |  | Completion Works
6.1 |  | Submission of certification package to Energex including: - Certificate of Test - As-Con Drawings - Product Audit | [12 empty] | Check & Verify | [7 empty] | Check Item
Responsible Officer | [21 empty] | Verifying Authority
Signature: | [21 empty] | Signature:
Print Name: | [13 empty] | Date: | [7 empty] | Print Name: | [13 empty] | Date:
Comments: