## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | 36.00 - MRTS92 Traffic Signal and Road Lighting Footings | itp |  |  |  |  | 36.00 - MRTS92 Traffic Signal and Road Lighting Footings
section | Pre-Construction
checkpoint | 1.1 - Construction procedure submitted to the Client.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - MRTS91 Cl.5.2
checkpoint | 1.2 - Asbestos presence assessment
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - MRTS91 Cl 6.1
checkpoint | 1.3 - Material certifications submitted to the Client.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - MRTS91 Cl.7.1
checkpoint | 1.4 - Drawing versions correct.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - IFC
checkpoint | 1.5 - Certificate of Supply (Authority to Construct) received
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - WCS34
checkpoint | 1.6 - Form 15 for footing design completed
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Clause 2.4.2 MUTCD
checkpoint | 1.7 - Conduit, pit, footing and slab location and finished level surveyed and SI approved.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Hold Point
label | Reference - Clause 2.4.3 MUTCD
holdpoint | HOLD POINT
section | Conduit Installation
checkpoint | 2.1 - Bottom of trench compacted to form a firm uniform surface free from loose material.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Witness Point
label | Reference - MRTS91 Cl.9.1
checkpoint | 2.2 - Boring/Jacking Contractor and equipment approved by the SI and works are carried out by experienced operators.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Hold Point
label | Reference - MRTS91 Cl.8.7
holdpoint | HOLD POINT
checkpoint | 2.3 - Conduit installation approved by Superintendent and conduit will properly drain, contains no blockages and is not lower than pits that they are connected to.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - MRTS91 Cl.9.1
checkpoint | 2.4 - Conduits in roadway backfill:
label | ○ TMR/GCCC/Energex - lean mix BCC – Unbound Pavement or Lean Mix to match existing permeability
label | ○ Passing Test Result: TMR - 95% RDD
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - MRTS91 Cl.13.2
checkpoint | 2.5 - Conduits in footpath backfilled with insitu material, else MRS11.05 Type 2 material where insitu cannot be compacted.
label | ○ Passing Test Result: TMR - 90% RDD
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - MRTS91 Cl.13.2
checkpoint | 2.6 - Conduit and conduit fittings proved by drawing a mandrel of following size:
label | ○ TMR – 95% of ID and 95% of ID in length
label | ○ Energex:- 6mm less than ID and 100mm in length
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Hold Point
label | Reference - MRTS91 Cl 9.1
holdpoint | HOLD POINT
checkpoint | 2.7 - Any joints made in the draw rope shall be capable of resisting the same tensile load as the draw rope without such a joint. The joint shall not appreciably increase the diameter of the rope.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Witness Point
label | Reference - MRTS91 Cl 9.13
checkpoint | 2.8 - Vermin proofing of conduits with unspecified sealing system.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - MRTS91 Cl 10.9
section | Pit Installation
checkpoint | 3.1 - Soil under pit compacted to 95% RDD
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Witness Point
label | Reference - MRTS91 Cl.10.4
checkpoint | 3.2 - Compact bedding material to density index 60.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - MRTS91 Cl.10.4
checkpoint | 3.3 - Lowest open end of conduits installed in poles and other field equipment enclosures shall be at least 50 mm higher than the surrounding finished surface level
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Witness Point
label | Reference - MRTS91 Cl.10.10
section | Footing and slab Installation
checkpoint | 4.1 - Depth, base and sidewalls of footing’s and slab’s confirmed for each location
label | Acceptance Criteria & Frequency (Project Specific) - Verify & Hold Point
label | Check Item - Hold Point
holdpoint | HOLD POINT
checkpoint | 4.2 - Ragbolt/reinforcement assembly inspected prior to concrete pour.
label | ○ Concrete poured in accordance with MRTS70.
label | ○ Concrete inspected to ensure correct vibration, monitor placing time and check that material is placed to avoid segregation. Check surface finish.
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - MRTS92 Cl.8.3.7, MRTS70
checkpoint | 4.3 - Concrete tested for slump and compressive strength by NATA laboratory
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - MRTS70
checkpoint | 4.4 - Form 16 provided to client verifying footing construction completed in accordance with drawings
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - Project Specific
section | Energex Concrete Insitu Pits
checkpoint | 5.1 - Form 15 provided by Pit Designer
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
checkpoint | 5.2 - Form 16 provided to client verifying pit construction completed in accordance with drawing
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
section | Completion Works
checkpoint | 6.1 - Submission of certification package to Energex including:
label | — Certificate of Test
label | — As-Con Drawings
label | — Product Audit
label | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
checkpoint | Final Verification
label | Responsible Officer
textbox | Print Name:
date | Date:
label | Verifying Authority
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off