## 28.01
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70
|  | CSF | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [31 empty] | Contractor's Camp and Site Facilities | [13 empty] | CSF | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Contractor's Camp and Site Facilities
[9 empty] | Logan City Council CE49, CE46, CE47, Blackspot Project | [16 empty] | Doval Project No. |  |  |  |  | 25 047 |  |  |  | Inspection and Test Plan
Client Project No.
[9 empty] | Lot Number |  |  |  | Description | [17 empty] | Date Opened
[9 empty] | CSF | 1 | 1 | [19 empty] | Date Started |  |  |  | MRTS28 (Nov 2019) 28.01 Rev 0 |  |  |  | Contractor's Camp and Site Facilities
| Location | [14 empty] | Control Line | [6 empty] | Chainage |  |  |  |  | - |  |  | Date Finished
| No. |  | Activity Description | [12 empty] | Acceptance Criteria & Frequency (Project Specific) | [7 empty] | Check Item |  |  |  | Inspection | [11 empty] | NCR |  | Related Lot #
[24 empty] | Reference |  |  |  | PE/WS/SS |  |  |  | CQR to Verify |  |  |  | Administrator
| 1 |  | the Contractor shall be responsible for obtaining any necessary areas either through purchase or rent, including obtaining any required licenses, permits and approvals. Facilities should avoid areas containing remnant native vegetation and should be sited within the approved project area. | [12 empty] | Visual | [7 empty] | Check Item
MRTS28 Cl. 4.2
| 2 |  | Properly constructed toilets, rubbish receptacles and wash facilities provided. | [12 empty] | Visual | [7 empty] | Check Item
MRTS28 Cl. 4.3
| 3 |  | Camp and facilities provide safe egress and ingress and do not impact on existing through traffic. | [12 empty] | Visual | [7 empty] | Check Item
MRTS28 Cl. 4.5.6
| 4 |  | Contractors camp complies with all requirements of MRTS52. | [12 empty] | Visual | [7 empty] | Check Item
MRTS52 Cl. 6
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
General Comments
|  | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification | [20 empty] | Administrator's Representative Verify that the Above has been Constructed according to Specification
|  | Print Name | [6 empty] | Signature | [6 empty] | Date | [6 empty] | Print Name | [6 empty] | Signature | [6 empty] | Date