## LCC 70.01
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70
|  | CNG | 1 | 1 | Clearing & Grubbing | Logan Reserve | 0 | 0 | 0 | 0 | 0 | 0 | [31 empty] | Clearing & Grubbing | [9 empty] | CNG | 1 | 1 | Clearing & Grubbing | Logan Reserve | 0 | 0 | 0 | 0 | 0 | 0 | Clearing & Grubbing
[9 empty] | Logan City Council CE49, CE46, CE47, Blackspot Project | [16 empty] | Doval Project No. |  |  |  |  | 25047 |  |  |  | Inspection and Test Plan
Client Project No.
[9 empty] | Lot Number | [6 empty] | Clearing & Grubbing | [14 empty] | Date Opened
[9 empty] | CNG | 1 | 1 | 1 | [18 empty] | Date Started |  |  |  | LCC Specification No. 1 & No. 2 |  |  |  | Clearing & Grubbing
| Location | [7 empty] | Logan Reserve | [6 empty] | Control Line | [6 empty] | Chainage |  |  |  |  | - |  |  | Date Finished
| No. |  | Activity Description | [12 empty] | Acceptance Criteria & Frequency (Project Specific) | [7 empty] | Check Item |  |  |  | Inspection | [11 empty] | NCR |  | Related Lot #
[24 empty] | Reference |  |  |  | SS/QA | [7 empty] | Client/Rep
| 1 |  | Erosion and sediment control, clearing and grubbing, stockpiles, softworks grades and earth mounds to be in accordance with Standard Specification No. 2 Cl 4. | [12 empty] | Visual | [7 empty] | Check Item
LCC Specification No. 2 Cl 4
|  |  | Before the commencement of any earthworks, “Dial before you dig” obtained | [12 empty] | Check & Verify | [7 empty] | Check Item
LCC Specification No. 1 Cl 4.4
|  |  | Where an area of the premises are required to be cleared, the clearing includes the removal of: (a) all artificial obstructions including fences, unnecessary structures, building foundations, obsolete pipelines and the like; (b) plants (including stumps and boulders) other than the plants required to be retained as shown on the approved drawings; (c) rubbish | [12 empty] | Visual | [7 empty] | Check Item
LCC Specification No. 1 Cl 2.1
|  |  | The extent of the cleared area is limited to: (a) the minimum area of the premises to be occupied by the completed earthworks; (b) 1 metre on each side of the completed earthworks; (c) the minimum area of the premises required to safely install a service | [12 empty] | Visual | [7 empty] | Check Item
LCC Specification No. 1 Cl 2.2
| 2 |  | Grubbing, being the removal from the ground of trees, roots and stumps to a depth of 300mm below the surface of the ground, is carried out across the entire cleared area. | [12 empty] | Visual | [7 empty] | Check Item
LCC Specification No. 1 Cl 3.1
General Comments
Final Sign off and Approval - Conformance with the Specification
|  | Name of Contractor's Representative | [6 empty] | Name of Contractor's Representative | [6 empty] | Name of Contractor's Representative | [6 empty] | Verified by Cient's Representative | [6 empty] | Name of Cient's Representative | [6 empty] | Name of Cient's Representative
|  | Print Name | [6 empty] | Signature | [6 empty] | Date | [6 empty] | Print Name | [6 empty] | Signature | [6 empty] | Date
Mitchell Terz