## LCC 70.01
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70
|  | CON | 1 | 0 | Footpath | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [31 empty] | Concrete | [9 empty] | CON | 1 | 0 | Footpath | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Concrete
[9 empty] | Logan City Council CE49, CE46, CE47, Blackspot Project | [16 empty] | Doval Project No. |  |  |  |  | 25047 |  |  |  | Inspection and Test Plan
Client Project No.
[9 empty] | Lot Number | [6 empty] | Footpath | [14 empty] | Date Opened
[9 empty] | CON | 1 |  | 1 | [18 empty] | Date Started |  |  |  | LCC Std Specification No. 7: Concrete & No. 8 Minor Conc Works |  |  |  | Concrete
| Location | [14 empty] | Control Line | [6 empty] | Chainage |  |  |  |  | - |  |  | Date Finished
| No. |  | Activity Description | [12 empty] | Acceptance Criteria & Frequency (Project Specific) | [7 empty] | Check Item |  |  |  | Inspection | [11 empty] | NCR |  | Related Lot #
[24 empty] | Reference |  |  |  | SS/QA | [7 empty] | Client/Rep
| 1 |  | Mix designs for each class of concrete forwarded to Administrator | [12 empty] | Visual | [7 empty] | Milestone
| 2 |  | No concrete is placed until the foundations have been approved by the local government. | [12 empty] | Visual | [7 empty] | Hold Point
LCC Specification No. 8 Cl.3.1.3
| 3 |  | A concrete path is constructed in accordance with standard drawing IPWEAQ R-0065 including the following: (a) thickness: 100mm (b) concrete—grade N25 Mpa/20; (c) reinforcement SL62 (d) finish—broomed; (e) expansion joints—R12, 300mm long at 300mm centres centrally located. | [12 empty] | Visual | [7 empty] | Check Item
LCC Specification No. 8 Cl 3.1.1
| 4 |  | Concrete placed and compacted within 1 hour and 15mins (conc. Temp<=30 degrees) and within 30 minutes of charging the mixer. | [12 empty] | Temperature | [7 empty] | Check Item
LCC Specification No. 7 Cl.4.3
| 5 |  | No concrete placed until formwork and reinforcement are inspected by the administrator, foreign material removed from forms and equipment. | [12 empty] | Visual | [7 empty] | Hold Point
LCC Specification No. 7 Cl.5.3.6
| 6 |  | Concrete slump is within tolerance (AS 1379 table 6) of approved target slump. | [12 empty] | Slump Test: 20MPA/Cast Insitu : 70-120 25/Cast Insitu : 70-120 32/Cast Insitu : 70-150 40/Cast Insitu : 60-150 50/Cast Insitu : 50-150 32-50/Pumped Concrete : 100-150 Every Load Tested | [7 empty] | Check Item
LCC Specification No. 7 - Table 2.4.1
|  |  | No extra water is added to the concrete on site unless: (a) the amount of the water being added is measured and recorded; (b) the concrete is thoroughly remixed and a slump test taken to ensure the consistency is still within the specified limits in this standard specification. | [12 empty] | Check & Verify | [7 empty] | Check Item
LCC Specification No. 7 Cl.2.4.3
| 7 |  | Samples for testing taken as required - (1) 7 day test result and two (2) 28 day test results | [12 empty] | Testing | [7 empty] | Check Item
AS 1012.1-1993
| 8 |  | Compaction of concrete commences immediately after deposition in accordance with approved procedures and equipment - minimum of two vibrators used with at least one per 4m3 of concrete placed per hour. | [12 empty] | Visual | [7 empty] | Check Item
LCC Specification No. 7 Cl.4.1.12
| 9 |  | Forms not removed early unless approved by the Superintendent | [12 empty] | Visual | [7 empty] | Hold Point
LCC Specification No. 7 6.2
| 10 |  | Curing to take place immediately after concrete has hardened, by method of a compound or by continuously wetting the surface for the curing period | [12 empty] | Visual Surfaces other that slabs - 7day cure Slabs - 14day cure | [7 empty] | Milestone
LCC Specification No. 7 Cl 6.3
| 11 |  | Procedures for surface dressing of concrete approved by the Superintendent. | [12 empty] | Visual | [7 empty] | Hold Point 7
MRTS70 Cl 25.1
| 12 |  | Following removal of forms * Fins and unwanted projections are ground off * Pockets and honeycombed areas repaired using approved methods | [12 empty] | Visual | [7 empty] | Check Item
LCC Specification No. 7 Cl 6.1.2
| 13 |  | Concrete installed to within positional, dimensional and relative tolerances | [12 empty] | Measure | [7 empty] | Check Item
LCC Specification No. 7 Tbl 6.4
| 14 |  | Acceptance or Rejection of Hardened Concrete | [12 empty] | f'c | [7 empty] | Check Item
24
25
26
27
28
29
30
| Schedule No. |  |  |  | Description | [15 empty] | QTY |  |  | Unit |  |  | Comments
General Comments
Final Sign off and Approval - Conformance with the Specification
|  | Name of Contractor's Representative | [6 empty] | Name of Contractor's Representative | [6 empty] | Name of Contractor's Representative | [6 empty] | Verified by Cient's Representative | [6 empty] | Name of Cient's Representative | [6 empty] | Name of Cient's Representative
|  | Print Name | [6 empty] | Signature | [6 empty] | Date | [6 empty] | Print Name | [6 empty] | Signature | [6 empty] | Date
Mitchell Terz