## LCC 70.01
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70
|  | KRB | 1 | 0 | Kerb & Channel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [31 empty] | Kerb & Channel | [9 empty] | KRB | 1 | 0 | Kerb & Channel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Kerb & Channel
[9 empty] | Logan City Council CE49, CE46, CE47, Blackspot Project | [16 empty] | Doval Project No. |  |  |  |  | 25047 |  |  |  | Inspection and Test Plan
Client Project No.
[9 empty] | Lot Number | [6 empty] | Kerb & Channel | [14 empty] | Date Opened
[9 empty] | KRB | 1 |  | 1 | [18 empty] | Date Started |  |  |  | LCC Std Specification No. 8 Minor Conc Works |  |  |  | Kerb & Channel
| Location | [14 empty] | Control Line | [6 empty] | Chainage |  |  |  |  | - |  |  | Date Finished
| No. |  | Activity Description | [12 empty] | Acceptance Criteria & Frequency (Project Specific) | [7 empty] | Check Item |  |  |  | Inspection | [11 empty] | NCR |  | Related Lot #
[24 empty] | Reference |  |  |  | SS/QA | [7 empty] | Client/Rep
| 1 |  | Kerb and channel complies with standard drawing number R-0080 and is one of the following profiles: B1, B2, SM5, M3, Median and Invert Kerbworks at CE46 & CE47 to be complete in accordance with IPWEA STD DWG RSD-200 as per Quotation note 1 (Concrete Works) | [12 empty] | Visual | [7 empty] | Check Item
LCC Specification No. 8 Cl.2.1
|  |  | Kerb ramps to be constructed in accordance with LCC drawing No 8-00412 as per Quotation note 4 (Concrete Works) | [12 empty] | Visual | [7 empty] | Check Item
Quotation Note 4 (Concrete Works)
| 2 |  | No concrete is placed until the foundations have been approved by the local government. Where the pavement thickness beneath kerb does not exceed 175mm in depth, the kerb and channel is to be firmly bedded on 100mm road base aggregate compacted to 95 percent modified dry density | [12 empty] | Visual | [7 empty] | Hold Point
LCC Specification No. 8 Cl.2.2.2
| 3 |  | Concrete for kerb and kerb and channel is 32 MPa strength grade complying with the requirements of AS 1379-2007 | [12 empty] | Testing | [7 empty] | Check Item
LCC Specification No. 8 Cl 2.3.1 AS 1379-2007
| 4 |  | Slump values for the concrete are: (i) machine finished (dry kerb) —12mm minimum—40mm maximum; (ii) hand finished—40mm minimum—80mm maximum; (iii) machine finished (wet kerb)—12mm minimum—40mm maximum. | [12 empty] | Slump Test | [7 empty] | Check Item
LCC Specification No. 8 Cl 2.3.1
| 5 |  | A contraction joint is provided at 4 metre centres which is finished square and at right angles to the section of kerb or kerb and channel. The kerb or kerb and channel at a contraction joint is guillotined to the full depth of the concrete and re-finished with a jointing tool to form neat joint lines not exceeding 3mm in width and 6mm in depth. | [12 empty] | Visual | [7 empty] | Check Item
LCC Specification No. 8 Cl 2.4.4
| 6 |  | Stormwater kerb adaptors provided for all stormwater connections to kerb in accordance with standard drawing IPWEAQ R-0081. | [12 empty] | Visual | [7 empty] | Check Item
LCC Specification No. 8 Cl.2.4.7
| 7 |  | The concrete kerb or kerb and channel joins neatly with the existing kerb or kerb and channel over a minimal transitional length of 2 metres | [12 empty] | Visual | [7 empty] | Check Item
LCC Specification No. 8 Cl.2.5
| 8 |  | A concrete test per 100 lineal metres | [12 empty] | Testing | [7 empty] | Check Item
LCC Specification No. 8 Cl 2.4.16
| 9 |  | The allowable tolerance to kerb or kerb and channel is +10mm/-10mm on grade levels | [12 empty] | Measure | [7 empty] | Hold Point
LCC Specification No. 8 Cl 2.4.11
| 10 |  | The kerb or kerb and channel is inspected by the local government for damage at the pre-seal stage and any damaged sections are replaced as directed by the local government. | [12 empty] | Visual | [7 empty] | Witness Point
LCC Specification No. 8 Cl 2.4.17
24
25
26
27
28
29
30
| Schedule No. |  |  |  | Description | [15 empty] | QTY |  |  | Unit |  |  | Comments
General Comments
Final Sign off and Approval - Conformance with the Specification
|  | Name of Contractor's Representative | [6 empty] | Name of Contractor's Representative | [6 empty] | Name of Contractor's Representative | [6 empty] | Verified by Cient's Representative | [6 empty] | Name of Cient's Representative | [6 empty] | Name of Cient's Representative
|  | Print Name | [6 empty] | Signature | [6 empty] | Date | [6 empty] | Print Name | [6 empty] | Signature | [6 empty] | Date