## 14.07
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70
|  | DRF | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 11: 0; 12: 0; 13: 0; 45: #REF!; 59: DRF; 60: 1; 61: 0; 62: 0; 63: 0; 64: 0; 65: 0; 66: 0; 67: 0; 68: 0; 69: 0; 70: 0
[9 empty] | Logan City Council CE49, CE46, CE47, Blackspot Project |  | 27: Doval Project No.; 32: 25 047; 40: Inspection and Test Plan ITP 14.07 (MRTS14 March 2022) Rev 0
Client Project No.
[9 empty] | Lot Number |  | 13: Description; 32: Date Opened
[9 empty] | DRF | 1 | 11: 1; 32: Date Started; 40: Demolition and Removal of Road Furniture
| Location | [9 empty] | 17: Control Line; 24: Chainage; 29: -; 32: Date Finished
| No. |  | Activity Description | [7 empty] | 17: Acceptance Criteria & Frequency (Project Specific); 25: Check Item; 29: Inspection; 41: NCR; 43: Related Lot #
[25 empty] | Reference |  |  |  | PE/WS/SS |  |  |  | Administrator
| 1 |  | Road furniture to be removed are as listed on the Project Drawings | [7 empty] | 17: Check & Verify; 25: Check Item
Project Drawings
| 2 |  | Existing road furniture demolished and removed in a manner which avoids damaging any adjacent work. | [7 empty] | 17: Visual; 25: Check Item
MRTS14 Cl.7.3
| 3 |  | Resulting excavations are backfilled and finished so the area is in a safe and free-draining state. | [7 empty] | 17: Visual; 25: Check Item
MRTS14 Cl.7.3
| 6 |  | The Constractor shall submit (7 days prior to work) a schedule of items of existing road furniture to be salvaged in accordance with the provisions of the design documentation | [7 empty] | 17: Submission of Schedule; 25: Milestone
MRTS14 Cl8.2
| 7 |  | Dismantling and removal shall not commence until expiration of the seven day period | [7 empty] | 17: Expiry of 7 days since submission of Schedule; 25: Hold Point 1
MRTS14 Cl8.2
| 8 |  | The Constractor shall submit (7 days prior to work) a schedule of items of existing road furniture to be dismantled for re-erection in accordance with the provisions of the design documentation | [7 empty] | 17: Submission of Schedule; 25: Milestone
MRTS14 Cl9.2
| 9 |  | Dismantling and removal shall not commence until epiration of the seven day period | [7 empty] | 17: Expiry of 7 days since submission of Schedule; 25: Hold Point 2
MRTS14 Cl9.2
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
| Schedule No. |  |  |  | Description | [5 empty] | 22: QTY; 25: Unit; 28: Comments
General Comments
|  | Supervisor/QA Verify that the Above has been Constructed according to Specification | [8 empty] | 24: Project Manager Verify that the Above has been Constructed according to Specification
|  | Print Name | [6 empty] | Signature |  | 17: Date; 24: Print Name; 31: Signature; 42: Date