## 51.01
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70
|  | ENV | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [31 empty] | Environmental Management Systems | [13 empty] | ENV | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Environmental Management Systems
[9 empty] | Logan City Council CE49, CE46, CE47, Blackspot Project | [16 empty] | Doval Project No. |  |  |  |  | 25047 |  |  |  | Inspection and Test Plan
Client Project No.
[9 empty] | Lot Number |  |  |  | Description | [17 empty] | Date Opened
[9 empty] | ENV | 1 |  | 1 | [18 empty] | Date Started |  |  |  | MRTS51 (July 2018) ITP 51.01 Rev 0 |  |  |  | Environmental Management Systems
| Location | [14 empty] | Control Line | [6 empty] | Chainage |  |  |  |  | - |  |  | Date Finished
| No. |  | Activity Description | [12 empty] | Acceptance Criteria & Frequency (Project Specific) | [7 empty] | Check Item |  |  |  | Inspection | [11 empty] | NCR |  | Related Lot #
[24 empty] | Reference |  |  |  | SS/QA | [7 empty] | Administrator
| 1 |  | Environmental Management Plan (Construction) EMP( C) submitted in accordance with General Conditions of Contract. | [12 empty] | Submission of EMP | [7 empty] | Milestone
MRTS51 Cl. 6.3
| 2 |  | Works under the Contract shall not start until the EMP( C) is assessed for suitability by the Administrator. | [12 empty] | EMP Approved by Administrator | [7 empty] | Hold Point 1
MRTS51 Cl. 6.3
| 3 |  | Any amendments to the EMP( C) shall be submitted on a monthly basis and be assessed for suitability by the Administrator. | [20 empty] | Hold Point 2
MRTS51 Cl. 6.4
| 4 |  | Environmental site inspections to be conducted daily, against all licences, permits, approvals and other environmental performance requirements. All Inspection to be documented with records being submitted to the Administrator on a monthly basis. | [12 empty] | Visual | [7 empty] | Check Item
MRTS51 Cl. 7.1
| 5 |  | Environmental records are to be included in the Quality Records under the Contract. Table 7.8 of this Technical Specification identifies environmental record requirements. Records and registers shall be made available to the Administrator upon request. | [20 empty] | Hold Point 3
MRTS51 Cl. 7.8
| 6 |  | The Contractor shall be responsible for the management of Indigenous and non-Indigenous cultural heritage artefacts, sites and values within the worksite | [12 empty] | Visual | [7 empty] | Check Item
MRTS51 Cl. 8.4.1
| 7 |  | The contractor shall at all times take measures to assist in minimising noise associated with construction activities so as not to cause environmental nuisance or harm. | [12 empty] | Visual | [7 empty] | Check Item
MRTS51 Cl. 8.5.2
| 8 |  | Project records shall include all noise monitoring results if required | [20 empty] | Check Item
MRTS51 Cl. 8.5.3
| #REF! |  | Project records that show compliance with the VMP and shall include all noise monitoring results (if required) | [20 empty] | Check Item
MRTS51.1 Cl. 8.6.2
| #REF! |  | The contractor shall at all times take reasonable and practicable management measures to avoid cuasing environmental nuisance or harm due to air quality. Burning of material shall not be permitted | [12 empty] | Visual | [7 empty] | Check Item
MRTS51 Cl. 8.7.2
| #REF! |  | The contractor shall be responsible for the management of acid Sulphate Soils and shall address the requirements of MRTS04 General earthworks including the requirements concerning the management of acid sulphate soils | [12 empty] | Visual | [7 empty] | Check Item
MRTS51 Cl. 8.8
| #REF! |  | The contractor shall be responsible for the management of contaminated sites ( contaminated soils, waste dumps, unexploded ordinances ) within the worksite. The contractor shall address the requirements of MRTS04 General earthworks including the requirements concerning the management of acid sulphate soils | [12 empty] | Visual | [7 empty] | Check Item
MRTS51 Cl. 8.9.1
| #REF! |  | The contractor shall take all due care to not harm native fauna. Contact details for emergency wildlife care shall be included on project emergency contact list. | [12 empty] | Visual | [7 empty] | Check Item
MRTS51 Cl. 8.10.1
| #REF! |  | No waste or litter shall be burnt on site. No waste or litter shall be buried on site unless approved by the Administrator and the administering authority. | [12 empty] | Visual | [7 empty] | Check Item
MRTS51 Cl. 8.13.2
| #REF! |  | The contractor shall be responsible for the management of all chemicals and fuels within the worksite so as not to cause environmental nuisance or harm. The contractor shall ensure spill kits response equipment are available on site for use in emergency | [12 empty] | Visual | [7 empty] | Check Item
MRTS51 Cl. 8.14.1
20
21
22
23
24
25
26
27
28
29
30
General Comments
|  | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification | [20 empty] | Administrator's Representative Verify that the Above has been Constructed according to Specification
|  | Print Name | [6 empty] | Signature | [6 empty] | Date | [6 empty] | Print Name | [6 empty] | Signature | [6 empty] | Date