## LCC 70.01
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70
|  | EXC | 1 | 1 | General Excavation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [31 empty] | General Excavation | [9 empty] | EXC | 1 | 1 | General Excavation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | General Excavation
[9 empty] | Logan City Council CE49, CE46, CE47, Blackspot Project | [16 empty] | Doval Project No. |  |  |  |  | 25047 |  |  |  | Inspection and Test Plan
Client Project No.
[9 empty] | Lot Number | [6 empty] | General Excavation | [14 empty] | Date Opened
[9 empty] | EXC | 1 | 1 | 1 | [18 empty] | Date Started |  |  |  | LCC Specification No. 1 |  |  |  | General Excavation
| Location | [14 empty] | Control Line | [6 empty] | Chainage |  |  |  |  | - |  |  | Date Finished
| No. |  | Activity Description | [12 empty] | Acceptance Criteria & Frequency (Project Specific) | [7 empty] | Check Item |  |  |  | Inspection | [11 empty] | NCR |  | Related Lot #
[24 empty] | Reference |  |  |  | SS/QA | [7 empty] | Client/Rep
| 1 |  | Earthworks are carried out in accordance with AS 3798–2007 and Amendment 1–2008, Guidelines on earthworks for commercial and residential developments, unless otherwise specified | [12 empty] | Check & Verify | [7 empty] | Check Item
LCC Specification No. 1 Cl 6.1
| 2 |  | Minimum Compaction Testing Frequency | [12 empty] | Type 3 Concentrated Operations (Less than 500m2) - 1 test per layer per 500m2; - 1 test per 100m3 distributed reasonably evenly throughout full depth and area; - 3 tests per visit Type 4 Confined Operations (Eg filling behind structures) - 1 test per 2 layers per 50m2 Trenches - 1 test per 2 layers per 40 linear metres | [7 empty] | Hold Point
LCC Specification No. 1 Cl 6.3 AS 3798-2007 Table 8.1
Subgrade
| 3 |  | Construction of sub-grade is to occur in accordance with the compacted layer method or the mechanical interlock method so as to achieve the specifications referred to in Part 7–Sub-grade above the existing surface of this standard specification. | [12 empty] | Check & Verify | [7 empty] | Check Item
LCC Specification No. 1 Cl 7.1
| 4 |  | Where the level of the sub-grade is 150mm or less above the existing surface, the existing soil is scarified to a depth of 150mm and compacted to 95 percent relative dry density standard compaction. Earthworks placed between the existing soil and the subgrade are also compacted to 95 percent relative dry density standard compaction. | [12 empty] | Compaction Testing | [7 empty] | Hold Point
LCC Specification No. 1 Cl 7.2
| 5 |  | Where the level of the sub-grade is between 150mm to 300mm above the existing surface, the whole of the earthworks placed, plus the existing soil directly under the earthworks, is compacted to ensure that a minimum thickness of 300mm immediately below the sub-grade level is compacted to 100 percent relative dry density standard compaction | [12 empty] | Compaction Testing | [7 empty] | Hold Point
LCC Specification No. 1 Cl 7.3
| 6 |  | Where the level of the sub-grade is more than 300mm above the existing surface: (a) the top 300mm of formation is compacted to 95 percent relative dry density standard compaction; (b) the remainder down to the level of the existing soil is compacted to 95 percent relative dry density standard compaction. | [12 empty] | Compaction Testing | [7 empty] | Hold Point
LCC Specification No. 1 Cl 7.4
| 7 |  | Shoulder Works Where a shoulder is required on new work or on sections of existing work that is to be reconstructed, the whole of any additional shoulder material above the sub-grade level is compacted to 100 percent relative dry density standard compaction. | [12 empty] | Compaction Testing | [7 empty] | Hold Point
LCC Specification No. 1 Cl 7.5
Tolerances
| 8 |  | The area of the finished earthworks is such that the top of an embankment batter and the toe of the batter in a cutting, does not vary from its true horizontal location by: (a) 50mm; or (b) +300mm, where +300mm would increase the width of the earthworks | [20 empty] | Check Item
LCC Specification No. 1 Cl 5.1
| 9 |  | The location of an excavation for a pavement does not vary from the location shown in the approved drawings such that the overall width of the pavement is reduced below the width shown in the approved drawings, at either: (a) the level of the sub-grade; or (b) the finished level; or (c) the level of the finished pavement | [20 empty] | Check Item
LCC Specification No. 1 Cl 5.2
| 10 |  | The surface at the finished subgrade is graded to within the tolerances of +0mm to -50mm on the finished level less the pavement thickness in accordance with: (a) the level shown in the approved drawings; or (b) calculated from data given in the approved drawings, with due allowance being made for the thickness of any pavement required | [20 empty] | Check Item
LCC Specification No. 1 Cl 5.4
|  |  | Crossfall (1) The crossfall of the surface of the finished sub-grade does not deviate from that shown in the approved drawings by more than 0.5 percent (2) A template and spirit level used for checking the cross profile is kept on each section of the work | [20 empty] | Check Item
LCC Specification No. 1 Cl 5.5
.
Final Sign off and Approval - Conformance with the Specification
|  | Name of Contractor's Representative | [6 empty] | Name of Contractor's Representative | [6 empty] | Name of Contractor's Representative | [6 empty] | Verified by Cient's Representative | [6 empty] | Name of Cient's Representative | [6 empty] | Name of Cient's Representative
|  | Print Name | [6 empty] | Signature | [6 empty] | Date | [6 empty] | Print Name | [6 empty] | Signature | [6 empty] | Date