## LCC 70.01
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70
|  | LSC | 1 | 1 | Topsoil & Turf | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [31 empty] | Landscaping | [9 empty] | LSC | 1 | 1 | Topsoil & Turf | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Landscaping
[9 empty] | Logan City Council CE49, CE46, CE47, Blackspot Project | [16 empty] | Doval Project No. |  |  |  |  | 25047 |  |  |  | Inspection and Test Plan
Client Project No.
[9 empty] | Lot Number | [6 empty] | Topsoil & Turf | [14 empty] | Date Opened
[9 empty] | LSC | 1 | 1 | 1 | [18 empty] | Date Started |  |  |  | LCC Specification No. 2 |  |  |  | Landscaping
| Location | [14 empty] | Control Line | [6 empty] | Chainage |  |  |  |  | - |  |  | Date Finished
| No. |  | Activity Description | [12 empty] | Acceptance Criteria & Frequency (Project Specific) | [7 empty] | Check Item |  |  |  | Inspection | [11 empty] | NCR |  | Related Lot #
[24 empty] | Reference |  |  |  | SS/QA | [7 empty] | Client/Rep
| 1 |  | Erosion and sediment control, clearing and grubbing, stockpiles, softworks grades and earth mounds to be in accordance with Standard Specification No. 2 Cl 4. | [12 empty] | Visual | [7 empty] | Check Item
LCC Specification No. 2 Cl 4
|  |  | Topsoil - Soil meets the requirements of LCC Specification No 2 Cl 6.2 | [12 empty] | Visual | [7 empty] | Hold Point
LCC Specification No. 2 Cl 6.2
|  |  | The minimum depth of soil for: (a) a turfed area and a seeded grass area is 100mm; (b) a garden bed is 300mm. | [12 empty] | Visual | [7 empty] | Check Item
LCC Specification No. 2 Cl 6.2
| 2 |  | Fertiliser is to be applied as per manufacturer's specification to ensure healthy long term growth | [12 empty] | Visual | [7 empty] | Check Item
LCC Specification No. 2 Cl 6.4.1
| 4 |  | The turf is delivered to the premises within 24 hours of being cut and the turf is laid within 36 hours of being cut. | [12 empty] | Visual | [7 empty] | Check Item
LCC Specification No. 2 Cl.6.4.3.2
| 6 |  | The edges of the finished grade of the turf are bevelled down a maximum 15mm below an abutting hard surface such as a kerb, a path, a mowing strip or other hard paved surface. | [12 empty] | Visual | [7 empty] | Check Item
LCC Specification No. 2 Cl.6.4.3.6
| 7 |  | The turf is not provided on a slope steeper than 1 in 4. | [12 empty] | Visual | [7 empty] | Check Item
LCC Specification No. 2 Cl.6.4.3.9
General Comments
Final Sign off and Approval - Conformance with the Specification
|  | Name of Contractor's Representative | [6 empty] | Name of Contractor's Representative | [6 empty] | Name of Contractor's Representative | [6 empty] | Verified by Cient's Representative | [6 empty] | Name of Cient's Representative | [6 empty] | Name of Cient's Representative
|  | Print Name | [6 empty] | Signature | [6 empty] | Date | [6 empty] | Print Name | [6 empty] | Signature | [6 empty] | Date