## 10.01
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70
|  | LTB | 1 | #REF! | Lightly Bound | 0 | 0 | 0 | 0 | 0 | 0 | [31 empty] | Plant Mixed Lightly Bound Pavements | [13 empty] | LTB | 1 | #REF! | Lightly Bound | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Plant Mixed Lightly Bound Pavements
[9 empty] | Logan City Council CE49, CE46, CE47, Blackspot Project | [15 empty] | Doval Project No. |  |  |  |  | 25047 |  |  |  | Inspection and Test Plan
Client Project No.
[9 empty] | Lot Number |  |  | Description |  |  | Lightly Bound | [14 empty] | Date Opened
[9 empty] | LTB | 1 | 1 | [18 empty] | Date Started |  |  |  | MRTS10 (Nov 2022) 10.01 Rev 0 |  |  |  | Plant Mixed Lightly Bound Pavements
| Location | [13 empty] | Control Line | [6 empty] | Chainage |  |  |  |  | - |  |  | Date Finished
| No. |  | Activity Description | [11 empty] | Acceptance Criteria & Frequency (Project Specific) | [7 empty] | Check Item |  |  |  | Inspection | [11 empty] | NCR |  | Related Lot #
[23 empty] | Reference |  |  |  | PE/WS/SS |  |  |  | CQR to Verify |  |  |  | Administrator
| 1 |  | Construction Procedure: Documented procedure shall be prepared for all construction processes as defined in Clause 6 of MRTS50 and shall be submitted for approval at least 14 days prior to commencement of lightly bound pavement works (No work shall commence until accepted by the Administrator) | [11 empty] | Acceptance | [7 empty] | Hold Point 1 Milestone
Clause 5.2 MRTS10
| 3 |  | Mix Design Report: A mix design must be submitted at least 14days before mixing operations commence. Construction of the lightly bound pavement layer shall not proceed until a conforming mix design (refer to Clause 7.2) has been deemed suitable and accepted by the Administrator. | [11 empty] | Acceptance | [7 empty] | Hold Point 3
MRTS10 Clause 7.1
| 4 |  | Moisture Content The Contractor shall nominate upper and lower moisture content limits as part of their Mix Design that will ensure: a) there is adequate moisture to achieve the specified compaction standard b) the constructed lightly bound pavement layer is trafficked in accordance with requirements of Clause 8.2.11, and c) the lightly bound pavement material does not exceed the optimum moisture content (OMC), determined in accordance with Test Method Q142A. | [11 empty] | Testing - AS1289.2.1.1 1 per 500m2 4 per lot | [7 empty] | Test Report
MRTS10 Clause 8.2.5 Clause 9.4.8 Table A3
| 5 |  | Construction - Trial Pavement Unless otherwise agreed by the Administator, a trial of the manufacturing and laying operations shall be caried out prior to commencement of the work. The trial pavement shall be located within the site and be not less than 1000m2. It shall determine the characteristics highlighted in Clause 8.1 MRTS10. The trial may be incorporated into the permanent works at the Administrators discression. The Contractor is to undertake the material and construction compliance testing nominated in Clause 8.1 and the finished pavement complies with the technical specification of MRTS10. If deemed not conforming, further trialing shall be undertaken. | [11 empty] | Visual & Check | [7 empty] | Witness Point 1 /Hold Point 4
MRTS10 Clause 8.1
| 6 |  | Material Compliance Testing Each supply lots shall be sampled and tested for compliance in accordance with the testing frequencies specify in MRTS05. No material shall be incorporated into the work unless it has demonstrated compliance fully with the requirements of MRTS05 and MRTS10 Material Type : _______________________________ Material Stockpile Lot Ref: _____________________ | [11 empty] | MRTS05 Cl. 7, Table A1 MRTS10 Cl.6, Table A2 | [7 empty] | Check Item
MRTS05 Clause 7
| 7 |  | Equipment Equipment as specified in approved construction procedure | [11 empty] | Construction Procedure Approval | [7 empty] | Contract Notice
MRTS10 Cl.8.2.1.4
| 8 |  | Weather Conditions CMB material shall not proceed when: a) air temperature is less than 10°C or greater than 40°C b) during rain or when rain is likely to fall during placement c) evaporation rate due to the combined effect of air temperature, wind and relative humidity may result in excessive drying of the CMB | [11 empty] | Check & Verify | [7 empty] | Check Item
MRTS10 Clause 8.2.4
| 9 |  | Allowable Working Time Define as the maximum period between mixing the modifying binder into the unbound granular material and the completion of compaction. The allowable working time for the plant-mixed lightly bound pavement is to be the lesser of the following a) Working time determined in accordance with Test Method Q136A b) Four hours | [11 empty] | Monitor | [7 empty] | Check Item
MRTS10 Clause 8.2.3
| 10 |  | Construction Joints Deemed to be fresh when the material compacted on each side of the joint has been modified, placed and compacted within the allowable working time. In multi layer of lightly bound pavement, longitudinal joints of each layer shall be offset from the underlying layer by a minimum of 150mm | [11 empty] | Check & Verify | [7 empty] | Check Item
MRTS10 Clause 8.2.10
| 11 |  | Fresh Joints Where fresh joint between adjoining or adjacent run is to be compacted, the outside 300mm of material from the first run shall be left uncompacted until the adjacent run is ready for compaction. | [11 empty] | Check & Verify | [7 empty] | Check Item
MRTS10 Cl. 8.2.10.1
| 12 |  | Other (Cold) Joints Joints that are not fresh shall be cut back to form a neat, clean vertical face. Cutback distance shall be a minimum of 150mm and before placing the adjoining layer or adjacent layer, the cut back edge of the existing layer shall have a cement/water slurry at a rate of 2kg/m2. The slurry cement/water ratio to be 0.6 and 0.7. | [11 empty] | Check & Verify | [7 empty] | Check Item
MRTS10 Cl. 8.2.10.2 Cl.6.4
| 13 |  | Curing of CMB Layers The surface of an existing layer of lightly bound pavement shall be water cured until placement of the next layer and/or bituminous surfacing is applied. Unless approved, within 7 days of placement the lightly bound pavement shall be covered by a subsequent layer and/or bituminous treatment. Water curing shall be completed in accordance with Cl. 8.2.1.5 | [11 empty] | Check & Verify | [7 empty] | Check Item
MRTS10 Clause 8.2.9
| 14 |  | Trafficking of CMB Layers during Construction Unless approved by the Administrator, lightly bound pavement layers shall not be opened to either construction traffic or general traffic until the lot has been tested for, and passes proof rolling (Cl 9.4.10) | [11 empty] | Check | [7 empty] | Check Item
MRTS10 Clause 8.2.11
| 15 |  | Compaction Standard The characteristic value of relative compaction shall not be less than 100% standard, except for the upper most layer of lightly bound base which shall not be less than 102% standard | [11 empty] | 102% standard upper most layer 100% standard lower layers (1/500m2, min 4/lot) (1/1000m2, min 4/lot) | [7 empty] | Test Report
MRTS10 Clause 8.3.4
| 16 |  | UCS Unconfined compressive strength between 1 - 2MPa | [11 empty] | UCS 1-2MPa (1 per lot) | [7 empty] | Check Item
MRTS10 Clause 9.4.9
| 17 |  | Stabilising Agent Content The actual content of stabilising agent for each lot shall be represented by both the: a) minimum characteristic value of the actual content of stabilising agent, and b) maximum characteristic value of the actual content of stabilising agent. When UCS tests are being undertaken, the sample being used must also be tested for stabilising agent content. | [11 empty] | Target content minus MPV Min. test 1 per lot | [7 empty] | Check Item
MRTS10 Clause 9.4.6
| 18 |  | Geometrics - Horizontal Tolerances Shall not be more than ± 50mm except for the following: a) Pavement edges not adjacent to any other part of the pavement and not adjacent to any structure or adjoining road, transverse tolerance shall be -50mm + 250mm b) Where alignment of the pavement with an existing structure is necessary, the new work shall be joined neatly to the existing in a smooth manner | [11 empty] | -50mm/+250mm (1 per 20m) | [7 empty] | Survey Report
MRTS10 Clause 8.3.5.2
| 19 |  | Geometrics - Primary Vertical Tolerances The vertical tolerances specified in Table 8.3.5.3 shall apply or: - the surface level measured at any point on the surface of any layer. - The average total thickness of the constructed course compared to the specified total thickness. | [11 empty] | ±15mm for layers that have been hard cut ±10mm for all other layers Layer thickness -20mm, +unspecified (1 per 20m at shoulders, lane lines & grade changes) | [7 empty] | Survey Report
MRTS10 Clause 8.3.5.3
| 20 |  | Geometrics - Deviation from a Straight - Edge Deviation of a straight edge place anywhere on the surface shall not exceed 5mm over 3m | [11 empty] | 5mm over 3m (1 per 20m and at joints) | [7 empty] | Check Sheet
MRTS10 Clause 8.3.6
| 21 |  | Geometrics - Crossfall Shall not differ from the designed crossfall by more than 0.5% absolute. | [11 empty] | Check | [7 empty] | Survey Report
MRTS10 Clause 8.3.5.4
| 22 |  | Proof Rolling The perceptible surface deformation test (Q723) shall be undertaken in the presence of the Administrator | [11 empty] | Visual | [7 empty] | Witnesss Point 2
MRTS10 Clause 9.4.10
| 23 |  | Acceptance No CMB layer shall be covered by a subsequent layer of pavement or surfacing untill all testing has been completed (other than UCS), the surface finish comlies with Clause 8.2.8 and the layer presented to the Administrator. | [11 empty] | Acceptance | [7 empty] | Hold Point 5
MRTS10 Clause 9.5.1
21
22
23
24
25
26
27
28
28
29
30
General Comments
|  | Supervisor/QA Verify that the Above has been Constructed according to Specification | [19 empty] | Project Manager Verify that the Above has been Constructed according to Specification
|  | Print Name | [6 empty] | Signature | [5 empty] | Date | [6 empty] | Print Name | [6 empty] | Signature | [6 empty] | Date