## 45.01
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70
|  | LIN | #REF! | 1 | 0 | 0 | 0 | 0 | 0 |  | 12: 0; 13: 0; 45: Road Surface Delineation; 59: LIN; 60: #REF!; 61: 1; 62: 0; 63: 0; 64: 0; 65: 0; 66: 0; 67: 0; 68: 0; 69: 0; 70: Road Surface Delineation
[9 empty] | Logan City Council CE49, CE46, CE47, Blackspot Project |  | 27: Doval Project No.; 32: 25047; 36: Inspection and Test Plan
Client Project No.
[9 empty] | Lot Number |  | 13: Description; 32: Date Opened
[9 empty] | LIN | 1 | 12: 1; 32: Date Started; 36: MRTS45 (July 2023) ITP 45.01; 40: Road Surface Delineation
| Location | [9 empty] | 17: Control Line; 24: Chainage; 29: -; 32: Date Finished
| No. |  | Activity Description | [7 empty] | 17: Acceptance Criteria & Frequency (Project Specific); 25: Check Item; 29: Inspection; 41: NCR; 43: Related Lot #
[24 empty] | Reference |  |  |  | SS/QA | [7 empty] | Client/Rep
| 1 |  | All material conforms to requirements set out in Clause 6 | [7 empty] | 17: Material product sheets; 25: Check Item
MRTS45 Cl 6
| 2 |  | Pavement markings not applied when freshly applied pavement markings may become damaged by rain, fog or condensation before they have dried or set. | [7 empty] | 17: Visual; 25: Check Item
MRTS45 Cl 7.2
|  |  | All pavement markings shall be uniformly and neatly applied and finished with sharp edges. Longitudinal markings shall have a smooth and even appearance located within the tolerances specified. New markings shall be smoothly transitioned to match existing markings at the limits of the work. | [7 empty] | 17: Visual; 25: Check Item
Quotation Notes No 4 (Linemarking)
| 3 |  | Pavement surface is thoroughly dry and free from all dirt, loose material and other contaminants immediately before applying the pavement markings | [7 empty] | 17: Visual; 25: Check Item
MRTS45 Cl 7.3
| 4 |  | In addition to the above requirements, new bitumen sealed surfaces which are to receive pavement markings shall be free of volatile material and solvents. | [7 empty] | 17: Visual; 25: Hold Point 1
MRTS45 Cl 7.3
| 5 |  | Spotting approved by the Administrator prior to any application of pavement markings | [7 empty] | 17: Visual; 25: Hold Point 2
MRTS45 Cl 7.4.1
| 6 |  | Construction procedure for application of pavement markings submitted to the Administrator | [7 empty] | 17: Visual; 25: Check Item
MRTS45 Cl 7.5
| 7 |  | All completed pavement markings shall be uniform in appearance, texture, width and thickness and the surface shall be free from un-beaded areas, traffic damage or other defects. Markings shall be straight or with smooth even curves where intended. All edges shall have a clean sharp cut off. Any marking material beyond the defined marking shall be removed to leave a neat marking on the wearing surface of the pavement | [7 empty] | 17: Visual; 25: Check Item
Quotation Notes No 5 (Linemarking)
Waterborne
| 8 |  | Waterborne Paint not heated to greater than 65°C and consists of two coats of paint and glass beads with application rates for the paint as per Table 7.5.2.4 | [7 empty] | 17: Visual Table 7.5.2.4; 25: Check Item
MRTS45 Cl 7.5.2.3 Cl 7.5.2.4
Thermoplastic
| 9 |  | If required, a primer of type recommended by manufacturer of the thermoplastic material shall be applied to the surface immediantly in advance of, but concurrent with, the application of thermoplastic material | [7 empty] | 17: Visual; 25: Check Item
MRTS45 Cl 7.5.3.1
| 10 |  | Thermoplastic shall be applied at a temperature between 180C-200C or as per the manufacturers specifications | [7 empty] | 17: Visual; 25: Check Item
MRTS45 Cl 7.5.3.2
| 11 |  | Thermoplastic applied at a minimum of 2mm thickness | [7 empty] | 17: Visual; 25: Check Item
MRTS45 Cl 7.5.3.3
Cold Applied Plastic
| 12 |  | If required, a primer of the type reccommended shall be applied to the surface immediately in advance of, but concurrent with the application of the Cold Applied Plastic materials | [7 empty] | 17: Visual; 25: Check Item
MRTS45 Cl 7.5.4.1
| 13 |  | Cold Applied Plastic shall be applied at a temperature as per the manufacturers specifications | [7 empty] | 17: Visual; 25: Check Item
MRTS45 Cl 7.5.4.2
| 14 |  | Cold applied Plastic shall be applied at the rates specified in Table 7.5.4.2 | [7 empty] | 17: Visual; 25: Check Item
MRTS45 Cl 7.5.4.2
| 15 |  | The use of Raised Retroreflective Pavement Markers shall be in accordance with Cl 5.6.2 of the MUTCD Part 2 | [7 empty] | 17: Visual; 25: Check Item
MRTS45 Cl 7.6.14
| 16 |  | Material complies with luminance and retro-reflectivity requirements. | [7 empty] | 17: Test procedure AS 4049.4; 25: Check Item
MRTS45 Cl 5.3 & Cl 7.7.6
| 17 |  | Material protected from damage by traffic or other causes until paint is dry and thermoplastic has hardened | [7 empty] | 17: Visual; 25: Check Item
MRTS45 Cl 7.8
| 18 |  | Completed Pavement Markings shall be uniform, clean and well-defined edges without deformation and conforms to dimensions as set out in the MUTCD | [7 empty] | 17: Visual; 25: Check Item
MRTS45 Cl 7.9
| 19 |  | Pavement Markings conform to all tolerances | [7 empty] | 17: Visual; 25: Check Item
MRTS45 Cl 7.9.1
General Comments
|  | Supervisor/QA Verify that the Above has been Constructed according to Specification | [8 empty] | 24: Project Manager Verify that the Above has been Constructed according to Specification
|  | Print Name | [6 empty] | Signature |  | 17: Date; 24: Print Name; 31: Signature; 38: Date