## 14.13
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70
|  | SRF | #REF! | 1 | Supply and Installation of Road Furniture | 0 | 0 | 0 | 0 |  | 12: 0; 13: 0; 45: Supply and Installation of Road Furniture; 59: SRF; 60: #REF!; 61: 1; 62: Supply and Installation of Road Furniture; 63: 0; 64: 0; 65: 0; 66: 0; 67: 0; 68: 0; 69: 0; 70: Supply and Installation of Road Furniture
[9 empty] | Logan City Council CE49, CE46, CE47, Blackspot Project |  | 27: Doval Project No.; 32: 25047; 36: Inspection and Test Plan
Client Project No.
[9 empty] | Lot Number |  | 13: Description; 17: Supply and Installation of Road Furniture; 32: Date Opened
[9 empty] | SRF | 1 | 12: 1; 32: Date Started; 36: MRTS14 (March 2022) ITP 14.13 Rev 0; 40: Supply and Installation of Road Furniture
| Location | [9 empty] | 17: Control Line; 24: Chainage; 29: -; 32: Date Finished
| No. |  | Activity Description | [7 empty] | 17: Acceptance Criteria & Frequency (Project Specific); 25: Check Item; 29: Inspection; 41: NCR; 43: Related Lot #
[24 empty] | Reference |  |  |  | SS/QA | [7 empty] | Client/Rep
| 1 |  | Not less than seven days prior to commencement of dismantling and removal of existing road furniture, the Contractor shall submit a schedule of items of existing road furniture to be disamantled or re-erection in accordance with the provisions of the design documentation. | [7 empty] | 17: Submission of Schedule; 25: Milestone
MRTS14 Cl 9.2
| 2 |  | Dismantling and removal shall not commence until the experation of the seven day period. | [7 empty] | 17: Expiry of 7 days since submission of Schedule; 25: Hold Point 2
MRTS14 Cl 9.2
| 3 |  | All legend elements, including letters, numerals, symbols, colours and borders in all sign faces conform to the MUTCD and project drawings. | [7 empty] | 17: Visual; 25: Check Item
MRTS14 CL 13.2
| 4 |  | Dimensional Tolerances conform to the requirements detailed in AS1743 and legends and lettering conforms to AS1744. | [7 empty] | 17: Visual; 25: Check Item
MRTS14 CL 13.2
| 5 |  | Sign Material conforms with the requirements as set out in Cl 13.3. | [7 empty] | 17: Visual; 25: Check Item
MRTS14 Cl 13.3
| 6 |  | The sign substrate shall be manufactured from aluminium. Other materials may be considered but evidence of the full approval of the department will be provided to the administrator prior to their use. | [7 empty] | 17: Visual; 25: Hold Point 3
MRTS14 CL 13.3.1.1
| 7 |  | Sign faces are fabricated in accordance with the requirements of Traffic and Road Use Management Manual (TRUM) Volume 3, Part 5. | [7 empty] | 17: Visual; 25: Check Item
MRTS14 Cl 13.4
| 8 |  | Sign posts shall be circular or rectangular hollow sections unless specifically shown otherwise in the design documentation. | [7 empty] | 17: Visual; 25: Check Item
MRTS14 Cl 14.2.3
| 9 |  | Post sizes and spacings shall conform to the design documentation with slip bases and fuse plates as required. | [7 empty] | 17: Visual; 25: Check Item
MRTS14 Cl 14.2.3
| 10 |  | Concrete footings shall conform to MRTS70 and to the dimenesions shown in the design documentation. | [7 empty] | 17: Visual; 25: Check Item
MRTS14 Cl 14.3
| 12 |  | Signs erected at the locations shown in the design documentation and the orientation shall be in accrodance with the MUTCD. | [7 empty] | 17: Visual; 25: Check Item
MRTS14 Cl 14.4.2
| 13 |  | Sign faces installed on the posts and/or frame once all other erection is complete. | [7 empty] | 17: Visual; 25: Check Item
MRTS14 Cl14.4.5
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
| Schedule No. |  |  |  | Description | [5 empty] | 22: QTY; 25: Unit; 28: Comments
| 15 |  | Install Fencing as per Manufacturer's Guidelines Fencing shall be constructed in the locations and to the details shown in the design documentation. | [7 empty] | 17: Visual; 25: Check Item
MRTS14 Cl 11 MRTS14 Cl 11.4
General Comments
|  | Supervisor/QA Verify that the Above has been Constructed according to Specification | [8 empty] | 24: Project Manager Verify that the Above has been Constructed according to Specification
|  | Print Name | [6 empty] | Signature |  | 17: Date; 24: Print Name; 31: Signature; 38: Date