## 02.01
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70
|  | TTM | 0 | 1 | Traffic Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [27 empty] | Traffic Management | [13 empty] | TTM | 0 | 1 | Traffic Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Traffic Management
[9 empty] | Logan City Council CE49, CE46, CE47, Blackspot Project | [16 empty] | Doval Project No. |  |  |  |  | 25047 | Inspection and Test Plan
Client Project No.
[9 empty] | Lot Number |  |  |  | Description |  |  | Traffic Management | [14 empty] | Date Opened
[9 empty] | TTM |  | 1 | 1 | [18 empty] | Date Started | MRTS02 (Nov 2023) ITP 02.01 Rev 0 |  |  |  | Traffic Management
| Location | [14 empty] | Control Line | [6 empty] | Chainage |  |  |  |  | - |  |  | Date Finished
| No. |  | Activity Description | [12 empty] | Acceptance Criteria & Frequency (Project Specific) | [7 empty] | Check Item |  |  |  | Inspection | [7 empty] | NCR |  | Related Lot #
[24 empty] | Reference |  |  |  | SE/PE/WS/SS |  |  |  | Administrator
| 1 |  | The Contractor's Nominated Traffic Officer submitted to the Administrator and meets the requirements as specified | [12 empty] | Accreditation Supplied to Administrator | [7 empty] | Check Item |  |  |  | Submitted with TMP __/__/____
MRTS02 Cl. 5.2
| 2 |  | No traffic rearrangements shall be carried out until after the Administrator has advised the Contractor that the submitted, and amended as directed, TMP is approved and suitable for use. | [12 empty] | Approval via Contract Notice - Per NTO | [7 empty] | Hold Point 1
MRTS02 Cl. 5.3
| 3 |  | All traffic control devices inspected and records kept in accordance with the specification | [12 empty] | Site Records - Daily | [7 empty] | Check Item
MRTS02 Cl. 5.6.4
| 4 |  | In the event of a traffic crash/incident within the site, the Contractor shall record the date and take time and date stamped photographs of the signs/devices in the vicinity of the crash. | [12 empty] | Incident Report - Per incident | [7 empty] | Check Item
MRTS02 Cl. 5.6.5
| 5 |  | All TGS's prepared by a suitably qualified person and submitted to the Administrator for review and shall be accompanied with a specific risk assessment, as required. Innovations, alternatives and departures from standards shall be certified by a RPEQ. | [12 empty] | TMD sign off of TGS and, RPEQ Risk Assessment as required | [7 empty] | Hold Point 2
MRTS02 Cl. 6.2
| 6 |  | The Traffic Management Inspection report to the Contractor for action, together with documentation of any actions taken in regard to findings. | [12 empty] | Submission of report to Administrator - Per inspection | [7 empty] | Milestone
MRTS02 Cl. 7.5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
General Comments
|  | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification | [20 empty] | Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
|  | Print Name | [6 empty] | Signature | [6 empty] | Date | [6 empty] | Print Name | [6 empty] | Signature |  |  | Date