## LCC 70.01
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70
|  | UNB | 1 | 0 | Unbound Pavement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [31 empty] | Unbound Pavement | [9 empty] | UNB | 1 | 0 | Unbound Pavement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Unbound Pavement
[9 empty] | Logan City Council CE49, CE46, CE47, Blackspot Project | [16 empty] | Doval Project No. |  |  |  |  | 25047 |  |  |  | Inspection and Test Plan
Client Project No.
[9 empty] | Lot Number | [6 empty] | Unbound Pavement | [14 empty] | Date Opened
[9 empty] | UNB | 1 |  | 1 | [18 empty] | Date Started |  |  |  | LCC Std Specification No. 6: Pavements |  |  |  | Unbound Pavement
| Location | [14 empty] | Control Line | [6 empty] | Chainage |  |  |  |  | - |  |  | Date Finished
| No. |  | Activity Description | [12 empty] | Acceptance Criteria & Frequency (Project Specific) | [7 empty] | Check Item |  |  |  | Inspection | [11 empty] | NCR |  | Related Lot #
[24 empty] | Reference |  |  |  | SS/QA | [7 empty] | Client/Rep
| 1 |  | Pavement material compliance testing is carried out by a NATA registered or equivalent accredited soils testing laboratory. | [12 empty] | Check & Verify | [7 empty] | Check Item
LCC Specification No 6 Cl 3.1
| 2 |  | Prior to the use of road base material, the developer is to submit current certified evidence obtained within the last twelve months, from a Geo-technical consultant indicating that the proposed unbound material does not contain Sulphate amounts in excess of quantities that may induce Sulphate blistering in the bitumen surfacing. | [12 empty] | Evidence Submission | [7 empty] | Hold Point
LCC Specification No 6 Cl 3.1
| 3 |  | A compliance testing certificate is forwarded to the local government prior to the commencement of construction of any pavement course | [12 empty] | Certificate Submission | [7 empty] | Hold Point
LCC Specification No 6 Cl 3.1
| 4 |  | Where the required compacted thickness of any pavement course is 200mm or less, the pavement material is spread and compacted in one layer. Where the required compacted thickness of any pavement course is more than 200mm, the pavement material is compacted in two or more layers each not less than 75mm compacted thickness and not greater than 150mm compacted thickness. | [12 empty] | Check & Verify | [7 empty] | Check Item
LCC Specification No 6 Cl 4.2
| 6 |  | The finished pavement complies with the alignment and dimensions shown on the approved drawings or within the tolerances specified in Table 5.1.1–Tolerance on the alignment, grade and crossfall of this standard specification. | [12 empty] | Survey | [7 empty] | Hold Point
LCC Specification No 6 Cl 5.1 Table 5.1.1
#VALUE!
| 7 |  | Each pavement layer is tested for compaction and degree of saturation in accordance with Table 6.1.1–Compaction and moisture control standards of this standard specification | [12 empty] | Compaction Test | [7 empty] | Hold Point
LCC Specification No 6 Cl 6.1 Table 6.1.1
#VALUE!
| 8 |  | Proof Roll Use a loaded water truck, with a single rear axle, and with a gross mass of not less than 15 tonne, or a similar vehicle approved by the local government, for proof rolling. No visible movement shall occur under the rear axle when proof rolling. | [12 empty] | Visual | [7 empty] | Witness Point
LCC Specification No 6 Cl 4.2.20
| 9 |  | A compliance testing certificate is forwarded to the local government prior to the commencement of construction of any subsequent course | [12 empty] | Compaction Test Result Submission | [7 empty] | Hold Point
LCC Specification No 6 Cl 6.1.5
25
26
27
28
29
30
| Schedule No. |  |  |  | Description | [15 empty] | QTY |  |  | Unit |  |  | Comments
General Comments
Final Sign off and Approval - Conformance with the Specification
|  | Name of Contractor's Representative | [6 empty] | Name of Contractor's Representative | [6 empty] | Name of Contractor's Representative | [6 empty] | Verified by Cient's Representative | [6 empty] | Name of Cient's Representative | [6 empty] | Name of Cient's Representative
|  | Print Name | [6 empty] | Signature | [6 empty] | Date | [6 empty] | Print Name | [6 empty] | Signature | [6 empty] | Date