## 04.09
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70
|  | UNS | 1 | 0 | Unsuitable Material | 0 | 0 | 0 | 0 |  | 11: 0; 12: 0; 13: 0; 45: Unsuitable Material; 59: UNS; 60: 1; 61: 0; 62: Unsuitable Material; 63: 0; 64: 0; 65: 0; 66: 0; 67: 0; 68: 0; 69: 0; 70: Unsuitable Material
[9 empty] | Logan City Council CE49, CE46, CE47, Blackspot Project |  | 27: Doval Project No.; 32: 25047; 40: Inspection and Test Plan LCC Specification No 1 ITP 04.09 Rev 0
Client Project No.
[9 empty] | Lot Number |  | 13: Description; 17: Unsuitable Material; 32: Date Opened
[9 empty] | UNS | 1 | 11: 1; 32: Date Started; 40: Unsuitable Material
| Location | [9 empty] | 17: Control Line; 24: Chainage; 29: -; 32: Date Finished
| No. |  | Activity Description | [7 empty] | 17: Acceptance Criteria & Frequency (Project Specific); 25: Check Item; 29: Inspection; 41: NCR; 43: Related Lot #
[25 empty] | Reference |  |  |  | PE/WS/SS |  |  |  | Administrator
| 1 |  | Unsuitable material below the level of the sub-grade in an excavation is: (a) removed and run to spoil in accordance with section 12.1–Spoil of LCC Specifications; (b) replaced with select backfill in accordance with section 8.3–Selected gravel fill or selected backfill of LCC specifications; (c) compacted to 95 percent relative dry density standard compaction | [7 empty] | 17: Visual; 25: Check Item
LCC Specification No 1 Cl 9.3
| 2 |  | Surplus material which is run to spoil is: (a) not loosely tipped over the side of an embankment; (b) neatly spread adjacent to the work; or (c) used to uniformly flatten the slope of an embankment | [7 empty] | 17: Visual; 25: Check Item
LCC Specification No 1 Cl 12.1.1
| 3 |  | Spoil which is spread on the site is: (a) compacted as specified in this standard specification; (b) left in a neat, tidy and self draining condition with a slope of not flatter than 1 in 100 unless otherwise shown in the approved drawings. | [7 empty] | 17: Visual; 25: Check Item
LCC Specification No 1 Cl 12.1.2
| 4 |  | Rock and other material is removed from the site which is: (a) surplus to the requirements of the job; (b) unsuitable for disposal on the site. | [7 empty] | 17: Visual; 25: Check Item
LCC Specification No 1 Cl 12.1.3
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
General Comments
|  | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification | [8 empty] | 24: Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
|  | Print Name | [6 empty] | Signature |  | 17: Date; 24: Print Name; 31: Signature; 38: Date