## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DN1210-029 ITP Chipseal Pavement Type 7 | itp |  |  |  |  | DN1210-029 ITP Chipseal Pavement Type 7 Rev 0
section | Design
checkpoint | Chipseal Design
label | Verification Activity - Peer review by Authorised Seal Design Approver
label | Methods or Reference - Chipsealing in NZ
label | Frequency - One per design prior to commencing onsite
label | Acceptance Criteria - Design meets requirements of P3
label | Hold / Witness Point - Mandatory HOLD POINT - Seal Design peer Reviwer - Client Approval
label | Records - Peer Reviewed Seal Designs
label | Responsible Person - Engineer
holdpoint | AUTHORITY HOLDPOINT
section | Materials Testing
checkpoint | Size (Grades 2-5)
label | Verification Activity - Lab Test
label | Methods or Reference - NZTA M/6
label | Frequency - 1/500m3
label | Acceptance Criteria - Size (ald mm)
label | ○ G2 9.5-12.0
label | ○ G3 7.5-10.0
label | ○ G4 5.5-8.0
label | ○ G5 Report
label | Hold / Witness Point - Witness Point
label | Responsible Person - SE
checkpoint | Cleanliness (Grades 2-6)
label | Verification Activity - Lab Test
label | Methods or Reference - NZTA M/6
label | Frequency - 1/500m3
label | Acceptance Criteria - Cleanness value
label | ○ G2 = 89
label | ○ G3 = 87
label | ○ G4 = 85
label | ○ G5 & G6 Report only
label | Hold / Witness Point - Witness Point
label | Responsible Person - SE
checkpoint | Compatibility (Multi Layered seals)
label | Verification Activity - Comparison Of Chip ALD
label | Methods or Reference - Chipsealing in New Zealand NZTA (NZTA 2005)
label | Frequency - 6.69, 4.51
label | Acceptance Criteria - Two Coat Seal Aggregate Compatibility
label | Hold / Witness Point - Witness Point
label | Responsible Person - SE
checkpoint | Bitumen Distributor
label | Verification Activity - IANZ Lab E/2 Results
label | Methods or Reference - Code of Compliance
label | Frequency - Annual
label | Acceptance Criteria - Speed Test(+-3% over 100m), Dipstick Test (+-50L over 2000L), Matt Test (app rate within 0.10L/m2, longitudinal within 10%, thirds within 5%, transverse within 20%)
label | Hold / Witness Point - Mandatory HOLD POINT - Client - Engineer Witness
label | Records - RNZ E2 Certificate
label | Responsible Person - SE
holdpoint | AUTHORITY HOLDPOINT
section | Surface Inspection
checkpoint | Pre Seal Survey
label | Verification Activity - Downer Survey or MS Forms Pre Reseal Inspection
label | Methods or Reference - Downer Survey or MS Forms Pre Reseal Inspection
label | Frequency - At time of Seal Inspection
label | Acceptance Criteria - Record & any noted issues / Client
label | Hold / Witness Point - Witness Point
label | Records - Downer Survey
label | Responsible Person - SE
section | Seal Construction
checkpoint | Road Furniture
label | Verification Activity - Visual Inspection
label | Methods or Reference - Crew Breifing Plan / Visual
label | Frequency - Prior to sealing on each site
label | Acceptance Criteria - Protect all road furniture in accordance with Crew Breifing Plan
label | Hold / Witness Point - Witness Point
label | Records - None
label | Responsible Person - Foreperson
checkpoint | Sumps protected
label | Verification Activity - Visual Inspection
label | Methods or Reference - Crew Breifing Plan / Visual
label | Frequency - Prior to sealing on each site
label | Acceptance Criteria - Fabric & protect all sumps
label | Hold / Witness Point - Witness Point
label | Records - None
label | Responsible Person - Foreperson
checkpoint | Stockpiles
label | Verification Activity - Visual Inspection
label | Methods or Reference - CBP
label | Frequency - Each Stockpile
label | Acceptance Criteria - Correct Source, Grade and quantity. Uniquely Identified.
label | Hold / Witness Point - Witness Point
label | Records - Sealing Data Docket
label | Responsible Person - Foreperson
checkpoint | Spraying
label | Verification Activity - Paper Start and Finish all runs
label | Methods or Reference - Spray Runs
label | Frequency - All Runs
label | Acceptance Criteria - Mark out start / Finish
label | Hold / Witness Point - Witness Point
label | Responsible Person - Foreperson
checkpoint | Sealing
label | Verification Activity - Longitudinal Joints out side of wheel tracks
label | Methods or Reference - Spray Runs
label | Frequency - All Runs
label | Acceptance Criteria - Mark out lane lines by construction team
label | Hold / Witness Point - Witness Point
label | Responsible Person - Foreperson
checkpoint | Spraying
label | Verification Activity - Spray application rate
label | Methods or Reference - Spray sheet
label | Frequency - All runs
label | Acceptance Criteria - Note down spray application rates as per design provided.
label | Hold / Witness Point - Witness Point
label | Responsible Person - Engineer
checkpoint | Emulsion - BitumenTesting
label | Verification Activity - Lab Testing
label | Methods or Reference - Manufacture Specification
label | Frequency - Per Emulsion/Bitumen Production Batch
label | Acceptance Criteria - Bitumen Content, ITM 11-01, Viscosity, ITM 10-02, PH ITM-08-02
label | Hold / Witness Point - Witness Point
label | Records - IANZ Lab Reports
label | Responsible Person - Road Science
checkpoint | Removal of Surplus Chip
label | Verification Activity - Physical / Visual
label | Methods or Reference - Front Mounted Broom / Suction Truck, Downer Survey or MS Forms Post Seal Inspection
label | Frequency - At conclusion of positive traffication within 48 hours
label | Acceptance Criteria - All sump and road furniture protection removed. Meets requirements of P/17 Table 2.
label | Hold / Witness Point - Witness Point
label | Records - Post Seal Inspection
label | Responsible Person - Sealing / Rehab Contract Manager / Engineer
section | Post Seal Construction
checkpoint | Asbuilts and RAMM data
label | Verification Activity - RAMM Update Sheet
label | Methods or Reference - RAMM Database
label | Frequency - Data provided from the site
label | Acceptance Criteria - RAMM update sheet 100% complete and accurate, note data provided for RAMM update to be uploaded by others
label | Hold / Witness Point - Witness Point
label | Records - As built information/RAMM Update Sheet
label | Responsible Person - Sealing Contract Manager/ QA
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature