## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | YTTP-BT-ITP-002 - Structural Piles | itp |  |  |  |  | YTTP-BT-ITP-002 - Structural Piles
section | Design and Submissions
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | — using the correct and complete set of drawings
label | — all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.3 Approval of mix design
label | FREQUENCY: Prior to the first concrete pour
label | ACCEPTANCE CRITERIA: Structural Concrete Design & Submission ITP completed and signed.
label | REFERENCE DOCUMENTS: AS 3600
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed, Teambinder records
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.4 Reinforcement schedule
label | FREQUENCY: Prior to concrete pour
label | ACCEPTANCE CRITERIA: Reinforcement schedule has been prepared for the reinforcement supply, to ensure that it achieves the specified tolerances on member dimensions, concrete cover and specified locations
label | REFERENCE DOCUMENTS: AS 4671
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
section | Construction/Erection of Formwork
checkpoint | 2.1 Excavation (Pile)
label | FREQUENCY: Prior to concrete pour
label | ACCEPTANCE CRITERIA: The Contractor shall notify FH engineer for inspection of the pile excavation by the Superintendent. Prior to inspection, the pile excavation shall be de‑watered and the walls and base of the pile cleaned out, including the internal surface of the casing, to remove all mud, loose or foreign material. Depth of pile is to be confirmed by on site geotech to ensure rock socket as per structural drawings
label | REFERENCE DOCUMENTS: Structural Drawings
label | INSPECTION/TEST METHOD: Inspect
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer/Geotech
textbox | Date Completed:
checkpoint | 2.2 Construction Methodology
label | FREQUENCY: Prior to erection
label | ACCEPTANCE CRITERIA: Designed and constructed in such a manner so it can be removed without damage to the concrete. Formwork/shoring shall be placed in locations where steel reinforcement and other fixtures can be inspected, and sufficiently tight at joints to prevent loss of slurry
label | REFERENCE DOCUMENTS:
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.3 Construction Methodology (Pile)
label | FREQUENCY: Prior to construction
label | ACCEPTANCE CRITERIA: Further to the requirements of clause 611.10 spacers and supports for bored pile steel reinforcement shall be placed at intervals of no more than 2 m along the full length of the steel reinforcement cage to ensure that the specified concrete cover to the steel reinforcement is maintained.
label | REFERENCE DOCUMENTS:
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
section | Pre-Pour Planning and Inspection
checkpoint | 3.1 Cleaning formwork
label | FREQUENCY: Each concrete pour
label | ACCEPTANCE CRITERIA: Concrete shall not be placed until all foreign material has been completely removed from the forms
label | REFERENCE DOCUMENTS:
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 3.2 Correct forms, reinforcements, rag bolt assembly and embedments
label | FREQUENCY: Prior to concrete pour
label | ACCEPTANCE CRITERIA: FH engineer confirms that the inspected formwork, reinforcement, rag bolt assembly and embedments comply with the project drawings and specifications.
label | ○ Pre-pour checklist completed and signed.
label | REFERENCE DOCUMENTS:
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed & Pre-Pour checklist completed
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer/Building Surveyor
textbox | Date Completed:
checkpoint | 3.3 Reinforcement assembly of piles
label | FREQUENCY: Prior to concrete pour
label | ACCEPTANCE CRITERIA: Reinforcement and/or concrete shall not be placed until the proposed method of removing mud, loose rock or similar materials has been reviewed by FH engineer
label | REFERENCE DOCUMENTS:
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
checkpoint | 3.4 Monitoring weather
label | FREQUENCY: Prior to concrete pour
label | ACCEPTANCE CRITERIA: Concrete shall not be place when temperature is <5°C or > 35°C
label | ○ All steel components that are in contact with the concrete shall be cooled to below 32°C before concrete is placed
label | REFERENCE DOCUMENTS:
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
section | Placing and Finishing Concrete
checkpoint | 4.1 Carry out sampling of concrete
label | FREQUENCY: Each concrete pour
label | ACCEPTANCE CRITERIA: Sampling in accordance with AS 1012
label | REFERENCE DOCUMENTS:
label | INSPECTION/TEST METHOD: Checklist
label | RECORD OF CONFORMITY: This ITP signed, Delivery dockets
label | IP
label | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
checkpoint | 4.2 Discharge time
label | FREQUENCY: Each concrete pour
label | ACCEPTANCE CRITERIA: Discharge time (concrete placed and compacted) < 90 minutes from batch time unless approved otherwise. Batch to be used has a discharge time of 180 minutes.
label | REFERENCE DOCUMENTS:
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed. Accurate Site Notes & Load Mapping if req.
label | IP
label | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
checkpoint | 4.3 Methodology of placement (structural)
label | FREQUENCY: Each concrete pour
label | ACCEPTANCE CRITERIA: Concrete shall be tansported, handled and placed in a manner that will prevent segregation or loss of materials
label | ○ In continuous pours the max. time lag between truckloads on site is 25 minutes
label | REFERENCE DOCUMENTS:
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
checkpoint | 4.4 Methodology of placement (piles)
label | FREQUENCY: Each concrete pour
label | ACCEPTANCE CRITERIA: Unless otherwise approved by the FH Engineer, temporary casing shall be used to prevent collapse of holes during the excavation operation.
label | ○ Care shall be taken to prevent soil and rock dislodging from the side of the hole and contaminating the concrete forming the minimum cover to the reinforcement.
label | REFERENCE DOCUMENTS:
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
section | Post-Pour Details and Inspection
checkpoint | 5.1 Curing
label | FREQUENCY: Each concrete pour
label | ACCEPTANCE CRITERIA: Sufficient time shall be given for the concrete to cure prior to loading.
label | REFERENCE DOCUMENTS:
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
checkpoint | 5.2 Formwork removal
label | FREQUENCY: Each concrete pour
label | ACCEPTANCE CRITERIA: Formwork shall be removed carefully and in such a manner as to avoid damage to the member or the concrete surfaces and maintain safety at all stages of removal. Formwork and formwork supports shall not be disturbed or adjusted during the concreting operation
label | REFERENCE DOCUMENTS:
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
checkpoint | 5.3 Positional tolerance and dimensions of concrete members and piles
label | FREQUENCY: Each concrete pour
label | ACCEPTANCE CRITERIA: The centre of the pile head shall be in the specified plan position ±75 mm;
label | REFERENCE DOCUMENTS: AS 2159
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed, Post Pour Checklist completed
label | IP
label | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
checkpoint | 5.4 Protection of Adjacent Piles
label | FREQUENCY: Prior to commencing any piling
label | ACCEPTANCE CRITERIA: No pile construction shall be commenced within 2.5m clear distance of a newly cast pile until the concrete in the pile has attained a strength of 15 MPa.
label | ○ Installation of piles by methods which involve driven temporary casing or result in significant vibration shall not be carried out within the distance 2.5 m to 9.0 m until the concrete in the pile has attained a strength of 15 MPa and set for a minimum of 24 hours.
label | REFERENCE DOCUMENTS: Structural Drawings
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
checkpoint | 5.5 Testing Post-Pour
label | FREQUENCY: Prior to lot closure
label | ACCEPTANCE CRITERIA: Pile integrity testing is to completed on the first 6 piles poured, and then on every 3rd there after, providing the first 6 pass.
label | REFERENCE DOCUMENTS: Structural Drawings
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | TP
label | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
checkpoint | 5.6 As Built Drawings
label | FREQUENCY: Prior to lot closure
label | ACCEPTANCE CRITERIA: Recorded of as-built drawings
label | REFERENCE DOCUMENTS: Fulton Hogan Procedure
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed, Lot maps
label | IP
label | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date: