## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
f81b70c2-e899-4438-8d7f-2df53507f795 | checklist | ITP-028 - Street Furniture (Supply & Installation) Rev1 | itp | ITP-028 - Street Furniture (Supply & Installation)
| section | Preliminary Works
| checkpoint | 1.1 Check for correct documentation
| note | FREQUENCY: Prior to commencing any activity
| note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the most current and updated set of complete construction drawings
| note | REFERENCE DOCUMENTS: Drawings and drawing registers
| note | INSPECTION/TEST METHOD: Visual inspection
| note | RECORD OF CONFORMITY: This ITP signed off
| note | HP*
| note | RESPONSIBILITY: Fulton Hogan Engineer
| textbox | Date Completed:
| checkpoint | 1.2 Implementation of all measures and controls
| note | FREQUENCY: Prior to commencing any activity
| note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: EMP, SWMS & WP
| note | REFERENCE DOCUMENTS: EMP, SWMS, WP
| note | INSPECTION/TEST METHOD: Visual Inspection
| note | RECORD OF CONFORMITY: This ITP signed off
| note | HP*
| note | RESPONSIBILITY: Fulton Hogan Engineer
| textbox | Date Completed:
| checkpoint | 1.3 Check Materials
| note | FREQUENCY: Prior to commencing any activity
| note | ACCEPTANCE CRITERIA: Confirm manufacturing process with supplier, fencing material shall be laser cut with clean finish, linished, pickled and electropolished
| note | ○ Welding shall be in accordance with AS1554
| note | ○ Ensure all components and fastenings are procured to the materials, sizes and grades specified in STD_T6000
| note | REFERENCE DOCUMENTS: STD_T6000 CE-021-ST-0012 cl 4.3.1.4
| note | INSPECTION/TEST METHOD: Verify
| note | RECORD OF CONFORMITY: This ITP signed off
| note | HP*
| note | RESPONSIBILITY: Fulton Hogan Engineer
| textbox | Date Completed:
| checkpoint | 1.4 Confirm Footings position
| note | FREQUENCY: Prior to commencing any activity
| note | ACCEPTANCE CRITERIA: Confirm footings are set out to locations specified on design drawings
| note | REFERENCE DOCUMENTS: Construction Drawings
| note | INSPECTION/TEST METHOD: Verify
| note | RECORD OF CONFORMITY: This ITP signed off
| note | HP*
| note | RESPONSIBILITY: Fulton Hogan Engineer
| textbox | Date Completed:
| checkpoint | 1.5 Bonds
| note | FREQUENCY: Prior to commencing any activity
| note | ACCEPTANCE CRITERIA: Ensure fencing is isolated and earthed to achieve electrical isolation.
| note | ○ Lug shall be fitted to baseplate at specified fencing location
| note | REFERENCE DOCUMENTS: STD_T6000
| note | INSPECTION/TEST METHOD: Verify
| note | RECORD OF CONFORMITY: This ITP signed off
| note | HP*
| note | RESPONSIBILITY: Fulton Hogan Engineer
| textbox | Date Completed:
| section | Construction Works
| checkpoint | 2.1 Footing Installation
| note | FREQUENCY: Prior to Asphalt
| note | ACCEPTANCE CRITERIA: Concrete shall be of minimum strength N20
| note | ○ 4 M16 hot dipped galvanised bolts shall be chemset 175mm into embedment, per footing
| note | REFERENCE DOCUMENTS: STD_T6002
| note | INSPECTION/TEST METHOD: Verify
| note | RECORD OF CONFORMITY: This ITP signed off
| note | IP
| note | RESPONSIBILITY: Fulton Hogan Engineer
| textbox | Date Completed:
| checkpoint | 2.2 Post Installation
| note | FREQUENCY: Each Lot
| note | ACCEPTANCE CRITERIA: Post shall be installed to designated height and level
| note | ○ Installed to footings with bolt assembly
| note | ○ All bolts shall be insulated from base plates, using non metallic sleeves and washers
| note | ○ The top of fence base plate shall be level with surrounding pavement
| note | REFERENCE DOCUMENTS: STD_T6002
| note | INSPECTION/TEST METHOD: Verify
| note | RECORD OF CONFORMITY: This ITP signed off
| note | IP
| note | RESPONSIBILITY: Fulton Hogan Engineer
| textbox | Date Completed:
| checkpoint | 2.3 Grout Installation
| note | FREQUENCY: Each Lot
| note | ACCEPTANCE CRITERIA: Footing surface shall be cleaned and roughened before application
| note | ○ 50mm of Non shrink dry pack grout shall be placed under base plate
| note | REFERENCE DOCUMENTS: STD_T6002
| note | INSPECTION/TEST METHOD: Visual inspection
| note | RECORD OF CONFORMITY: This ITP signed off
| note | WP
| note | RESPONSIBILITY: Fulton Hogan Engineer
| textbox | Date Completed:
| checkpoint | 2.4 Continuous Handrails
| note | FREQUENCY: Each Lot
| note | ACCEPTANCE CRITERIA: 5mm cap plate on handrail returns
| note | ○ All sections to be welded as per AS 1554
| note | ○ All sharp edges and welds to be ground back to smooth finish
| note | ○ Domed buttons to be welded on top of handrail 150mm from the post centreline
| note | REFERENCE DOCUMENTS: STD_T6001 & T6002
| note | INSPECTION/TEST METHOD: Verify
| note | RECORD OF CONFORMITY: This ITP signed off
| note | IP
| note | RESPONSIBILITY: Fulton Hogan Engineer
| textbox | Date Completed:
| checkpoint | 2.5 Wire Rope Tensioners
| note | FREQUENCY: Each Lot
| note | ACCEPTANCE CRITERIA: Architectural wire rope cables to be inserted into ferrel on fence post and to be tensioned with tamper proof fastenings (Loctite 243 Threadlock)
| note | REFERENCE DOCUMENTS: STD_T6000, T6001 & T6002
| note | INSPECTION/TEST METHOD: Verify
| note | RECORD OF CONFORMITY: This ITP signed off
| note | IP
| note | RESPONSIBILITY: Fulton Hogan Engineer
| textbox | Date Completed:
95afd524-ea5e-4a21-98cb-fce2c6998ee8 | checkpoint | Final Inspection
c74eb7d5-3983-51dd-b8b8-517c3c2ec223 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
ae0bd643-2a41-5cc2-85db-7595c4c8e2b5 | textbox | Print Name:
74423900-a2fb-55ba-9e74-ea4bb63bc486 | textbox | Position:
f690c326-6cc6-5ae9-ae26-174158e99789 | textbox | Date: