## Chip Seal
Contractor = Contractors nominated representative Principals Rep = Principals Representative Quality Manager = Contactors Quality Manager
CONTRACTOR: HIGGINS - BAY OF PLENTY |  |  |  |  | LOCATION | EBOP NOC 25/26 Reseal sites
CHIPSEAL INSPECTION AND TEST PLAN |  |  |  |  | Prepared by Contract Manager | Signature__________________________________ | H = Hold Point = Principal inspection/review and approval of work before next activity can take place
[5 empty] | Reviewed by Design Manager/Asset Manager | Signature___________________________________ | W = Witness Point = Principal invited to inspect, next Activity can take place should Principal not attend
Complete DAILY with all relevant QA records for that day attached |  |  |  |  | Approved by Quality Manager | Signature __________________________________ | DR = Document or Record review, prior works activity or post activity to verify compliance
No. | Inspection & Test Activity | Applicable Standard & Acceptance Criteria (NZTA- Template ) | Applicable Standard & Acceptance Criteria (Higgins) | Higgins (Comment) | Frequency | Criteria Notes | Inspect / Approve / Initial Sign Off |  | Records & Remarks
[7 empty] | Contractor | Principals Rep | Update as required/confirm document
1.0 Pre-Commencement Activities (Design suitability)
1.1 | Surface texture measurement (1) | NZTA P03 | NZTA P03 | NZTA P03 (First Coat seal) and P 04 is client provided designs | As per NZTA P03 | Sandcircle Measurement, or Laser Texture, or Principals HSD | H | — | Tabulated worksheet
1.1 | Surface texture measurement (2) | NZTA P04 | NZTA P17 4.3 Surface Texture | NZTA is contractor supplied | As per NZTA P17 | Sandcircle Measurement, or Laser Texture, or Principals HSD | H | — | Tabulated worksheet
1.2 | Treatment selection confirmed | — | — | — | Pre site works | Principal agreed treatment selection | H | — | Records of Contractors Design
1.3 | Chip skid performance | NZTA T10 | NZTA T10 | — | Pre site works | Aggregate Peformance Report submitted & accepted by Principal. | H | — | Included in chipseal design report
1.4 | Chipseal Design | NZTA P18 | NZTA P17 | NZTA P18 is principal designed | Pre site works | Design meets contractual requirements | H | — | Seal design provided to principal
1.5 | Multilayer compatibility | NZTA P18 Fig 1 | Chip seal NZ | NZTA P18 is principal designed | 1 per design | Both ALD results identified on graph | — | W | Included in chipseal design report
1.6 | Renewal Quality Plan | — | — | — | One overarching for all reseal sites | RQP Approved | H | — | Principal approval signature
| HP – Chipseal design verified for site commencement | — | — | — | — | Contractor checklist copied to Principal | — | W | Pre-commencement checklist signed and filed
2.0 Material Compliance
2.1 | Bitumen compliance | NZTA M02, P03, P04 | NZTA M1 | Currently all seal is completed with Cut Back Bitumen as per M01 | 1 test certificate per bulk shipment | Lab Test Report | — | W | Property Test, NZTA M01
2.2 | Chip source property compliance | NZTA M06 | NZTA M06 | same | Annually for each source | Lab test results | — | W | Source property checklist: PSV, CR, WR
2.3 | Chip production property compliance (Quarry or stockpile, dependent on where on site materials is coming from) | NZTA M06, P18 | NZTA M06, | same | < 100m3, minimum 1 sample 100 - 500m3, minimum 2 samples >500m3, minimum 3 samples | Lab test results | — | W | Cleanness (Grades 2 – 6); Sealing chip size & shape; Broken faces (if reqd); PSD
| HP – Material compliance confirmed (binder, source & production properties) | — | — | — | — | Material compliance checklist copied to Principal | — | W | Material compliance checklist signed & filed
3.0 Seal construction
3.1 | Pre-Seal Site Checklist (week prior) | Confirming site is ready for sealing | Confirming site is ready for sealing | same | Following ALL pre seal works | — | — | H | Inspection Notes (Standard Form)Include Photographic Evidence and add in the Site Records
3.2 | Bitumen Distributor | BPG 02 | E2 | Bitumen Distributor is certified under NZTA E2 | Annually | Speed Test, Dipstick Test, Distribution (Pad)Test | — | W | E2 Certificate
3.3 | Go/No Go Checklist | Weather, readiness of materials and plant, air temperature, pavement temperature, et al | Weather, readiness of materials and plant, air temperature, pavement temperature, et al | same | Prior to sealing on each site | Visual on site and check list sign off | — | H | Pre-commencement checklist (ie pre-start reqs, by foreman/crew manager)
3.4 | Spraying – site measurements | NZTA P03, P04 | NZTA P17 | — | Per Site | Application rates within design & tolerances + or - 5% | — | — | Spray sheet
3.5 | Geotextile reinforced seals (GRS ) | As per P18 & specific design requirements | As per specific design requirements and P17 | — | Per Site | Accurate RP start/end location & offset Application rates within design & tolerances + or - 5% | — | — | Spray sheet
4.0 Clean-up
4.1 | Post-seal (exit) inspection | NZTA P03, P04 | NZTA P17 | NZTA P17 Notes section 18 | Per Site | To open for trafficking | — | — | Chip Sealing Quality and Site Checklist
4.2 | Removal of surplus chip | NZTA P03, P04 | NZTA P17 | NZTA P17 Notes section 22.2 | Per Site | Loose chip complies with P03 or P04 as appropriate | — | — | Chip Sealing Quality and Site Checklist
4.3 | Post-Seal Site Management | NZTA P03, P04 | NZTA P17 | NZTA P17 section 7 | Per Site | Implementation of positive traffic control when loose chip quantities pose a risk to public safety | — | — | —
5.0 Post-construction
5.1 | Post seal inspection (Final TTM Removal) | NZTA P03, P04 | NZTA P17 | NZTA P17 section 7 | — | On completion of roadmarking Surplus chip to be removed | — | W | Chip Sealing Quality and Site Checklist
5.2 | QA Handover | NZTA P03, P04 or P18 and contract drawings | NZTA P17 and contract drawings | Quality Plan | For each site on the project | Materials, construction compliance and extents | — | W | Evidence provided demonstrating full compliance with specified design
5.3 | RAMM update | RAMM updates completed | RAMM updates completed | — | — | Review of RAMM update and confirmation | — | W | Site records of RAMM update to be reviewed and confirmed
Quality Record Close Out:
|  | Digital Signature | Digital Signature |  |  | Quality Manager Name |  | Date
S

## Comments
Contractor = Contractors nominated representative Principals Rep = Principals Representative Quality Manager = Contactors Quality Manager
CONTRACTOR ________________________________ |  |  |  |  | LOCATION | Identify Site ______________________________________
CHIPSEAL INSPECTION AND TEST PLAN |  |  |  |  | Prepared by Contract Manager | Signature_______________________________________ | H = Hold Point = Principal inspection/review and approval of work before next activity can take place
[5 empty] | Reviewed by Design Manager/Asset Manager | Signature_______________________________________ | W = Witness Point = Principal invited to inspect, next Activity can take place should Principal not attend
Complete DAILY with all relevant QA records for that day attached |  |  |  |  | Approved by Quality Manager | Signature _________________________________________ | DR = Document or Record review, prior works activity or post activity to verify compliance
No. | Inspection & Test Activity | Applicable Standard & Acceptance Criteria (NZTA- Template ) | Applicable Standard & Acceptance Criteria (Higgins) | Higgins (Comment) | Frequency | Criteria Notes | Inspect / Approve / Initial Sign Off |  | Records & Remarks
[7 empty] | Contractor | Principals Rep | Update as required/confirm document | Comments
1.0 Pre-Commencement Activities (Design suitability) | [9 empty] | Quality Team
1.1 | Surface texture measurement | NZTA P03 | NZTA P03 | NZTA P03 (First Coat seal) and P 04 is client provided designs | As per NZTA P17 | Sandcircle Measurement, or Laser Texture, or Principals HSD | H |  | Tabulated worksheet
|  | NZTA P04 | NZTA P17 | NZTA is contractor supplied | As per NZTA P03 | Sandcircle Measurement, or Laser Texture, or Principals HSD |  |  |  | 1.Applicable Standard: NZTA P17; 4.3 Surface Texture
1.2 | Treatment selection confirmed |  |  |  | Pre site works | Principal agreed treatment selection | H |  | Records of Contractors Design
1.3 | Chip skid performance | NZTA T10 | NZTA T10 |  | Pre site works | Aggregate Peformance Report submitted & accepted by Principal. | H |  | Included in chipseal design report | remove the highlight
1.4 | Chipseal Design | NZTA P18 | NZTA P17 | NZTA P18 is principal designed | Pre site works | Design meets contractual requirements | H |  | Seal design provided to principal
1.5 | Multilayer compatibility | NZTA P18 Fig 1 | Chip seal NZ | NZTA P18 is principal designed | 1 per design | Both ALD results identified on graph |  | W | Included in chipseal design report
1.6 | Renewal Quality Plan |  |  |  | One overarching for all reseal sites | RQP Approved | H |  | Principal approval signature
| HP – Chipseal design verified for site commencement |  |  |  |  | Contractor checklist copied to Principal |  | W | Pre-commencement checklist signed and filed
2.0 Material Compliance
2.1 | Bitumen compliance | NZTA M02, P03, P04 | NZTA M1 | Currently all seal is completed with Cut Back Bitumen as per M01 | 1 test certificate per bulk shipment | Lab Test Report |  | W | Property Test, NZTA M01
2.2 | Chip source property compliance | NZTA M06 | NZTA M06 | same | Annually for each source | Lab test results |  | W | Source property checklist: PSV, CR, WR
2.3 | Chip production property compliance (Quarry or stockpile, dependent on where on site materials is coming from) | NZTA M06, P18 | NZTA M06, | same | < 100m3, minimum 1 sample 100 - 500m3, minimum 2 samples >500m3, minimum 3 samples | Lab test results |  | W | Cleanness (Grades 2 – 6); Sealing chip size & shape; Broken faces (if reqd); PSD
| HP – Material compliance confirmed (binder, source & production properties) |  |  |  |  | Material compliance checklist copied to Principal |  | W | Material compliance checklist signed & filed
3.0 Seal construction
3.1 | Pre-Seal Site Checklist (week prior) | Confirming site is ready for sealing | Confirming site is ready for sealing | same | Following ALL pre seal works |  |  | H | Inspection Notes (Standard Form)Include Photographic Evidence and add in the Site Records
3.2 | Bitumen Distributor | BPG 02 | E2 | Bitumen Distributor is certified under NZTA E2 | Annually | Speed Test, Dipstick Test, Distribution (Pad)Test |  | W | E2 Certificate
3.3 | Go/No Go Checklist | Weather, readiness of materials and plant, air temperature, pavement temperature, et al | Weather, readiness of materials and plant, air temperature, pavement temperature, et al | same | Prior to sealing on each site | Visual on site and check list sign off |  | H | Pre-commencement checklist (ie pre-start reqs, by foreman/crew manager)
3.4 | Spraying – site measurements | NZTA P03, P04 | NZTA P17 |  | Per Site | Application rates within design & tolerances + or - 5% |  |  | Site records | Spraysheet
3.5 | Geotextile reinforced seals (GRS ) | As per P18 & specific design requirements | As per specific design requirements and P17 |  | Per Site | Accurate RP start/end location & offset Application rates within design & tolerances + or - 5% |  |  | Site records
4.0 Clean-up
4.1 | Post-seal (exit) inspection | NZTA P03, P04 | NZTA P17 | NZTA P17 Notes section 18 | Per Site | To open for trafficking |  |  | Clean up checklist | Chip Sealing Quality and Site Checklist
4.2 | Removal of surplus chip | NZTA P03, P04 | NZTA P17 | NZTA P17 Notes section 22.2 | Per Site | Loose chip complies with P03 or P04 as appropriate |  |  |  | Chip Sealing Quality and Site Checklist
4.3 | Post-Seal Site Management | NZTA P03, P04 | NZTA P17 | NZTA P17 section 7 | Per Site | Minimum 48 hours trafficking
5.0 Post-construction
5.1 | Post seal inspection (Final TTM Removal) | NZTA P03, P04 | NZTA P17 | NZTA P17 section 7 |  | On completion of roadmarking Surplus chip to be removed |  | W | Post construction checklist completed & filed | Chip Sealing Quality and Site Checklist
5.2 | QA Handover | NZTA P03, P04 or P18 and contract drawings | NZTA P17 and contract drawings | Quality Plan | For each site on the project | Materials, construction compliance and extents |  | W | Evidence provided demonstrating full compliance with specified design
5.3 | RAMM update | RAMM updates completed | RAMM updates completed |  |  | Review of RAMM update and confirmation |  | W | Site records of RAMM update to be reviewed and confirmed
Quality Record Close Out:
|  | Digital Signature | Digital Signature |  |  | Quality Manager Name |  | Date
S