## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Chipseal | itp |  |  |  |  | ITP - Chipseal
section | 1.0 Pre-Commencement Activities (Design suitability)
checkpoint | 1.1 - Surface texture measurement (1)
label | Applicable Standard & Acceptance Criteria (NZTA- Template) - NZTA P03
label | Applicable Standard & Acceptance Criteria (Higgins) - NZTA P03
label | Higgins (Comment) - NZTA P03 (First Coat seal) and P 04 is client provided designs
label | Frequency - As per NZTA P03
label | Criteria Notes - Sandcircle Measurement, or Laser Texture, or Principals HSD
label | Contractor - H
label | Records & Remarks - Tabulated worksheet
holdpoint | HOLD POINT
checkpoint | 1.1 - Surface texture measurement (2)
label | Applicable Standard & Acceptance Criteria (NZTA- Template) - NZTA P04
label | Applicable Standard & Acceptance Criteria (Higgins) - NZTA P17 4.3 Surface Texture
label | Higgins (Comment) - NZTA is contractor supplied
label | Frequency - As per NZTA P17
label | Criteria Notes - Sandcircle Measurement, or Laser Texture, or Principals HSD
label | Contractor - H
label | Records & Remarks - Tabulated worksheet
holdpoint | HOLD POINT
checkpoint | 1.2 - Treatment selection confirmed
label | Frequency - Pre site works
label | Criteria Notes - Principal agreed treatment selection
label | Contractor - H
label | Records & Remarks - Records of Contractors Design
holdpoint | HOLD POINT
checkpoint | 1.3 - Chip skid performance
label | Applicable Standard & Acceptance Criteria (NZTA- Template) - NZTA T10
label | Applicable Standard & Acceptance Criteria (Higgins) - NZTA T10
label | Frequency - Pre site works
label | Criteria Notes - Aggregate Peformance Report submitted & accepted by Principal.
label | Contractor - H
label | Records & Remarks - Included in chipseal design report
holdpoint | HOLD POINT
checkpoint | 1.4 - Chipseal Design
label | Applicable Standard & Acceptance Criteria (NZTA- Template) - NZTA P18
label | Applicable Standard & Acceptance Criteria (Higgins) - NZTA P17
label | Higgins (Comment) - NZTA P18 is principal designed
label | Frequency - Pre site works
label | Criteria Notes - Design meets contractual requirements
label | Contractor - H
label | Records & Remarks - Seal design provided to principal
holdpoint | HOLD POINT
checkpoint | 1.5 - Multilayer compatibility
label | Applicable Standard & Acceptance Criteria (NZTA- Template) - NZTA P18 Fig 1
label | Applicable Standard & Acceptance Criteria (Higgins) - Chip seal NZ
label | Higgins (Comment) - NZTA P18 is principal designed
label | Frequency - 1 per design
label | Criteria Notes - Both ALD results identified on graph
label | Principals Rep - W
label | Records & Remarks - Included in chipseal design report
checkpoint | 1.6 - Renewal Quality Plan
label | Frequency - One overarching for all reseal sites
label | Criteria Notes - RQP Approved
label | Contractor - H
label | Records & Remarks - Principal approval signature
holdpoint | HOLD POINT
checkpoint | HP – Chipseal design verified for site commencement
label | Criteria Notes - Contractor checklist copied to Principal
label | Principals Rep - W
label | Records & Remarks - Pre-commencement checklist signed and filed
section | 2.0 Material Compliance
checkpoint | 2.1 - Bitumen compliance
label | Applicable Standard & Acceptance Criteria (NZTA- Template) - NZTA M02, P03, P04
label | Applicable Standard & Acceptance Criteria (Higgins) - NZTA M1
label | Higgins (Comment) - Currently all seal is completed with Cut Back Bitumen as per M01
label | Frequency - 1 test certificate per bulk shipment
label | Criteria Notes - Lab Test Report
label | Principals Rep - W
label | Records & Remarks - Property Test, NZTA M01
checkpoint | 2.2 - Chip source property compliance
label | Applicable Standard & Acceptance Criteria (NZTA- Template) - NZTA M06
label | Applicable Standard & Acceptance Criteria (Higgins) - NZTA M06
label | Higgins (Comment) - same
label | Frequency - Annually for each source
label | Criteria Notes - Lab test results
label | Principals Rep - W
label | Records & Remarks - Source property checklist: PSV, CR, WR
checkpoint | 2.3 - Chip production property compliance (Quarry or stockpile, dependent on where on site materials is coming from)
label | Applicable Standard & Acceptance Criteria (NZTA- Template) - NZTA M06, P18
label | Applicable Standard & Acceptance Criteria (Higgins) - NZTA M06,
label | Higgins (Comment) - same
label | Frequency - < 100m3, minimum 1 sample
label | ○ 100 - 500m3, minimum 2 samples
label | ○ >500m3, minimum 3 samples
label | Criteria Notes - Lab test results
label | Principals Rep - W
label | Records & Remarks - Cleanness (Grades 2 – 6); Sealing chip size & shape; Broken faces (if reqd); PSD
checkpoint | HP – Material compliance confirmed (binder, source & production properties)
label | Criteria Notes - Material compliance checklist copied to Principal
label | Principals Rep - W
label | Records & Remarks - Material compliance checklist signed & filed
section | 3.0 Seal construction
checkpoint | 3.1 - Pre-Seal Site Checklist (week prior)
label | Applicable Standard & Acceptance Criteria (NZTA- Template) - Confirming site is ready for sealing
label | Applicable Standard & Acceptance Criteria (Higgins) - Confirming site is ready for sealing
label | Higgins (Comment) - same
label | Frequency - Following ALL pre seal works
label | Principals Rep - H
label | Records & Remarks - Inspection Notes (Standard Form)Include Photographic Evidence and add in the Site Records
holdpoint | HOLD POINT
checkpoint | 3.2 - Bitumen Distributor
label | Applicable Standard & Acceptance Criteria (NZTA- Template) - BPG 02
label | Applicable Standard & Acceptance Criteria (Higgins) - E2
label | Higgins (Comment) - Bitumen Distributor is certified under NZTA E2
label | Frequency - Annually
label | Criteria Notes - Speed Test, Dipstick Test, Distribution (Pad)Test
label | Principals Rep - W
label | Records & Remarks - E2 Certificate
checkpoint | 3.3 - Go/No Go Checklist
label | Applicable Standard & Acceptance Criteria (NZTA- Template) - Weather, readiness of materials and plant, air temperature, pavement temperature, et al
label | Applicable Standard & Acceptance Criteria (Higgins) - Weather, readiness of materials and plant, air temperature, pavement temperature, et al
label | Higgins (Comment) - same
label | Frequency - Prior to sealing on each site
label | Criteria Notes - Visual on site and check list sign off
label | Principals Rep - H
label | Records & Remarks - Pre-commencement checklist (ie pre-start reqs, by foreman/crew manager)
holdpoint | HOLD POINT
checkpoint | 3.4 - Spraying – site measurements
label | Applicable Standard & Acceptance Criteria (NZTA- Template) - NZTA P03, P04
label | Applicable Standard & Acceptance Criteria (Higgins) - NZTA P17
label | Frequency - Per Site
label | Criteria Notes - Application rates within design & tolerances + or - 5%
label | Records & Remarks - Spray sheet
checkpoint | 3.5 - Geotextile reinforced seals (GRS )
label | Applicable Standard & Acceptance Criteria (NZTA- Template) - As per P18 & specific design requirements
label | Applicable Standard & Acceptance Criteria (Higgins) - As per specific design requirements and P17
label | Frequency - Per Site
label | Criteria Notes - Accurate RP start/end location & offset
label | ○ Application rates within design & tolerances + or - 5%
label | Records & Remarks - Spray sheet
section | 4.0 Clean-up
checkpoint | 4.1 - Post-seal (exit) inspection
label | Applicable Standard & Acceptance Criteria (NZTA- Template) - NZTA P03, P04
label | Applicable Standard & Acceptance Criteria (Higgins) - NZTA P17
label | Higgins (Comment) - NZTA P17 Notes section 18
label | Frequency - Per Site
label | Criteria Notes - To open for trafficking
label | Records & Remarks - Chip Sealing Quality and Site Checklist
checkpoint | 4.2 - Removal of surplus chip
label | Applicable Standard & Acceptance Criteria (NZTA- Template) - NZTA P03, P04
label | Applicable Standard & Acceptance Criteria (Higgins) - NZTA P17
label | Higgins (Comment) - NZTA P17 Notes section 22.2
label | Frequency - Per Site
label | Criteria Notes - Loose chip complies with P03 or P04 as appropriate
label | Records & Remarks - Chip Sealing Quality and Site Checklist
checkpoint | 4.3 - Post-Seal Site Management
label | Applicable Standard & Acceptance Criteria (NZTA- Template) - NZTA P03, P04
label | Applicable Standard & Acceptance Criteria (Higgins) - NZTA P17
label | Higgins (Comment) - NZTA P17 section 7
label | Frequency - Per Site
label | Criteria Notes - Implementation of positive traffic control when loose chip quantities pose a risk to public safety
section | 5.0 Post-construction
checkpoint | 5.1 - Post seal inspection (Final TTM Removal)
label | Applicable Standard & Acceptance Criteria (NZTA- Template) - NZTA P03, P04
label | Applicable Standard & Acceptance Criteria (Higgins) - NZTA P17
label | Higgins (Comment) - NZTA P17 section 7
label | Criteria Notes - On completion of roadmarking Surplus chip to be removed
label | Principals Rep - W
label | Records & Remarks - Chip Sealing Quality and Site Checklist
checkpoint | 5.2 - QA Handover
label | Applicable Standard & Acceptance Criteria (NZTA- Template) - NZTA P03, P04 or P18 and contract drawings
label | Applicable Standard & Acceptance Criteria (Higgins) - NZTA P17 and contract drawings
label | Higgins (Comment) - Quality Plan
label | Frequency - For each site on the project
label | Criteria Notes - Materials, construction compliance and extents
label | Principals Rep - W
label | Records & Remarks - Evidence provided demonstrating full compliance with specified design
checkpoint | 5.3 - RAMM update
label | Applicable Standard & Acceptance Criteria (NZTA- Template) - RAMM updates completed
label | Applicable Standard & Acceptance Criteria (Higgins) - RAMM updates completed
label | Criteria Notes - Review of RAMM update and confirmation
label | Principals Rep - W
label | Records & Remarks - Site records of RAMM update to be reviewed and confirmed
checkpoint | Quality Record Close Out:
textbox | Quality Manager Name:
date | Date:
signoff | Add Signature