## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
3fedfdad-869a-4875-8a34-d100953b5250 | checklist | RSA.BitumenEdgeSeal.ITP | itp | RSA.BitumenEdgeSeal.ITP
e271fda3-1ff6-45da-a07b-5a14da023624 | section | 1 - Preliminary
903e921f-1de1-45bc-abb4-590b7d6a5123 | checkpoint | 1.1 - Access Documentation
d0717423-c446-53fd-ab5c-f981cccacc60 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Relevant ATW, LARS / PTA/ Concil Permits/ TMR Permits/ TCP/ TMP
be7e257d-5124-5ca1-a1bb-be003f96d70f | note | Frequency - Prior to Start
263165a8-88ff-5044-b8cb-2ff0224dc5d6 | note | Test Method - Review
1ac7b5b1-3b8c-55be-b833-1833c09f67a8 | note | Acceptance Criteria - All documents in place and correct.
2a665e79-f55c-51a1-bc70-ffde32d9ba00 | note | Verifying Documents - LARS / PTA
ec442e92-70d9-51ae-bbcc-3da9b79b23d1 | note | ○ Landholder Notification
2f1e7baa-17e5-55e9-90bc-3654a7ab638d | note | ○ Traffic Control Permit/Plan
e2d6ecab-dc25-5a7a-a368-29174d864874 | note | ○ TMR Permits
5d37d114-82c1-5e65-9026-55ad529ed974 | note | ○ Species and Fauna Management
b9ce8301-420a-5565-a6d7-4f2ae5599cdb | note | ○ Cultural Heritage Induction Attendance Register
5c911d55-6a65-5f44-ad29-443d915b67c1 | note | ○ Cultural Heritage Clearance Report / Form
8b6771b6-cda4-5f47-9ecd-37566e897abc | note | Responsibility: RSA - H
79c26ab3-034b-4ee5-9cc2-8a348c9e3505 | signoff | HOLD POINT
14015f23-11ff-4afa-82b1-a3419ea8d469 | checkpoint | 1.2 - Mobilise Machinery & Fit For Purpose (FFP) Inspection
c2ff73b2-e738-5d1a-9e6d-9101327148ff | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Permit To Access (PTA), Land Access Rules (LARs),PRA
7433eff0-e0f8-558f-9d0d-51b5f1332545 | note | Frequency - Prior to Start
7a5ca575-7667-54d4-be97-64e5a894948d | note | Test Method - Review
a6e6081b-78af-5653-941f-1d8dd18b34d9 | note | Acceptance Criteria - Valid Weed Hygiene Certification for all vehicles and plant.
43686d98-c7f1-5b3d-8a02-adb981bc1003 | note | Verifying Documents - Weed Declaration Certificate. Appenate FFP Form
384406e7-4c4f-522f-95b8-ac770e0d5cdd | note | Responsibility: RSA - H
3b695acf-77a6-4737-a47d-e68fcb9d6f36 | signoff | HOLD POINT
ce338ea4-33bc-4d6f-85a7-78c789ce784a | checkpoint | 1.3 - Gravel Compliance
0a1ad606-b038-5556-80b4-0aeaabcc04fb | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specifications OPS-QLDS-CI-SPE-002: Section 6
f8d86f14-74f1-5536-aeb2-6108a3b35b85 | note | Frequency - Each Quarry
031fdcc9-f1b2-51be-b115-2c0d066098f9 | note | Test Method - Lab Testing
5b2253b4-1b0b-5dec-940a-080c78b59a52 | note | Acceptance Criteria - Type 2.2 Road Base
17ad3b6f-bdcc-5e5f-9bb8-6edd02326037 | note | Verifying Documents - NATA Test Report
27c71495-b714-5430-a705-1c21ce69ab37 | note | Responsibility: RSA - R
3ef68eb5-a0c0-49b1-a302-2943c3867445 | section | 2 - Entry Turnout
198d9030-b61f-415d-bd69-aa2769210256 | checkpoint | 2.1 - Set out Entry Turnout Dimensions and delineate clearance boundaries
1598cddc-d910-52d5-8d26-35bf223336a5 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Site Specific IFC Drawings
772f628c-5c5a-547c-ac36-a86cb6b5d6e4 | note | Frequency - Each Entry
8f84b9dc-aa18-5a7a-a79c-7802846a2d75 | note | Test Method - Visual Inspection, Set out by Licensed Surveyor
55fedaa5-d312-5a40-86bc-92f8c2e05243 | note | Acceptance Criteria - In accordance with IFC Drawing, Where no traffic lane or edge is marked on the road, the shoulder edge shall be interpreted as the intended traffic lane or edge lane.
44c371ca-da77-5281-8211-51438750eda3 | note | Verifying Documents - Entry Turnout FIC
df1f1b38-c1f8-5bb4-8a75-16fc6d55a0d3 | note | Responsibility: RSA - M
57633b63-4bb4-4162-95a0-4a6cb49c5bb3 | checkpoint | 2.2 - Clear & Grub
2329b8a3-ee65-5b61-bd8a-d6d5a5a5b91a | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specifications OPS-QLDS-CI-SPE-002: Section 3.2
55916c26-c32b-5a52-9d81-df000785216f | note | Frequency - Each Entry
41571961-8b4c-5f6e-8433-84aa30df90ab | note | Test Method - Visual Inspection
0109c1bb-e74d-5908-93c6-8153f47e7f9f | note | Acceptance Criteria - Cleared vegetation stockpiled at regular intervals, As Required on site
143247a3-617d-517a-a81f-b659f6ef37e6 | note | Verifying Documents - Entry Turnout FIC
39c886b6-6196-588f-8aea-c5b736f29996 | note | Responsibility: RSA - M
8698f89f-e1dd-43e5-b8e4-833b50cdd86a | checkpoint | 2.3 - Box Out if required
357254e0-ea17-5a0a-ae3f-cbd8f4ecf40b | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Site Specific IFC Drawings
2c9978f9-5bcc-5be5-9804-7f57444eb741 | note | Frequency - Each Entry
0c548ea5-9f2d-5fe5-a083-a5c6758045dd | note | Test Method - Visual Inspection
ce9821ec-b7d4-5b0b-abef-e43b7673fcef | note | Acceptance Criteria - As Required on site
4fb92cdf-5072-5b63-ae44-843fe6c5d2d0 | note | Verifying Documents - Entry Turnout FIC
73ecfdad-902f-5b52-9599-31f2209bc5a7 | note | Responsibility: RSA - M
560c6665-490b-4d08-a787-5d6639053452 | checkpoint | 2.4 - Install Invert Table Drain if required
d6c85272-35cd-5d46-82eb-cfdbaa0d3d2a | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Site Specific IFC Drawings
15eb4d01-a5f6-5554-a16c-99d755416927 | note | Frequency - Each Entry
f8ff29a5-07a1-5fcc-9ca0-a4609804fec3 | note | Test Method - Visual Inspection
82604f0d-a863-59bb-8d23-d1eb17e525d5 | note | Acceptance Criteria - Adequate darinage shall be provided to avoid water polling within the turnout area, Invert level at turnout to be such that flow in table drain is not restricted in any way. The lowest point of the new invert drain shall be the same as the lowest point of the existing table drain
be2950fa-dce2-5627-9a5f-61e1fd1a0102 | note | Verifying Documents - Entry Turnout FIC
c9aaa1d3-401a-5b4b-b4ee-fadb5ece3cef | note | Responsibility: RSA - M
75e2c547-cd52-4bf0-b995-8fba92da4ff5 | checkpoint | 2.5 - Gravel Cap Entry Pavement and trim
989ed885-f5f8-5b5c-8c20-004dd3f5a4d3 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Site Specific IFC Drawings
6f59b995-eebf-5ce1-bc22-996fca8f8533 | note | Frequency - Each Entry
6635e2ca-7d74-521c-9576-fedff27bf80f | note | Test Method - Visual Inspection
4616de4f-7055-58b5-888f-43e64d7ef385 | note | Acceptance Criteria - All new pavement layers shall be adequately compacted and have the minimum required thickness.
65ab2acc-25f9-5196-8bcc-5c6a5f388aa2 | note | Verifying Documents - Entry Turnout FIC
de6aefdd-063c-5ed4-a2bf-9372f9153c31 | note | Responsibility: RSA - H
61f72e1c-daa3-4bf9-8319-2696060e7643 | signoff | HOLD POINT
7bfa1a1b-4750-4af8-8324-73c0886868c7 | checkpoint | 2.6 - Install Bitumen Two Coat Seal - 14/10mm C170
7ea1a771-baeb-5452-bd6f-2dd4e10f111d | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Site Specific IFC Drawings
71ca08be-41c2-51f5-964e-b75dd4c2cf9f | note | Frequency - Each Entry
997aa73f-c098-50c5-a6ee-6a53f72f1f6b | note | Test Method - Visual Inspection
d018c500-f7f7-5fe3-9a2a-52bad5f2015e | note | Acceptance Criteria - Bitumen edge seal to be applied to ensure surface durability and continuity with existing road pavement.
3fcab38a-5a29-503d-ae6b-cbb1114b9e5b | note | Verifying Documents - Entry Turnout FIC
69f7d212-58e5-5704-a200-c623919d7455 | note | Responsibility: RSA - M
b0abac05-0437-4b3e-9e82-f2cd59dae07b | checkpoint | 2.7 - As Built Completed
715b2862-bf70-5415-a33c-123e83a78d0b | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - IFC Entry Turnouts gravel capping, Seal, Invert Table Drain, SOW
a7a04edf-e241-5b62-bbbf-6da6f383de4b | note | Frequency - Each Entry
8a88d045-d205-5f71-88ce-4b48cbc77736 | note | Test Method - As Built Measurement
1f151cce-48e5-5427-8515-3775c2d02846 | note | Acceptance Criteria - As built Entry Turnout Layout Drawing
8d74c099-7310-503d-8c45-366b48f2b298 | note | Verifying Documents - Entry Turnout FIC
54816a75-a09b-5736-8671-0f073b446281 | note | Responsibility: RSA - D
eac8a731-2aa7-454c-86bc-b07c6d9c2c92 | checkpoint | 2.8 - RSA QA inspection
5dd4fc61-b04e-51c9-adc4-730153394e7e | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specifications OPS-QLDS-CI-SPE-002: Section 7.1.2, Site Specific IFC Drawings
be93596e-77a0-5a66-b982-e647d886d2b0 | note | Frequency - Each Entry
3fd6cd29-89c3-5070-a97f-7d22cb9b754b | note | Test Method - Visual Inspection
d13f2418-9d7f-5d6f-a182-65c3a630a662 | note | Acceptance Criteria - RSA Supervisor to inspect and accept the works are complete.
793dd7ad-b360-527e-8eac-94a7e9ab0908 | note | Verifying Documents - Entry Turnout FIC
17750c22-a884-5906-9706-f1714a141efe | note | Responsibility: RSA - H
d2034f06-8973-430f-9de3-c03bce5d90dc | signoff | HOLD POINT
0d457569-ef35-4e60-9f13-50784bea8d0b | section | Reference Documents
6540a283-1649-48cd-a6ab-08a7eb23e1e5 | checkpoint-no-value | Reference Documents:
0aad34f1-a71c-5b8c-bef8-77fc8e706974 | note | SENEX-QLDS-EN-PRC-003 rev 1 (Queensland Erosion and Sediment Control Procedure)
a22b4e29-42d8-5085-8bac-bd7909e0eb9b | note | OPS-QLDS-CN-GDL-002 (Survey Peg Identification Guide)
78b1d46e-db9a-54bb-b2cc-a9f68c1ea0bc | note | OPS-QLDS-CS-DWG-011(Senex Standard Property Enrty/Exit Turnout Drawing)
9c26b796-82e1-5bdd-89a4-64f2b79697bc | note | R-004 & R-007 WDRC Council Road Turnout Dwgs
6d2eb744-da26-465e-8f67-ea55e700e13a | section | To be completed upon completion of all work activities
a6706e81-4e96-4ee6-9501-56b8ec93a19a | checkpoint | This is to confirm that the above ITP has been completely signed off. All necessary inspections have been completed, the verifying documents have been provided, and the works conform to the contract specification
723c0db6-9434-53eb-bdb8-1132046456b5 | note | Completed By:
40a5562f-df75-52b8-892a-2962a1321d14 | textbox | Contractor Representative - Name:
5f0dcbee-fe76-5e7f-a8e3-6b4e2d72d08f | textbox | Contractor Representative - Position:
2fe1a7ba-7c79-59e9-b11e-efb6ff7cfede | textbox | Senex Construction Representative - Name:
9d51eff6-d2d5-58d2-8938-b4bb82e7af94 | textbox | Senex Construction Representative - Position:
3f59c20d-a154-534a-bdbf-bf7105acc2bb | note | Approved By:
dc52b22c-5be6-54e3-ba76-85495bfc35ac | textbox | Client Representative - Name:
b59a54ec-98a6-50be-83f3-1b3991a7d93d | textbox | Client Representative - Position:
a55c976d-577a-558b-a9dd-5f7ccd5280d4 | date | Date:
4478a658-cc8c-4411-b122-324aede027e6 | signoff | Add Signature
6e0f74e3-b86b-4860-9c4a-0788402f5609 | checklist | RSA.WP20.FIC Entry Turnout |  | RSA.WP20.FIC Entry Turnout
1f58a6bc-29a6-4fe1-9a2c-6a9c568a97b4 | section | FIELD INSPECTION CHECKLIST ENTRY TURNOUT
c26ccd5e-89e9-4b92-b771-17ff53a81d2f | checkpoint | Set out Entry Turnout dimensions and Delineate Clearance Boundaries
e5b79a62-347a-4bd5-84fc-cdcb04183bd0 | checkpoint | Clear & Grub
a86b15e4-6e3f-4341-9d1d-92300b35ef8a | checkpoint | Box out if required
fe9a4094-0ef7-47f2-a4ee-0d6cf8cd36a1 | checkpoint | Install Invert Table Drain if required
d7ef4c0c-674e-486d-9740-14da27df8e5e | checkpoint | Gravel cap Entry Pavement
a492f774-4b93-4628-b2ea-ada716b755a1 | signoff | HOLD POINT
c162eb55-e6f6-45bd-a390-5006a7c25ce6 | checkpoint | Install Bitumen Two Coat Seal - 14/10mm C170
d6863c9f-00e4-455c-9b04-0f09be44bbed | checkpoint | As Built Completed
ddc3ad6c-2298-4440-9764-28e3a9722f1b | checkpoint | RSA QA Inspection
ad4429ab-30cf-44ec-a901-b895d62b2bfe | signoff | HOLD POINT