## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
6e0f74e3-b86b-4860-9c4a-0788402f5609 | checklist | RSA.WP20.FIC Entry Turnout |  | RSA.WP20.FIC Entry Turnout
1f58a6bc-29a6-4fe1-9a2c-6a9c568a97b4 | section | FIELD INSPECTION CHECKLIST ENTRY TURNOUT
c26ccd5e-89e9-4b92-b771-17ff53a81d2f | checkpoint | Set out Entry Turnout dimensions and Delineate Clearance Boundaries
| textbox | Applicable
| textbox | Not Applicable/Pre-existing
e5b79a62-347a-4bd5-84fc-cdcb04183bd0 | checkpoint | Clear & Grub
| textbox | Applicable
| textbox | Not Applicable/Pre-existing
a86b15e4-6e3f-4341-9d1d-92300b35ef8a | checkpoint | Box out if required
| textbox | Applicable
| textbox | Not Applicable/Pre-existing
fe9a4094-0ef7-47f2-a4ee-0d6cf8cd36a1 | checkpoint | Install Invert Table Drain if required
| textbox | Applicable
| textbox | Not Applicable/Pre-existing
d7ef4c0c-674e-486d-9740-14da27df8e5e | checkpoint | Gravel cap Entry Pavement
| textbox | Applicable
| textbox | Not Applicable/Pre-existing
a492f774-4b93-4628-b2ea-ada716b755a1 | signoff | HOLD POINT
c162eb55-e6f6-45bd-a390-5006a7c25ce6 | checkpoint | Install Bitumen Two Coat Seal - 14/10mm C170
| textbox | Applicable
| textbox | Not Applicable/Pre-existing
d6863c9f-00e4-455c-9b04-0f09be44bbed | checkpoint | As Built Completed
| textbox | Applicable
| textbox | Not Applicable/Pre-existing
ddc3ad6c-2298-4440-9764-28e3a9722f1b | checkpoint | RSA QA Inspection
| textbox | Applicable
| textbox | Not Applicable/Pre-existing
ad4429ab-30cf-44ec-a901-b895d62b2bfe | signoff | HOLD POINT