## Master List Templates
Id | Type | Name | Values | Prompting Name
6824d8e7-41a9-4dca-bef7-b072ac9b82c0 | checklist | RSA.WP28.FIC - ACCESS TRACK - Rev2.0 | itp | RSA.WP28.FIC - ACCESS TRACK
69387c76-6a81-4cd5-b6a1-5fb8b21f99b2 | section | FIELD INSPECTION CHECKLIST ACCESS TRACK
022fd95d-5237-41be-947f-5d65485e7d37 | checkpoint | CH and FDM clearance
ecd64d70-71b0-4c45-b19d-ef348573705d | signoff | HOLD POINT
fa656ecc-8a11-4fd3-8b48-e85d2de166a8 | checkpoint | Identify extent of work area, clearance boundaries and any required surveying works
9cd406a0-7916-4cf2-84aa-1cd3ef7f23f8 | checkpoint | Measure access road dimensions as per IFC
39d8127c-4df2-42da-8a43-20634c7914c7 | checkpoint | Clear & Grub
62d483f9-9717-459b-8507-3c390f3b7ae2 | checkpoint | Form track profile
9d0dbe2b-ba18-4b5d-9190-d8dc61793978 | checkpoint | Construct erosion and sediment controls
db5541c9-66d7-4b26-be35-507e91222438 | checkpoint | Construct water way barriers crossings
8ef879d7-2257-4f9d-8429-40efeb51cab3 | checkpoint | Gravel cap access track (if applicable)
d5e14f03-a3cf-4b9e-8d46-0b9588da4993 | checkpoint | As Built Completed
e5960946-98c8-450c-9374-3a9adb1efd53 | checkpoint | RSA QA Inspection
29102593-1758-4123-b5b7-25627eede0c1 | signoff | HOLD POINT
81ac979c-6389-4763-b9a5-182d12096eed | checklist | RSA.WP28.FIC - FENCING & GRIDS - Rev2.0 | itp | RSA.WP28.FIC - FENCING & GRIDS
fe3b6b3a-395c-4e1f-8cd6-8457c3d37cfd | section | FIELD INSPECTION CHECKLIST FENCING & GRIDS
c5e2fbfd-517c-47a7-8dd3-585197f53867 | checkpoint | CH & FDM Clearance
1d86cd3c-1c45-4588-b040-928cd6bc756d | signoff | HOLD POINT
91f45ff0-2a78-47a0-b18c-cc897ff200b9 | checkpoint | Identify Work Area, boundaries of Fencing
e43dae43-2af4-4f3f-a2ab-44e7d07ffb44 | checkpoint | Inspect fencing materials
83ff1169-bd15-4472-afda-be13ec4fa6fc | checkpoint | Installation of fencing
c399b626-d3e9-432e-bcb7-a2cef7acefed | checkpoint | Concrete for base of fencing
9050c22d-0cdb-4f8d-9d98-38e9efb6d067 | checkpoint | Fence posts caps
ec952728-95a9-4d3d-a797-3adfa2b5b196 | checkpoint | Welding
b242b80f-c61d-43c0-8377-a8fa2db5acbb | checkpoint | Welds Galvanized Painting
15c7992f-55d2-4ca0-84bb-369113072faa | checkpoint | Gate Chain and Carabiner clips
b187d229-1ef3-4c62-b0a7-f8af9f2b6f85 | checkpoint | Box Out Grid Footings and Prep Site
41b71f21-327e-4afc-98df-9bb78afd6bcc | checkpoint | Inspect grid materials
9a7e08f6-af83-4ec6-bee7-06a88c9d9d64 | checkpoint | Compaction for Grid base
1d1e0818-68eb-45c6-a7b3-bac784e6d73b | checkpoint | Concrete Abutment / Install Base Slab (if required)
0465663b-a0b6-4e62-8519-809113177a84 | checkpoint | Position and Install Grid
25579f57-9e69-48df-ba45-9be41f42cdda | checkpoint | Install and Compact Gravel Ramps
95318c65-425c-4f30-a7bf-e01cabbed195 | checkpoint | Attach Fence to Box Assembly
99485ed6-e7ff-4695-afb1-f454172a9332 | checkpoint | RSA QA inspection
6f4cfae8-0531-44f8-814c-049e6334ab2a | signoff | HOLD POINT
a2f28301-ad52-4600-adf7-85ceaf790734 | checklist | RSA.WP28.FIC - LEASE PADS - Rev2.0 | itp | RSA.WP28.FIC - LEASE PADS
f51fedc0-fa6b-44cd-8b0c-d780ffaae9f9 | section | FIELD INSPECTION CHECKLIST LEASE PADS
cb8b0a99-5fd0-425a-873d-86dc491fb502 | checkpoint | CH and FDM clearance
1e094529-19b3-411a-991b-ac1018ed126a | signoff | HOLD POINT
f6a6b65f-46f3-4688-ab37-57a92dfdcbaf | checkpoint | Identify work area, boundaries and survey requirement
8f18f6f6-44ad-42d2-92a1-800791b3005d | checkpoint | Clear & Grub Topsoil and stack timber
072d34b6-613b-42ce-ab8e-f599f3531cfc | checkpoint | Lease Entry Construction
ed51c11b-1006-4c98-afed-520a9534beee | checkpoint | Lease construction
a2365bd3-d844-4786-83a5-b0ac4ce0e38a | checkpoint | Compaction of layers in 300mm layers
bac5b8eb-e813-4801-b37f-1ea055a7e56a | checkpoint | Proof roll
4417cd67-86a5-4a89-864a-b89288a0154a | checkpoint | Verification of cross falls/laser set ups
d46dac32-34bb-4c41-8565-14db0cbb69cb | checkpoint | Final Trim
3b5097b0-2749-47cb-b951-529fd87b3445 | signoff | HOLD POINT
11e7a05b-3b5e-4256-b29f-fe3bdebdc116 | checkpoint | DCP Testing
09866dc9-38ea-445d-b786-c575f4420528 | signoff | WITNESS POINT
a14f9901-271b-47fa-9a7a-69026aa125c9 | checkpoint | Gravel Cap (as required)
b26012a9-9c09-4e9e-9c05-edecfd3751de | checkpoint | Install ESC
5ad1a4c9-4620-4f50-8b61-85c29a8338ca | checkpoint | Cellar Installation
7bd2a227-6be0-425a-9790-f512d0f7cc09 | checkpoint | Conductor Installation – Record plumb
366fb9b2-36ce-410c-b910-bf5811ebfcd2 | checkpoint | Conductor cemented in place
54f716c1-ada9-41ef-88aa-52dfd809f0ca | checkpoint | 4 x cattle panels to be installed
2e30158d-48d1-403f-8c98-fe7eb452d3db | checkpoint | Well signage and Pipeline entry mark completed
be858ad0-ac49-4b59-b219-f5d25fe7793e | checkpoint | As Built Completed
df28eb7c-e3c4-48ba-87b1-76f9672bb41e | checkpoint | RSA supervisor inspection
8bedfbdd-7ac2-42bd-9c27-ec20351f38ec | signoff | HOLD POINT
cf576cdc-3ae5-41af-bd9b-2d78c5d476d2 | checklist | RSA.WP28.FIC - PRELIMINARY - Rev2.0 | itp | RSA.WP28.FIC - PRELIMINARY
113ae58b-3e03-4a2d-941d-8b9bceb8d1a9 | section | FIELD INSPECTION CHECKLIST LEASE PADS
93e363bd-3c35-4235-9930-675bbefbd32d | checkpoint | Access documentation of relevant ATW, LARs/PTA, Cultural Heritage, Clearance Request
e9bc2d2f-7b2e-432f-aaa8-91b07b26a2cf | signoff | HOLD POINT
25c23025-b9a2-4229-9c53-72be2794cffb | checkpoint | Mobilisation of Machinery & Fit for Purpose inspection
141eb26d-6031-4789-9d7f-2588c2ddf3d1 | signoff | HOLD POINT
0fd53f78-656e-40d9-aed1-433c179fa64f | checkpoint | Gravel Compliance
db9e68e9-2210-4718-b706-26a3fef98fa7 | checklist | RSA.WP28.ITP | itp | RSA.WP28.ITP
3b25b908-a6c8-48de-bf4b-65181a189d03 | section | 1 - Preliminary
850f0d2d-e837-45e1-957a-2c0c2bea1604 | checkpoint | 1.1 - Access Documentation
71c2652f-7ab6-5b8e-afd5-0999f1ee4481 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Relevant ATW
97ae41d2-6732-56ca-9fb9-64ea2941a8d4 | note | ○ LARS / PTA
6a0359e9-cc47-5927-a9b2-ed9b4a787f82 | note | ○ Cultural Heritage Clearance Request (Works Notice)
d604ac57-73cc-5b5f-afb5-440d174be5f0 | note | Frequency - Prior to Start
a800cf7d-c606-50ae-bacc-65efa86b9387 | note | Test Method - Review
7ff3cadf-d9f2-57b3-9200-a0a6909f0805 | note | Acceptance Criteria - All documents in place and correct.
0150894b-d52f-5631-843d-2ee874db1a54 | note | Verifying Documents - LARS / PTA
75400374-4aef-59a7-9fd6-d101805f10b0 | note | ○ Landholder Notification
588b7862-2838-583b-a2aa-f3eb6a7f436c | note | ○ Weed Washdown Cert.
122e8c07-037c-5d44-9453-3f33288412e8 | note | ○ Species and Fauna Management
3d6d9a8f-a1d6-5ee0-aae3-5ed7ff8a237e | note | ○ Cultural Heritage Induction Attendance Register
a1557186-6986-583d-a255-dee2bc65ba71 | note | ○ Cultural Heritage Clearance Report / Form
d8dd3f3b-5552-5f65-bc70-2b66681032fd | note | Responsibility: RSA - H
9a85cf4c-a1e4-584a-8f63-bf382649b517 | note | Responsibility: Senex - H
6714bc34-c61a-4e96-88cc-4323e4cde7a5 | signoff | HOLD POINT
19b16ff4-7eef-4840-a386-028e5d20bc96 | checkpoint | 1.2 - Mobilise Machinery & Fit For Purpose (FFP) Inspection
381c782b-00ca-5ca8-9c5c-4382d4c9d6bf | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Permit To Access (PTA), Land Access Rules (LARs), and Construction Management Plan (CMP)
065bd560-768b-5cb9-841d-a84d4043fa81 | note | Frequency - Prior to Start
18f47546-90e5-54e6-af8e-d3c69fcdfa8a | note | Test Method - Review
eae80768-863c-5915-beb3-671f35b3d196 | note | Acceptance Criteria - Valid Weed Hygiene Certification for all vehicles and plant.
211967ee-ba0d-541b-9ee4-03158a196dd9 | note | Verifying Documents - Weed Declaration Certificate.
e12e18f0-78ca-51f0-89c9-a93ce4c77fff | note | ○ Appenate FFP Form
8c4945ca-d2cf-5cf6-8a42-87bae3f60b96 | note | Responsibility: RSA - H
4dd3db65-480c-5365-9730-f2b736ccec03 | note | Responsibility: Senex - W
a6fba66c-3e3c-4f01-9799-288ac753c774 | signoff | HOLD POINT
8229142c-0706-4362-9241-0bd14005ecc6 | checkpoint | 1.3 - Gravel Compliance
385afd1d-df84-575e-af4f-af410405c9fc | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specifications OPS-QLDS-CI-SPE-002: Section 6
c76360b0-71ba-5e28-8c3b-538f04689c68 | note | Frequency - Each Quarry
e2bc2527-6b8a-5ab2-810b-f252894cae43 | note | Test Method - Lab Testing
ed741200-ce4a-5f2b-9775-8b07097075b0 | note | Acceptance Criteria - Grading C
2e089bff-de73-5253-91c0-d9b81a026d66 | note | Verifying Documents - NATA Test Report
bb87964a-eb52-58e6-b550-0871125d05a3 | note | Responsibility: RSA - R
9af022e6-a69e-5ac8-8524-c5679a55f3f0 | note | Responsibility: Senex - W
9a667e0f-dc3b-424b-83b1-8497bcd09dbb | section | 2 - Access Tracks
a3291f52-3917-4123-8864-3e08c9e1a4dc | checkpoint | 2.1 - RSA QA inspection
42cb65bf-b111-5a54-9e12-d023367d0056 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specifications OPS-QLDS-CI-SPE-002: Section 7.1.2
a5fb43a7-60e2-59a2-80fd-7de67421d4d0 | note | Frequency - Each Track
f0e6481a-cf1b-569d-9463-a83cd1da767b | note | Test Method - Visual Inspection
9121480d-2407-559a-8bf1-b9c9f13ddd01 | note | Acceptance Criteria - RSA Supervisor to inspect and accept the works are complete.
32c2b27f-7e05-59f6-bcc3-17253cec4dee | note | Verifying Documents - Access Track FIC
22ce588f-7126-50c2-a198-7dfb5d8d4ada | note | Responsibility: RSA - H
346b5b1d-0537-5430-a530-106858ac772d | note | Responsibility: Senex - N/A
b2cc6697-593d-4085-9e7e-1956e09bf93d | signoff | HOLD POINT
f479ab23-723e-4f5e-819a-15ef56e38d9e | checkpoint | 2.2 - Client Signoff
4219a84c-6515-54e9-807a-b7eaf042211b | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specifications OPS-QLDS-CI-SPE-002: Section 7.1.2
aa1e469f-600a-50f3-a12e-d67ea71254c7 | note | Frequency - Each Track
7bacc9ff-be70-5434-9243-1d327a5c1360 | note | Test Method - Visual Inspection
27ce9cd6-7a35-5aff-adfc-4fa7f95b1d6d | note | Acceptance Criteria - Senex Civil Supervisor to inspect and approve access road is fit for purpose prior to machinery being demobilised.
662a3ebc-87f1-5885-a949-fe8da499983d | note | Verifying Documents - Access Track FIC
6a7fb81d-d50b-5272-9319-b6206065559f | note | Responsibility: RSA - N/A
9cd8c4d0-ca51-5faf-bf9a-d14173d90998 | note | Responsibility: Senex - H
48512afa-dd59-43da-bd3d-2b72143fd68a | signoff | HOLD POINT
0f3e0f6b-895d-48d6-9211-041617e0cb24 | section | 3 - In Field, Property Fencing and Grid (Fencing)
6338b478-60e3-4d55-9bd2-e1ca0fa199a8 | checkpoint | 3.1 - RSA QA inspection
56315118-5a29-5e84-9bd2-88ef1f7c930d | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-003 REV 0: Section 4
9eee845a-5b64-5c36-8f4d-d3f5a3fa2d30 | note | Frequency - Each Grid
28d75ef2-bf0a-51f2-97d2-caec73f52535 | note | Test Method - Visual Inspection
709f73e5-5ed6-5bfa-8f9c-0754c64a268f | note | Acceptance Criteria - RSA Supervisor to inspect and accept the works are complete.
eae51c37-ff80-5163-8230-41d1557a0c2b | note | Verifying Documents - Grid &Fence Installation FIC
b596122e-8d39-5884-9a03-f1a684141ed7 | note | Responsibility: RSA - H
ee404a61-27a2-5ef5-8b4e-521351410070 | note | Responsibility: Senex - N/A
73b830a9-79f6-4513-960f-e638094163fb | signoff | HOLD POINT
a16c5e69-7d9e-43bd-b97c-01bbbe101c85 | checkpoint | 3.2 - Client Signoff
6a7cf3e6-3ed5-5c55-8705-dc44201f45e8 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - OPS-QLDS-CI-SPE-003 REV 0: Section 4
13d3f1b0-c976-5230-b04a-ed0f42cc97aa | note | Frequency - Each Grid
f21911c7-8756-5f97-bb7a-bb894e684879 | note | Test Method - Visual Inspection
5f43cbe5-5342-5944-b9b2-e4319ba05cc1 | note | Acceptance Criteria - Senex Civil Supervisor to inspect and approve Grid is fit for purpose prior to machinery being demobilised.
a33a9079-484e-5a64-bd18-766210d3da69 | note | Verifying Documents - Grid &Fence Installation FIC
ac71f739-5a26-5541-a671-d593c1b00c23 | note | Responsibility: RSA - N/A
3e74f123-d7fc-5b78-a196-3be2f982dd2b | note | Responsibility: Senex - H
8aaf4bb8-1163-4b9b-bae2-183bded972b4 | signoff | HOLD POINT
0f33aece-7d30-4cd1-b16f-902899fdc216 | section | 4 - Lease Pads
d0aa8a66-adb2-4dd7-9eba-be0da54aeef1 | checkpoint | 4.1 - RSA Supervispr inspection
4ee7d60d-e2c5-59f0-8e3b-05c4ca55c924 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - SENEX-QLDS-DR-SPE-001 & OPS-QLDS-CI-SPE-002
00575f72-aa66-5277-8117-554ee62e5478 | note | Frequency - Each Pad
f5f49b26-7082-5a7a-b866-42e9036127f8 | note | Test Method - Visual Inspection
d24190e2-c105-531d-b793-bb998067e882 | note | Acceptance Criteria - RSA Supervisor to inspect and accept the works are complete.
4f395cd1-bfb3-5d4c-befc-daf2a66a69c0 | note | Verifying Documents - Lease Pad FIC
756f6fdc-b986-53af-8bb1-d3ecea6f6ad4 | note | Responsibility: RSA - H
cdd81c8b-ced8-5dd7-b1c0-d50eb79d9493 | note | Responsibility: Senex - N/A
2b320a1c-8a4b-4c86-bbc6-b9667ad8fd31 | signoff | HOLD POINT
0c74c43e-afea-40e4-8428-5e1f82948ea1 | checkpoint | 4.2 - Client Signoff
88adf751-88f7-5499-a75a-2e36121818e2 | note | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - SENEX-QLDS-DR-SPE-001 &OPS-QLDS-CI-SPE-002
faa9f5ef-0a27-50d6-8cc9-215865a2dacc | note | Frequency - Each Pad
1a19e18e-9b90-5df5-a56a-7deac1e079ea | note | Test Method - Visual Inspection
54502229-c3d2-5db9-8c46-4e8887db476f | note | Acceptance Criteria - Senex Civil Supervisor to inspect and approve Grid is fit for purpose prior to machinery being demobilised.
945a166e-e965-5f6b-a45e-79ff36c32594 | note | Verifying Documents - Lease Pad FIC
2505f2c3-85cf-54a4-9d71-58b8af01ee35 | note | Responsibility: RSA - N/A
9e8deef2-a7a5-520b-b5f8-be931d629273 | note | Responsibility: Senex - H
3c4a1e69-50c3-46aa-b2e6-419eb29659ac | signoff | HOLD POINT
2f0e9f06-b599-40c2-a349-b81952e15585 | section | Reference Documents
cd4bac6c-b1fe-408a-9f3c-40a6ca6ee8b2 | checkpoint-no-value | Reference Documents:
3ee55128-e638-55c7-9e0a-edd08bd54646 | note | SENEX-QLDS-EN-PRC-003 rev 1 (Queensland Erosion and Sediment Control Procedure)
f5931ffb-1737-5e76-ba25-8703364e0121 | note | OPS-QLDS-CI-SPE-003 REV 0 (Fencing, Grids and Gateways Civil Specification)
bbfb6c57-357c-50a4-a756-77ed7aac2e62 | note | OPS-QLDS-CI-SPE-002 Rev 0 (Lease Pads, Hardstands, Access Roads Civil Specification)
7df7496a-a078-50fd-8964-3bf189030bfb | note | OPS-QLDS-CN-GDL-002 (Survey Peg Identification Guide)
1cc94b81-18d8-5fc7-af30-e21707fbd93e | note | SENEX-QLDS-CI-GDL-001 Rev D (Whoa-Boy Construction Guidelines)
1871146a-0de5-5b5d-bd4f-3e2b4a5af22c | note | SENEX-QLDS-DR-SPE-001 Rev 4 (Conductor and Cellar Installation Specification)
e0800e5c-727d-5637-8ad4-114f4d2cce0d | note | OPS-QLDS-CN-GDL-002 (Survey Peg Identification Guide)
587ac5ea-06b4-57ce-8c29-1d7eb5192a15 | note | OPS-QLDS-CI-GAR-001 Rev 1A (Well Lease Layout Standard Drill Rig Civil General Arrangement)
7ec76482-c08a-457a-a805-27986355c9d2 | section | To be completed upon completion of all work activities
cf62cb0b-e4c6-4298-b0e1-4d0e8730e64f | checkpoint | This is to confirm that the above ITP has been completely signed off. All necessary inspections have been completed, the verifying documents have been provided, and the works conform to the contract specification
5f584e7a-a84f-53b7-909c-18ae703aa8c5 | note | Completed By:
8ad45b02-c269-529a-bcc1-de4a886cdb7f | textbox | Contractor Representative - Name:
32a5bead-bd3e-5e5a-825c-2b50efd28c74 | textbox | Contractor Representative - Position:
179cf659-e8c0-5fdc-adf7-3575bd95f808 | textbox | Senex Construction Representative - Name:
2b59d25d-8fe3-5658-9beb-6456c0232a50 | textbox | Senex Construction Representative - Position:
b559f123-c776-59b3-9f83-bccacbc9cc0f | note | Approved By:
282912a7-00bb-5ab8-9f41-44fcb38d7107 | textbox | Client Representative - Name:
5c80d40c-d465-54ca-b9d0-8291c6abb015 | textbox | Client Representative - Position:
db995536-f190-5a12-a959-de32801538fd | date | Date:
96a60e51-6445-4c84-b9e5-dceb1db5722f | signoff | Add Signature