## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | RSA.WP52A.FIC - Access Track
section | FIELD INSPECTION CHECKLIST ACCESS TRACK
checkpoint | CH and FDM clearance
holdpoint | HOLD POINT
checkpoint | Identify extent of work area, clearance boundaries and any required surveying works
checkpoint | Confirm Dimensions
checkpoint | Clear & Grub
checkpoint | Form track profile
checkpoint | Construct erosion and sediment controls
checkpoint | Construct water way barriers crossings and Gullies
checkpoint | Gravel cap access track (if applicable)
checkpoint | As Built Completed
checkpoint | RSA QA Inspection
holdpoint | HOLD POINT
checklist | RSA.WP52A.FIC - Grids and Fencing
section | FIELD INSPECTION CHECKLIST FENCING & GRIDS
checkpoint | CH & FDM Clearance
holdpoint | HOLD POINT
checkpoint | Identify Work Area, boundaries of Fencing
checkpoint | Inspect fencing materials
checkpoint | Installation of fencing
checkpoint | Concrete for base of fencing
checkpoint | Fence posts caps
checkpoint | Welding
checkpoint | Galvanized Painting at Welds
checkpoint | Gate Chain and Carabiner Clips
checkpoint | Box Out Grid Footings and Prep Site
checkpoint | Inspect grid materials
checkpoint | Compaction for Grid base
checkpoint | Concrete Abutment / Install Base Slab (if required)
checkpoint | Position and Install Grid
checkpoint | Install and Compact Gravel Ramps
checkpoint | Attach Grid Wings to the Grid
checkpoint | RSA QA inspection
holdpoint | HOLD POINT
checklist | RSA.WP52A.FIC - Lease Pad
section | FIELD INSPECTION CHECKLIST LEASE PADS
checkpoint | CH and FDM clearance
holdpoint | HOLD POINT
checkpoint | Identify work area, boundaries and survey requirement
checkpoint | Evenly spread DAP fertilizer onto the topsoil prior to stripping
checkpoint | Clear & Grub Topsoil and stack timber
checkpoint | Lease Entry Construction
checkpoint | Lease construction
checkpoint | Compaction of layers in 300mm layers
checkpoint | Proof roll
checkpoint | Verification of cross falls/laser set ups
checkpoint | Final Trim
holdpoint | HOLD POINT
checkpoint | DCP Testing
checkpoint | Gravel Cap (as required)
checkpoint | Install ESC
checkpoint | Cellar Installation
checkpoint | Conductor Installation – Record plumb
checkpoint | Conductor cemented in place
checkpoint | 4 x cattle panels to be installed
checkpoint | Well signage and Pipeline entry mark completed
checkpoint | As Built Completed
checkpoint | RSA supervisor inspection
holdpoint | HOLD POINT
checklist | RSA.WP52A.FIC - Preliminary
section | FIELD INSPECTION CHECKLIST PRELIMINARY
checkpoint | Access documentation of relevant ATW, LARs/PTA, Cultural Heritage, Clearance Request
holdpoint | HOLD POINT
checkpoint | Mobilisation of Machinery & Fit for Purpose inspection
holdpoint | HOLD POINT
checkpoint | Gravel Compliance