## Project Breakdown
LTU Bundoora Smoke Seal |  |  | Checklists
QA / ITP's
Fire Seal
|  | North Level 1 | smoke seal
|  | North Level 2 | smoke seal
|  | North Level 3 | smoke seal
|  | North Level 4 | smoke seal
South
|  | South Level 1 | smoke seal
|  | South Level 2 | smoke seal
|  | South Level 3 | smoke seal
|  | South Level 4 | smoke seal
East
|  | East Level 1 | smoke seal
|  | East Level 2 | smoke seal
|  | East Level 3 | smoke seal
|  | East Level 4 | smoke seal
West
|  | West Level 1 | smoke seal
|  | West Level 2 | smoke seal
|  | West Level 3 | smoke seal
|  | West Level 4 | smoke seal

## Example Project Area
checklist | smoke seal
section | Material Inspection
checkpoint | 90 degree 2mm Aluminium Angle
checkpoint | waferhead screw
checkpoint | Bostik Fireban
section | Installation
checkpoint | Flashing mechanically fixed with Waferhead Screw
checkpoint | Fireban One caulking applied with continuous bead, no gaps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative: