## Sheet1
Unsuitable material below the level of the sub-grade in an excavation is: (a) removed and run to spoil in accordance with section 12.1–Spoil of LCC Specifications; (b) replaced with select backfill in accordance with section 8.3–Selected gravel fill or selected backfill of LCC specifications; (c) compacted to 95 percent relative dry density standard compaction | Visual | Check Item | Unsuitable material below the level of the sub-grade in an excavation is: (a) removed and run to spoil in accordance with section 12.1–Spoil of LCC Specifications; (b) replaced with select backfill in accordance with section 8.3–Selected gravel fill or selected backfill of LCC specifications; (c) compacted to 95 percent relative dry density standard compaction | Acceptance Criteria and Frequency (Project Specific) - Visual | Check Item - Check Item | Reference - LCC Specification No 1 Cl 9.3 | Unsuitable material below the level of the sub-grade in an excavation is: (a) removed and run to spoil in accordance with section 12.1–Spoil of LCC Specifications; (b) replaced with select backfill in accordance with section 8.3–Selected gravel fill or selected backfill of LCC specifications; (c) compacted to 95 percent relative dry density standard compaction
|  | LCC Specification No 1 Cl 9.3 |  |  |  |  | Acceptance Criteria and Frequency (Project Specific) - Visual
Surplus material which is run to spoil is: (a) not loosely tipped over the side of an embankment; (b) neatly spread adjacent to the work; or (c) used to uniformly flatten the slope of an embankment | Visual | Check Item | Surplus material which is run to spoil is: (a) not loosely tipped over the side of an embankment; (b) neatly spread adjacent to the work; or (c) used to uniformly flatten the slope of an embankment | Acceptance Criteria and Frequency (Project Specific) - Visual | Check Item - Check Item | Reference - LCC Specification No 1 Cl 12.1.1 | Check Item - Check Item
|  | LCC Specification No 1 Cl 12.1.1 |  |  |  |  | Reference - LCC Specification No 1 Cl 9.3
Spoil which is spread on the site is: (a) compacted as specified in this standard specification; (b) left in a neat, tidy and self draining condition with a slope of not flatter than 1 in 100 unless otherwise shown in the approved drawings. | Visual | Check Item | Spoil which is spread on the site is: (a) compacted as specified in this standard specification; (b) left in a neat, tidy and self draining condition with a slope of not flatter than 1 in 100 unless otherwise shown in the approved drawings. | Acceptance Criteria and Frequency (Project Specific) - Visual | Check Item - Check Item | Reference - LCC Specification No 1 Cl 12.1.2 | Surplus material which is run to spoil is: (a) not loosely tipped over the side of an embankment; (b) neatly spread adjacent to the work; or (c) used to uniformly flatten the slope of an embankment
|  | LCC Specification No 1 Cl 12.1.2 |  |  |  |  | Acceptance Criteria and Frequency (Project Specific) - Visual
Rock and other material is removed from the site which is: (a) surplus to the requirements of the job; (b) unsuitable for disposal on the site. | Visual | Check Item | Rock and other material is removed from the site which is: (a) surplus to the requirements of the job; (b) unsuitable for disposal on the site. | Acceptance Criteria and Frequency (Project Specific) - Visual | Check Item - Check Item | Reference - LCC Specification No 1 Cl 12.1.3 | Check Item - Check Item
|  | LCC Specification No 1 Cl 12.1.3 |  |  |  |  | Reference - LCC Specification No 1 Cl 12.1.1
Spoil which is spread on the site is: (a) compacted as specified in this standard specification; (b) left in a neat, tidy and self draining condition with a slope of not flatter than 1 in 100 unless otherwise shown in the approved drawings.
Acceptance Criteria and Frequency (Project Specific) - Visual
Check Item - Check Item
Reference - LCC Specification No 1 Cl 12.1.2
Rock and other material is removed from the site which is: (a) surplus to the requirements of the job; (b) unsuitable for disposal on the site.
Acceptance Criteria and Frequency (Project Specific) - Visual
Check Item - Check Item
Reference - LCC Specification No 1 Cl 12.1.3