## Sheet1
1.1 | Surface texture measurement (1) | NZTA P03 | NZTA P03 | NZTA P03 (First Coat seal) and P 04 is client provided designs | As per NZTA P03 | Sandcircle Measurement, or Laser Texture, or Principals HSD | H | — | Tabulated worksheet | 1.1 - Surface texture measurement (1) | Applicable Standard CHAR(AMP) Acceptance Criteria (NZTA- Template) - NZTA P03 | Applicable Standard CHAR(AMP) Acceptance Criteria (Higgins) - NZTA P03 | Higgins (Comment) - NZTA P03 (First Coat seal) and P 04 is client provided designs | Frequency - As per NZTA P03 | Criteria Notes - Sandcircle Measurement, or Laser Texture, or Principals HSD | Contractor - H | Principals Rep - — | Records CHAR(AMP) Remarks - Tabulated worksheet | 1.1 - Surface texture measurement (1)
1.1 | Surface texture measurement (2) | NZTA P04 | NZTA P17 4.3 Surface Texture | NZTA is contractor supplied | As per NZTA P17 | Sandcircle Measurement, or Laser Texture, or Principals HSD | H | — | Tabulated worksheet | 1.1 - Surface texture measurement (2) | Applicable Standard CHAR(AMP) Acceptance Criteria (NZTA- Template) - NZTA P04 | Applicable Standard CHAR(AMP) Acceptance Criteria (Higgins) - NZTA P17 4.3 Surface Texture | Higgins (Comment) - NZTA is contractor supplied | Frequency - As per NZTA P17 | Criteria Notes - Sandcircle Measurement, or Laser Texture, or Principals HSD | Contractor - H | Principals Rep - — | Records CHAR(AMP) Remarks - Tabulated worksheet | Applicable Standard CHAR(AMP) Acceptance Criteria (NZTA- Template) - NZTA P03
1.2 | Treatment selection confirmed | — | — | — | Pre site works | Principal agreed treatment selection | H | — | Records of Contractors Design | 1.2 - Treatment selection confirmed | Applicable Standard CHAR(AMP) Acceptance Criteria (NZTA- Template) - — | Applicable Standard CHAR(AMP) Acceptance Criteria (Higgins) - — | Higgins (Comment) - — | Frequency - Pre site works | Criteria Notes - Principal agreed treatment selection | Contractor - H | Principals Rep - — | Records CHAR(AMP) Remarks - Records of Contractors Design | Applicable Standard CHAR(AMP) Acceptance Criteria (Higgins) - NZTA P03
1.3 | Chip skid performance | NZTA T10 | NZTA T10 | — | Pre site works | Aggregate Peformance Report submitted CHAR(AMP) accepted by Principal. | H | — | Included in chipseal design report | 1.3 - Chip skid performance | Applicable Standard CHAR(AMP) Acceptance Criteria (NZTA- Template) - NZTA T10 | Applicable Standard CHAR(AMP) Acceptance Criteria (Higgins) - NZTA T10 | Higgins (Comment) - — | Frequency - Pre site works | Criteria Notes - Aggregate Peformance Report submitted CHAR(AMP) accepted by Principal. | Contractor - H | Principals Rep - — | Records CHAR(AMP) Remarks - Included in chipseal design report | Higgins (Comment) - NZTA P03 (First Coat seal) and P 04 is client provided designs
1.4 | Chipseal Design | NZTA P18 | NZTA P17 | NZTA P18 is principal designed | Pre site works | Design meets contractual requirements | H | — | Seal design provided to principal | 1.4 - Chipseal Design | Applicable Standard CHAR(AMP) Acceptance Criteria (NZTA- Template) - NZTA P18 | Applicable Standard CHAR(AMP) Acceptance Criteria (Higgins) - NZTA P17 | Higgins (Comment) - NZTA P18 is principal designed | Frequency - Pre site works | Criteria Notes - Design meets contractual requirements | Contractor - H | Principals Rep - — | Records CHAR(AMP) Remarks - Seal design provided to principal | Frequency - As per NZTA P03
1.5 | Multilayer compatibility | NZTA P18 Fig 1 | Chip seal NZ | NZTA P18 is principal designed | 1 per design | Both ALD results identified on graph | — | W | Included in chipseal design report | 1.5 - Multilayer compatibility | Applicable Standard CHAR(AMP) Acceptance Criteria (NZTA- Template) - NZTA P18 Fig 1 | Applicable Standard CHAR(AMP) Acceptance Criteria (Higgins) - Chip seal NZ | Higgins (Comment) - NZTA P18 is principal designed | Frequency - 1 per design | Criteria Notes - Both ALD results identified on graph | Contractor - — | Principals Rep - W | Records CHAR(AMP) Remarks - Included in chipseal design report | Criteria Notes - Sandcircle Measurement, or Laser Texture, or Principals HSD
1.6 | Renewal Quality Plan | — | — | — | One overarching for all reseal sites | RQP Approved | H | — | Principal approval signature | 1.6 - Renewal Quality Plan | Applicable Standard CHAR(AMP) Acceptance Criteria (NZTA- Template) - — | Applicable Standard CHAR(AMP) Acceptance Criteria (Higgins) - — | Higgins (Comment) - — | Frequency - One overarching for all reseal sites | Criteria Notes - RQP Approved | Contractor - H | Principals Rep - — | Records CHAR(AMP) Remarks - Principal approval signature | Contractor - H
| HP – Chipseal design verified for site commencement | — | — | — | — | Contractor checklist copied to Principal | — | W | Pre-commencement checklist signed and filed | - HP – Chipseal design verified for site commencement | Applicable Standard CHAR(AMP) Acceptance Criteria (NZTA- Template) - — | Applicable Standard CHAR(AMP) Acceptance Criteria (Higgins) - — | Higgins (Comment) - — | Frequency - — | Criteria Notes - Contractor checklist copied to Principal | Contractor - — | Principals Rep - W | Records CHAR(AMP) Remarks - Pre-commencement checklist signed and filed | Principals Rep - —
2.1 | Bitumen compliance | NZTA M02, P03, P04 | NZTA M1 | Currently all seal is completed with Cut Back Bitumen as per M01 | 1 test certificate per bulk shipment | Lab Test Report | — | W | Property Test, NZTA M01 | 2.1 - Bitumen compliance | Applicable Standard CHAR(AMP) Acceptance Criteria (NZTA- Template) - NZTA M02, P03, P04 | Applicable Standard CHAR(AMP) Acceptance Criteria (Higgins) - NZTA M1 | Higgins (Comment) - Currently all seal is completed with Cut Back Bitumen as per M01 | Frequency - 1 test certificate per bulk shipment | Criteria Notes - Lab Test Report | Contractor - — | Principals Rep - W | Records CHAR(AMP) Remarks - Property Test, NZTA M01 | Records CHAR(AMP) Remarks - Tabulated worksheet
2.2 | Chip source property compliance | NZTA M06 | NZTA M06 | same | Annually for each source | Lab test results | — | W | Source property checklist: PSV, CR, WR | 2.2 - Chip source property compliance | Applicable Standard CHAR(AMP) Acceptance Criteria (NZTA- Template) - NZTA M06 | Applicable Standard CHAR(AMP) Acceptance Criteria (Higgins) - NZTA M06 | Higgins (Comment) - same | Frequency - Annually for each source | Criteria Notes - Lab test results | Contractor - — | Principals Rep - W | Records CHAR(AMP) Remarks - Source property checklist: PSV, CR, WR | 1.1 - Surface texture measurement (2)
2.3 | Chip production property compliance (Quarry or stockpile, dependent on where on site materials is coming from) | NZTA M06, P18 | NZTA M06, | same | CHAR(LESS) 100m3, minimum 1 sample 100 - 500m3, minimum 2 samples >500m3, minimum 3 samples | Lab test results | — | W | Cleanness (Grades 2 – 6); Sealing chip size CHAR(AMP) shape; Broken faces (if reqd); PSD | 2.3 - Chip production property compliance (Quarry or stockpile, dependent on where on site materials is coming from) | Applicable Standard CHAR(AMP) Acceptance Criteria (NZTA- Template) - NZTA M06, P18 | Applicable Standard CHAR(AMP) Acceptance Criteria (Higgins) - NZTA M06, | Higgins (Comment) - same | Frequency - CHAR(LESS) 100m3, minimum 1 sample 100 - 500m3, minimum 2 samples >500m3, minimum 3 samples | Criteria Notes - Lab test results | Contractor - — | Principals Rep - W | Records CHAR(AMP) Remarks - Cleanness (Grades 2 – 6); Sealing chip size CHAR(AMP) shape; Broken faces (if reqd); PSD | Applicable Standard CHAR(AMP) Acceptance Criteria (NZTA- Template) - NZTA P04
| HP – Material compliance confirmed (binder, source CHAR(AMP) production properties) | — | — | — | — | Material compliance checklist copied to Principal | — | W | Material compliance checklist signed CHAR(AMP) filed | - HP – Material compliance confirmed (binder, source CHAR(AMP) production properties) | Applicable Standard CHAR(AMP) Acceptance Criteria (NZTA- Template) - — | Applicable Standard CHAR(AMP) Acceptance Criteria (Higgins) - — | Higgins (Comment) - — | Frequency - — | Criteria Notes - Material compliance checklist copied to Principal | Contractor - — | Principals Rep - W | Records CHAR(AMP) Remarks - Material compliance checklist signed CHAR(AMP) filed | Applicable Standard CHAR(AMP) Acceptance Criteria (Higgins) - NZTA P17 4.3 Surface Texture
3.1 | Pre-Seal Site Checklist (week prior) | Confirming site is ready for sealing | Confirming site is ready for sealing | same | Following ALL pre seal works | — | — | H | Inspection Notes (Standard Form)Include Photographic Evidence and add in the Site Records | 3.1 - Pre-Seal Site Checklist (week prior) | Applicable Standard CHAR(AMP) Acceptance Criteria (NZTA- Template) - Confirming site is ready for sealing | Applicable Standard CHAR(AMP) Acceptance Criteria (Higgins) - Confirming site is ready for sealing | Higgins (Comment) - same | Frequency - Following ALL pre seal works | Criteria Notes - — | Contractor - — | Principals Rep - H | Records CHAR(AMP) Remarks - Inspection Notes (Standard Form)Include Photographic Evidence and add in the Site Records | Higgins (Comment) - NZTA is contractor supplied
3.2 | Bitumen Distributor | BPG 02 | E2 | Bitumen Distributor is certified under NZTA E2 | Annually | Speed Test, Dipstick Test, Distribution (Pad)Test | — | W | E2 Certificate | 3.2 - Bitumen Distributor | Applicable Standard CHAR(AMP) Acceptance Criteria (NZTA- Template) - BPG 02 | Applicable Standard CHAR(AMP) Acceptance Criteria (Higgins) - E2 | Higgins (Comment) - Bitumen Distributor is certified under NZTA E2 | Frequency - Annually | Criteria Notes - Speed Test, Dipstick Test, Distribution (Pad)Test | Contractor - — | Principals Rep - W | Records CHAR(AMP) Remarks - E2 Certificate | Frequency - As per NZTA P17
3.3 | Go/No Go Checklist | Weather, readiness of materials and plant, air temperature, pavement temperature, et al | Weather, readiness of materials and plant, air temperature, pavement temperature, et al | same | Prior to sealing on each site | Visual on site and check list sign off | — | H | Pre-commencement checklist (ie pre-start reqs, by foreman/crew manager) | 3.3 - Go/No Go Checklist | Applicable Standard CHAR(AMP) Acceptance Criteria (NZTA- Template) - Weather, readiness of materials and plant, air temperature, pavement temperature, et al | Applicable Standard CHAR(AMP) Acceptance Criteria (Higgins) - Weather, readiness of materials and plant, air temperature, pavement temperature, et al | Higgins (Comment) - same | Frequency - Prior to sealing on each site | Criteria Notes - Visual on site and check list sign off | Contractor - — | Principals Rep - H | Records CHAR(AMP) Remarks - Pre-commencement checklist (ie pre-start reqs, by foreman/crew manager) | Criteria Notes - Sandcircle Measurement, or Laser Texture, or Principals HSD
3.4 | Spraying – site measurements | NZTA P03, P04 | NZTA P17 | — | Per Site | Application rates within design CHAR(AMP) tolerances + or - 5% | — | — | Spray sheet | 3.4 - Spraying – site measurements | Applicable Standard CHAR(AMP) Acceptance Criteria (NZTA- Template) - NZTA P03, P04 | Applicable Standard CHAR(AMP) Acceptance Criteria (Higgins) - NZTA P17 | Higgins (Comment) - — | Frequency - Per Site | Criteria Notes - Application rates within design CHAR(AMP) tolerances + or - 5% | Contractor - — | Principals Rep - — | Records CHAR(AMP) Remarks - Spray sheet | Contractor - H
3.5 | Geotextile reinforced seals (GRS ) | As per P18 CHAR(AMP) specific design requirements | As per specific design requirements and P17 | — | Per Site | Accurate RP start/end location CHAR(AMP) offset Application rates within design CHAR(AMP) tolerances + or - 5% | — | — | Spray sheet | 3.5 - Geotextile reinforced seals (GRS ) | Applicable Standard CHAR(AMP) Acceptance Criteria (NZTA- Template) - As per P18 CHAR(AMP) specific design requirements | Applicable Standard CHAR(AMP) Acceptance Criteria (Higgins) - As per specific design requirements and P17 | Higgins (Comment) - — | Frequency - Per Site | Criteria Notes - Accurate RP start/end location CHAR(AMP) offset Application rates within design CHAR(AMP) tolerances + or - 5% | Contractor - — | Principals Rep - — | Records CHAR(AMP) Remarks - Spray sheet | Principals Rep - —
4.1 | Post-seal (exit) inspection | NZTA P03, P04 | NZTA P17 | NZTA P17 Notes section 18 | Per Site | To open for trafficking | — | — | Chip Sealing Quality and Site Checklist | 4.1 - Post-seal (exit) inspection | Applicable Standard CHAR(AMP) Acceptance Criteria (NZTA- Template) - NZTA P03, P04 | Applicable Standard CHAR(AMP) Acceptance Criteria (Higgins) - NZTA P17 | Higgins (Comment) - NZTA P17 Notes section 18 | Frequency - Per Site | Criteria Notes - To open for trafficking | Contractor - — | Principals Rep - — | Records CHAR(AMP) Remarks - Chip Sealing Quality and Site Checklist | Records CHAR(AMP) Remarks - Tabulated worksheet
4.2 | Removal of surplus chip | NZTA P03, P04 | NZTA P17 | NZTA P17 Notes section 22.2 | Per Site | Loose chip complies with P03 or P04 as appropriate | — | — | Chip Sealing Quality and Site Checklist | 4.2 - Removal of surplus chip | Applicable Standard CHAR(AMP) Acceptance Criteria (NZTA- Template) - NZTA P03, P04 | Applicable Standard CHAR(AMP) Acceptance Criteria (Higgins) - NZTA P17 | Higgins (Comment) - NZTA P17 Notes section 22.2 | Frequency - Per Site | Criteria Notes - Loose chip complies with P03 or P04 as appropriate | Contractor - — | Principals Rep - — | Records CHAR(AMP) Remarks - Chip Sealing Quality and Site Checklist | 1.2 - Treatment selection confirmed
4.3 | Post-Seal Site Management | NZTA P03, P04 | NZTA P17 | NZTA P17 section 7 | Per Site | Implementation of positive traffic control when loose chip quantities pose a risk to public safety | — | — | — | 4.3 - Post-Seal Site Management | Applicable Standard CHAR(AMP) Acceptance Criteria (NZTA- Template) - NZTA P03, P04 | Applicable Standard CHAR(AMP) Acceptance Criteria (Higgins) - NZTA P17 | Higgins (Comment) - NZTA P17 section 7 | Frequency - Per Site | Criteria Notes - Implementation of positive traffic control when loose chip quantities pose a risk to public safety | Contractor - — | Principals Rep - — | Records CHAR(AMP) Remarks - — | Applicable Standard CHAR(AMP) Acceptance Criteria (NZTA- Template) - —
5.1 | Post seal inspection (Final TTM Removal) | NZTA P03, P04 | NZTA P17 | NZTA P17 section 7 | — | On completion of roadmarking Surplus chip to be removed | — | W | Chip Sealing Quality and Site Checklist | 5.1 - Post seal inspection (Final TTM Removal) | Applicable Standard CHAR(AMP) Acceptance Criteria (NZTA- Template) - NZTA P03, P04 | Applicable Standard CHAR(AMP) Acceptance Criteria (Higgins) - NZTA P17 | Higgins (Comment) - NZTA P17 section 7 | Frequency - — | Criteria Notes - On completion of roadmarking Surplus chip to be removed | Contractor - — | Principals Rep - W | Records CHAR(AMP) Remarks - Chip Sealing Quality and Site Checklist | Applicable Standard CHAR(AMP) Acceptance Criteria (Higgins) - —
5.2 | QA Handover | NZTA P03, P04 or P18 and contract drawings | NZTA P17 and contract drawings | Quality Plan | For each site on the project | Materials, construction compliance and extents | — | W | Evidence provided demonstrating full compliance with specified design | 5.2 - QA Handover | Applicable Standard CHAR(AMP) Acceptance Criteria (NZTA- Template) - NZTA P03, P04 or P18 and contract drawings | Applicable Standard CHAR(AMP) Acceptance Criteria (Higgins) - NZTA P17 and contract drawings | Higgins (Comment) - Quality Plan | Frequency - For each site on the project | Criteria Notes - Materials, construction compliance and extents | Contractor - — | Principals Rep - W | Records CHAR(AMP) Remarks - Evidence provided demonstrating full compliance with specified design | Higgins (Comment) - —
5.3 | RAMM update | RAMM updates completed | RAMM updates completed | — | — | Review of RAMM update and confirmation | — | W | Site records of RAMM update to be reviewed and confirmed | 5.3 - RAMM update | Applicable Standard CHAR(AMP) Acceptance Criteria (NZTA- Template) - RAMM updates completed | Applicable Standard CHAR(AMP) Acceptance Criteria (Higgins) - RAMM updates completed | Higgins (Comment) - — | Frequency - — | Criteria Notes - Review of RAMM update and confirmation | Contractor - — | Principals Rep - W | Records CHAR(AMP) Remarks - Site records of RAMM update to be reviewed and confirmed | Frequency - Pre site works
Criteria Notes - Principal agreed treatment selection
Contractor - H
Principals Rep - —
Records CHAR(AMP) Remarks - Records of Contractors Design
1.3 - Chip skid performance
Applicable Standard CHAR(AMP) Acceptance Criteria (NZTA- Template) - NZTA T10
Applicable Standard CHAR(AMP) Acceptance Criteria (Higgins) - NZTA T10
Higgins (Comment) - —
Frequency - Pre site works
Criteria Notes - Aggregate Peformance Report submitted CHAR(AMP) accepted by Principal.
Contractor - H
Principals Rep - —
Records CHAR(AMP) Remarks - Included in chipseal design report
1.4 - Chipseal Design
Applicable Standard CHAR(AMP) Acceptance Criteria (NZTA- Template) - NZTA P18
Applicable Standard CHAR(AMP) Acceptance Criteria (Higgins) - NZTA P17
Higgins (Comment) - NZTA P18 is principal designed
Frequency - Pre site works
Criteria Notes - Design meets contractual requirements
Contractor - H
Principals Rep - —
Records CHAR(AMP) Remarks - Seal design provided to principal
1.5 - Multilayer compatibility
Applicable Standard CHAR(AMP) Acceptance Criteria (NZTA- Template) - NZTA P18 Fig 1
Applicable Standard CHAR(AMP) Acceptance Criteria (Higgins) - Chip seal NZ
Higgins (Comment) - NZTA P18 is principal designed
Frequency - 1 per design
Criteria Notes - Both ALD results identified on graph
Contractor - —
Principals Rep - W
Records CHAR(AMP) Remarks - Included in chipseal design report
1.6 - Renewal Quality Plan
Applicable Standard CHAR(AMP) Acceptance Criteria (NZTA- Template) - —
Applicable Standard CHAR(AMP) Acceptance Criteria (Higgins) - —
Higgins (Comment) - —
Frequency - One overarching for all reseal sites
Criteria Notes - RQP Approved
Contractor - H
Principals Rep - —
Records CHAR(AMP) Remarks - Principal approval signature
- HP – Chipseal design verified for site commencement
Applicable Standard CHAR(AMP) Acceptance Criteria (NZTA- Template) - —
Applicable Standard CHAR(AMP) Acceptance Criteria (Higgins) - —
Higgins (Comment) - —
Frequency - —
Criteria Notes - Contractor checklist copied to Principal
Contractor - —
Principals Rep - W
Records CHAR(AMP) Remarks - Pre-commencement checklist signed and filed
2.1 - Bitumen compliance
Applicable Standard CHAR(AMP) Acceptance Criteria (NZTA- Template) - NZTA M02, P03, P04
Applicable Standard CHAR(AMP) Acceptance Criteria (Higgins) - NZTA M1
Higgins (Comment) - Currently all seal is completed with Cut Back Bitumen as per M01
Frequency - 1 test certificate per bulk shipment
Criteria Notes - Lab Test Report
Contractor - —
Principals Rep - W
Records CHAR(AMP) Remarks - Property Test, NZTA M01
2.2 - Chip source property compliance
Applicable Standard CHAR(AMP) Acceptance Criteria (NZTA- Template) - NZTA M06
Applicable Standard CHAR(AMP) Acceptance Criteria (Higgins) - NZTA M06
Higgins (Comment) - same
Frequency - Annually for each source
Criteria Notes - Lab test results
Contractor - —
Principals Rep - W
Records CHAR(AMP) Remarks - Source property checklist: PSV, CR, WR
2.3 - Chip production property compliance (Quarry or stockpile, dependent on where on site materials is coming from)
Applicable Standard CHAR(AMP) Acceptance Criteria (NZTA- Template) - NZTA M06, P18
Applicable Standard CHAR(AMP) Acceptance Criteria (Higgins) - NZTA M06,
Higgins (Comment) - same
Frequency - CHAR(LESS) 100m3, minimum 1 sample 100 - 500m3, minimum 2 samples >500m3, minimum 3 samples
Criteria Notes - Lab test results
Contractor - —
Principals Rep - W
Records CHAR(AMP) Remarks - Cleanness (Grades 2 – 6); Sealing chip size CHAR(AMP) shape; Broken faces (if reqd); PSD
- HP – Material compliance confirmed (binder, source CHAR(AMP) production properties)
Applicable Standard CHAR(AMP) Acceptance Criteria (NZTA- Template) - —
Applicable Standard CHAR(AMP) Acceptance Criteria (Higgins) - —
Higgins (Comment) - —
Frequency - —
Criteria Notes - Material compliance checklist copied to Principal
Contractor - —
Principals Rep - W
Records CHAR(AMP) Remarks - Material compliance checklist signed CHAR(AMP) filed
3.1 - Pre-Seal Site Checklist (week prior)
Applicable Standard CHAR(AMP) Acceptance Criteria (NZTA- Template) - Confirming site is ready for sealing
Applicable Standard CHAR(AMP) Acceptance Criteria (Higgins) - Confirming site is ready for sealing
Higgins (Comment) - same
Frequency - Following ALL pre seal works
Criteria Notes - —
Contractor - —
Principals Rep - H
Records CHAR(AMP) Remarks - Inspection Notes (Standard Form)Include Photographic Evidence and add in the Site Records
3.2 - Bitumen Distributor
Applicable Standard CHAR(AMP) Acceptance Criteria (NZTA- Template) - BPG 02
Applicable Standard CHAR(AMP) Acceptance Criteria (Higgins) - E2
Higgins (Comment) - Bitumen Distributor is certified under NZTA E2
Frequency - Annually
Criteria Notes - Speed Test, Dipstick Test, Distribution (Pad)Test
Contractor - —
Principals Rep - W
Records CHAR(AMP) Remarks - E2 Certificate
3.3 - Go/No Go Checklist
Applicable Standard CHAR(AMP) Acceptance Criteria (NZTA- Template) - Weather, readiness of materials and plant, air temperature, pavement temperature, et al
Applicable Standard CHAR(AMP) Acceptance Criteria (Higgins) - Weather, readiness of materials and plant, air temperature, pavement temperature, et al
Higgins (Comment) - same
Frequency - Prior to sealing on each site
Criteria Notes - Visual on site and check list sign off
Contractor - —
Principals Rep - H
Records CHAR(AMP) Remarks - Pre-commencement checklist (ie pre-start reqs, by foreman/crew manager)
3.4 - Spraying – site measurements
Applicable Standard CHAR(AMP) Acceptance Criteria (NZTA- Template) - NZTA P03, P04
Applicable Standard CHAR(AMP) Acceptance Criteria (Higgins) - NZTA P17
Higgins (Comment) - —
Frequency - Per Site
Criteria Notes - Application rates within design CHAR(AMP) tolerances + or - 5%
Contractor - —
Principals Rep - —
Records CHAR(AMP) Remarks - Spray sheet
3.5 - Geotextile reinforced seals (GRS )
Applicable Standard CHAR(AMP) Acceptance Criteria (NZTA- Template) - As per P18 CHAR(AMP) specific design requirements
Applicable Standard CHAR(AMP) Acceptance Criteria (Higgins) - As per specific design requirements and P17
Higgins (Comment) - —
Frequency - Per Site
Criteria Notes - Accurate RP start/end location CHAR(AMP) offset Application rates within design CHAR(AMP) tolerances + or - 5%
Contractor - —
Principals Rep - —
Records CHAR(AMP) Remarks - Spray sheet
4.1 - Post-seal (exit) inspection
Applicable Standard CHAR(AMP) Acceptance Criteria (NZTA- Template) - NZTA P03, P04
Applicable Standard CHAR(AMP) Acceptance Criteria (Higgins) - NZTA P17
Higgins (Comment) - NZTA P17 Notes section 18
Frequency - Per Site
Criteria Notes - To open for trafficking
Contractor - —
Principals Rep - —
Records CHAR(AMP) Remarks - Chip Sealing Quality and Site Checklist
4.2 - Removal of surplus chip
Applicable Standard CHAR(AMP) Acceptance Criteria (NZTA- Template) - NZTA P03, P04
Applicable Standard CHAR(AMP) Acceptance Criteria (Higgins) - NZTA P17
Higgins (Comment) - NZTA P17 Notes section 22.2
Frequency - Per Site
Criteria Notes - Loose chip complies with P03 or P04 as appropriate
Contractor - —
Principals Rep - —
Records CHAR(AMP) Remarks - Chip Sealing Quality and Site Checklist
4.3 - Post-Seal Site Management
Applicable Standard CHAR(AMP) Acceptance Criteria (NZTA- Template) - NZTA P03, P04
Applicable Standard CHAR(AMP) Acceptance Criteria (Higgins) - NZTA P17
Higgins (Comment) - NZTA P17 section 7
Frequency - Per Site
Criteria Notes - Implementation of positive traffic control when loose chip quantities pose a risk to public safety
Contractor - —
Principals Rep - —
Records CHAR(AMP) Remarks - —
5.1 - Post seal inspection (Final TTM Removal)
Applicable Standard CHAR(AMP) Acceptance Criteria (NZTA- Template) - NZTA P03, P04
Applicable Standard CHAR(AMP) Acceptance Criteria (Higgins) - NZTA P17
Higgins (Comment) - NZTA P17 section 7
Frequency - —
Criteria Notes - On completion of roadmarking Surplus chip to be removed
Contractor - —
Principals Rep - W
Records CHAR(AMP) Remarks - Chip Sealing Quality and Site Checklist
5.2 - QA Handover
Applicable Standard CHAR(AMP) Acceptance Criteria (NZTA- Template) - NZTA P03, P04 or P18 and contract drawings
Applicable Standard CHAR(AMP) Acceptance Criteria (Higgins) - NZTA P17 and contract drawings
Higgins (Comment) - Quality Plan
Frequency - For each site on the project
Criteria Notes - Materials, construction compliance and extents
Contractor - —
Principals Rep - W
Records CHAR(AMP) Remarks - Evidence provided demonstrating full compliance with specified design
5.3 - RAMM update
Applicable Standard CHAR(AMP) Acceptance Criteria (NZTA- Template) - RAMM updates completed
Applicable Standard CHAR(AMP) Acceptance Criteria (Higgins) - RAMM updates completed
Higgins (Comment) - —
Frequency - —
Criteria Notes - Review of RAMM update and confirmation
Contractor - —
Principals Rep - W
Records CHAR(AMP) Remarks - Site records of RAMM update to be reviewed and confirmed