## Master List Templates
Id | Type | Name | Values | Prompting Name
be0821af-0812-4143-86b0-6054e6508cd9 | checklist | ITP - Chipseal | itp | ITP - Chipseal
7f202172-5a75-413d-8312-99ce30488a1c | section | 1.0 Pre-Commencement Activities (Design suitability)
401fe3c3-072d-4e98-988c-143de632d238 | checkpoint | 1.1 - Surface texture measurement (1)
44f8b73e-1cdc-5cd2-baba-73a12c0c7589 | note | Applicable Standard & Acceptance Criteria (NZTA- Template) - NZTA P03
3ba0de5f-6cdd-59da-924d-1881bd9d294c | note | Applicable Standard & Acceptance Criteria (Higgins) - NZTA P03
2d7e62e1-fc17-54c2-a82b-0e7b8457f8a9 | note | Higgins (Comment) - NZTA P03 (First Coat seal) and P 04 is client provided designs
dd498689-f034-5d12-8ef2-2656865afb81 | note | Frequency - As per NZTA P03
ac69a977-c833-5807-9f03-57d29dd0506e | note | Criteria Notes - Sandcircle Measurement, or Laser Texture, or Principals HSD
90ae79a9-db0e-51d6-8eba-7f7ccc8135dd | note | Contractor - H
dff87a0a-9802-5726-b81a-6d953b98d3a8 | note | Records & Remarks - Tabulated worksheet
a81dbb7f-1dfb-4b56-a46a-e85b28b2480b | signoff | HOLD POINT
3742517c-5eb9-48cc-914e-3683100987e6 | checkpoint | 1.1 - Surface texture measurement (2)
26ab086d-21be-5fc7-bc6c-aa14d3a28270 | note | Applicable Standard & Acceptance Criteria (NZTA- Template) - NZTA P04
9cfae3e9-7a74-58d3-ba82-8907ff029128 | note | Applicable Standard & Acceptance Criteria (Higgins) - NZTA P17 4.3 Surface Texture
015cfdfc-ab5d-54f9-b507-0de5a94bda75 | note | Higgins (Comment) - NZTA is contractor supplied
3b31c665-02ce-53e2-98a5-25a6a02e019c | note | Frequency - As per NZTA P17
642df900-b7da-5ab4-b0e7-334bb5d7ce99 | note | Criteria Notes - Sandcircle Measurement, or Laser Texture, or Principals HSD
12a9c09e-2cbe-5168-a8e8-4d4e589c9083 | note | Contractor - H
44d2b816-ebfa-5fd6-9bb0-f4cbb0766058 | note | Records & Remarks - Tabulated worksheet
bbd8c135-c8f4-4656-8a73-a3e388412677 | signoff | HOLD POINT
3725f305-b0f4-492f-b2f3-b7167a46231e | checkpoint | 1.2 - Treatment selection confirmed
cb18585f-2b03-57c4-a18d-6c7ce06817d9 | note | Frequency - Pre site works
e5709b76-db27-5b50-a86e-60a0c17cffa7 | note | Criteria Notes - Principal agreed treatment selection
cd7fc413-3481-5daa-86e6-f847bd7a278f | note | Contractor - H
b871b2a1-bcca-5151-8ef7-b9c70ea313c7 | note | Records & Remarks - Records of Contractors Design
0fe0a0ee-a2b3-4389-86f8-8e1ff68c3ede | signoff | HOLD POINT
ba6e2a8f-863b-4c94-b809-652917b2edd2 | checkpoint | 1.3 - Chip skid performance
368663d2-ec62-5214-811b-7595d26d5424 | note | Applicable Standard & Acceptance Criteria (NZTA- Template) - NZTA T10
b8758f49-d3d6-531d-bc59-b085976a03bf | note | Applicable Standard & Acceptance Criteria (Higgins) - NZTA T10
71e256e6-6a17-5fc3-9652-dc3938f70b6f | note | Frequency - Pre site works
85ea9332-2e84-54b7-b4a8-35c97103b40e | note | Criteria Notes - Aggregate Peformance Report submitted & accepted by Principal.
7f5c7f83-d197-5ef4-bde8-27ea3e7caa33 | note | Contractor - H
7b08822a-e684-5a57-8f0f-ed4fbe52567c | note | Records & Remarks - Included in chipseal design report
7d86faae-aade-4b7b-b527-33931bd92ad3 | signoff | HOLD POINT
d29c2946-5fce-49ef-9098-751e58b07956 | checkpoint | 1.4 - Chipseal Design
b5d5962d-4246-51d0-a2ed-44044ed9c2ad | note | Applicable Standard & Acceptance Criteria (NZTA- Template) - NZTA P18
e261c45a-8eaa-5f47-b724-623ad4202e2b | note | Applicable Standard & Acceptance Criteria (Higgins) - NZTA P17
348857e3-b1ce-54a6-acb6-b86926d74c41 | note | Higgins (Comment) - NZTA P18 is principal designed
d7b3b2bc-70b4-5c97-8926-4b3f76c45b0b | note | Frequency - Pre site works
fccbab16-e275-5049-8d3c-705d0d6bf64d | note | Criteria Notes - Design meets contractual requirements
3ff5aa86-14e5-5661-bb22-c4c90b015570 | note | Contractor - H
c99f631a-cdbb-545c-b7aa-a73f7f1f504a | note | Records & Remarks - Seal design provided to principal
79128254-dcdf-4c02-a963-ed04a6208d83 | signoff | HOLD POINT
55812aed-072a-4d1a-ae30-237a1496297e | checkpoint | 1.5 - Multilayer compatibility
6bea49a6-70ba-5aa8-a989-a1bf96133c00 | note | Applicable Standard & Acceptance Criteria (NZTA- Template) - NZTA P18 Fig 1
8c1ddf60-dac2-5556-97b6-3722a9417e52 | note | Applicable Standard & Acceptance Criteria (Higgins) - Chip seal NZ
b444d6a0-74f7-5b1e-aeaa-1b82adb7101b | note | Higgins (Comment) - NZTA P18 is principal designed
6777585b-d77a-5432-a855-b809a0cdb1df | note | Frequency - 1 per design
20549f5d-7758-55f5-8787-33a4fd40de61 | note | Criteria Notes - Both ALD results identified on graph
333369f3-0a8a-566b-aa68-c4ae12f2ee54 | note | Principals Rep - W
abd6a840-96e8-5e7c-ad4d-5342f2639c07 | note | Records & Remarks - Included in chipseal design report
8af8d99e-912f-45e3-8f5c-385c6fce0549 | checkpoint | 1.6 - Renewal Quality Plan
c8130edc-7179-55c1-81d9-81008a59af89 | note | Frequency - One overarching for all reseal sites
c11c7823-3c87-57d0-ba33-c77cd7e1b563 | note | Criteria Notes - RQP Approved
4e05552b-ca4b-5172-a21e-4d974a6906d5 | note | Contractor - H
11f92868-9f76-5ecf-a7a7-85d8562563fc | note | Records & Remarks - Principal approval signature
0f24fe9c-d5f2-4be7-b5fa-c0f36c7353d7 | signoff | HOLD POINT
3d729f2b-2cf2-436c-aba6-e784c0302aab | checkpoint | HP – Chipseal design verified for site commencement
0eff4e7f-6935-5e99-be3b-d6e0976c85d7 | note | Criteria Notes - Contractor checklist copied to Principal
690dda18-92db-57d6-9914-16749b06aab9 | note | Principals Rep - W
ff1532db-c0b9-5d6a-8b69-3c018fb24786 | note | Records & Remarks - Pre-commencement checklist signed and filed
6169331e-878e-42be-8863-75f862209cd6 | section | 2.0 Material Compliance
2244b4ea-a143-4172-aae8-b89a6ef006da | checkpoint | 2.1 - Bitumen compliance
6f383f08-1270-5936-9c57-1e86bab02716 | note | Applicable Standard & Acceptance Criteria (NZTA- Template) - NZTA M02, P03, P04
778a37e7-81f2-5992-9bb3-52de4c2d3c9e | note | Applicable Standard & Acceptance Criteria (Higgins) - NZTA M1
68f6e75f-6017-5115-abcf-fb6c98654264 | note | Higgins (Comment) - Currently all seal is completed with Cut Back Bitumen as per M01
81cdca0c-b8c8-5bf6-b467-23fbda152442 | note | Frequency - 1 test certificate per bulk shipment
a47bf167-58f2-598e-ab67-b57eb868e971 | note | Criteria Notes - Lab Test Report
945a83d6-1883-50e5-ba42-5fa1f9bd13fc | note | Principals Rep - W
aac9c3b0-ebc9-560c-86fa-e36eda0f2712 | note | Records & Remarks - Property Test, NZTA M01
71a23fe0-67d8-4478-8c22-8487ba6e3c83 | checkpoint | 2.2 - Chip source property compliance
d23942f7-93ee-5d1c-90fd-5cd7b0913b39 | note | Applicable Standard & Acceptance Criteria (NZTA- Template) - NZTA M06
b2a5c9b2-98c4-5c85-9bf2-8b62daf47a77 | note | Applicable Standard & Acceptance Criteria (Higgins) - NZTA M06
30321e1f-c0ac-5c25-b0e0-9369a54c8a95 | note | Higgins (Comment) - same
6a31a041-6e08-53c7-a89a-9c7e87681378 | note | Frequency - Annually for each source
72e58981-0fc1-59f2-ae0d-d80431217950 | note | Criteria Notes - Lab test results
89330110-5d79-5546-be09-a5bc2ae62278 | note | Principals Rep - W
cc794aff-6b9c-55d3-ae49-c2479e8343d9 | note | Records & Remarks - Source property checklist: PSV, CR, WR
bfd15eac-8a7d-430f-9b6e-90e22d481a1f | checkpoint | 2.3 - Chip production property compliance (Quarry or stockpile, dependent on where on site materials is coming from)
d84c6460-a1b4-5f3b-a806-8385443f28bc | note | Applicable Standard & Acceptance Criteria (NZTA- Template) - NZTA M06, P18
e5323749-fc22-5328-a821-4e78ff431f74 | note | Applicable Standard & Acceptance Criteria (Higgins) - NZTA M06,
0a6146fa-4f71-5bb4-bb2f-1aa94f82d71d | note | Higgins (Comment) - same
4fa56a07-c9e1-5f5c-8bca-e3dd1dfae324 | note | Frequency - < 100m3, minimum 1 sample
c374e499-33ec-521c-af2e-c53bf23cb06d | note | ○ 100 - 500m3, minimum 2 samples
268dfe80-c28b-5b81-b7b7-d04ea764e81d | note | ○ >500m3, minimum 3 samples
7520bc98-8150-51b5-89d0-17d4f714fa14 | note | Criteria Notes - Lab test results
5b34f2cc-98d0-588d-85b8-ac31fab71b0d | note | Principals Rep - W
9c2ca1ef-d5b4-502f-a6ad-491d2c8beb09 | note | Records & Remarks - Cleanness (Grades 2 – 6); Sealing chip size & shape; Broken faces (if reqd); PSD
432b9b91-9ea4-4844-b729-c725039b606a | checkpoint | HP – Material compliance confirmed (binder, source & production properties)
d235d724-c653-52d1-b068-5c3067051516 | note | Criteria Notes - Material compliance checklist copied to Principal
75c754a1-068d-565b-b432-2d22cc8e3af9 | note | Principals Rep - W
aa2f5408-a424-591f-a076-836a202c038c | note | Records & Remarks - Material compliance checklist signed & filed
a36bc2df-4a58-4642-ba2c-09b0c481cd98 | section | 3.0 Seal construction
cf8e2e0d-362c-42c4-9c19-5520ebf4a663 | checkpoint | 3.1 - Pre-Seal Site Checklist (week prior)
e8dcf7d1-7ff9-5443-823c-7c150b25c8f8 | note | Applicable Standard & Acceptance Criteria (NZTA- Template) - Confirming site is ready for sealing
f49dbe14-2c80-5ea4-8907-ab584a2a9898 | note | Applicable Standard & Acceptance Criteria (Higgins) - Confirming site is ready for sealing
2ea0a7a8-7553-53ef-8477-8d05ffcc7383 | note | Higgins (Comment) - same
027cf52c-c164-55ad-81aa-61d2327132b3 | note | Frequency - Following ALL pre seal works
32899384-2706-54b5-b9ed-5ef33b476c3e | note | Principals Rep - H
1af4f703-247d-5364-9d12-08262ed7884c | note | Records & Remarks - Inspection Notes (Standard Form)Include Photographic Evidence and add in the Site Records
d91bf495-5da0-4008-a6ef-790223d288eb | signoff | HOLD POINT
455d839d-9c55-47be-bfa3-ea218a3325d7 | checkpoint | 3.2 - Bitumen Distributor
e7f5c21f-6e83-5997-b21c-84c9d5de85a5 | note | Applicable Standard & Acceptance Criteria (NZTA- Template) - BPG 02
212b7ff3-88a0-530a-a38e-878bfc9df84b | note | Applicable Standard & Acceptance Criteria (Higgins) - E2
c32ce549-7f27-5481-8100-29e777baa8f9 | note | Higgins (Comment) - Bitumen Distributor is certified under NZTA E2
d375d4af-3b18-5413-8789-8b9aad3276b6 | note | Frequency - Annually
0d4afa9d-3d74-559c-8240-7eff7f973539 | note | Criteria Notes - Speed Test, Dipstick Test, Distribution (Pad)Test
3e82f10f-af82-5b2d-8818-3ff716133476 | note | Principals Rep - W
f43fe886-ed26-55e5-ba72-7c18bd7c2e5d | note | Records & Remarks - E2 Certificate
39dae4de-3931-4064-8239-e67645adc37b | checkpoint | 3.3 - Go/No Go Checklist
792ff0a2-c3af-580d-95f7-94d8aa423f70 | note | Applicable Standard & Acceptance Criteria (NZTA- Template) - Weather, readiness of materials and plant, air temperature, pavement temperature, et al
ca885309-e6a4-53e5-bac7-ee94118519fd | note | Applicable Standard & Acceptance Criteria (Higgins) - Weather, readiness of materials and plant, air temperature, pavement temperature, et al
869d6da5-e135-5dbe-8f54-d6db22caaa31 | note | Higgins (Comment) - same
3bc9e252-f67a-5ed5-a586-e34bbdd87100 | note | Frequency - Prior to sealing on each site
9a12d0e5-6635-5b53-84e3-3272eef45232 | note | Criteria Notes - Visual on site and check list sign off
f9944dc3-d7e3-50f6-8db8-d5b1d87bcf91 | note | Principals Rep - H
9427f621-8f21-592d-bec8-2da72159cfa0 | note | Records & Remarks - Pre-commencement checklist (ie pre-start reqs, by foreman/crew manager)
c6c6165a-41f5-4969-97b3-ba72f4f1ccb7 | signoff | HOLD POINT
7d15f2ef-acb3-440d-9885-58351e84c942 | checkpoint | 3.4 - Spraying – site measurements
30e84a88-2308-58ab-b0d5-cf1968d5edea | note | Applicable Standard & Acceptance Criteria (NZTA- Template) - NZTA P03, P04
4cd53e1c-ba2d-5b34-a592-69c9aa1b63eb | note | Applicable Standard & Acceptance Criteria (Higgins) - NZTA P17
79ee306a-7db2-52b8-a017-08fd2bf1fdc5 | note | Frequency - Per Site
3ee515e6-4dc5-5dca-b8f3-caef33ac5c93 | note | Criteria Notes - Application rates within design & tolerances + or - 5%
351087fe-99a8-57be-a8f0-0d3e5af1f22c | note | Records & Remarks - Spray sheet
6ac06cfe-4d52-4c1d-b672-7e8a48d3af2f | checkpoint | 3.5 - Geotextile reinforced seals (GRS )
155fd4a3-a58e-5bf4-b4dc-e3338f0b6fa3 | note | Applicable Standard & Acceptance Criteria (NZTA- Template) - As per P18 & specific design requirements
f6c4af35-bb21-554c-bb50-d93f9f1e4b5a | note | Applicable Standard & Acceptance Criteria (Higgins) - As per specific design requirements and P17
cf78d7e4-f7d7-537d-ad50-39b12132b880 | note | Frequency - Per Site
d34faefa-c1e4-55e8-90b4-8f52559281b2 | note | Criteria Notes - Accurate RP start/end location & offset
471a22ed-1c88-5c00-a02a-3ab6b3b6e833 | note | ○ Application rates within design & tolerances + or - 5%
c8d8f5ad-99c1-5719-bed1-3afe4c392207 | note | Records & Remarks - Spray sheet
111c5272-ff4f-49fc-9fae-21ab2b00dc36 | section | 4.0 Clean-up
c2accdaf-4139-4d37-9210-507333745e38 | checkpoint | 4.1 - Post-seal (exit) inspection
084c5822-587d-5ef6-8514-23889115b54d | note | Applicable Standard & Acceptance Criteria (NZTA- Template) - NZTA P03, P04
7fa6be6a-fe15-56db-a737-926afd68139c | note | Applicable Standard & Acceptance Criteria (Higgins) - NZTA P17
da4a461c-96da-5ab6-8cbe-c36338425560 | note | Higgins (Comment) - NZTA P17 Notes section 18
614f846e-9685-588d-bbff-5c8b5bac9cca | note | Frequency - Per Site
1f3648c6-b1eb-58d7-a928-5607b6709b09 | note | Criteria Notes - To open for trafficking
34fe6b98-59f4-5463-be4e-83fe8413e716 | note | Records & Remarks - Chip Sealing Quality and Site Checklist
e1b01149-b9f7-480d-86a3-9e39dc1b4553 | checkpoint | 4.2 - Removal of surplus chip
675a14b0-e580-5d87-baea-682f4fba9e89 | note | Applicable Standard & Acceptance Criteria (NZTA- Template) - NZTA P03, P04
72732a36-6a89-583e-9f25-a62e277742ad | note | Applicable Standard & Acceptance Criteria (Higgins) - NZTA P17
272aa5a2-64c8-527c-b057-7f01be9375c3 | note | Higgins (Comment) - NZTA P17 Notes section 22.2
7eb94d07-e16f-512d-8479-0bb38664ba1e | note | Frequency - Per Site
ac079a4c-bd1f-508c-97b0-ec131c90e986 | note | Criteria Notes - Loose chip complies with P03 or P04 as appropriate
cc9bdf6a-5a5c-5379-af3e-22ef9c6cc312 | note | Records & Remarks - Chip Sealing Quality and Site Checklist
0b0db315-7d6d-44c8-b91a-0f289d4f31e5 | checkpoint | 4.3 - Post-Seal Site Management
7761b3c2-2dca-5d3d-8dd8-18846cdd26d1 | note | Applicable Standard & Acceptance Criteria (NZTA- Template) - NZTA P03, P04
29225741-d2d8-5357-afb7-c3a05713b487 | note | Applicable Standard & Acceptance Criteria (Higgins) - NZTA P17
2a4f4259-a575-5fe7-a31c-041902ac667f | note | Higgins (Comment) - NZTA P17 section 7
db38c504-6b9b-55cf-bacd-81adc74d265d | note | Frequency - Per Site
bb3c9d3c-6779-568a-8e8f-7222474beaf5 | note | Criteria Notes - Implementation of positive traffic control when loose chip quantities pose a risk to public safety
072ac084-3f9f-4eb9-90ae-df68aae0345c | section | 5.0 Post-construction
e3ba8413-039d-4cb4-abc3-c06c9d443b6c | checkpoint | 5.1 - Post seal inspection (Final TTM Removal)
436cdd59-d094-5ce7-98ce-1c38950a573b | note | Applicable Standard & Acceptance Criteria (NZTA- Template) - NZTA P03, P04
5999de2f-593a-5a03-8727-3d2b46d96e35 | note | Applicable Standard & Acceptance Criteria (Higgins) - NZTA P17
b95a0b85-9972-55c8-9150-4093c5f393d5 | note | Higgins (Comment) - NZTA P17 section 7
0ca80fad-9181-506a-96fd-5aa747db0298 | note | Criteria Notes - On completion of roadmarking Surplus chip to be removed
4354dc3e-fafc-5d0e-87b2-ab63a788ea86 | note | Principals Rep - W
c1fc3e58-31f4-55f2-9d54-af54453fd69f | note | Records & Remarks - Chip Sealing Quality and Site Checklist
b6f0ba1f-5b1d-4206-86b2-ee160be77518 | checkpoint | 5.2 - QA Handover
f47d9e36-e8f9-5a57-b1d2-49528c520256 | note | Applicable Standard & Acceptance Criteria (NZTA- Template) - NZTA P03, P04 or P18 and contract drawings
5ee19e32-da77-5533-98d5-d8cbd7218b7e | note | Applicable Standard & Acceptance Criteria (Higgins) - NZTA P17 and contract drawings
6aa5a02a-bb49-5529-82d0-7c07e03cd840 | note | Higgins (Comment) - Quality Plan
ecfcfe6f-80c7-5c0c-bfa6-70f10be98725 | note | Frequency - For each site on the project
505c05e0-13fb-55dc-bc77-e85bd4eb7ade | note | Criteria Notes - Materials, construction compliance and extents
0719065b-b3cd-590f-9166-5adefea19d71 | note | Principals Rep - W
8617c01c-7c9e-541a-9c13-430e7defdfb1 | note | Records & Remarks - Evidence provided demonstrating full compliance with specified design
4aaa23bc-5196-4dc8-b16a-f7f7042b5a3a | checkpoint | 5.3 - RAMM update
efea4322-1b07-5072-abee-1ee109cf4e38 | note | Applicable Standard & Acceptance Criteria (NZTA- Template) - RAMM updates completed
20da98da-49c3-50e3-b40e-7bc5509be5d0 | note | Applicable Standard & Acceptance Criteria (Higgins) - RAMM updates completed
d684471e-dc16-5bfc-a145-dad1a822eb62 | note | Criteria Notes - Review of RAMM update and confirmation
9fd38f79-29b1-5ff4-8184-5f46a24e7752 | note | Principals Rep - W
a1493e08-becb-5291-8fdf-e6d7fedfda71 | note | Records & Remarks - Site records of RAMM update to be reviewed and confirmed
553acd8a-f7fc-42de-a9b8-1af67b680450 | checkpoint | Quality Record Close Out:
81321d32-9817-5ba9-a531-36e149d9d96c | textbox | Quality Manager Name:
df098857-d598-56cb-9afc-8bdadf3490c7 | date | Date:
d38a9420-fa12-4b7a-8325-9ccda2378e96 | signoff | Add Signature
7141f147-bdae-47a0-a6d3-96a7acdc3702 | checklist | ITP - Pavement Rehab - SH 05 - Boundary Road South | itp | ITP - Pavement Rehab - SH 05 - Boundary Road South
1ca59300-19c4-4fc2-b0af-836585e3df2c | section | 1. Procurement - Design
bd7fcf88-4b1c-4fb3-b4d1-4940bd82e15d | checkpoint | Geometric Design
644e3ac6-3586-587c-8a9d-99ca424d1460 | note | Controlling Documents - Austroads Guide to Road Design Part 3: Geometric Design, TNZ State Highway Geometric Design Manual
5689a434-e18b-532b-b864-6ffe63fa8700 | note | Acceptance Criteria - Principal Approval
ea74fb7f-c4c5-57af-bc0d-7e5019c30332 | note | Inspection or Test: Method - Contractor and Principal peer review
b13d6d09-975c-5b99-85bf-08f0e53c5aa7 | note | Inspection or Test: Frequency - per design revision
d395d79f-8013-51a3-a35c-417460232816 | note | Inspection / Test Authority: Conduct - C or S
3075736e-2075-5cd3-a91c-5d0647b58d77 | note | Inspection / Test Authority: Produce Record - C
8f0ebc64-cd62-57fb-bf08-2525192a70d6 | note | Inspection / Test Authority: Approval - E
a4db01f1-48db-5327-a92e-2076e7413c99 | note | Hold Point - Y
c68ed9ab-76f6-4520-885c-85a315a27fad | signoff | HOLD POINT
04dea26e-18cb-4615-8b7e-be2f9b3293fa | checkpoint | Pavement Treatment Design
be6cdff8-2b4b-525b-8a46-3bd366b8716f | note | Controlling Documents - Austroads Guide to Pavement Technology, New Zealand Guide to Pavement Evaluation and Treatment Design:2018 (Version 1.2)
21d514a8-689d-5e39-99c4-18c0a1698f84 | note | Acceptance Criteria - Principal Approval
2674da28-650f-521e-9b2e-1d8fc99a5810 | note | Inspection or Test: Method - Contractor and Principal peer review
4faf0964-43bd-51f8-9982-5990dfd3ed87 | note | Inspection or Test: Frequency - per design
e1f94d6c-8b78-5380-861e-efb2eca9fc53 | note | Verifying Document - Pavement Rehabilitation Design Report
f4ac2c10-9947-50c0-bcdc-b9e222924bf5 | note | Inspection / Test Authority: Conduct - C or S
def6f7da-1005-5ccc-b9c8-21c454868f13 | note | Inspection / Test Authority: Produce Record - C
d7c57b7f-310a-51de-93b5-b5570c268503 | note | Inspection / Test Authority: Approval - E
a784b15e-5f7b-5392-af11-c218e7915ea9 | note | Hold Point - Y
3fe384fb-0f47-4eac-bc29-005bf9b30ea1 | signoff | HOLD POINT
2b8ff648-cbcb-4820-ac0c-99b0c0594e93 | section | 1. Procurement - Materials: GAP 65 Pre-treatment Material
88a81b6c-507a-4b0e-bb5d-77d99efa1145 | checkpoint | Aggregate Sampling
e46eb6bf-2419-5517-b28c-bbbde041a086 | note | Controlling Documents - NZS 4407:2015, WSP Rotorua Sampling Guide
c49942d2-6e94-5b3b-bec8-db7454d1bdfe | note | Verifying Document - Sampling Worksheet
9d02eca7-8f49-5d04-8124-102625c7953a | note | Inspection / Test Authority: Conduct - C or S
914c89b6-5f4c-5f6d-a50f-1aca10821c17 | note | Inspection / Test Authority: Approval - S
4ca99cff-dd5c-5cf0-82ed-e9b6e7e4bf80 | note | Hold Point - Y
36cd797d-e9cd-4085-b122-e188d25721ac | signoff | HOLD POINT
28e5e609-a40d-4598-bcb9-3c238e957246 | checkpoint | Source Property Test
eddcb733-8330-58b5-be48-c32181a9c50b | note | Controlling Documents - CBR - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3
0ea24809-27be-54e4-80c0-218f20b37471 | note | Acceptance Criteria - Soaked CBR ≥ 40
aed9dff9-126b-5447-bbd2-f93b8759b94e | note | Inspection or Test: Method - Soaked CBR test (NZS:4407:2015:3.15)
da0a1205-746c-533e-94e0-c2a685e1214a | note | Inspection or Test: Responsible Person - Supervisor
7a0eec26-0ac5-5924-9227-3676a3229838 | note | Verifying Document - Test Report
ff5b4f41-4323-56ce-8c3b-d8e09dd44064 | note | Inspection / Test Authority: Conduct - Sp or C or S
c2afbad5-657c-552e-ad64-c200bbc57991 | note | Inspection / Test Authority: Produce Record - Sp or S
900d6b93-fd81-50ac-bfe2-4d1ebb47bf28 | note | Inspection / Test Authority: Approval - E
35388427-391a-59aa-9bbf-d3559243c51a | note | Hold Point - Y
819ffd33-5010-43ab-9f78-0af2e4c38577 | signoff | HOLD POINT
44313984-a6b6-4607-9195-4d48e13dfe07 | checkpoint | Production Property Test
1e863c8a-725f-52f0-b2f0-2310305ccf72 | note | Controlling Documents - Sand Equivalent - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3
d94ba8fb-4b77-55ac-bd4f-9c922608497c | note | Acceptance Criteria - Sand Equivalent >35, OR <35 but well graded with no more than 10% by mass passing through a 0.425mm sieve
bce953aa-6b5e-5e9a-97c2-762c1ef2b1b2 | note | Inspection or Test: Method - Sand Equivalent Test (NZS:4407:2015, 3.6)
d3d6df69-9dd7-5092-ba61-ea43b2f9fb6f | note | Inspection or Test: Responsible Person - Supervisor
d5cad12d-c11f-5b63-be7e-279fec3d2db1 | note | Verifying Document - Test Report
445f68f6-34d9-5782-983f-5d1aa621660d | note | Inspection / Test Authority: Conduct - Sp or C or S
b493c031-f4d0-5715-8e89-b4d4017c6cc5 | note | Inspection / Test Authority: Produce Record - Sp or S
23e593a1-d33d-552c-985a-ffac8f57098a | note | Inspection / Test Authority: Approval - E
1cce4bf4-529d-5862-af4f-974f4c17110b | note | Hold Point - Y
7e30db38-b44b-4023-b864-ac684b7b40a2 | signoff | HOLD POINT
09917c79-7948-4245-b506-bbc19fc960a7 | section | 1. Procurement - Materials: M/4 AP40 Basecourse Material
64061b33-e35b-49f2-a856-c342d24f2077 | checkpoint | Aggregate Sampling
f8d15460-ee22-5b9b-8ebf-21073a0858b5 | note | Controlling Documents - NZS 4407:2015, WSP Rotorua Sampling Guide
522cf364-40fe-5806-a6f5-f086691bec70 | note | Verifying Document - Sampling Worksheet
01f991e2-af96-4c34-ab03-d311471e7329 | checkpoint | Source Property Test (1)
8c08e66b-8ea6-5cd2-8aae-0ef2a4cf31ce | note | Controlling Documents - Crushing Resistance (3.3.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.10 (The Crushing Resistance Test)
3a1e2c93-074b-54c3-a1d4-ba96675601d3 | note | Acceptance Criteria - less than 10% fines passing 2.36mm sieve size under a load of 130kN
483729de-b976-53d1-a519-1c7ea9ef542e | note | Inspection or Test: Method - Curshing Resistance Test (NZS 4407:1991, Test 3.10)
663c089f-5570-5637-b38f-59b0f0fd27c0 | note | Inspection or Test: Frequency - One test for every 10,000m³ of source material
21641231-e072-506b-8d3e-06fc0cdcc0d0 | note | Inspection or Test: Responsible Person - Quality Controller
b19bf9d9-82a6-568d-a43c-b914774bdc5a | note | Verifying Document - Test Report
efa03311-bb38-5260-bc76-ada5c839c2d0 | note | Inspection / Test Authority: Conduct - Sp or C or S
999a8755-5f28-56d6-b58b-9791fa34bbfb | note | Inspection / Test Authority: Produce Record - Sp or S
2c6e7063-0166-5e6d-8b88-63e1dd62d48f | note | Inspection / Test Authority: Approval - E
005afb9a-e392-561b-95a4-6313b639c0ca | note | Hold Point - Y
7d81d958-48d9-4a0c-8235-76dafb4a86bb | signoff | HOLD POINT
572c7212-833b-4d7c-ae65-8cbde1551c59 | checkpoint | Source Property Test (2)
4fcb3abd-14c9-53bd-a63e-9f94d3be3f66 | note | Controlling Documents - Weathering Quality Index (3.3.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.11 (Weathering Quality Index Test)
6fac0ec7-ed1c-56d4-a545-5d07bbda8702 | note | Acceptance Criteria - AA, AB, AC, BA, BB or CA
1f70a493-c219-5be2-9bd9-b2f6bf8db1b2 | note | Inspection or Test: Method - Weathering Quality Index Test (NZS 4407: 1991, Test 3.11)
18d4955d-5e7a-5ef6-8f45-2d087bb720a1 | note | Inspection or Test: Frequency - One test for every 10,000m³ of source material
3215aa32-47d1-595f-bf6b-9d0e83e893cc | note | Inspection or Test: Responsible Person - Quality Controller
14c61c05-262a-5fc4-9c97-077bf0aff004 | note | Verifying Document - Test Report
e19367fe-f376-5363-a28f-58db6a4b41bf | note | Inspection / Test Authority: Conduct - Sp or C or S
93e99849-bd95-5909-9481-043d360fb0a0 | note | Inspection / Test Authority: Produce Record - Sp or S
5723478e-f976-5066-a6c9-2fd66b6e72c2 | note | Inspection / Test Authority: Approval - E
3fec80c9-dfb8-5bc7-af31-7f68ea25c02a | note | Hold Point - Y
851816c9-b3db-4286-b313-6f79c43d57ac | signoff | HOLD POINT
5320ea7c-0739-41a8-93d0-3aa03a16dc52 | checkpoint | Source Property Test (3)
f12d146c-2865-55bb-b885-2a2f58a1cea4 | note | Controlling Documents - California Bearing Ratio (3.3.3) - TNZ M/4: 2006, NZS 4402: 1986 Test 4.1.3, NZS 4407: 1991 Test 3.15 (California Bearing Ratio Test)
94c3f813-7a19-5695-b4fd-84f62639aace | note | Acceptance Criteria - Soaked CBR ≥ 80%
b442fa7c-229f-5a9c-8a7d-fc3a7750c5e8 | note | Inspection or Test: Method - California Bearing Ratio Test (NZS 4407: 1991, Test 3.15) after being compacted according to Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3)
57fe9aa5-ecc7-5d7a-a17f-8b0bee1e2571 | note | Inspection or Test: Frequency - One test for every 10,000m³ of source material
6d246341-edb5-5fb5-9dba-8c3b9d73869c | note | Inspection or Test: Responsible Person - Quality Controller
4197f54e-ea4b-53ff-996f-4f3b7f3d52ee | note | Verifying Document - Test Report
71524b41-ccfb-5a18-ab6d-1d2159c3c579 | note | Inspection / Test Authority: Conduct - Sp or C or S
13e5b23e-6871-53dc-900e-95ef513aa4be | note | Inspection / Test Authority: Produce Record - Sp or S
8cdbf66e-300a-5dbd-a5ca-686837175bec | note | Inspection / Test Authority: Approval - E
8ad2f6c1-4a47-5a7b-8c5b-cc26e02db608 | note | Hold Point - Y
5869aaa5-f7ff-4419-b7c0-d064702f10e5 | signoff | HOLD POINT
3c75b259-7847-4556-9694-84c97033c7bc | checkpoint | Production Property Test (1)
88b883cc-5f4c-590e-83c2-2cbe635e63fe | note | Controlling Documents - Sand Equivalent (4.2.1.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.6 or Clay Index (4.2.1.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.5 or Plasticity Index (4.2.1.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.4
95c1f342-e73f-574a-a3e0-4468793bcda5 | note | Acceptance Criteria - Sand Equivalent ≥40; or Clay Index ≤3; or Plasticity Index ≤5
7494071d-e7c8-5ee8-8e49-796ad0154051 | note | Inspection or Test: Method - Sand Equivalent Test (NZS:4407:2015, 3.6); or Clay Index Test (NZS:4407: 1991, 3.5); or Plasticity Index Test (NZS 4407:1991, 3.4)
70ca0057-6cf7-5392-9024-4d2a4fbff3ef | note | Inspection or Test: Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
549c10df-c6be-5234-8bcf-656275720524 | note | Inspection or Test: Responsible Person - Quality Controller
4392f738-d467-5d6b-93c9-6af3af140303 | note | Verifying Document - Test Report
fa88403a-4244-5477-8d96-372c59930e52 | note | Inspection / Test Authority: Conduct - Sp or C or S
597082e5-36c3-5730-a5b4-914909fd5a82 | note | Inspection / Test Authority: Produce Record - Sp or S
41c20a97-9272-5aec-9dc6-a84599e9cb19 | note | Inspection / Test Authority: Approval - E
e36a33f0-68e2-5c18-a0a7-b1c22a37158f | note | Hold Point - Y
a9d5e131-767e-4a86-8baf-50e5e82b1384 | signoff | HOLD POINT
b9ef8cba-14c4-443f-9740-6f0f886ceffc | checkpoint | Production Property Test (2)
f56c6664-594a-5130-9928-5caa139a2759 | note | Controlling Documents - Broken Face Content (4.2.2) - TNZ M/4: 2006, NZS:4407: 1991 Test 3.14
12beec12-67ff-5b47-9cde-6cccc277ca79 | note | Acceptance Criteria - Broken Face Content ≥70% between 37.5mm and 4.75mm sieve and ≥2 broken faces
71f6d433-cc95-501c-8500-4dc7b251fd12 | note | Inspection or Test: Method - Broken Face Test (NZS:4407: 1991, Test 3.4)
c376d471-38ea-5785-8e7b-2e4278a48090 | note | Inspection or Test: Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
55f460af-8641-5d6c-8e13-ada2dc4c9bbd | note | Inspection or Test: Responsible Person - Quality Controller
48e25f10-7daf-5a23-95cf-57e6d634386e | note | Verifying Document - Test Report
92a240b6-d539-5fd8-9af5-cc1544663d2a | note | Inspection / Test Authority: Conduct - Sp or C or S
1d2bb745-98b5-57a1-b8c2-b436b3f7b50c | note | Inspection / Test Authority: Produce Record - Sp or S
4fc5a503-e11f-529e-91aa-fae116d697b8 | note | Inspection / Test Authority: Approval - E
188e771f-37a8-5788-8c5a-6b1ba705f4db | note | Hold Point - Y
0aa65d22-05ee-43fb-9848-5768076b6192 | signoff | HOLD POINT
33e491dd-d442-4362-92c0-d151cc82328d | checkpoint | Production Property Test (3)
47350bc5-823c-586e-8614-ea9fc0f8c958 | note | Controlling Documents - Particle Size Distribution (4.2.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.8.1 (Wet Sieving Test)
34f650cf-0c33-501b-b46f-c9151d765568 | note | Acceptance Criteria - Particle size distribution as per Table 2 and Table 3, 4.2.3 Particle Size Distribution
d75a3d0c-2b9b-5b82-8da4-93dbcbe46b7d | note | Inspection or Test: Method - Wet Sieving Test (NZS 4407: 1991, Test 3.8.1)
d1c5232f-56f7-5449-8716-9c7bf46b98fa | note | Inspection or Test: Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006
15987af6-8c07-5803-8c9a-c08d9cb5a444 | note | Inspection or Test: Responsible Person - Quality Controller
d63d3d8b-bdf4-58b7-a0e7-bb5fc694e672 | note | Verifying Document - Test Report
87071bdb-d92a-5534-94cc-a1d1768362c4 | note | Inspection / Test Authority: Conduct - Sp or C or S
14943f2e-cfcc-59b2-8c61-9017fe78f337 | note | Inspection / Test Authority: Produce Record - Sp or S
20addf6f-e270-5780-be52-311bec24c925 | note | Inspection / Test Authority: Approval - E
a547be7b-8132-5422-a24f-37f22d509411 | note | Hold Point - Y
9e31adfa-e0bc-49e7-8898-b811763a57de | signoff | HOLD POINT
e2407041-8657-4f92-a295-c28b6e17402d | section | 1. Procurement - Materials: Cement
9b5668cb-25b5-4fd9-9e95-d102c89d15d2 | checkpoint | Stabilising Agent Selection
0aa6d8f4-54c5-54d3-8fde-b609c0b3ab99 | note | Controlling Documents - Cement (4.1.2) - TNZ B/5: 2008
67ba4dc8-2bbb-5339-b431-5e4d41ad543b | note | Acceptance Criteria - GP
0920d8e6-c50d-5f33-9aba-5a3b1b3c41a4 | note | Inspection or Test: Method - Visual inspection of supplier docket
b298e778-f98f-5215-903b-38f2d57faa4c | note | Inspection or Test: Frequency - per truck load
d41baeba-a5f6-53ef-bf87-7ee256e55888 | note | Inspection or Test: Responsible Person - Quality Controller
0ff1dcb5-cbda-5bf2-bae0-fdc515422b94 | note | Verifying Document - Supplier Docket, Supplier Cert
c7abac1b-d4fd-5040-b375-8b4b50267e59 | note | Inspection / Test Authority: Conduct - Sp or S
6475cbb6-173f-50f2-8fbd-96a7d12f800b | note | Inspection / Test Authority: Produce Record - Sp or S
5a3ad44b-8c3e-58cd-a434-f5fab6b20dcc | note | Inspection / Test Authority: Approval - C
da76d8c5-0087-50d6-85c6-22c4437275d1 | note | Hold Point - Y
1cee98e2-9786-4e0b-982b-0735bfd773dd | signoff | HOLD POINT
059fdd03-6161-477b-9727-660f5ff10ea9 | section | 1. Procurement - Materials: Water
16390631-c340-41c9-9eff-8bb372d136b8 | checkpoint | Water draw for stabilising
cbde19f1-4834-54bd-bdda-19d0cf1e9225 | note | Controlling Documents - Water (5.0.0) - TNZ B/5: 2008
6081c591-5e94-5b89-97b3-3dea930bf85e | note | Acceptance Criteria - Free from impurities justified by use of municipal water supply
f3a8cff0-0370-54b8-bdcf-cc27b06e0e4a | note | Inspection or Test: Method - Visual inspection
ce5e70a1-fe9f-50ec-bec2-54de5a9c1766 | note | Inspection or Test: Frequency - per truck load
43838bbe-213d-5a72-9ac6-63cfc598f169 | note | Inspection or Test: Responsible Person - Quality Controller
3c4c3c8d-a6a6-571d-af4f-0d451129c78e | note | Verifying Document - Hydrant use form
fcdcc0ff-27c3-5636-9ab2-eb2a7b8b3c10 | note | Inspection / Test Authority: Conduct - Sp or S
802a80e8-703b-5cee-84d3-a640a17c418a | note | Inspection / Test Authority: Produce Record - Sp or S
61d2cebd-0220-5f06-ad3e-34f9a781eca2 | note | Inspection / Test Authority: Approval - C
3b603bfe-3318-50b5-a105-25c22ffe93ae | note | Hold Point - Y
0688bd32-6209-4f8d-ad80-8e9262a554d6 | signoff | HOLD POINT
4ed52922-49a6-4086-8630-8695e260a49c | section | 1. Procurement - Materials: Geotextile
642701d2-8ecc-4c43-b363-d2d380cabfc2 | checkpoint | Geotextile (Strength Class C) A29 or greater
bddcaad8-6fd8-5ef2-94e4-87bb0f24155b | note | Controlling Documents - TNZ F7 Specification
95a5e8b6-c362-59c2-8d41-6ee6c9391d77 | note | Acceptance Criteria - Details on Docket
26fcf9e3-8401-5b93-8ef0-e22b4082b7cb | note | Inspection or Test: Method - Visual inspection
7f810466-642b-5249-99a1-c6ff8e2f2434 | note | Inspection or Test: Frequency - Per Delivery
8ef2c27b-96d6-5e0f-b0a0-879194d65972 | note | Inspection or Test: Responsible Person - Quality Controller
93b20ba1-a607-5243-8f14-cc4306b1ea55 | note | Verifying Document - MDS
a5834265-017b-51dd-a470-0d86647d37c9 | note | Inspection / Test Authority: Conduct - Sp or S
1e4beec2-18b9-5668-8c6d-1ce9285ed78a | note | Inspection / Test Authority: Produce Record - Sp or S
a2f750c9-846b-56a0-91ea-5dec96dc99f3 | note | Inspection / Test Authority: Approval - C
73d4524f-606e-5f06-8a05-676cebeeea34 | note | Hold Point - Y
07addb33-014b-4499-a123-11ffc722f700 | signoff | HOLD POINT
79e69efc-89be-4525-a7df-8d4c344cc0de | section | 2. Pre-Implementation
2d76ac9b-6370-453a-85ac-ad3b07aa4530 | checkpoint | Production Testing of stabilised material - OMC/MDD
5a7ff710-153d-5785-8e0b-5d32fd5967a7 | note | Controlling Documents - TNZ B/5 section 7.5 & 7.7.1
78c5d242-10a6-57d7-9e8a-e35483f0ebbe | note | Acceptance Criteria - To obtain OMC & MDD
933111ca-6c52-53a2-b83a-980e9e4db7b5 | note | Inspection or Test: Method - NZS 4402, test 4.1.3, New Zealand vibrating hammer compaction test.
2a9d2068-bf6b-5ff9-91b3-6315038025d5 | note | Inspection or Test: Frequency - Once on commencement and then each stablilised layer at one test per 5000m2
b44bbad0-2d33-56f8-995b-09a48758bf32 | note | Inspection or Test: Responsible Person - Quality Controller
7ed29be6-76d6-5f87-8cc6-c0434c05130d | note | Verifying Document - Test report
cae1af9e-8ca4-5b12-bfcc-3098a1398991 | note | Inspection / Test Authority: Conduct - C
e4e9fcde-7e57-58a3-a50a-35a3051ea913 | note | Inspection / Test Authority: Witness - C
52c90e5f-a0ea-5a14-9638-b0db2ab8f709 | note | Inspection / Test Authority: Produce Record - C
5b9bf473-dc55-5451-8bff-97c73eb030a4 | note | Witness Point - Y
fe70af60-9cdc-44a2-af0f-54c5dccb8a4a | checkpoint | Production Testing of stabilised material - Solid Density
a7ec8cd2-0891-557c-8995-317bbc4cf6c5 | note | Controlling Documents - TNZ B/5 section 7.7
919473b8-11c1-54c7-92b9-89dc9218ec06 | note | Acceptance Criteria - For info. and use in MDD calculation
d309796d-03a4-5926-b163-443282b36da5 | note | Inspection or Test: Method - NZS 4407; test 3.7.1
4f3ac400-eff1-5ab3-a9f3-3f3c19175390 | note | Inspection or Test: Frequency - Once on commencement and if any materials change
584a8b72-cbf5-5312-969e-474aaa8fd0b7 | note | Inspection or Test: Responsible Person - Quality Controller
59e7a533-fb1c-5d8f-b6fa-308e5630c420 | note | Verifying Document - Test report
0717a634-6e73-5e99-8230-897e12830a8b | note | Inspection / Test Authority: Conduct - C
76a791e4-52dc-5eff-bc50-968828f64e40 | note | Inspection / Test Authority: Witness - C
35bfe780-fd2b-590d-8a22-ae99e8d2d47d | note | Inspection / Test Authority: Produce Record - C
30cfd67d-27af-5c0d-b950-62a82ffc5897 | note | Witness Point - Y
73f9b8b7-8edf-46bb-8a3a-7bf7bfef6cea | checkpoint | Project survey setting out
15963842-2722-52cc-8619-313faec1c2e6 | note | Controlling Documents - Reference from Project Drawings
787de435-1a7f-5adc-bbe5-c68886fd809c | note | Inspection or Test: Method - Survey/Mobile Roads, Marks with Dazzle
4ae2fed7-54b1-5f44-b8c2-9db675705c59 | note | Inspection or Test: Frequency - Chainages for every different pavement sections
b45ed9f3-a2c8-5a6e-84a7-ac763b9d1932 | note | Inspection or Test: Responsible Person - Subcontractor/ Engineer
5108bdae-60ea-547b-990c-5875940a70ea | note | Verifying Document - Construction drawings
a411a29d-9421-5e52-85f0-5c395e392f37 | note | Inspection / Test Authority: Conduct - C
c7a99bd7-9778-5aed-a409-1a46ac1f44b5 | note | Inspection / Test Authority: Produce Record - C
2bd95e1b-4591-5ff3-baac-67d0244db7b5 | note | Witness Point - Y
d8916ed7-c7f9-4696-9de5-b1857971d3be | section | 3. Construction - Pre-treatment Digouts
e9eb0ebe-0e55-4140-a360-a9845deed337 | checkpoint | Pre-treatment Repair Method Selection
bc720e0b-5d5b-5781-8e34-f75ad9c58059 | note | Controlling Documents - Site specifics to be confirmed
e6ee788a-89e7-5ab1-ab80-c745ee61fd32 | note | Acceptance Criteria - Confirm scala acceptance criteria based on treatment type
d0bcef0d-8c36-5bcc-87e1-e549f6be4825 | note | Inspection or Test: Method - Scala Penetrometer on Excavation Floor
5b897e3d-d2bb-567f-a988-4c8e2016b8b0 | note | Inspection or Test: Frequency - As required
c93a57ad-d9b6-5257-989a-48fcb52a03ec | note | Inspection or Test: Responsible Person - Quality Controller
0c28b6c1-26f4-57b0-a286-dd653d32e2b7 | note | Verifying Document - Agreed treatment plan
b2f01738-be58-50f5-9662-7d08f2ecfa00 | note | Inspection / Test Authority: Conduct - S
cbb36196-1194-5959-aff0-7003568f6da2 | note | Inspection / Test Authority: Witness - C
3ffeee03-efeb-517a-b435-351beec9caef | note | Inspection / Test Authority: Produce Record - S
b4d851ca-d8f0-5478-94e4-f1cba356f1b2 | note | Inspection / Test Authority: Approval - E
75d8fc2a-ed6d-5aaf-bc6a-f92bae36d172 | note | Witness Point - Y
335d3639-8714-4322-a80f-4d2df7eabc5d | checkpoint | Digout of Patches to repair
6ed0e819-33a8-5084-9416-1c7e93af177e | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
89e68fef-8be5-5d22-bc4f-f9dbdc14546c | note | Acceptance Criteria - 250mm deep unless specified
a3362b65-b8c1-5aa4-9312-0c3aa7913c2c | note | Inspection or Test: Method - Visual inspection
47b8b782-d72b-5e36-914d-826901108561 | note | Inspection or Test: Frequency - As required
a0142372-87de-5923-b50f-62c9a7c943c8 | note | Inspection or Test: Responsible Person - Quality Controller
f90bc3f1-cf97-5f69-9752-a348c75634ea | note | Verifying Document - Dig out site records/ Asbuilt
0aefc4ab-0595-5f30-b09c-5c2dee102dd8 | note | Inspection / Test Authority: Conduct - S
02cb198e-caca-5d17-94a5-b3e85029437c | note | Inspection / Test Authority: Witness - C
5cb76fff-b57a-57eb-8f31-5597ae03314e | note | Inspection / Test Authority: Produce Record - S
85e161c2-57a0-5788-b768-be6c76729085 | note | Inspection / Test Authority: Approval - C
8cc45a22-efe8-5ef9-b08c-c329592da976 | note | Witness Point - Y
69188968-ca2c-461c-9973-a2a1098c5305 | checkpoint | Subgrade material hardness, Check base of excavation
b76c499d-0af4-5a87-bc36-613b55412255 | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
3c5f3ec7-7e91-5a51-8e6f-b967bb5720f8 | note | Acceptance Criteria - Scala > 3 blows per 100mm
9f20d644-2c18-5b0c-b179-4ce9a5cc12b8 | note | Inspection or Test: Method - Scala Penetrometer test on base of digout
12a24390-aa0e-5f83-b6bc-5d040b15b8d8 | note | Inspection or Test: Frequency - As required depending on size of digout
9b3aac9c-94a2-5a0e-8082-91b1e72a412d | note | Inspection or Test: Responsible Person - Quality Controller
39664e24-880d-587d-a175-a27be8053d36 | note | Verifying Document - Test report
acf4c6df-2ce8-581d-ad85-2eb633840596 | note | Inspection / Test Authority: Conduct - S/C
f5e763d4-d300-5fc3-8b90-dad7ce42831a | note | Inspection / Test Authority: Witness - C
18d07528-1f37-5c43-bb3f-ca5b9e0f9cc0 | note | Inspection / Test Authority: Produce Record - S/C
f4647f02-17d9-5e39-867e-504c7698a732 | note | Inspection / Test Authority: Approval - E
f7cf5b80-5409-503d-8474-3afa9ac938a6 | note | Witness Point - Y
c7e4be82-e94c-4c20-af68-b6a1bf73d44f | checkpoint | Geotextile (Strength Class C = A29) Layer beneath treatment layer (if rqd)
b68abe2e-4817-5aef-9429-fb8a0c40b135 | note | Controlling Documents - TNZ F7 Specification
fc466622-c51f-53a3-8d36-d9f43d7f0a2c | note | Acceptance Criteria - Meet TNZ F7 Spec.
171c553c-a7b2-5d17-9f3e-0c68c729dd2e | note | Inspection or Test: Method - Visual inspection
bd456fdd-cb87-582e-ac75-614ff92fd99f | note | Inspection or Test: Frequency - Per Delivery
a0057325-be54-5399-9074-b47e34bdec78 | note | Inspection or Test: Responsible Person - Quality Controller
c6cffbd4-e20b-5eb0-acdc-81cadc3dc63f | note | Verifying Document - Certificate of conformance
4c2be017-7a5f-5c78-866b-0653f50e4805 | note | Inspection / Test Authority: Conduct - Sp or S
7e2d8d4f-215d-598d-87e5-48773922746a | note | Inspection / Test Authority: Produce Record - C
cd25dca0-867f-50e7-9a01-2bcbd434668d | note | Inspection / Test Authority: Approval - C
a9026e3f-2938-58a8-83e6-e897ee60844b | note | Witness Point - Y
c6e97265-97ec-4d89-b45c-4dc1022f6841 | checkpoint | Place and compact GAP65 in digout area
fc81e680-67b0-5cdd-8e61-d3e2ea9f3af3 | note | Controlling Documents - Higgins SOP 0128 - Digout Repair
4f635bfd-a887-5994-98ca-d70b351163c5 | note | Acceptance Criteria - Clegg value > 45
724ca453-ec0c-55bf-8819-757ddb5b27f0 | note | Inspection or Test: Method - Clegg Test
756dde66-fb29-5075-a449-b7ac93e20b25 | note | Inspection or Test: Frequency - Min. 2 per digout
54786702-4513-542e-8249-5b1c33742e96 | note | Inspection or Test: Responsible Person - Quality Controller
5f756737-cd04-5edc-8c98-a72f5698265b | note | Verifying Document - Test report
4faaf34f-8c2c-5419-8e1d-61d121ef249a | note | Inspection / Test Authority: Conduct - S/C
284bcbee-bee1-5841-b1a4-5b548b220cf2 | note | Inspection / Test Authority: Witness - C
acceeee3-938a-5b70-b668-a390bb6af816 | note | Inspection / Test Authority: Produce Record - S/C
4a759cf0-5bb1-5768-8c20-023863721102 | note | Inspection / Test Authority: Approval - E
9b599195-0397-57aa-a047-ece94fa8c87d | note | Witness Point - Y
5d1a73bb-d6f8-4dff-8eeb-e1139530420e | section | 4. Construction - Granular make up and In-situ Modification
da3f02a2-9c60-4d25-92b5-74061f19321a | checkpoint | Place M/4 AP40 Basecourse Material
18d9d13d-292d-5555-ac39-7afe18b21a5d | note | Controlling Documents - TNZ B/5 (section 7)
de307442-bf34-58cf-ad51-9da3f08dc607 | note | Acceptance Criteria - Evenly spread, no segregation, placed near optimium moisture content
42af3aed-8fda-5ae3-8c95-6344ff76b889 | note | Inspection or Test: Method - Visual Inspection
3e4876e6-e864-5288-bb2b-b5b72ff93a2f | note | Inspection or Test: Frequency - On completion of placement
c2d0bc91-b1b6-59ff-8b53-16b4f7928c02 | note | Inspection or Test: Responsible Person - Quality Controller
3894f64a-d94b-5b60-b210-19210f9b2b8d | note | Verifying Document - Photographs and Daily Site Record
a1082260-227d-51eb-97ce-9dc42b1c2303 | note | Inspection / Test Authority: Conduct - S or C
3d5e92b5-b735-5b87-a97d-8d10753615aa | note | Inspection / Test Authority: Produce Record - S or C
73ad62e0-b67f-5ac1-b88e-7e29d997f7dd | note | Inspection / Test Authority: Approval - C
8cbb59bb-6723-5283-b259-a303dd2c0bec | note | Witness Point - Y
58aacd56-8bf8-4af4-a53d-7e41cb3ff84c | checkpoint | Spreading of Cement
77cf1189-4b4a-58d2-ad6a-801870821b99 | note | Controlling Documents - Spreading of Cement (7.3) - TNZ B/5: 2008
ba99140f-2ec5-513c-8652-17b2e9f6b1cc | note | Acceptance Criteria - Within ± 0.5 kg/m² of the specified rate and within ± 2.5% of the specified rate
0b0527bb-b078-58e3-b400-5dc960d6668e | note | Inspection or Test: Method - Mat test (1m² canvas) and Average Usage Test
7d4c57f8-8d17-5ff6-bada-8435eaab96f1 | note | Inspection or Test: Frequency - per 400m² and upon emptying the spreader
b13029a9-e5c8-5f81-badf-f8a3619bdafc | note | Inspection or Test: Responsible Person - Quality Controller
08c8d381-d7dd-5763-a8b6-6dd82c09f565 | note | Verifying Document - Mat Test Form and truck dockets
88640ed6-ede3-5e6b-8c3f-bae1c7cd5910 | note | Inspection / Test Authority: Conduct - S or Sp
f23de8f9-2096-535f-8276-9a53f3ebbefb | note | Inspection / Test Authority: Witness - C
804974fa-fc2e-562e-8791-1f1480da9ad5 | note | Inspection / Test Authority: Produce Record - S
31916213-5679-569d-b7a3-2f3e109d48d0 | note | Inspection / Test Authority: Approval - E
20ec9f0d-c9df-507c-9d30-25c3de2eb466 | note | Witness Point - Y
2d58b073-ee8f-4b6b-bb6d-46c315a2ae3c | checkpoint | Addition of Water
b2d4c0ec-9918-5184-b665-2a74ccb501af | note | Controlling Documents - Addition of Water (7.5) - TNZ B/5: 2008
6dad7a3e-9b22-5936-a15c-f57e4b6411cb | note | Acceptance Criteria - 90-100% OWC
6dd732a1-ffc8-535b-a1bc-adc169117918 | note | Inspection or Test: Method - Nuclear Densometer Testing prior to Stabilisation
4d636e1e-daa3-56dc-8d3b-5b83618eb59b | note | Inspection or Test: Frequency - ≥1 per 1000m² lot
1fd31863-4c79-5e04-b912-b9da97573261 | note | Inspection or Test: Responsible Person - Quality Controller
23466adf-7b89-5c04-ab35-7560cbf6e135 | note | Verifying Document - NDM Record
ab9cec8d-6733-5da7-b158-58af66111f18 | note | Inspection / Test Authority: Conduct - S
7674fa0f-11ca-58e4-9b4f-9520721788e7 | note | Inspection / Test Authority: Produce Record - S
04a6aa83-ef0e-57e5-b089-cd587d8ad3de | note | Inspection / Test Authority: Approval - C
e748fc05-3194-50c4-a33d-700e4b12670b | note | Witness Point - Y
57c0442f-529a-4b23-8090-5f2ad6dd44bd | checkpoint | Cut Depth
10b59058-9b94-5260-a464-311036c990d6 | note | Controlling Documents - Control of cut depth (7.6.1) - TNZ B/5: 2008
21e29e63-ed94-54da-b8cb-9c7b808ba923 | note | Acceptance Criteria - -5mm and +15mm of design stab depth
37b7090d-0f48-5d8f-827e-ce1906100efd | note | Inspection or Test: Method - Physical Measure and Visual Record
2b5b1271-f582-58f0-8aa4-84604225f1db | note | Inspection or Test: Frequency - ≥1 per 200m of cut length
ac3b45a4-7f68-5e54-92a3-4b93e66dbae9 | note | Inspection or Test: Responsible Person - Quality Controller
3ae0b16b-6a41-58d0-af29-f4e51229ee1b | note | Verifying Document - Photographs and Daily Site Record
2bd20a74-cda0-5d23-bcce-a70b37abff82 | note | Inspection / Test Authority: Conduct - S
4bfd326a-44d8-52dc-ad8a-c9ff6a27591e | note | Inspection / Test Authority: Produce Record - S
c1fb8c8c-a652-53f8-8c42-2e6adedf2c77 | note | Inspection / Test Authority: Approval - C
93d0287d-85dd-5f7b-af70-d5d7a5132467 | note | Witness Point - Y
6acfe076-37d5-4ba0-a5e4-7136509ec839 | checkpoint | Longitudinal Joints
cb638e2a-d091-5d70-b63a-f6f6c4fabd12 | note | Controlling Documents - Overlap on longitudinal joints (7.6.2) - TNZ B/5: 2008
689abe89-81ff-5cb2-b447-06fde0154bae | note | Acceptance Criteria - The minimum of 100mm or half the layer thickness
5e3066e7-1d15-5805-a40f-dafb3092f6e9 | note | Inspection or Test: Method - Visual Record
dacc1727-ec3b-505b-ba92-3b656bd18e96 | note | Inspection or Test: Frequency - per sucessive cut
4f5d5c5f-99ea-516d-9ae3-5ff26a44c5f6 | note | Inspection or Test: Responsible Person - Quality Controller
d52c9675-08bb-5dda-8f8f-7714db25cec5 | note | Verifying Document - Photographs, Daily Site Record and Stabilising Plan
140ae0a9-d9df-54bc-804f-5ec85c359af0 | note | Inspection / Test Authority: Conduct - S
d3c388c7-ad7b-58b7-b191-be4a6c4873f2 | note | Inspection / Test Authority: Produce Record - S
14cc2442-94f3-5bc8-b69c-93ccf1e382e4 | note | Inspection / Test Authority: Approval - C
7cd5f047-e336-51a2-84f7-5529b25a66e9 | note | Witness Point - Y
33af1c63-9b8e-4165-805d-2637e6c7da25 | checkpoint | Continuity of Layer
ecb69365-0bf7-55f9-9953-2fc640a5d8b2 | note | Controlling Documents - Continuity of stabilised layer (7.6.3) - TNZ B/5: 2008
979a8767-6b8a-5485-bbc4-ca901640f1c5 | note | Acceptance Criteria - Longitudinal overlap 1m for cement, 5m for bituminous stabilising agents
a5c44a5c-102e-5cbe-9481-19ead2bd79ef | note | Inspection or Test: Method - Visual Record
097a5e20-6a95-52d4-9d2d-b5f99d8d57b4 | note | Inspection or Test: Frequency - per sucessive cut
5e44be84-d3ad-5329-b378-c4862a5cdbe2 | note | Inspection or Test: Responsible Person - Quality Controller
33cac8eb-3edd-57b9-9916-d04cbc41a89e | note | Verifying Document - Photographs, Daily Site Record and Stabilising Plan
e3954323-d4fb-5fba-bc02-9311c82208ae | note | Inspection / Test Authority: Conduct - S
c0946171-296b-5067-9db2-812373d2cc74 | note | Inspection / Test Authority: Produce Record - S
c9b5e02a-4171-5e59-a377-5ca661cb7220 | note | Inspection / Test Authority: Approval - C
acb7b73e-e7b5-5f96-814f-c829745506f6 | note | Witness Point - Y
bf55b511-840a-43c9-b803-fd30477183bd | checkpoint | Stabilised Material Particle Size
a90c6629-06e0-5f4f-bda3-90230456efb5 | note | Controlling Documents - Particle size distribution of stabilised material (7.6.4) - TNZ B/5: 2008
4a013ab8-0390-51b8-9dab-95dbf6afea06 | note | Acceptance Criteria - No excessive breakdown of stabilised material
7be13453-31a2-5717-8200-4beb14f4c4ea | note | Inspection or Test: Method - Visual Record
e700bfc5-d5b0-594e-8e48-a9bc3621ef45 | note | Inspection or Test: Frequency - within 20m of each section and then regularly based on material variability
c1883c9f-92f8-56b7-85aa-79c1cadab749 | note | Inspection or Test: Responsible Person - Quality Controller
ee401d88-898d-50a1-b24a-0cd71434d928 | note | Verifying Document - Photographs
92883e7a-3192-5ca4-85a6-cb16ebe6cd0e | note | Inspection / Test Authority: Conduct - S or C
c38ecd5c-acf1-5e44-b9d2-9300d9920da4 | note | Inspection / Test Authority: Produce Record - S or C
9ea334b8-00ed-5545-b61b-3c46c0ab55bd | note | Inspection / Test Authority: Approval - C
d043f73f-67d7-5f0e-9bff-2e7cf44dcace | note | Witness Point - Y
07948c37-fc51-49d9-9696-b7cd4d46b0e5 | checkpoint | Establish Compaction Methodology - type of plant, number and speed of passes
d2002ada-63f1-5620-94d9-a8788fe90f63 | note | Controlling Documents - Compaction (7.7) - TNZ B/5: 2008
3f6e70c7-ba0a-5d5a-9b70-976c8e1ce035 | note | Acceptance Criteria - To establish type of plant, number and speed of passes to achieve MDD
c1ca89bc-ab98-5669-94db-cb325d5b2f74 | note | Inspection or Test: Method - Plateau Density Testing
16147299-24cc-585a-ac94-34c9cac94cd3 | note | Inspection or Test: Frequency - 1 time, or additional tests when material changes visually
5932e08c-0f02-5dad-b715-7dd20de8522d | note | Inspection or Test: Responsible Person - Supervisor
cc29d40a-a710-5164-9e2e-0d885f1f887e | note | Verifying Document - Test record
3a3c9e11-d3f3-51b6-ad75-b4ca5426d3a4 | note | Inspection / Test Authority: Conduct - S or C
bbb5c031-91c5-50e6-a130-bd9310712298 | note | Inspection / Test Authority: Produce Record - S or C
9e42a3bc-3e6a-5b61-8221-d070b3d0ed64 | note | Inspection / Test Authority: Approval - C
16e7500a-d39b-54a3-b868-28435332ed3a | note | Witness Point - Y
1a9c48ed-175c-4db4-b2f8-9b2b01822a80 | checkpoint | Establish Compaction Target
7121a32d-2776-56d5-a71b-9be768f310d4 | note | Controlling Documents - Compaction (7.7) - TNZ B/5: 2008
77538ae0-1f57-5834-a492-e1df265bc35f | note | Acceptance Criteria - To provide MDD for NDM testing
71cc9a63-7a00-5d5c-94d2-262d4fcfa01c | note | Inspection or Test: Method - Plateau Density Testing
5cd16ac6-da13-59a1-b96f-dd23fc59e0ce | note | Inspection or Test: Frequency - Minimum once per Lot. A lot shall not exceed 1000 m2.
215f74b9-85d2-59c8-878d-657f5919f095 | note | Inspection or Test: Responsible Person - Quality Controller
a282520a-3302-5375-ae45-69d420c9b2fd | note | Verifying Document - Test Record
5afe7002-0233-598f-b5aa-f7a968e00b33 | note | Inspection / Test Authority: Conduct - S or C
666d3f51-74dc-5b3a-9787-212cb28d0955 | note | Inspection / Test Authority: Produce Record - S or C
8a831c28-e8bd-50d0-8822-6e3d2074869b | note | Inspection / Test Authority: Approval - E
5c6571ef-3170-530d-84bb-ba3d5b056c2d | note | Witness Point - Y
7981a93d-7094-41df-a953-62dbe001ed1d | checkpoint | Degree of Compaction - MDD to obtain target for NDM testing (1)
4ee2010a-a735-575d-980f-d60e3a0c8090 | note | Controlling Documents - Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008
3fd600cb-3e60-5a73-a5ef-b9f1a08d2376 | note | Acceptance Criteria - To provide MDD for NDM testing
a478e7d3-f873-585b-a84b-16ad8e253c48 | note | Inspection or Test: Method - Laboratory MDD at OMC NZS 4402 test 4.1.3.
b76a5d90-c7e5-55a8-bc40-b4c85a7e1da5 | note | Inspection or Test: Frequency - Minimum once per Lot. A lot shall not exceed 5000 m2.
3c850e66-0c60-56dd-9530-2b28ea3967f4 | note | Inspection or Test: Responsible Person - Quality Controller
08722ad6-7f81-50c7-a8f2-fac0da28571d | note | Verifying Document - Test Record
8a6797f6-d816-5382-b20c-c5333853350f | note | Inspection / Test Authority: Conduct - S or C
478af0bf-69cf-5428-b36b-aae21b2b890a | note | Inspection / Test Authority: Produce Record - S or C
e1df8f1a-81ea-5614-93a7-8d8b4c391679 | note | Inspection / Test Authority: Approval - C
d6ae9bca-5e4f-5246-89da-313e4e37f1e8 | note | Witness Point - Y
72ec71fa-d409-4523-ad66-ee7a17962fa9 | checkpoint | Degree of Compaction - MDD to obtain target for NDM testing (2)
52a4ed2d-9f0f-583e-a737-5dd15b239edd | note | Controlling Documents - Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008
999b95cc-bce0-58d7-986a-e969d7991701 | note | Acceptance Criteria - Formally agree with the Engineer the MDD target, based on review of the lab. MDD and the site plateau test
02b7e7fc-264d-5f38-b350-8026343ed518 | note | Inspection or Test: Method - Plateau Density Testing Lab. MDD
6766d45e-a95b-511f-adc5-3050c4c1ed44 | note | Inspection or Test: Frequency - At commencement of construction and whenever materials change
69c44744-eaf4-5e16-8375-a4df9e9f65a3 | note | Inspection or Test: Responsible Person - Quality Controller Engineer
c96571bb-707f-5ef4-b09a-1b8e0d343055 | note | Verifying Document - Notice to Contractor/ Notice to Engineer
edab5a01-096b-5fff-b3b0-657cbb37bc23 | note | Inspection / Test Authority: Conduct - S or C
ccca77a6-6ccb-53a2-993c-599eb7456793 | note | Inspection / Test Authority: Produce Record - S or C
1d9a1be5-7722-57fc-91fb-c7c907791cfc | note | Inspection / Test Authority: Approval - E
0f8d3083-45b6-540c-b07a-c6c8c09bd9f3 | note | Witness Point - Y
92b14b99-7aa0-462f-b283-7c0f0de2918d | checkpoint | Compaction Acceptance
d5eda3d9-87cc-5367-a278-511bf89ee34c | note | Controlling Documents - Acceptance criteria for stabilised pavement layer compaction (7.7.1) and Table 5 - TNZ B/5: 2008,
07ceaea9-04e7-5939-8f0f-b4461f52435a | note | Acceptance Criteria - Mean value ≥ 98% and Minimum Value ≥ 95%
7e968d91-aed8-5f86-8087-5417dcdbfab8 | note | Inspection or Test: Method - Nuclear Densometer Testing
379da687-ba57-50eb-a92c-f00a1e35cd81 | note | Inspection or Test: Frequency - ≥ 5 tests per 1000m² lot
396d8071-777a-5930-92c2-a1d73b2d521f | note | Inspection or Test: Responsible Person - Quality Controller
3341d6d9-e240-5e73-abfb-ec2fb18d0f0a | note | Verifying Document - NDM Record
3f17535e-de55-5228-8ac6-6ac804f40d3c | note | Inspection / Test Authority: Conduct - S or C
776682f3-690b-55e6-8062-25945fa86dc6 | note | Inspection / Test Authority: Produce Record - S or C
e714a92a-50e3-5fe1-b5f9-002fdd7c4eb9 | note | Inspection / Test Authority: Approval - E
b53293f7-6d97-5efd-bd8b-de897b054405 | note | Hold Point - Y
6f49f8c5-2dc2-42ca-8735-85028b64c7b3 | signoff | HOLD POINT
d05012e7-0325-49dc-a020-f04a7ed86efb | checkpoint | Control Testing (if required)
32c65757-7103-5dd2-bf73-32daad73e735 | note | Controlling Documents - Control testing during and after construction (7.7.2) - TNZ B/5: 2008
bc9e3026-fc9a-5c18-82ca-43e3d4e2a29a | note | Acceptance Criteria - Nil
c37efe73-c678-513e-bd32-caaffd81856b | note | Inspection or Test: Method - Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3)
48e2cb48-066f-58c0-8fc2-38a911cc10e0 | note | Inspection or Test: Frequency - when agreed with the Engineer
8ddda0fb-550d-5b0a-8fbc-135eabc5e3f6 | note | Inspection or Test: Responsible Person - Quality Controller
1646518a-0bbf-568a-9aa1-ccef8e5da359 | note | Verifying Document - Test Report
6853c4cc-8fcb-5f7b-8f24-36c91a5571c5 | note | Inspection / Test Authority: Conduct - S or C
67fe362c-7495-5ed3-bb37-70b9ab9769ea | note | Inspection / Test Authority: Produce Record - S or C
7c73a1d6-83c9-5bb9-a061-8765a6acb6f3 | note | Inspection / Test Authority: Approval - E
15ff7386-1dc2-5046-b791-b16c759b9856 | note | Witness Point - Y
5dbcb3ac-7b9e-4282-be5d-3f8708f13615 | checkpoint | Surface Smoothness
82896ab8-e039-573f-b10e-c1d3b9413ce0 | note | Controlling Documents - Surface shape (7.8) - TNZ B/5: 2008
16bc41f7-1c4a-5f6e-82ff-a3401d75faeb | note | Acceptance Criteria - ± 10mm deviation along a 3m straight edge, No water ponding
e988f056-5b5d-532c-bb42-8f7a215eb173 | note | Inspection or Test: Method - 3m Straight Edge
62f98971-c420-5abc-9113-fbe18c1ca026 | note | Inspection or Test: Frequency - during construction and prior to seal
5981ed23-a84f-5c05-a52f-6ea18f95e4ac | note | Inspection or Test: Responsible Person - Supervisor
b794e721-7d85-54df-99fc-502928765119 | note | Verifying Document - Photographs
f5a2fd35-6b29-5254-b5b5-10607231fb7b | note | Inspection / Test Authority: Conduct - S or C
130544c7-321e-57a1-905f-bdb5f5f3522b | note | Inspection / Test Authority: Witness - C and E
0051c1cc-db67-5f71-97a0-3eed1ae244f1 | note | Inspection / Test Authority: Produce Record - S or C
4f27457f-f179-5699-8e0d-e9bf0b805b33 | note | Inspection / Test Authority: Approval - E
ae3fc963-9bdd-50f1-8142-ec24c11ab806 | note | Witness Point - Y
a1089b5f-24e6-40d7-bccc-2f932222ed48 | checkpoint | Surface Shape
04aa4e94-27e6-5c71-b7e0-9503bf157a72 | note | Controlling Documents - Surface shape (7.8) - TNZ B/5: 2008
6cd2ad0d-039a-5e7c-8f09-9565dcba0947 | note | Acceptance Criteria - Between -5mm and +15mm
d8c31755-562e-5001-a54b-82d70e6e413b | note | Inspection or Test: Method - String lines or Survey Asbuilt
8f2662d6-d153-59a3-aad5-80d026c0e627 | note | Inspection or Test: Frequency - during construction and prior to seal
58551138-8769-5432-b3c5-3cda83ad831b | note | Inspection or Test: Responsible Person - Supervisor
6e648dc5-443c-511b-808f-234e646e0bf3 | note | Verifying Document - String Sheet/Survey Asbuilts
af8e6d6e-f754-517b-9b50-fb9a285efbe8 | note | Inspection / Test Authority: Conduct - S or C
ace3b349-d1a8-5d39-9b11-14fdf2b8a152 | note | Inspection / Test Authority: Witness - C and E
1799f3a2-6ded-5589-96b1-7b8df4a90ad2 | note | Inspection / Test Authority: Produce Record - S or C
cec4d15e-14cc-57ec-b882-21e34f45eab6 | note | Inspection / Test Authority: Approval - E
a53013ee-126c-5bcd-aaed-49b0ecbe3b4c | note | Witness Point - Y
41912605-7475-4ab2-9f4e-b85bf7d6ff66 | checkpoint | Cross Fall
c73290f5-0d4b-5078-8a19-4e365c5b5689 | note | Controlling Documents - Crossfall (7.9) - TNZ B/5: 2008
08b31051-4299-5c40-a013-8a403467d520 | note | Acceptance Criteria - 0.5% ≤ X ≤ -0.5%
017fddb2-19b0-5aa6-91a3-c24d5afca260 | note | Inspection or Test: Method - 3m straight edge or Survey Asbuilt
3b37e7d2-c5bb-5b86-85dd-41b9b650537c | note | Inspection or Test: Frequency - during construction and prior to seal
bd0ece61-2047-584d-aa71-ef158599e43b | note | Inspection or Test: Responsible Person - Supervisor
86a7196e-1e82-59f4-bed8-47ce86bd8681 | note | Verifying Document - Cross Fall Records/Survey Asbuilts
fe334129-2f8b-5eaf-9a0f-ec1b8987647c | note | Inspection / Test Authority: Conduct - S or C
eb9240e4-95b6-5f22-90bc-6c72b6447b1f | note | Inspection / Test Authority: Witness - C and E
35793324-15f7-5d6b-9541-4dc75743cd74 | note | Inspection / Test Authority: Produce Record - S or C
cadba572-fa87-5bcb-9352-ec82aa68cc7e | note | Inspection / Test Authority: Approval - E
785cdcc5-9638-5afb-a4b2-06d4d67084a1 | note | Witness Point - Y
78dc6aab-773a-408e-bb35-b042318bae4a | checkpoint | Surface Finish
86141e7c-ff1f-576a-bc1c-95e2d9ba215b | note | Controlling Documents - Surface finish (7.10) - TNZ B/5: 2008
14cfd44d-8d14-551b-9ab3-1af1ce1890d1 | note | Acceptance Criteria - Tightly bound matrix post sweep
7fffa3bd-40fc-5972-9bfe-5a948c8273c5 | note | Inspection or Test: Method - Visual inpsection
0daff8f2-305e-53dd-be67-9a943f0c3041 | note | Inspection or Test: Frequency - prior to seal
faadedd5-015b-5912-879b-4ef699046637 | note | Inspection or Test: Responsible Person - Supervisor
bee99316-02b1-5724-b8eb-0eff892dff54 | note | Verifying Document - Pre-seal inspection sheet
4871ef9d-c788-5c0a-a06e-006b31e540bc | note | Inspection / Test Authority: Conduct - S or C
b3143059-34b8-574b-91df-12a797f0998f | note | Inspection / Test Authority: Witness - C and E
4e02ad59-2da9-5c75-b96e-0642c32aef07 | note | Inspection / Test Authority: Produce Record - S or C
4cf25520-a648-58d0-9e6c-84b02958569a | note | Inspection / Test Authority: Approval - E
22bdca25-fa47-5aaa-b9cb-19e0cb6db4d1 | note | Witness Point - Y
ef02b4bc-fdfd-4cf9-bd72-c61b42f85e27 | checkpoint | Degree of Saturation, DOS
3a91868d-691f-5412-a523-3856b300d678 | note | Controlling Documents - Pre-sealing requirements (7.12) - TNZ B/5: 2008,
8b8f9189-db6b-5427-ac03-a4f76d38893f | note | Acceptance Criteria - ≤80%, however 65% is ideal
98ac4788-5aa5-5f40-b344-e61ad640d6c7 | note | Inspection or Test: Method - Nuclear Densometer Testing
9e5cb5a5-07c3-5c15-9b21-45f5e778627d | note | Inspection or Test: Frequency - ≥5 tests per 1000m² lot
8e63e8a3-a6c5-58a9-acf2-206ca0865554 | note | Inspection or Test: Responsible Person - Quality Controller
c19d8323-3132-5298-951f-40406110693f | note | Verifying Document - NDM Record
8ea7f97e-f977-553c-9897-86feb94a63d0 | note | Inspection / Test Authority: Conduct - S or C
cf6d3c17-af79-5e6b-9a32-4b7eb3866a8c | note | Inspection / Test Authority: Witness - C and E
d5ba5d34-0655-5f27-804e-ba956cbf5df2 | note | Inspection / Test Authority: Produce Record - S or C
57da92fb-a361-54d3-80bc-b987dcb60db6 | note | Inspection / Test Authority: Approval - E
0a844d12-d677-50ee-81f3-6b54bde301d6 | note | Witness Point - Y
9786d472-a243-4666-b28b-1b377789bf52 | checkpoint | Roughness (NAASRA)
d796ea33-393f-5f3b-afde-c653cb984530 | note | Controlling Documents - NZTA Maintainence specification section 6.1.2
ed668dee-71b5-50d0-9f52-482e2e2bca85 | note | Acceptance Criteria - For chipseal or non structural AC surfacing; No 100m moving average shall exceed 2.9 lane IRI.qc m/km 75 NAASRA counts/km
4ae74ee6-26d2-5ca2-80e1-5d1cc14f2aa2 | note | Inspection or Test: Method - NZTA Maintainence specification section 6.1.2
41c6c7db-0698-5de5-87a0-3ea6d2858cb9 | note | Inspection or Test: Frequency - Average of three replica runs for each lane reported at 20m intervals.
27956184-8a8b-514b-abc5-47c1238bb659 | note | Inspection or Test: Responsible Person - Quality Controller
0b9b3298-f615-51de-bb23-41aafe1c6405 | note | Verifying Document - Test Records
15eb6a92-dd66-5fa4-9dae-75f35b3006e6 | note | Inspection / Test Authority: Conduct - S or C
bf1f05a6-fae7-5ac6-8bf5-0b672bbd0e02 | note | Inspection / Test Authority: Witness - C and E
a61c8b1d-2483-535a-ae45-a69a050896e0 | note | Inspection / Test Authority: Produce Record - S or C
71fffa68-f4a5-5f2d-9fd0-c24a4f1a66fa | note | Inspection / Test Authority: Approval - E
ace6fa68-17a0-5c7e-82de-fcbde72e0ccd | note | Hold Point - Y
3e81dfae-f06f-463e-9092-43ba3d721041 | signoff | HOLD POINT
01ce564f-7fc2-4e46-acb8-a1f9a0e20d45 | section | 5. Chip Sealing - 5.1. Procurement - Chipseal Resurfacing
97d66873-8dc3-4054-9b4e-e10b7368de76 | checkpoint | Binder - Penetration Grade
be0ffe82-94ca-5d8d-b209-f2f808644768 | note | Controlling Documents - TNZ M/1
fcacae7b-f1c9-5055-a4c3-2a2055230ec1 | note | Acceptance Criteria - Table 1
04795652-c384-56c7-916f-254807d4ec76 | note | Inspection or Test: Method - Property Test
7bba96df-889d-51fa-b7e6-124412aee5a4 | note | Inspection or Test: Frequency - Annual
6996d93a-9ae1-5dbd-bbc5-2830477d5762 | note | Inspection or Test: Responsible Person - Bitumen Supplier/ Surfacing Project Manager
73a9b140-daba-5bad-a26b-7f0c06db0f96 | note | Verifying Document - IANZ Report's
309c0823-79c0-5c5c-9e74-552ed1de902d | note | Inspection / Test Authority: Conduct - C
fbadaf17-0315-52ae-84a4-fad94569b257 | note | Inspection / Test Authority: Produce Record - C
4961b918-4c60-5049-883b-af19cc11ca28 | note | Inspection / Test Authority: Approval - N
fa453e15-84d6-50d4-a5d5-ae8bb5eaf3b6 | note | Witness Point - Y
94d1a831-bfad-45a9-a8b7-c5788c7d88e9 | checkpoint | Binder - Polymer Modified Emulsion
aae6ba43-3077-5fdb-9937-00e9c6bdb1c6 | note | Controlling Documents - Higgins Internal Specification
b2ac592d-9261-5736-9961-0af6241399fc | note | Acceptance Criteria - % PMB Required, PH, Residue by Evaporation, Viscosity
e1a422f3-cea9-56ab-90a8-1ad1c6bef7a8 | note | Inspection or Test: Method - Property Test
c5b0623e-8f1e-585f-905b-360c30864b14 | note | Inspection or Test: Frequency - 1/100,000 litres supplied
662cdb05-f89a-5846-8af1-188d06695fb8 | note | Inspection or Test: Responsible Person - Bitumen Supplier/ Surfacing Project Manager
78af65fe-13f6-54ab-b5fa-5d1f0238357c | note | Verifying Document - IANZ Report's
041b000b-ad92-592d-8607-a2f030546b4d | note | Inspection / Test Authority: Conduct - C
c7f880ed-8a38-51c3-b3d6-69916f435703 | note | Inspection / Test Authority: Produce Record - C
cd3836de-bef4-584c-ae47-5930266f94aa | note | Inspection / Test Authority: Approval - N
eb76e85a-8321-540c-93ff-ceed92ef0b98 | note | Witness Point - Y
fb9e3171-a444-4a06-91d3-0c3f7e2e4179 | checkpoint | Source Property -Coarse Aggregate - Crushing Resistance
c7619db3-b484-5046-9db7-e141271dfb75 | note | Controlling Documents - TNZ M6, RNZ 9805:2009
7cc49a18-6d08-546d-8135-6b9eb4912abb | note | Acceptance Criteria - <10% fines under 230kN minimum
9d0781ea-8341-5393-95af-3b5faea6d78c | note | Inspection or Test: Method - Sample Test - Crushing Resistance NZS 4407 Test 3.10
5dc443b7-2e26-5dd9-9fe3-b21ef2d65e42 | note | Inspection or Test: Frequency - 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum
2b1afbdd-557f-5797-9b86-74e7468d5c72 | note | Inspection or Test: Responsible Person - Surfacing Project Manager
c2e0dc5a-7d48-5e7a-a55a-3e8cd59888a5 | note | Verifying Document - IANZ Report's
5c81e38c-82dd-51b1-b48c-677ba98813f6 | note | Inspection / Test Authority: Conduct - C
64ace29f-c731-5543-bb51-e0ceb41f680a | note | Inspection / Test Authority: Produce Record - C
e1f3221b-91ee-5f2f-8c52-4fe50cf45e07 | note | Inspection / Test Authority: Approval - N
18036ad4-d233-5b03-8bde-16ad264aaeb2 | note | Hold Point - Y
00ca298f-dfd6-51c9-9bac-fe3b5dc9b65e | note | Witness Point - Y
ac8931d2-8d9a-4246-9a30-b58f657687aa | signoff | HOLD POINT
e979db6c-0f2b-42ac-943c-0047f9c5a0d2 | checkpoint | Source Property -Coarse Aggregate - Weathering Resistance
f30b011d-4ed6-5fc4-bdc3-64dc404e0c40 | note | Controlling Documents - TNZ M6, RNZ 9805:2009
f562cf46-016d-551b-b60a-1f891f443da9 | note | Acceptance Criteria - AA or BA
66294c43-1c37-5955-9fee-97a5032034ee | note | Inspection or Test: Method - Weathering Quality Index NZS 4407 Test 3.10
91ec6d54-b0ce-5585-9e7d-06692a326997 | note | Inspection or Test: Frequency - 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum
f9bb378b-fd39-5cd1-b8bb-fab15dc4c1d0 | note | Inspection or Test: Responsible Person - Surfacing Project Manager
b825d853-79ff-5c28-b3ae-9aec3a278aa4 | note | Verifying Document - IANZ Report's
f1b25657-6866-5c36-9f84-acad0e796bae | note | Inspection / Test Authority: Conduct - C
b9a8ff62-572c-5db6-8d63-aae2a8b377f8 | note | Inspection / Test Authority: Produce Record - C
0027537b-5400-5125-9bec-85e12f675e36 | note | Inspection / Test Authority: Approval - N
939a6901-c8b9-530d-afa2-b4caf151fc89 | note | Hold Point - Y
c208c3ea-b58b-590e-b3f3-cd1045291fc5 | note | Witness Point - Y
30ccddb0-6f94-44d2-9226-87a624c98fc6 | signoff | HOLD POINT
7a8c8333-b78b-4f63-ba11-19a2ded2194f | checkpoint | Source Property - Skid Resistance
53f23cec-d46f-5574-8fa7-367879863c9d | note | Controlling Documents - NZTA T/10
a0438c9f-d70e-5e92-abe3-921059b62b8d | note | Acceptance Criteria - Meet Skid performance Requirement
a9e64036-55b8-528a-8eed-477316b70f1e | note | Inspection or Test: Method - Aggregate Perfomance Method TNZ T/10 section 12.3
75d28255-4d5d-54b5-93c4-2074b05f0a7f | note | Inspection or Test: Frequency - Each Site
d680da33-f163-5e99-99d0-5712ea61cd55 | note | Inspection or Test: Responsible Person - Surfacing Project Manager
a9bf04e2-1eb4-558f-88f7-d0191cb8bfaf | note | Verifying Document - IANZ Report's
f3706845-c70b-5e1c-8589-cfceadca60aa | note | Inspection / Test Authority: Conduct - C
be6f65d1-2a54-5cad-9d7a-1aa4b9d767b2 | note | Inspection / Test Authority: Produce Record - C
7b5c6bc1-6542-52da-986c-024b14ae8a4c | note | Inspection / Test Authority: Approval - N
ea86ecd8-671c-5029-ad1d-481da58a09b4 | note | Hold Point - Y
43e899aa-3535-5b5b-a37d-2805ec001946 | note | Witness Point - Y
12cffd5c-5eaf-4ad4-a534-96dfbc6b5eba | signoff | HOLD POINT
62dc205f-3aa7-47e3-b9c5-137f45c62ef5 | checkpoint | Production Property - Cleaness Value
71ade3f1-c566-520e-a8a9-df41f45d2617 | note | Controlling Documents - NZTA P/17, M/6
c832ca80-7634-5d7d-a321-7f8f97d481cd | note | Acceptance Criteria - G2 - 89 min, G3 - 87 min, G4 - 85 min
45bfc635-e68c-5078-a4cd-8e9ac8fce28a | note | Inspection or Test: Method - Sample Test - Cleaness Value NZS 4407 Test 3.9
c4d658e5-1d7f-5ef7-adda-250ad7a6b8f0 | note | Inspection or Test: Frequency - Per Stockpile
5da5083b-3e24-541f-ab31-959e57fbcca3 | note | ○ <100m3 - 1 Sample
e2a2b1cb-fa80-50ba-aaec-4e9c8a8c5af4 | note | ○ 100-500m3 - 2 Samples
49c68e14-ccdb-5279-a606-aca9cd3549ce | note | ○ >500m3 - 3 Samples
7de23b40-200f-57ab-8dff-cde8158a75c2 | note | Inspection or Test: Responsible Person - Surfacing Project Manager
b9b5f2e3-04a0-50cf-91b5-8f58c21452ec | note | Verifying Document - IANZ Report's
8b44cf80-ee0e-5a7a-866f-a8754629e68a | note | Inspection / Test Authority: Conduct - C
91727578-a604-5b32-b764-d8d983da7588 | note | Inspection / Test Authority: Produce Record - C
8b988ccc-f9fd-53c6-af20-20a0f7a9116d | note | Inspection / Test Authority: Approval - N
657c25a4-b7f5-5e66-9bfd-0e4b742dd1b5 | note | Hold Point - Y
b6f4da06-f6ae-57bd-ad61-fcd7758c28b2 | note | Witness Point - Y
bb2e732a-87f1-4214-92ef-b707a3f800e8 | signoff | HOLD POINT
c31952e6-ec48-45b7-b46e-dff897a01363 | checkpoint | Production Property - Particle Size/Shape
12dc22d9-38af-574a-876c-20cdec930d2b | note | Controlling Documents - NZTA P/17, M/6
07b847b7-f43f-5709-9a69-0263e71ac702 | note | Acceptance Criteria - As per Table 3 NZTA M/6
d47620ea-6830-547c-9276-fea99f058c00 | note | Inspection or Test: Method - Sample Test - Particle Size/Shape NZS 4407 Test 3.13
87e4c356-f667-5301-a09c-41464f35f4f8 | note | Inspection or Test: Frequency - Per Stockpile
f0bac8cc-a45a-5d19-b8bb-0384bc331cc7 | note | ○ <100m3 - 1 Sample
3cafee66-79e3-50d6-9e1f-495d8203b576 | note | ○ 100-500m3 - 2 Samples
cdf8f64d-d556-5f68-b638-7dee5ebfb5a1 | note | ○ >500m3 - 3 Samples
3ff17c2d-8578-552d-baf4-cb14382aef68 | note | Inspection or Test: Responsible Person - Surfacing Project Manager
04c811f2-ba37-5402-a0ee-16eee7156054 | note | Verifying Document - IANZ Report's
50170345-554f-5ee2-9c4e-c4518ebc5205 | note | Inspection / Test Authority: Conduct - C
630216fb-e25c-5486-9712-2e7182b85a96 | note | Inspection / Test Authority: Produce Record - C
d20bd9d5-ccd4-55d4-8656-2fbd80ac8f06 | note | Inspection / Test Authority: Approval - N
6ef3be3a-06f6-5e6f-8e44-479aca4c7a24 | note | Hold Point - Y
fc36a0b7-829b-5ee4-987f-b5c68eda943c | note | Witness Point - Y
8407ed70-7caa-450d-9fdb-04ce5de0a18e | signoff | HOLD POINT
3dea09fd-4e32-41c0-85a2-dbdd4d4fe455 | checkpoint | Production Property - Broken Faces
6a90846d-d559-5a9e-9c7a-d4d045cccec9 | note | Controlling Documents - NZTA P/17, M/6
fc8cca34-b414-50ce-9d3e-254b80932b63 | note | Acceptance Criteria - Min. 98%
6b975901-cc18-5b5f-8da4-da35cc03c3c8 | note | Inspection or Test: Method - Sample Test - Broken Faces NZS 4407 Test 3.14
11027f80-0de5-554b-87fc-9fd51e093417 | note | Inspection or Test: Frequency - Per Stockpile
dfbabb83-f3eb-5aab-b9e9-46a5afb812e8 | note | ○ <100m3 - 1 Sample
05a70086-8a24-5750-a2f6-dc72286c2823 | note | ○ 100-500m3 - 2 Samples
f4c0283f-50a7-5cad-a876-05a23436fe27 | note | ○ >500m3 - 3 Samples
270b70fb-3958-5f17-ae24-2ec6495a42d9 | note | Inspection or Test: Responsible Person - Surfacing Project Manager
d22e5e94-1be7-5623-bedf-d5bfcea12550 | note | Verifying Document - IANZ Report's
1d3a3052-741e-5ce2-9ee1-e6ad7a36f693 | note | Inspection / Test Authority: Conduct - C
5fa47e63-844d-5d0f-821e-ff23a1c7d321 | note | Inspection / Test Authority: Produce Record - C
5a0a8ee6-4083-5ea4-a08f-98c6932452e4 | note | Inspection / Test Authority: Approval - N
ff2252f9-7ac9-5b75-b26a-45e5173d2b98 | note | Hold Point - Y
c7c01d37-ddd9-52f9-9e0b-4844e13ce861 | note | Witness Point - Y
32a8c764-09e4-47ff-a920-79f7e1bc00d6 | signoff | HOLD POINT
4e235870-1a58-4c09-bf3f-7d9b40ae5b07 | checkpoint | Chipseal Designs
c4b8b458-07ea-5e79-9dd5-7807b70c69ab | note | Controlling Documents - EBOP NOC Design Report, Chipsealing in NZ, NZTA P/17
7365a8e0-5d19-5549-a26a-154768d663f3 | note | Acceptance Criteria - Client Approval
450faa8b-afb1-5171-985e-b3af9a13524c | note | Inspection or Test: Method - Review
be5bfec8-97df-5fb0-9051-1db890e5d1a9 | note | Inspection or Test: Frequency - Annual
3a7f83ec-a8ec-5c53-96dc-c980a8b7eb5a | note | Inspection or Test: Responsible Person - Surfacing Project Manager
506f901d-c7f6-5e07-ad49-ea99bb99b80a | note | Verifying Document - EBOP NOC Design Report Acceptance
ef87014e-f7c5-5017-8ee0-25b5a45506c3 | note | Inspection / Test Authority: Conduct - C
ca4d36cd-fc28-5da3-976e-660ed67ddf00 | note | Inspection / Test Authority: Produce Record - C
076132c2-2985-5df0-adbb-2eabaf29fb7c | note | Inspection / Test Authority: Approval - N
de0a611e-8de5-57b9-9328-be29d7986345 | note | Hold Point - Y
99f6d730-016e-50b6-a038-eaee3019a89d | note | Witness Point - Y
4a180e14-826d-4b05-84b0-057475095d48 | signoff | HOLD POINT
de106dc7-c1fc-480e-a8cf-397be20dbe09 | section | 5. Chip Sealing - 5.2. Construction - Chipseal Resurfacing
9768388b-27cd-4d8d-a2b6-c2b3d05e36b9 | checkpoint | Ensure limits of site are marked
974eaf39-5dcc-58a7-9e05-09507c808e2d | note | Controlling Documents - EBOP NOC Design Report
942fafb0-0d21-561b-bc69-45199a76930d | note | Acceptance Criteria - Visual Inspection
5dadb68a-052c-5fc7-bdac-68e3d0918552 | note | Inspection or Test: Method - Visual
a9009499-b5a9-5305-948f-9de3c2b3e9fe | note | Inspection or Test: Frequency - Prior to start sealing each site
675f4096-ef16-5a5a-b9fa-da5f2c79a38c | note | Inspection or Test: Responsible Person - Surfacing Supervisor
52849465-5cbb-51ca-bea0-f87c18784502 | note | Verifying Document - Chip Sealing Quality and Site Record
fc4777c5-047a-5508-b74e-794f4f5050be | note | Inspection / Test Authority: Conduct - C
f24880ea-9b0b-55ac-9fc1-0915e505d8ef | note | Inspection / Test Authority: Produce Record - C
1fff19f7-c28d-5989-951b-ce80629e2d07 | note | Inspection / Test Authority: Approval - C
99a98b8a-4d9b-5d9d-9907-20a2c37072b7 | note | Witness Point - Y
ef1cf6b2-b042-402a-b588-04a786cf7b04 | checkpoint | Sweep surface clean of deleterious material
bee14dbe-bc14-50b2-9096-9f2c51cd5881 | note | Controlling Documents - P/17
6ec1ae29-29d3-51a1-a86d-3cbdc871e2f7 | note | Acceptance Criteria - Visual Inspection
2d9b5f5b-8767-566f-9416-c8b82052fa2e | note | Inspection or Test: Method - Visual
7462c0bc-1a11-52b1-b8fc-5cccfdc38270 | note | Inspection or Test: Frequency - Each site, prior to start of sealing
fff0818a-6997-584f-bdcb-b44df8b65b84 | note | Inspection or Test: Responsible Person - Surfacing Supervisor
1febdb2b-7419-5072-8081-2132c458e299 | note | Verifying Document - Chip Sealing Quality and Site Record
9a8b0a81-049f-5d15-99d9-e8b0a4aa34f1 | note | Inspection / Test Authority: Conduct - C
c0d08d68-e348-5a59-abc9-81e4c8f9434b | note | Inspection / Test Authority: Produce Record - C
103b8291-6dc6-5ec4-9148-c4bab291c459 | note | Inspection / Test Authority: Approval - C
f9ceb3e0-90a7-5c58-8e24-0355b2d4f165 | note | Witness Point - Y
adc658d0-b3a2-4ed7-bd29-b1f052f3e8c5 | checkpoint | Record ATP's on site
b020e3c3-409e-59b6-aaac-2660efb6758d | note | Controlling Documents - N/A
24b268ed-5983-54dc-b753-139b628eed5b | note | Acceptance Criteria - Visual Inspection
5d55c2a9-743d-5ee3-8e8d-49072f4b0625 | note | Inspection or Test: Method - Visual
85a5ea62-d013-5dec-9949-962aad069711 | note | Inspection or Test: Frequency - Each site, prior to start of sealing
dec6fa38-a71c-5191-9ed9-b055ad77c9a4 | note | Inspection or Test: Responsible Person - Surfacing Supervisor
15ab2b6d-7d7c-5989-bd6e-95428f87bf87 | note | Verifying Document - Chip Sealing Quality and Site Record
77eb6323-03e8-5471-9777-ee4bff63de92 | note | Inspection / Test Authority: Conduct - C
88c86052-e7a3-5e0d-bec8-9c047d875de6 | note | Inspection / Test Authority: Produce Record - C
dd001849-bfab-5bd5-9a2b-195176820b75 | note | Inspection / Test Authority: Approval - C
32e5b7b9-7da0-52d5-81ea-1d209fdd0bf5 | note | Witness Point - Y
4d676fd4-3d40-4ce3-94d4-1b0de7b3fa78 | checkpoint | Confirm correct treatment(s) and chip
c4ee5018-2603-5b86-bd7e-9e3734db09ae | note | Controlling Documents - EBOP NOC Design Report
13f08974-9f64-52b8-a95f-376083d6874c | note | Acceptance Criteria - Details/chip correct
f649c9bb-c977-56ab-a60f-aa9abc287b72 | note | Inspection or Test: Method - Visual
5c508923-a58b-5d1b-846e-d64fcdbaffc7 | note | Inspection or Test: Frequency - Each Site
ea023d2e-a51f-536e-980c-8b968d2d50c1 | note | Inspection or Test: Responsible Person - Surfacing Supervisor
d695141e-a885-522e-bcd4-0cc7e27d0d03 | note | Verifying Document - Chip Sealing Quality and Site Record
beff456f-1ddc-5cf1-8460-fb07a70e1f72 | note | Inspection / Test Authority: Conduct - C
c2f1049e-a561-521b-bd36-93a0db63b494 | note | Inspection / Test Authority: Produce Record - C
091e4260-8398-5fe6-a188-f712f806ed7e | note | Inspection / Test Authority: Approval - C
061d5a44-9037-51f4-8148-9bb522ddd901 | note | Hold Point - Y
6fa9ffd7-77d3-45c9-9db6-6668e546fbc1 | signoff | HOLD POINT
2088b9d8-4a83-4588-92c4-a5983b230a79 | checkpoint | Cutback Bitumen Blend
acaa9300-b755-5fe0-aa39-2c0a47768889 | note | Controlling Documents - RNZ 9803_0513
cf2ce8fe-6b89-5adf-acc0-bdf865575c23 | note | Acceptance Criteria - +/- 2PPH Cutter, +ve for Adhesion agent presence
54da722e-a077-56f0-aae6-5de0c08f5bc6 | note | Inspection or Test: Method - Sample and test
8df2adb5-3e34-5afd-8a40-a24984131150 | note | Inspection or Test: Frequency - 1 Sample per Per Sprayer load, tested at frequency of 1 per 100,000l sprayed
55e68613-2c74-51fa-a11b-ee1dfb34dd00 | note | Inspection or Test: Responsible Person - Surfacing Project Manager, Surfacing Supervisor
feaa8160-7eae-578a-ada6-5f483a360aae | note | Verifying Document - IANZ Report's
4a81c43a-e4b3-5fa2-8eff-ce7551530680 | note | Inspection / Test Authority: Conduct - C
7356dbb5-070e-56e0-ad14-a41d04c97ceb | note | Inspection / Test Authority: Produce Record - C
e1065d15-d50a-5183-9027-9768eb9c18f4 | note | Inspection / Test Authority: Approval - C
9149dc9e-6377-50c8-aa3c-1370a68a30ea | note | Witness Point - Y
670c799d-3efe-4a4e-b163-69b8a651412b | checkpoint | Bitumen Application Rate
1d769371-60f4-533e-8fff-deaf10440ecc | note | Controlling Documents - E/2 Certificate, Seal Design / Spray Instruction
9fe0ea53-8872-5c62-b5e6-e884104f2a17 | note | Acceptance Criteria - Current E/2 Certificate +/- 4% per Spray Run
18070342-ab9a-5176-8c39-a567cbae4e82 | note | Inspection or Test: Method - Test, Review
af092809-78b7-57b1-b309-f6f5a19c10f7 | note | Inspection or Test: Frequency - Per Sprayer, Per Site
cb353c2c-c550-54cf-ade2-ec6a94d04e77 | note | Inspection or Test: Responsible Person - Surfacing Supervisor
a1d8dcd7-630e-5eb5-a675-d8500d971705 | note | Verifying Document - E/2 Certificate. Spray Sheets
94d6ac3b-912f-50d9-b11b-0534fa2607f8 | note | Inspection / Test Authority: Conduct - C
0e5ae226-8c0c-5e28-9401-b194ff04688d | note | Inspection / Test Authority: Produce Record - C
470019c7-b686-5057-9d9c-bfda58b7088c | note | Inspection / Test Authority: Approval - C
90e25c87-b8a1-5c42-8d74-922d1f9b4a74 | note | Witness Point - Y
b3db02ae-969f-4691-b202-f8ee6c09af39 | checkpoint | Chip Application Rates
c3004fe6-7584-5fee-b464-85d2aa187fae | note | Controlling Documents - Chipsealing in NewZealand
46fa3574-5c1d-5f6d-9334-f6293c205e89 | note | Acceptance Criteria - As per Chipping Guide
174b0647-98e0-5092-acaf-9583651f46ad | note | Inspection or Test: Method - Visual
50a6c5f7-c4af-50df-848f-818674bd8176 | note | Inspection or Test: Frequency - Each Site
bdedeb94-5e77-540f-b88e-a474bd30f9cb | note | Inspection or Test: Responsible Person - Surfacing Supervisor
ed89b6e7-3c5b-54a8-b801-5046a184050a | note | Verifying Document - Chip application check sheet. Chip Sealing Quality and Site Record
9fd19b26-40de-52ca-b020-450a75f77600 | note | Inspection / Test Authority: Conduct - C
089146ba-01b7-5d1c-9b7a-4f4df664eb7b | note | Inspection / Test Authority: Produce Record - C
61b38901-1615-5b9e-9ebb-080604f082f2 | note | Inspection / Test Authority: Approval - C
2dca0b58-7c60-5b87-88dc-4d67a81ce7d7 | note | Witness Point - Y
990e5adc-1da6-4132-8f29-4d9c51ec8cf6 | checkpoint | Rolling
060f8246-b1c3-54df-9f9a-4d5cd8bca86e | note | Controlling Documents - Chipsealing in NewZealand
57dd87b1-07aa-571e-bc8b-acfa41f6ac7b | note | Acceptance Criteria - Mimimum as per CS in NZ - Bit volume / 3600
0f70b86b-aef3-5b0d-af05-56ed834ce353 | note | Inspection or Test: Method - Visual
b53e5b9d-ddea-521c-a44f-f3becb2466b0 | note | Inspection or Test: Frequency - Each Site
84220542-5a77-55f9-90a1-2ff6b50a2977 | note | Inspection or Test: Responsible Person - Surfacing Supervisor
4a701846-39f4-5d5e-9066-8a595f14dad9 | note | Verifying Document - Chip Sealing Quality and Site Record
25b19d6d-6847-5ed5-918a-7b3ad25791ec | note | Inspection / Test Authority: Conduct - C
0b612aac-54d9-5beb-bd45-217170c4494e | note | Inspection / Test Authority: Produce Record - C
dbbc91f5-6a42-524c-9ab0-a3ee8b1b0be1 | note | Inspection / Test Authority: Approval - C
7af83484-6af0-5674-87c6-4dcceb50610d | note | Witness Point - Y
23361e86-4272-4c72-b1dd-2d91552bbc9c | checkpoint | Cleanup
c13a8cef-2f64-50c4-9b13-a0c4764023f8 | note | Controlling Documents - Chipsealing in NewZealand
a9009601-aba5-58d5-a522-f10e3b11ae04 | note | Acceptance Criteria - Site including adjacent surfaces free of loose chip
21e04dfa-e7f7-54d6-8068-b17ab5a30bf8 | note | Inspection or Test: Method - Visual
61c7ac6c-072b-5c96-a3cd-273233ec5e66 | note | Inspection or Test: Frequency - Each Site
cba87b6e-4e29-5297-8c51-8c008e3019c1 | note | Inspection or Test: Responsible Person - Surfacing Supervisor
4fb8e0a8-862e-5197-a4e8-47a2b8fa7db9 | note | Verifying Document - Chip Sealing Quality and Site Record
a11cbb86-3735-57a5-8c13-80c68ac5b834 | note | Inspection / Test Authority: Conduct - C
4d518479-dae7-58a1-92e2-a326a50489c4 | note | Inspection / Test Authority: Produce Record - C
afae2ad7-0596-51c7-bbbb-fa0427749a32 | note | Inspection / Test Authority: Approval - C
1e72c7ca-3d03-514f-838d-e6a63ff11582 | note | Witness Point - Y
9472dd57-1a18-4c17-8dc9-542ec3adb1c1 | checkpoint | Post Sweeping
86d61f42-6b3f-5e38-9d35-f4057c818f4a | note | Controlling Documents - Chipsealing in NewZealand
1cc735ce-dd91-5f81-af7a-45fe365b57fb | note | Acceptance Criteria - Site including adjacent surfaces free of loose chip
e14f80b6-f4a3-5fe9-8d16-998f864c3d01 | note | Inspection or Test: Method - Visual
1620f932-8087-5217-81d3-7e18f994423d | note | Inspection or Test: Frequency - Each Site
a8fa2b71-4a11-5e11-8e13-f2303a8f05f3 | note | Inspection or Test: Responsible Person - Surfacing Supervisor
ed9aab1c-5310-51ec-876f-014fd8f94707 | note | Verifying Document - Site Record
2e7953a4-4d9a-5ebf-9adc-c7c9d6a34b5f | note | Inspection / Test Authority: Conduct - C
d3fad9ca-4f90-5b03-b6d1-da9693e24a39 | note | Inspection / Test Authority: Produce Record - C
da38be39-23c3-59f6-aec3-6bb994bb1321 | note | Inspection / Test Authority: Approval - C
024b01ea-c09b-5cf4-beb5-840f247d9ddb | note | Witness Point - Y
eb48e1be-b7ca-4e64-9802-351cc5750159 | checkpoint | Linemarking and RRPM Reinstated
f38e37ff-15a5-58a0-85a5-af1f3595dc34 | note | Controlling Documents - MOTSAM
5f291c9f-70d9-5db7-ac7d-f1c80bda337e | note | Acceptance Criteria - Matches previous linemarking - within 48hours of sealing
c80bb205-057d-5b36-8604-0a47a009208d | note | Inspection or Test: Method - Visual
3085da5b-032d-5076-99e9-506fe3ac0733 | note | Inspection or Test: Frequency - Each Site
9ad00148-843e-5aec-9be0-13bbaabf5cb4 | note | Inspection or Test: Responsible Person - Surfacing Supervisor
02cb1f04-323e-5ee5-b0c6-449080b0b5f2 | note | Verifying Document - Site Record
5f0e9d40-fc0c-59a3-9cc7-7300f65907c9 | note | Inspection / Test Authority: Conduct - C
ef544a30-5ab6-5add-abe9-e7e11a883029 | note | Inspection / Test Authority: Produce Record - C
1c5b8443-3b78-5336-aa20-63a80ac467df | note | Inspection / Test Authority: Approval - C
31eae5e2-81df-5b4c-bf05-585b6c24ac48 | note | Witness Point - Y
94d3198b-6cbc-4694-a7be-398daf38c4a7 | section | 5. Chip Sealing - 5.3. Post Construction - Chipseal Resurfacing
4a2a9081-e432-4b31-bbe4-30b3f4d38fc8 | checkpoint | Post Construction Walkover
1bc92217-6cc9-5695-b19f-498e0b89f92d | note | Acceptance Criteria - Formal Agreement
335b9e90-d22a-53c7-9ec7-ca03ffa5d10a | note | Inspection or Test: Method - Visual Inspection
3890ded1-2f8b-5452-9075-b80eec89a662 | note | Inspection or Test: Frequency - Post seal sweep
8157b7cc-08be-550e-945e-c575a225ea13 | note | Inspection or Test: Responsible Person - Quality Controller, Supervisor and Engineer
6934802c-a1b6-5f75-9272-0d032923e399 | note | Verifying Document - Meeting Minutes
d2a5e754-c1ec-577c-b8e2-147abb8ad112 | note | Inspection / Test Authority: Conduct - C
a9d2bd7d-302a-559c-ae48-83e4d359c601 | note | Inspection / Test Authority: Witness - C, S and E
718b14a0-f822-5781-8978-1324d4978a11 | note | Inspection / Test Authority: Produce Record - C
1d253630-5682-5632-91d5-0b01939563e0 | note | Inspection / Test Authority: Approval - E
6132893f-fe2c-59ef-9cb7-0438f8f2631d | note | Hold Point - Y
e4269e17-6e74-48a3-a027-4a550de231bb | signoff | HOLD POINT
6adac9f6-a530-4581-9ae0-3148699a198a | checkpoint | Resurfacing Construction Completion report
a1b99809-52f1-520c-ad02-47827f4d6dfd | note | Controlling Documents - NOC; MS 6.1.3
d6642fb8-82f4-511b-b66c-37cd58a2e2a0 | note | Acceptance Criteria - Comply with Requirement of NOC MS 6.1.3
d6812163-6413-5ec3-9e6c-46f897c3606e | note | Inspection or Test: Method - Record
cbe3804a-549c-5a5e-a913-17c2ab397afe | note | Inspection or Test: Frequency - Within 2 months of completing the annual resurfacing programme
b9647098-18e9-5c29-8515-212229de11cb | note | Inspection or Test: Responsible Person - Surfacing Manager
ab1b27fe-d848-588b-9bf3-0239199104bf | note | Verifying Document - Construction Completion Report
59b01f2d-995f-5741-a799-c159db8043d1 | note | Inspection / Test Authority: Conduct - C
06d4c7ce-4ec5-5fb6-8241-b6a63028e5fb | note | Inspection / Test Authority: Produce Record - C
b3ced148-1839-5116-ab1e-9449fbaecb31 | note | Inspection / Test Authority: Approval - C
82744643-ea27-5109-9a94-b981173517d2 | note | Hold Point - Y
c59477eb-2e15-4351-8091-52c1fbd64883 | signoff | HOLD POINT
29ea31d0-5b41-4a6c-a93f-f73dbb2d836d | section | 6. Close Out
101f5f8c-1fd1-472e-9342-86a4b4a472bf | checkpoint | Pavement Rehabilitation Construction Completion Report
ff2e451a-94f0-51c7-930b-6b037da83123 | note | Controlling Documents - Pavement Rehabilitation Construction Completion Report (6.1.2) - BOPE 2_14-001_601 Maintenance Specification
a4b00e92-5aa3-57d1-a297-14ec824c878a | note | Acceptance Criteria - Engineer Approval
0570cef6-266c-531c-88d4-fef5ca3906d1 | note | Inspection or Test: Method - Visual Inspection
303031b3-3c8d-5154-af55-1285faf20389 | note | Inspection or Test: Frequency - ≤2 months of 1st Coat Seal
d55ca7ab-c198-5410-8247-3d30d298c190 | note | Inspection or Test: Responsible Person - Quality Controller/ Contract Manager
fbee4ba4-6d7a-5da6-b76e-3f1ab8c87862 | note | Verifying Document - Signed Report
2daaac08-bd30-5296-85b1-4966bad3d7c1 | note | Inspection / Test Authority: Conduct - C
1c6e4988-188d-54a8-ad5e-ac79ae6cbd02 | note | Inspection / Test Authority: Witness - C, S and E
3b6b15ef-1043-5b81-9f44-518bac7bc4ee | note | Inspection / Test Authority: Produce Record - C
5ee73653-b9e7-5e2e-93e3-fa5f0f343746 | note | Inspection / Test Authority: Approval - E
6c513263-ee5e-5f17-873f-ff8e95c0508e | note | Hold Point - Y
ded96e93-cbd2-4631-9d6a-d160ce7334b8 | signoff | HOLD POINT

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
70182140-a89e-402a-b6c3-7f3740ce0b9c | checklist | ITP - Asphalt | itp | ITP - Asphalt
ec598cb8-22a1-4e12-9ade-8c429a790591 | section | 1.0 ASPHALT CONSTRUCTION INSPECTION AND TEST PLAN
4dcb4bf8-556d-4731-8f39-19b16cbd581b | checkpoint | 1.1 - Contractor checklist
6beed11e-209f-56d8-8006-9c04a093e7a2 | note | Detail of Activity - Obtain necessary Consents and Permits, and ensure differet lines of information are aligned
86119901-321b-5ecd-b6d7-5b041c9a6026 | note | Action (H/W/M/C) - Check
6a188f04-33d3-5d00-8eb1-b593505da95f | note | Frequency - Prior to commencement
098fef8b-effc-58f0-92b5-aaf6fac80bcb | note | Inspection / Test method - Review
c932c6a0-0891-5937-add3-8d01c8b6cbe2 | note | Acceptance Criteria - Items in checklist completed or send out for action
d2e71446-aff5-5c62-8e5c-03bf5eb9671a | note | Verification Record Documents - Contractor checklist
d4ad279c-5d32-51c2-b393-8fca45c8417b | note | Responsibilities - RM, PE, SE
e2e2eadb-2187-4746-80fc-6b67830e8cd1 | checkpoint | 1.2 - Previous lots completed
93e25a1e-daea-5c02-818e-9d60c97d8d53 | note | Detail of Activity - Confirm ITP items for underlying works have got confirmation and sign off received from client
e1e2b3df-9848-5189-95a7-d16b0d9c0d77 | note | Action (H/W/M/C) - Hold Point
015a4796-44d2-566b-94af-2330ebae8445 | note | Frequency - Per site prior to commencement
000a6b19-e763-5d8f-b7b0-fac6a477b161 | note | Inspection / Test method - Review
4e1fff5f-383b-54dd-a3da-d2e2939cb7bf | note | Acceptance Criteria - Sign off received
d38fe4b6-a087-57c1-9616-1456b66fc690 | note | Specification/ Contract Clause Reference - Project Specification
4ca58b3b-3494-578e-8e17-aa6663a1277b | note | Verification Record Documents - Copy of signed ITP
1d0e3f94-8176-5d53-b5b2-abf4b627f84a | note | Responsibilities - RM, CR
7875d5de-ff4c-49b9-95ca-3a4fd7a94ab4 | signoff | HOLD POINT
d4d65d4e-e1d7-40e3-abce-5bc2cbbad795 | checkpoint | 1.2 - Design
ff16a4ff-0eaa-5c75-ba4f-192e4f907fca | note | Detail of Activity - Ensure that the design is approved and drawings are of the latest revision
e68b3a1f-d46c-526c-9d47-24edd93fba1b | note | Action (H/W/M/C) - Hold Point
aeeaa736-357c-57ab-84ca-44921217ce41 | note | Frequency - Prior to commencement and as required for revisions during the works
aec097de-fadd-5f8f-b4ae-ab92aed8b054 | note | Inspection / Test method - Review
a5d7f12e-fb4e-5adf-9f2c-b9bef356e157 | note | Acceptance Criteria - Design document with principal approval signature
4b7de15b-eaaf-5449-a1dc-6c35737a114d | note | Verification Record Documents - Design report
771daa53-f7bc-5cbe-ac56-060defba73dc | note | Responsibilities - RM, CR
3489703d-d354-4700-a52b-188d3c03f74f | signoff | HOLD POINT
193b1d1f-1659-4a83-8b07-c393a7c9addb | checkpoint | 1.3 - Renewal Quality Plan
46f792d1-5804-529f-8b28-24e81447b1b6 | note | Detail of Activity - Quality plan for the site that looks at site specific requirements
2b921e49-5378-54a6-94da-3b21b5830afa | note | Action (H/W/M/C) - Hold point
8af8a1b0-9c84-51a3-a04a-04676830be11 | note | Frequency - Prior to commencement
0d9dcf21-4778-5001-b991-bd6a874ea054 | note | Inspection / Test method - Review
f7c30a4c-e802-53eb-8faa-c3dc9d41e012 | note | Acceptance Criteria - RQP with principal approval signature
f0d52609-a41a-5729-ad01-15d3de914b46 | note | Verification Record Documents - RQP
ebeb017f-05f2-56f9-9f46-abe91bb2bb05 | note | Responsibilities - RM, CR
c5bbe99c-ad00-4df9-a511-8563fdacf7f0 | signoff | HOLD POINT
aa90f99f-56be-491b-80d7-953205510a45 | section | 2.0 Material Conformance Inspection (2.1 Material Procurement)
c0ce7174-3781-4886-afbe-117ce6f4494a | checkpoint | 2.1.1 - Asphalt mix
e5b3c3e7-0ce1-5624-a7f1-8d04d4711863 | note | Detail of Activity - Confirm compliant Mix design is in place
87335f57-b1ca-5e47-9e23-1d17af0e99db | note | Action (H/W/M/C) - Hold Point
c24f707f-752b-5a2b-8c02-c00c8900f198 | note | Frequency - Prior to commencement with revision uploaded when it reaches expiry date; per mixtype and plant
13d1be44-c17f-5d2f-b3f9-2c2519b8e319 | note | Inspection / Test method - Review
a98f05b3-e7b3-5f9b-80ae-b6b1e55a4b49 | note | Acceptance Criteria - Dates valid and performance aligns with requirements SMA12.5 PG64V, AC20 PG64V
e654ac57-430e-5537-9e2d-b329491c4cbd | note | Specification/ Contract Clause Reference - NZTA M10 & M27 Mix design report submitted to NZTA
b232a6ad-e72b-537b-bf2e-6b760b7ca49e | note | Verification Record Documents - Approved JMF
09c691fd-f654-5eb7-afeb-0bac734d30d9 | note | Responsibilities - RM
f1578616-9dd3-5d18-9986-00663be4b99e | note | Comments/ Verification - Approval of Contract Administrator &/or Design Engineer
d5137649-368d-4718-8ce9-9f326fadba26 | signoff | HOLD POINT
a48c1aa9-20b6-4477-9f29-925568bc471c | checkpoint | 2.1.2 - Material compliance
22caf07d-e7d6-522a-823e-0da34344316a | note | Detail of Activity - Confirmation of compliant materials used in mix
12c29da0-34e7-54b4-af69-670574bd0382 | note | Action (H/W/M/C) - Hold Point
6cdd4a2f-28ab-5552-96ca-a139f7289207 | note | Frequency - Prior to commencement with revision uploaded when it reaches expiry date; per mixtype and asphalt plant
300e402e-af04-5a34-9576-4e076f5015d7 | note | Inspection / Test method - Review
7700f56a-fbeb-532d-a286-a82ffb757c53 | note | Acceptance Criteria - IANZ accredited test reports that meet relevant specification
ef59c30d-2f98-5114-9030-56411b4d5bf5 | note | Specification/ Contract Clause Reference - M01 - A NZTA M10: 2020: sec 2
571e5ee6-2133-5926-b8a8-51f03cd63d24 | note | Verification Record Documents - Checklist
1d5a5d53-2d01-5377-93cc-f7f3c161ce2e | note | Responsibilities - PE
91e6b354-67c2-5c42-bc81-f45b60ab7ce2 | note | Comments/ Verification - All individual test reports need to be available for review by client as requested
7760c58c-866e-4489-bb80-51025d2d70a7 | signoff | HOLD POINT
e9ebb4a8-03bd-4978-b7ed-acc34e2ee308 | checkpoint | 2.1.3 - Lay down trial
eed0b702-82b1-5c98-af20-60eeea9b2f16 | note | Detail of Activity - review lay down trial records
b19f2d23-9955-5149-b94d-1b401185a6b5 | note | Action (H/W/M/C) - review
ccc65dc2-7df9-5ec4-9560-7ad0895f3052 | note | Frequency - Prior to commencement per mix
3ee5872e-a6eb-53d2-9fdc-414de767e3b2 | note | Inspection / Test method - Review
5ac8580d-0b46-520e-b6b9-f659f7a03660 | note | Acceptance Criteria - Mix design results achieved
9383aef1-cc3f-518b-9ef0-c7ff5dfa3dde | note | Responsibilities - Sup, PE
3f3f74a9-e97b-4f01-8bc7-a9ad252c22d9 | section | 2.0 Material Conformance Inspection (2.2 Material Production)
aa13c74a-941d-4a9a-b26f-b7debf4148bd | checkpoint | 2.2.1 - Production testing
87812e2c-45d5-5a24-9018-4c4a645d2746 | note | Detail of Activity - Binder and Grading Testing - Particle Size Distribution and Binder Content
db597220-e7df-5226-9518-59535b11e7b4 | note | Action (H/W/M/C) - Check / Monitor
76d0e742-45c2-59ef-b8e3-08a8124ef2fd | note | Frequency - Minimum of 1 test for every 200T produced, per mixtype and asphalt plant
cd586ca2-7528-579e-8788-5a505e3f540c | note | Inspection / Test method - Field / Lab Testing
aa6b6945-3122-5fe6-b68a-d5252ba6eb4a | note | Acceptance Criteria - For individual tests: 1.18mm sieve and larger: ±8
8429c542-a47a-51f2-831f-78a16d5b46c8 | note | ○ 0.600, 0.300 mm sieves: ±6
ea154bf9-c3d0-5fa3-8caa-9b2bc46c5c11 | note | ○ 0.150, 0.075 mm sieves: ±3
9278eb0a-fcb4-50cf-811e-851415f92dd7 | note | For mean of 3 tests: 1.18mm sieve and larger: ±5 0.
b108d771-9a1d-524a-9639-e12004becdda | note | ○ 600, 0.300 mm sieves: ±4
194b0bec-2777-599c-9fda-c1265414587e | note | ○ 0.150, 0.075 mm sieves: ±2
c3efb97e-7feb-5e80-88c1-bea69407d3a6 | note | Specification/ Contract Clause Reference - NZTA M10: 2020: 5.1-5.3 ; M27
e86bcafd-956d-56f7-8a9b-359f8ab0e562 | note | Verification Record Documents - IANZ accredited test report
6d4ab96c-75e2-58d4-a084-1b421c00c247 | note | Responsibilities - PE
27a72932-0478-5152-ab98-84ada8b60b83 | note | Comments/ Verification - When 3 or more tests are required for a project a rolling average can be calcuated.
43d52ad1-7a17-58be-9dc2-0a290c07959e | note | ○ Tolerances are the maximum allowable on the JMF.
a0e77de7-2efc-4532-828b-78f4a6407f34 | checkpoint | 2.2.2 - Production testing
db788bce-0a05-5f5b-bc07-05eef8e2badf | note | Detail of Activity - Volumetrics Testing - Maximimum Specific Gravity and Airvoids
e9ae3cd4-06bb-507d-822b-8128dbbc7582 | note | Action (H/W/M/C) - Check / Monitor
aa0d4219-cb84-5ff4-9f18-4b64362cdfda | note | Frequency - Minimum 1 test for every 600Tproduced, per mixtype and asphalt plant
e2b8ef85-2b44-5a92-af60-99f0a0792ebf | note | Inspection / Test method - Field / Lab Testing
3bb87ec4-e6bd-50ce-bcc6-e4de735f8a19 | note | Acceptance Criteria - For individual tests: Binder content, percent by mass: ±0.5 Air voids: +2,-1
351cc39a-ce65-5b40-89f8-91a68c2824ba | note | ○ For mean of 3 tests: Binder content, percent by mass: ±0.3 Air voids: +1.2,-0.6
92e187e3-fac3-59f4-949e-ef6dfcb8cf6a | note | Specification/ Contract Clause Reference - NZTA M10: 2020: 5.1-5.3 ; M27
37c05ec7-abe7-5a06-86db-5a4249e9c234 | note | Verification Record Documents - IANZ accredited test report
10e92b38-2d43-5536-8a56-15fee9144dca | note | Responsibilities - PE
c87da9e6-405f-5984-8462-79722195e900 | note | Comments/ Verification - When 3 or more tests are required for a project a rolling average can be calcuated.
9f20eca0-2915-51a0-b8dd-a6af60526984 | note | ○ Tolerances are the maximum allowable on the JMF.
cdbb3ac9-cf31-4fa9-be65-061dca507a0d | section | 3.0 Construction process (3.1 Site Setup)
d975baf0-38a2-419f-82d5-6d4845bdc24c | checkpoint | 3.1.1 - Pre AC construction site checklist
f15cfbf4-cfca-54b6-a6ec-003c70d2ba09 | note | Detail of Activity - Ensure everything is in place for works to go ahead and outstanding Items from contractor checklist have been actioned
34fe5cf3-93c2-5e07-a8b6-ff803697f34c | note | Action (H/W/M/C) - Check/Monitor
337958c9-24f7-5387-a6d6-4ab33bdad0ed | note | Frequency - week prior to paving
d9799d13-32ca-51d6-8974-6c30b1df7f0a | note | Inspection / Test method - Review
b8dcd858-a133-5eb2-8b2e-a4d624459b8d | note | Acceptance Criteria - Complete Pre AC construction site checklist
b85c48f7-a98c-5729-a46c-7e47c66a3531 | note | Verification Record Documents - Pre AC construction site checklist attached
c3693189-d562-5ac6-a79c-8ddf5967c770 | note | Responsibilities - PE
14b1cc70-0647-4665-83d7-5ff4924d2d32 | checkpoint | 3.1.2 - Go/No Go checklist
8e8cdfb3-90c3-5128-b682-c72dcc5e0008 | note | Detail of Activity - Ensure everything is in place and all outstanding items and previous holdpoints have been actioned or released.
7a9fb6cc-c547-53ef-9e99-49aaa885e42a | note | Action (H/W/M/C) - Hold point
204b8043-08b8-54a7-a933-01831ee13a3b | note | Frequency - within 24 hours
ab4d5ac5-d983-5993-806b-6275f8e80e0a | note | Inspection / Test method - Review
e3aab2e7-a69e-599d-85d5-b0930fef967a | note | Acceptance Criteria - Complete go/no go checklist
2a5f0221-c314-5832-b861-1c84f96fbbbc | note | Verification Record Documents - Complete go/no go checklist
61461d2d-ceee-5529-9423-95c181dc4f3b | note | Responsibilities - PE
c8dd1362-5819-4686-a974-4704119a59ed | signoff | HOLD POINT
928d76aa-3809-433e-b498-6354470e5a8c | section | 3.0 Construction process (3.2 Paving Preparation)
86ab7cf0-9d01-4f94-b95d-6dea0e19578c | checkpoint | 3.2.1 - Milling Depth
9dacc890-0a7f-570d-ac10-94e8e5cfff0d | note | Detail of Activity - The existing road surface and underlying pavement shall be milled to the specified AC depth and area covered
12c629cf-6f75-599f-929f-c3d48f0ec92b | note | Action (H/W/M/C) - Hold Point
1f0c95fc-c9f9-50db-9fce-49097b22817f | note | Frequency - 20m left right and centre behind the milling machine
ff1d2cda-cb24-5e65-ac06-174d5b4abfe7 | note | Inspection / Test method - Field Testing /Survey
dc3ebd6f-039e-5216-b9d0-738b80f74b73 | note | Acceptance Criteria - SMA12.5 design thickness = 50mm
1055bc4b-0f3e-5463-b410-d52f0b12dccc | note | ○ AC20 = Design Thickness 100mm
0dd8f54e-5117-5d37-954f-d9e4d40494a8 | note | ○ Minimum milling depth = 155mm
5d5ef615-f74f-5dd3-8813-91a558e70eda | note | Verification Record Documents - stringline sheet from QA pack
d93a3ef5-0054-54eb-95de-d2ae464af37d | note | ○ Pictures for verification
cb70ea03-3e51-5f05-bd9c-b915f9f2d203 | note | Responsibilities - QA Site Engineer
f30c162a-ef04-575f-a301-68cf154bfa26 | note | Comments/ Verification - dipchecks behind the mill can be completed instead or in addition to stringlines
42194582-a7f7-4718-8307-e0beb5c20d40 | signoff | HOLD POINT
071e4eab-d56c-4d18-89ab-0960b3e2ae35 | checkpoint | 3.2.3 - Proofrolling
3efe5df2-7c4d-53b8-b519-bc8b60fddbd6 | note | Detail of Activity - Proofrolling to be done on milled surface
2bdf05b3-9c72-5a72-8353-061f21c9a37d | note | ○ Use PTR or loaded Asphalt truck, to proofrol milled area's. If it shows movement or has loose material please contact renewals or cotracts manager.
3ab2120b-9a17-562f-a319-37593964c663 | note | Action (H/W/M/C) - Witness Point
d23d2380-11bb-558d-93df-3b7c557b4e23 | note | Frequency - Full surface area
bfdb9538-6ab7-50c7-a459-6c682dbd0553 | note | Inspection / Test method - Field testing
4bcfb1d8-6f71-56d3-a8a3-b25a4b7df4d0 | note | Acceptance Criteria - Surface finish shall present a tightly consolidated surface after sweeping.
fa27fbea-2c8d-5251-88d1-98b38094a14c | note | Verification Record Documents - Pictures or video
a0ce3e69-29eb-52ba-8325-c8e32e0e36ab | note | ○ Written communication if any additional instructions received
b2c02281-260c-5061-86aa-bea190008817 | note | Responsibilities - QA Site Engineer
eeda8e9c-ec49-49d2-87aa-eae2f8a5a52d | checkpoint | 3.2.5 - Membrane (Subbase Material only)
60e1b8c1-ab55-5a4e-a581-6d103e567217 | note | Detail of Activity - G4 or 5 Memberane
412bec10-6670-5d03-94f8-03875c5aecc0 | note | Action (H/W/M/C) - Witness Point
2d7495cb-44bb-5332-9f89-26afa3bc84cd | note | Frequency - Prior to paving on exposed Sub Base
af664f82-6dc0-5fda-874d-4f3b96280ab2 | note | Inspection / Test method - Visual Inspection
c765f9ae-7902-53b4-a260-0094af7d583d | note | Acceptance Criteria - 1.0 l/m² residual binder minimum
5b7465cb-49f2-5bb6-99dd-5dc2c8102997 | note | Specification/ Contract Clause Reference - NZTA M10: 9.3.2;
3c2bc132-5e23-52ea-af33-a9a78c0e69ea | note | Verification Record Documents - Spraysheet with RP's and pictures for verification
414f1c71-9a4e-52ec-9ee3-efbec72999c2 | note | Responsibilities - QA Site Engineer
25e4cae6-36be-5f57-9a09-bc2414e9d89e | note | Comments/ Verification - Looks for stripping or any other damages.
22c0cb9c-185e-5f3f-a928-f72f1c3d2798 | note | ○ Spray vertical faces and transverse joints as well.
77ebfc78-090b-4050-a297-45f5a8145138 | checkpoint | 3.2.6 - Tackcoat (Asphalt)
eb91ff74-4f2c-5473-8158-31b18fed67f0 | note | Detail of Activity - An emulsion tack coat must be sprayed between all Asphalt Layers.
6f3abed3-86a2-58ca-bc3f-4e5fca19b493 | note | Action (H/W/M/C) - Witness Point
c654b2fc-3c8d-5311-bce5-ec27bb38746c | note | Frequency - Prior to paving on top of existing Asphalt layer
727d9ec8-03eb-5a90-aa93-533876ac6960 | note | Inspection / Test method - Visual Inspection
0e240e3c-f0f5-56a1-b6b7-4a9ce1c9ddf4 | note | Acceptance Criteria - 0.2-0.6 L/m2
576bd2b7-8097-58e0-b429-7f835e36c3ce | note | Specification/ Contract Clause Reference - NZTA M10: 9.3.1;
6e488924-ee74-5a1a-8e14-2bf63d97f013 | note | Verification Record Documents - Spraysheet(s) or pictures for verification
1e03cecd-3181-5c74-a35b-0076321565f6 | note | Responsibilities - QA Site Engineer
da517c86-67a5-5fc5-b870-74017a864ed5 | note | Comments/ Verification - Spray vertical faces and transverse joints as well
738508e7-7886-434d-93f6-f5c7958c4911 | checkpoint | 3.2.7 - Joint Preparation
e491127f-570f-59d7-a7b3-5f3cf0983342 | note | Detail of Activity - Transverse joints to be milled/cut back to provide a square edge and emulsion must be handsprayed on the vertical face. Succesive transverse joints must be staggered by a minimum of 2m
8fe54f0c-a8ac-5854-95f3-21b8e21c4c1d | note | Action (H/W/M/C) - Witness Point
642aa521-10c5-516a-8b73-864140a5c728 | note | Frequency - All transverse joints
f7f41b70-2b85-5496-9a8d-543b12b90106 | note | Inspection / Test method - Visual Inspection
621a1d55-2ffd-54f5-be7e-a6fe18fa6d19 | note | Verification Record Documents - Pictures for verification
7d21e036-cc7b-5b45-b3a6-a45c096e6b14 | note | Responsibilities - QA Site Engineer
29a23719-e832-4046-af28-e8a244fb1884 | section | 3.3 Asphalt Paving (3.3.0 Structural Layer)
8a08894f-bcfb-4237-886b-3b75c5c7dbad | checkpoint | 3.3.1 - Temperatures
0fa39c14-bcd4-5567-a904-1b42c71b83b2 | note | Detail of Activity - Delivery and compaction temperatures to be monitored throughout the paving process
1c4022cc-0be3-5d8d-9220-72d44a743493 | note | Action (H/W/M/C) - Check / Monitor
6f9c2e58-3674-5a69-8348-c45fbb56723f | note | Frequency - Each truckload that arrives on site prior to paving
a1743fa2-4747-5384-8408-7d5387f182d6 | note | Inspection / Test method - Infrared Thermometer
e87bb365-17f1-5876-bfa7-e4f01d42be35 | note | Acceptance Criteria - A minimum of -30 degrees from the recommended mixing temperature of 160-175°C To be recorded when mix is tipped into the paver.
5267b779-381a-5d22-b859-b9a87a29e965 | note | ○ Manager to be notified if temperature falls below: AC20 PG64V 130°C
f8d2c96f-12b2-53f4-b98c-45261fb48b2f | note | Specification/ Contract Clause Reference - NZTA M10: 2020: Notes; Higgins asphalt bitumen guide, NZTA M1A 2019
917469d9-af0a-5226-857f-41184fe553d3 | note | Verification Record Documents - Mix tracking sheet from QA pack; contains delivery temperature, temp when in paver, temp inside the screed and rolling temp on AC
cbb75b3d-eecc-5adb-8732-d7316c9c30f6 | note | Responsibilities - QA Site Engineer
fae331c9-e3f3-5923-9d46-f91ed9dd65a7 | note | Comments/ Verification - It is critical to ensure a temperature representative of the full load and not surface temperatures of the mix are measured.
c6ee4334-bdd3-4452-a083-ac35ed174e63 | checkpoint | 3.3.2 - Layer thickness / Structural Asphalt
9aa26153-73a6-553a-a12a-23bf3df606f5 | note | Detail of Activity - Monitor layer thickness throughout paving process. By keeping track of the spreadrates and performing dipchecks behind the paver.
6391172b-eb81-5a55-b153-2ee24dc68e7d | note | Action (H/W/M/C) - Check / Monitor
15a43b02-b372-5f91-aebb-fa5351ca3c5f | note | Frequency - For each truckload that gets paved, 1 mix tracking sheet per shift and a site diagram per layer
8fcea08b-e371-5bd8-893e-7176422df30f | note | Inspection / Test method - Survey, Field / Lab Testing
0556c967-a1de-5d3d-8f67-12e97e903d1d | note | Acceptance Criteria - a minimum of 90% specified layer thickness to be achieved, but maximum minus 10mm of Specified layer thickness from design, with a minimum of 80mm per layer for AC20 PG64V.
c4c74ba6-9776-5fe2-81e1-3025e73bfbff | note | ○ MINIMUM Thickness = 100mm as per design
ff7e4bcd-df32-5a28-8ec5-1f250063edcc | note | Specification/ Contract Clause Reference - NZTA M10: 2020: 9.7 and table 3.1
049448b7-ab75-5ffd-81aa-c801ce71fafe | note | Verification Record Documents - Mix tracking sheet and site diagram in QA pack and photographic evidence to prove dipchecks have been performed
76485b1b-2c1f-53d8-a9b5-2754a6ddd9d2 | note | Responsibilities - QA
84322f04-57fa-5c53-bea5-b77c5fff49f7 | note | Comments/ Verification - These are deemed operational checks and will get verified through cores as specified in items 3.3.6 and 3.4.6
57f06abf-5fe5-457d-ba30-8b5a96ede01f | checkpoint | 3.3.3 - Compaction
50e5fd80-20c0-5a4c-bb2f-260f457596fb | note | Detail of Activity - Plateau testing to be performed to set rolling pattern
41cb48b2-2d42-5926-ad6f-abe189217873 | note | Action (H/W/M/C) - Check/monitor
b05d4886-7400-5961-bc8e-15ff4e24bdba | note | Frequency - for each mix type
597c2981-88dd-568a-a0fa-bf7939ec5d84 | note | Inspection / Test method - Field / Lab Testing
1a8f7dac-5b55-5be6-b4ba-df3bad8a2f33 | note | Acceptance Criteria - completed/not completed
2ab21e8a-ffb1-5d35-808d-82ef21ca24a6 | note | Specification/ Contract Clause Reference -
27980678-0877-5627-a506-6f67d2a3fc50 | note | Verification Record Documents - Asphalt plateau density test sheet from QA pack
26b6a2c5-cf1d-5e7c-be9e-74198031aefe | note | Responsibilities - QA site engineer
96554bb2-6d1f-4d02-b244-50f0cd5e6699 | checkpoint | 3.3.4 - Compaction
3033c720-8188-5255-b867-93db85f8cbe9 | note | Detail of Activity - Monitor compaction throughout paving process for quality control by the use of a NDM gauge
ef696a22-17e3-536e-98c9-cec04782c51a | note | Action (H/W/M/C) - Check / Monitor
45d53695-33b7-5300-bd74-08e3f0c5b4ed | note | Frequency - Minimum of 1 test per 20 linear meters per run and minimum 1 every 100m on Longitudinal Joints
b7aa05d5-69e3-5a20-b88a-e64d76a2841e | note | Inspection / Test method - Field / Lab Testing
2686fc60-0743-56e8-b674-4882c0a82aa3 | note | Acceptance Criteria - Asphalt shall be uniformly compacted to the standards specified in clause 9.9.1 as soon as the asphalt has cooled sufficiently to support the compaction equipment without undue displacement.
5fe57925-7929-5b71-9128-2ca52bbfa3e2 | note | Specification/ Contract Clause Reference - NZTA M10: 9.9.1 - 9.9.2
6d600a61-d17d-5a2d-9a00-1e1ea8a85e37 | note | Verification Record Documents - NDM sheet in QA pack
e5e7496d-9ba0-52b0-8f71-a44f6bb4be40 | note | ○ Pictures for verification
763c3732-637e-5713-8b11-5b935ecc9b9f | note | Responsibilities - Super Site Engineer, Foreman, PS QA
746ee7fd-9d35-5c35-a1ab-a8605dbc8baf | note | Comments/ Verification - These are operational quality control checks and will be formally verified through cores as specified in items 3.3.5 .
bfd2f516-46bf-476d-aef2-6dd8f9b80c41 | checkpoint-no-value | As the Deeplift on this site is less than 30T it does not count as a lot and therefore no AC20 cores are required as per M10. If there is any concearn for the AC20 having failed, contact manager prior to continue paving surface layer. To get additional instruction on whether or not to continue or postpone
3b0ec1b7-e368-4b37-a2c6-55c807c927ee | section | 3.4 Paving - Surfacing Layer
5c439ef9-c8d3-47b0-bea3-e8db4dbd1c9d | checkpoint | 3.4.1 - Temperatures
ceaa526e-3a26-5387-bb15-5466f5879ba1 | note | Detail of Activity - Delivery and compaction temperatures to be monitored throughout the paving process
b372df02-0ce1-5ed1-93ce-75edc5bfc25b | note | Action (H/W/M/C) - Check / Monitor
a3e929df-8ce2-59b2-a8bc-d6b1c117cfc6 | note | Frequency - Each truckload that arrives on site prior to paving
ab0e1d32-09c9-5f81-abff-1991b37522cc | note | Inspection / Test method - Field / Lab Testing
41bcd48a-5e95-578c-81b5-6883304bb4e0 | note | Acceptance Criteria - A minimum of -30 degrees from the recommended mixing temperature of 155-170°C To be recorded when mix is tipped into the paver.
5ec338b2-ca3a-57dd-b6ab-bdefa6dc5a0c | note | ○ Manager to be notified if temperature falls below: SMA12.5 PG64V 125°C
e77d84bc-d01b-5596-a2c0-d7e4b4dc462e | note | Specification/ Contract Clause Reference - NZTA M10: 2020: M27 Notes; Higgins asphalt bitumen guide, NZTA M1A 2019
c0c7a63a-87b7-5a5c-93a1-a94c3c88b715 | note | Verification Record Documents - Mix tracking sheet from QA pack; contains delivery temperature, temp when in paver, temp inside the screed and rolling temp on AC
fa6279c3-d865-534f-b10c-d62c4b0dbc1a | note | Responsibilities - QA Site Engineer
e7f5e943-0ed6-5364-a8a0-3180a4d3428f | note | Comments/ Verification - It is critical to ensure a temperature representative of the full load and not surface temperatures of the mix are measured.
6167b696-57ad-41a5-9b03-183a246f3027 | checkpoint | 3.4.2 - Layer thickness / Structural Asphalt
75e33588-1392-5e16-9d95-5c4f18693cb0 | note | Detail of Activity - Monitor layer thickness throughout paving process. By keeping track of the spreadrates and performing dipchecks behind the paver.
5ce6ce66-a401-5789-940c-b2743565ba62 | note | Action (H/W/M/C) - Check / Monitor
313c7f05-7efb-5986-bf68-e805ac9c4db6 | note | Frequency - For each truckload that gets paved, 1 mix tracking sheet per shift and a site diagram per layer
02a25917-fedf-5d4b-a26c-0d7460d20965 | note | Inspection / Test method - Survey, Field / Lab Testing
cba5d226-cab8-53bb-9827-10fa39cc998a | note | Acceptance Criteria - Average depth > min specified depth
2be560fe-7960-5369-85db-8bc40dc0ceba | note | ○ As per M10 for layer thicknesses below spec. an LCV of -5mm of specified thickness is allowed.
589c664a-4e9a-5eb6-9d8e-8a1313e330a7 | note | ○ Thickness Req: 50mm as per design
256db1de-f06c-5c8d-af49-fe040ca77242 | note | Specification/ Contract Clause Reference - NZTA M10: 2020: 9.7 and table 3.1; M27
a1a615a3-eeda-55e6-a8e3-33dbae5a88d2 | note | Verification Record Documents - Layer sheet and site diagram in QA pack and photographic evidence to prove dipchecks have been performed
57bfb74d-0e39-5ddb-9d73-c8989be75861 | note | Responsibilities - QA
03297e1c-021d-57dd-abbf-cd41f4fa6102 | note | Comments/ Verification - These are deemed operational checks and will get verified through cores as specified in items 3.3.6 and 3.4.6
ab3863fd-4875-45b7-825b-c5db27a75276 | checkpoint | 3.4.3 - Compaction
40549172-2c88-581f-b5d3-ac42a9f847b7 | note | Detail of Activity - Plateau testing to be performed to set rolling pattern
7f6163c6-f59f-5c25-9937-adbec7de2ec9 | note | Action (H/W/M/C) - Check/monitor
e70368c0-3429-5733-b2b9-377f4bf5cce3 | note | Frequency - for each mix type
c6a9801b-7df9-52e9-8f63-93b147a9ee89 | note | Inspection / Test method - Field / Lab Testing
471518a8-832d-526e-9e1c-084423df45dc | note | Acceptance Criteria - completed/not completed
20c8d373-d3c1-5cc2-9e43-187c85249a42 | note | Verification Record Documents - Asphalt plateau density test sheet from QA pack
a4e46445-e9b7-5a71-ae1c-21f37694e5d0 | note | Responsibilities - QA site engineer
037fe5d7-0b94-42c4-87f1-7bd4d4ae6f80 | checkpoint | 3.4.4 - Compaction
0af11063-4cc9-54cf-a1b6-e252d46ede26 | note | Detail of Activity - Monitor compaction throughout paving process for quality control by the use of a NDM gauge
bb6c071e-0be4-5528-aa5a-4ec5fbbbc284 | note | Action (H/W/M/C) - Check / Monitor
d06a77c0-7904-5c48-aff9-8672736deb6c | note | Frequency - Joint: 1 per 100m /minimum. 3 per Lot Mat: 1 per 300m2 / minimum. 8 per Lot
3f45c915-c384-5e3b-a4ed-832142c1c3b7 | note | Inspection / Test method - Field / Lab Testing
abf6044d-117f-5814-b4b9-020d47b3259f | note | Acceptance Criteria - Asphalt shall be uniformly compacted to the standards specified in clause 9.9.1 as soon as the asphalt has cooled sufficiently to support the compaction equipment without undue displacement.
d77d75ac-5e95-5083-b15f-bab929e09f5d | note | Specification/ Contract Clause Reference - NZTA M10: 9.9.1 - 9.9.2 M27
df774232-b9a5-5679-8d00-0b9c4c698d46 | note | Verification Record Documents - NDM sheet in QA pack
276e8281-0d5e-58c6-a131-c94c01d15a9b | note | ○ Pictures for verification
0e76f64e-e544-563e-a1fc-88f37900c06b | note | Responsibilities - Super Site Engineer, Foreman, PS QA
7dd98991-629d-5e75-88af-6fef167db3b0 | note | Comments/ Verification - These are internal quality control checks and will be formally verified through cores as specified in items 3.4.5
7acbf97f-8470-47b5-8965-39b12993608f | checkpoint | 3.4.5 - Cores
6d63ad58-1e86-5930-ba33-f3b4dd3f70ca | note | Detail of Activity - Cores to be taken post construction to prove layer thickness and air voids.
bbd268f2-074a-51f6-83fd-ddafc54db9b2 | note | Action (H/W/M/C) - Check / Monitor
a174904e-370b-5e68-8172-c7cd8d3401b6 | note | Frequency - Joint: 1 per 100m /minimum. 3 per Lot Mat: 1 per 300m2 / minimum. 8 per Lot
e7b1108d-d5f1-5dce-9f1b-7600849ecdb0 | note | Inspection / Test method - Field / Lab Testing
c7843659-20df-5787-9dd5-560eef114602 | note | Acceptance Criteria - Layer thickness testing :4no. core thickness tests to be taken before trimming. with a picture of each measurement.
1803152a-157f-56b1-827c-d6daae0c5ca2 | note | ○ Accepted Airvoids = 2 - 7 % - Matt; 2 - 9 % Joint
15901b13-f2a3-5ddc-b1e2-75bd880c3ce5 | note | Specification/ Contract Clause Reference - NZTA M10: 2020: 9.7, 9.9, 10.3 M27
07c34d8b-30f1-55f3-a049-9155595251a5 | note | Verification Record Documents - IANZ Accredited Test Report
fae10e4d-fe5f-5ddc-a6ab-62c898d84712 | note | ○ Picture of each Core
a7d5484c-731a-5780-9910-5e63af17c611 | note | ○ Coring Site Diagram in AC QA Pack
6a23d0b1-3c3e-5224-980e-f1afba57f327 | note | Responsibilities - Site Engineer, QA Foreman, Paving Supervisor
5dd6ab32-9d86-4b89-9d67-f81fad29961a | checkpoint | 3.4.6 - Overbanding/Joint Filling
b1fe10e8-fef7-555a-8534-3fafc7ac67dd | note | Detail of Activity - Joints between new asphalt and existing surfacings are to be over banded with a suitable bituminous filler to prevent water ingress.
4b33f6c2-d71e-50a0-af30-9ab01f56e039 | note | Action (H/W/M/C) - Monitor
1ead9bb3-c17e-5363-9170-3e7ff220aca1 | note | Frequency - Between Joints of Existing and new Asphalt
e3a5fe8e-0f9b-5078-b53e-9f9bca9f09b4 | note | Inspection / Test method - Visual Verification
4798013e-f441-555d-bc90-c56d5a8f54c8 | note | Acceptance Criteria - Satisfactorily completed
51423ce7-9b9e-5409-97f3-0ebc83473fa4 | note | Verification Record Documents - Mention quantities of Bandage Seal in AC QA Pack
1f19adee-dfd6-51e6-99fb-bf8cec274b85 | note | ○ Pictures uploaded into Site Diary of Procore
69b35cff-e89a-4696-83ee-19bed88b79cc | section | 4.0 Post construction
05412f4e-e8cd-4b37-bbed-276ccbd132c4 | checkpoint | 4.1 - Post seal inspection
9e5f99af-d326-591e-80f3-21e5124c05fb | note | Detail of Activity - Ensure the shape and levels of finished surface is acceptable
b001d7dd-8c6a-5df3-9a2c-6319ab9c424f | note | Action (H/W/M/C) - check/monitor
0180dc3f-56e2-5aa0-858a-8b2836ec9bb3 | note | Frequency - at completion of paving
60be5f51-3d0a-527a-8387-ec411be30801 | note | Inspection / Test method - visual verification/ field testing
5ac9c287-701b-5d0c-893a-6ee10b2f68bb | note | Acceptance Criteria - Roughness - Where the length of the site or the geometry is such that a road roughness-measuring vehicle cannot be used then the straight edge can be used for checking the surface shape.
c6894110-647f-56ba-85d0-3d5ca949d71e | note | ○ Not more than 5mm under a 3m Straight Edge.
5eea27a7-4a1f-5222-af8a-0edcf8876759 | note | ○ Level - -0 < +5mm from Specified Level
2f786dab-0195-5f9a-b19d-66de08c9bc23 | note | ○ Where there is Kerb and Channel shall be flush with or no more than 5mm above the LOC.
f08139b6-1c4b-5263-97c1-0976452fb1fb | note | Specification/ Contract Clause Reference - NZTA M10 9.8 and M27 10.2
a71ebf41-9bed-5f80-a303-baf802972f18 | note | Verification Record Documents - Pictures and completion checklist
61f41c23-64e6-5a7d-a963-d089239f0162 | note | Responsibilities - SE, Sup
43ee3ab5-7ca1-409f-95c7-4a1707b358a4 | checkpoint | 4.3 - QA Handover
29601d76-e659-588f-8e34-2fa9e5c1a335 | note | Frequency - For each site on the project
8414fbc0-a928-5217-b2f6-b4139da81b7a | note | Acceptance Criteria - Over milled and Deep lift extents recorded and verified by Contract Engineer / QA
6ed545f0-fd96-5fc0-892f-9a02ef898dc2 | note | ○ Spray sheets for membrane area received by Contract Engineer from Sealing Team.
c5386d7a-4dd9-50c3-82e1-b95a1edeea76 | note | ○ Surfacing layer extents recorded and verified by Contract Engineer.
6332b726-c375-53a0-9566-73dc8c89e200 | note | Specification/ Contract Clause Reference - NZTA M10, M27 as appropriate and contract drawings
a6d2c235-d9c5-5fee-b0f8-adcab7b09038 | note | Verification Record Documents - Evidence provided demonstrating full compliance with specified design
749f6ece-d04c-575b-ab15-726ee931b24c | note | Responsibilities - QA Site Engineer, PE, RM
423bc532-9cbc-4a7e-9dc2-2fc6cdea1afe | checkpoint | 4.4 - Linemarking and RRPM reinstated - Matches previous linemarking - within 48 hours of sealing
71a2cf6d-e5e3-5fa1-abb7-bada4d4a34a0 | note | Detail of Activity - On completion of surfacing pavement markings and reflective raised pavement markers are to be reinstated
843e22a5-5645-54ef-9e82-33a4bbe46ef5 | note | Action (H/W/M/C) - Check Point
c09177fe-1f7c-523f-aa76-3493154b7c86 | note | Frequency - at completion of site
de5f42f5-283c-57a8-b6fa-470e0c44e45f | note | Inspection / Test method - visual verification
c497201b-6363-547d-9fe7-8d20c43e5778 | note | Acceptance Criteria - Everything reinstated
21e684c5-1f82-5513-a071-76d92de245f3 | note | Specification/ Contract Clause Reference - MOTSAM
9cee4f56-18ed-5dd5-bdfa-cfb6dc3799ae | note | Verification Record Documents - Pictures for verification
c42afe70-e870-52e5-a9c9-ff50b2012067 | note | Responsibilities - SE, Sup, PE
62dfeb9e-1bba-46be-b167-92d003a9a5cd | checkpoint | 4.5 - Collect RAMM data
1ea55c86-52bf-5c50-8570-26478a795cca | note | Detail of Activity - RAMM update to be completed
bb679680-673e-5e66-92ee-e46eb0637c29 | note | Action (H/W/M/C) - Check Point
df41da1a-b867-5510-ae45-c8e6111c9b5e | note | Frequency - at completion of site
f21ec5f1-08ed-5816-8382-ac6ecee4bc3d | note | Inspection / Test method - Verification
e7dcb099-806a-58f4-bdef-cf0d0909be62 | note | Acceptance Criteria - completed/not completed
69e03b45-f61b-5aed-bf7d-e16c8239399c | note | Responsibilities - Surveyor, CPM, SE
a806868d-238d-4a0c-bc82-a759b07567cf | section | 5.0 Final Sign Off
ae9243af-8453-4981-9c40-6106b6c633b8 | checkpoint | Client Final Inspection: The signature below verifies that this ITP has been completed in conformance with the contract requirements and and other relevant specifications.
3d10dc54-7e22-532b-806a-2edec112fc4f | textbox | Contractor's Rep Name:
94d50e7e-2c85-56c6-a70e-be9090f7301e | textbox | Contract Administrator:
f3698af7-909d-55ee-b38e-cca5feebe004 | textbox | Project Manager Name:
a60f3b55-32d0-532b-96b0-9d27b77d28cd | textbox | Quality Manager Name:
4e8c4e5e-a2ff-4305-bd99-30cd37d12646 | signoff | Signatures: