## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - SH34 - Fletcher Ave | itp |  |  |  |  | ITP - SH34 - Fletcher Ave
section | 1.0 ASPHALT CONSTRUCTION INSPECTION AND TEST PLAN
checkpoint | 1.1 - Contractor checklist
label | Detail of Activity - Obtain necessary Consents and Permits, and ensure differet lines of information are aligned
label | Action (H/W/M/C) - Check
label | Frequency - Prior to commencement
label | Inspection/Test method - Review
label | Acceptance Criteria - Items in checklist completed or send out for action
label | Verification Record Documents - Contractor checklist
label | Responsibilities - RM, PE, SE
checkpoint | 1.2 - Design
label | Detail of Activity - Ensure that the design is approved and drawings are of the latest revision
label | Action (H/W/M/C) - Hold Point
label | Frequency - Prior to commencement and as required for revisions during the works
label | Inspection/Test method - Review
label | Acceptance Criteria - Design document with principal approval signature
label | Verification Record Documents - Design report
label | Responsibilities - RM, CR
holdpoint | HOLD POINT
checkpoint | 1.3 - Renewal Quality Plan
label | Detail of Activity - Quality plan for the site that looks at site specific requirements
label | Action (H/W/M/C) - Hold point
label | Frequency - Prior to commencement
label | Inspection/Test method - Review
label | Acceptance Criteria - RQP with principal approval signature
label | Verification Record Documents - RQP
label | Responsibilities - RM, CR
holdpoint | HOLD POINT
section | 2.0 Material Conformance Inspection (Material Procurement)
checkpoint | 2.1 - Asphalt mix
label | Detail of Activity - Confirm compliant Mix design is in place
label | Action (H/W/M/C) - Hold Point
label | Frequency - Prior to commencement with revision uploaded when it reaches expiry date; per mixtype and plant
label | Inspection/Test method - Review
label | Acceptance Criteria - Dates valid and performance aligns with requirements
label | ○ SMA9.5 Melter
label | ○ AC20 PG64V
label | Specification/Contract Clause Reference - NZTA M10 & M27, Mix design report submitted to NZTA
label | Verification Record Documents - Approved JMF
label | Responsibilities - RM
label | Comments/ Verification - Approval of Contract Administrator &/or Design Engineer
holdpoint | HOLD POINT
checkpoint | 2.2 - Material compliance
label | Detail of Activity - Confirmation of compliant materials used in mix
label | Action (H/W/M/C) - Hold Point
label | Frequency - Prior to commencement with revision uploaded when it reaches expiry date; per mixtype and asphalt plant
label | Inspection/Test method - Review
label | Acceptance Criteria - IANZ accredited test reports that meet relevant specification
label | Specification/Contract Clause Reference - M01 - A, NZTA M10: 2020: sec 2
label | Verification Record Documents - Checklist
label | Responsibilities - PE
label | Comments/ Verification - All individual test reports need to be available for review by client as requested
holdpoint | HOLD POINT
checkpoint | 2.3 - Lay down trial
label | Detail of Activity - review lay down trial records
label | Action (H/W/M/C) - review
label | Frequency - Prior to commencement per mix
label | Inspection/Test method - Review
label | Acceptance Criteria - Mix design results achieved
label | Responsibilities - Sup, PE
section | 2.0 Material Conformance Inspection (Material Production)
checkpoint | 2.4 - Production testing
label | Detail of Activity - Binder and Grading Testing - Particle Size Distribution and Binder Content
label | Action (H/W/M/C) - Check / Monitor
label | Frequency - Minimum of 1 test for every 200T produced, per mixtype and asphalt plant
label | Inspection/Test method - Field / Lab Testing
label | Acceptance Criteria - For individual tests: 1.18mm sieve and larger: ±8
label | ○ 0.600, 0.300 mm sieves: ±6
label | ○ 0.150, 0.075 mm sieves: ±3
label | For mean of 3 tests: 1.18mm sieve and larger: ±5 0.
label | ○ 600, 0.300 mm sieves: ±4
label | ○ 0.150, 0.075 mm sieves: ±2
label | Specification/Contract Clause Reference - NZTA M10: 2020: 5.1-5.3 ; M27
label | Verification Record Documents - IANZ accredited test report
label | Responsibilities - PE
label | Comments/ Verification - When 3 or more tests are required for a project a rolling average can be calcuated.
label | ○ Tolerances are the maximum allowable on the JMF.
checkpoint | 2.5 - Production testing
label | Detail of Activity - Volumetrics Testing - Maximimum Specific Gravity and Airvoids
label | Action (H/W/M/C) - Check / Monitor
label | Frequency - Minimum 1 test for every 600Tproduced, per mixtype and asphalt plant
label | Inspection/Test method - Field / Lab Testing
label | Acceptance Criteria - For individual tests: Binder content, percent by mass: ±0.5 Air voids: +2,-1
label | For mean of 3 tests: Binder content, percent by mass: ±0.3 Air voids: +1.2,-0.6
label | Specification/Contract Clause Reference - NZTA M10: 2020: 5.1-5.3 ; M27
label | Verification Record Documents - IANZ accredited test report
label | Responsibilities - PE
label | Comments/ Verification - When 3 or more tests are required for a project a rolling average can be calcuated. Tolerances are the maximum allowable on the JMF.
section | 3.0 Site Setup
checkpoint | 3.1 - Pre AC construction site checklist
label | Detail of Activity - Ensure everything is in place for works to go ahead and outstanding Items from contractor checklist have been actioned
label | Action (H/W/M/C) - Check/Monitor
label | Frequency - Week prior to paving
label | Inspection/Test method - Review
label | Acceptance Criteria - Complete Pre AC construction site checklist
label | Verification Record Documents - Pre AC construction site checklist attached
label | Responsibilities - PE
checkpoint | 3.2 - Go/No Go checklist
label | Detail of Activity - Ensure everything is in place and all outstanding items and previous holdpoints have been actioned or released.
label | Action (H/W/M/C) - Hold point
label | Frequency - Within 24 hours
label | Inspection/Test method - Review
label | Acceptance Criteria - Complete go/no go checklist
label | Verification Record Documents - Complete go/no go checklist
label | Responsibilities - PE
holdpoint | HOLD POINT
section | 4.0 Paving Preparation
checkpoint | 4.1 - Milling Depth
label | Detail of Activity - The existing road surface and underlying pavement shall be milled to the specified AC depth and area covered
label | Action (H/W/M/C) - Hold Point
label | Frequency - 20m left right and centre behind the milling machine
label | Inspection/Test method - Field Testing /Survey
label | Acceptance Criteria - SMA9.5 design thickness = 45mm
label | ○ AC20 = Design Thickness 100mm
label | ○ Minimum milling depth = 150mm3
label | Verification Record Documents - Stringline sheet from QA pack, Pictures for verification
label | Responsibilities - QA, Site Engineer
label | Comments/ Verification - Dipchecks behind the mill can be completed instead or in addition to stringlines
holdpoint | HOLD POINT
checkpoint | 4.2 - Proofrolling
label | Detail of Activity - Proofrolling to be done on milled surface
label | ○ Use PTR or loaded Asphalt truck, to proofrol milled area's. If it shows movement or has loose material please contact renewals or cotracts manager.
label | Action (H/W/M/C) - Witness Point
label | Frequency - Full surface area
label | Inspection/Test method - Field testing
label | Acceptance Criteria - Surface finish shall present a tightly consolidated surface after sweeping.
label | Verification Record Documents - Pictures or video, Written communication if any additional instructions received
label | Responsibilities - QA, Site Engineer
checkpoint | 4.3 - Membrane (Subbase Material only)
label | Detail of Activity - G4 or 5 Memberane
label | Action (H/W/M/C) - Witness Point
label | Frequency - Prior to paving on exposed Sub Base
label | Inspection/Test method - Visual Inspection
label | Acceptance Criteria - 1.0 l/m² residual binder minimum
label | Specification/Contract Clause Reference - NZTA M10: 9.3.2;
label | Verification Record Documents - Spraysheet with RP's and pictures for verification
label | Responsibilities - QA, Site Engineer
label | Comments/ Verification - Looks for stripping or any other damages.
label | ○ Spray vertical faces and transverse joints as well.
checkpoint | 4.4 - Tackcoat (Asphalt)
label | Detail of Activity - An emulsion tack coat must be sprayed between all Asphalt Layers.
label | Action (H/W/M/C) - Witness Point
label | Frequency - Prior to paving on top of existing Asphalt layer
label | Inspection/Test method - Visual Inspection
label | Acceptance Criteria - 0.2-0.6 L/m2
label | Specification/Contract Clause Reference - NZTA M10: 9.3.1;
label | Verification Record Documents - Spraysheet(s) or pictures for verification
label | Responsibilities - QA, Site Engineer
label | Comments/ Verification - Spray vertical faces and transverse joints as well
checkpoint | 4.5 - Joint Preparation
label | Detail of Activity - Transverse joints to be milled/cut back to provide a square edge and emulsion must be handsprayed on the vertical face. Succesive transverse joints must be staggered by a minimum of 2m
label | Action (H/W/M/C) - Witness Point
label | Frequency - All transverse joints
label | Inspection/Test method - Visual Inspection
label | Verification Record Documents - Pictures for verification
label | Responsibilities - QA, Site Engineer
section | 5.0 Structural Layer
checkpoint | 5.1 - Temperatures
label | Detail of Activity - Delivery and compaction temperatures to be monitored throughout the paving process
label | Action (H/W/M/C) - Check / Monitor
label | Frequency - Each truckload that arrives on site prior to paving
label | Inspection/Test method - Infrared Thermometer
label | Acceptance Criteria - A minimum of -30 degrees from the recommended mixing temperature of 160-175°C To be recorded when mix is tipped into the paver.
label | ○ Manager to be notified if temperature falls below: AC20 PG64V 130°C
label | Specification/Contract Clause Reference - NZTA M10: 2020:
label | ○ Notes; Higgins asphalt bitumen guide, NZTA M1A 2019
label | Verification Record Documents - Mix tracking sheet from QA pack; contains delivery temperature, temp when in paver, temp inside the screed and rolling temp on AC
label | Responsibilities - QA, Site Engineer
label | Comments/ Verification - It is critical to ensure a temperature representative of the full load and not surface temperatures of the mix are measured.
checkpoint | 5.2 - Layer thickness / Structural Asphalt
label | Detail of Activity - Monitor layer thickness throughout paving process. By keeping track of the spreadrates and performing dipchecks behind the paver.
label | Action (H/W/M/C) - Check / Monitor
label | Frequency - For each truckload that gets paved, 1 mix tracking sheet per shift and a site diagram per layer
label | Inspection/Test method - Survey, Field / Lab Testing
label | Acceptance Criteria - A minimum of 90% specified layer thickness to be achieved, but maximum minus 10mm of Specified layer thickness from design, with a minimum of 80mm per layer for AC20 PG64V.
label | ○ MINIMUM Thickness = 100mm as per design
label | Specification/Contract Clause Reference - NZTA M10: 2020: 9.7 and table 3.1
label | Verification Record Documents - Mix tracking sheet and site diagram in QA pack and photographic evidence to prove dipchecks have been performed
label | Responsibilities - QA
label | Comments/ Verification - These are deemed operational checks and will get verified through cores as specified in item 5.5
checkpoint | 5.3 - Compaction
label | Detail of Activity - Plateau testing to be performed to set rolling pattern
label | Action (H/W/M/C) - Check/monitor
label | Frequency - for each mix type
label | Inspection/Test method - Field / Lab Testing
label | Acceptance Criteria - Completed/Not completed
label | Verification Record Documents - Asphalt plateau density test sheet from QA pack
label | Responsibilities - QA site engineer
checkpoint | 5.5 - Cores
label | Detail of Activity - Cores to be taken post construction to prove layer thickness and air voids.
label | Action (H/W/M/C) - Check / Monitor
label | Frequency - Reduced frequency proposed in RQP due to minimal area, total of 4 cores to be taken for the site.
label | Inspection/Test method - Field / Lab Testing
label | Acceptance Criteria - Layer thickness testing :4no. core thickness tests to be taken before trimming. with a picture of each measurement.
label | ○ A minimum of 90% specified layer thickness to be achieved, but maximum minus 10mm
label | ○ Airvoids: A lot is deemed acceptable when the Characteristic values of the mat come back within the range of 2 - 7 % - Matt; 2 - 9 % Joint
label | Specification/Contract Clause Reference - NZTA M10: 2020: 9.7, 9.9, 10.3
label | Verification Record Documents - IANZ Accredited Test Report, Picture of each Cores and measurements for verification
label | Responsibilities - Site Engineer, QA Foreman, Paving Supervisor
label | Comments/ Verification - If there is any concern for the AC20 having failed, contact manager prior to continue paving surface layer. To get additional instruction on whether or not to continue or postpone
section | 6.0 Paving - Surfacing Layer
checkpoint | 6.1 - Temperatures
label | Detail of Activity - Delivery and compaction temperatures to be monitored throughout the paving process
label | Action (H/W/M/C) - Check / Monitor
label | Frequency - Each truckload that arrives on site prior to paving
label | Inspection/Test method - Field / Lab Testing
label | Acceptance Criteria - A minimum of -30 degrees from the recommended mixing temperature of 155-170°C To be recorded when mix is tipped into the paver.
label | ○ Manager to be notified if temperature falls below: SMA9.5 Melt PG64V 125°C
label | Specification/Contract Clause Reference - NZTA M10: 2020: M27
label | ○ Notes; Higgins asphalt bitumen guide, NZTA M1A 2019
label | Verification Record Documents - Mix tracking sheet from QA pack; contains delivery temperature, temp when in paver, temp inside the screed and rolling temp on AC
label | Responsibilities - QA, Site Engineer
label | Comments/ Verification - It is critical to ensure a temperature representative of the full load and not surface temperatures of the mix are measured.
checkpoint | 6.2 - Layer thickness / Structural Asphalt
label | Detail of Activity - Monitor layer thickness throughout paving process. By keeping track of the spreadrates and performing dipchecks behind the paver.
label | Action (H/W/M/C) - Check / Monitor
label | Frequency - For each truckload that gets paved, 1 mix tracking sheet per shift and a site diagram per layer
label | Inspection/Test method - Survey, Field / Lab Testing
label | Acceptance Criteria - Average depth > min specified depth
label | ○ As per M10 for layer thicknesses below spec. an LCV of -5mm of specified thickness is allowed.
label | ○ Thickness Req: 45mm as per design
label | Specification/Contract Clause Reference - NZTA M10: 2020: 9.7 and table 3.1; M27
label | Verification Record Documents - Layer sheet and site diagram in QA pack and photographic evidence to prove dipchecks have been performed
label | Responsibilities - QA
label | Comments/ Verification - These are deemed operational checks and will get verified through cores as specified in items 6.3
checkpoint | 6.3 - Cores
label | Detail of Activity - Cores to be taken post construction to prove layer thickness and air voids.
label | Action (H/W/M/C) - Check / Monitor
label | Frequency - Joint: 1 per 100m /minimum. 3 per Lot Mat: 1 per 300m2 / minimum. 8 per Lot
label | Inspection/Test method - Field / Lab Testing
label | Acceptance Criteria - Layer thickness testing :4no. core thickness tests to be taken before trimming. with a picture of each measurement.
label | ○ Accepted Airvoids = 2 - 7 % - Matt; 2 - 9 % Joint
label | Specification/Contract Clause Reference - NZTA M10: 2020: 9.7, 9.9, 10.3, M27
label | Verification Record Documents - IANZ Accredited Test Report
label | ○ Picture of each Core
label | ○ Coring Site Diagram in AC QA Pack
label | Responsibilities - Site Engineer, QA Foreman, Paving Supervisor
checkpoint | 6.4 - Overbanding/Joint Filling
label | Detail of Activity - Joints between new asphalt and existing surfacings are to be over banded with a suitable bituminous filler to prevent water ingress.
label | Action (H/W/M/C) - Monitor
label | Frequency - Between Joints of Existing and new Asphalt
label | Inspection/Test method - Visual Verification
label | Acceptance Criteria - Satisfactorily completed
label | Verification Record Documents - Mention quantities of Bandage Seal in AC QA Pack
label | ○ Pictures uploaded into Site Diary of Procore
section | 7.0 Post construction
checkpoint | 7.1 - Post seal inspection
label | Detail of Activity - Ensure the shape and levels of finished surface is acceptable
label | Action (H/W/M/C) - check/monitor
label | Frequency - at completion of paving
label | Inspection/Test method - Visual verification/ Field testing
label | Acceptance Criteria - Roughness - Where the length of the site or the geometry is such that a road roughness-measuring vehicle cannot be used then the straight edge can be used for checking the surface shape.
label | ○ Not more than 5mm under a 3m Straight Edge.
label | ○ Level - -0 < +5mm from Specified Level
label | ○ Where there is Kerb and Channel shall be flush with or no more than 5mm above the LOC.
label | Specification/Contract Clause Reference - NZTA M10 9.8 and M27 10.2
label | Verification Record Documents - Pictures and completion checklist
label | Responsibilities - SE, Sup
checkpoint | 7.2 - QA Handover
label | Frequency - For each site on the project
label | Acceptance Criteria - Over milled and Deep lift extents recorded and verified by Contract Engineer / QA
label | ○ Spray sheets for membrane area received by Contract Engineer from Sealing Team.
label | ○ Surfacing layer extents recorded and verified by Contract Engineer.
label | Specification/Contract Clause Reference - NZTA M10, M27 as appropriate and contract drawings
label | Verification Record Documents - Evidence provided demonstrating full compliance with specified design
label | Responsibilities - QA Site Engineer, PE, RM
checkpoint | 7.3 - Linemarking and RRPM reinstated Matches previous linemarking - within 48 hours of sealing
label | Detail of Activity - On completion of surfacing pavement markings and reflective raised pavement markers are to be reinstated
label | Action (H/W/M/C) - Check Point
label | Frequency - at completion of site
label | Inspection/Test method - Visual verification
label | Acceptance Criteria - Everything reinstated
label | Specification/Contract Clause Reference - MOTSAM
label | Verification Record Documents - Pictures for verification
label | Responsibilities - SE, Sup, PE
checkpoint | 7.4 - Collect RAMM data
label | Detail of Activity - RAMM update to be completed
label | Action (H/W/M/C) - Check Point
label | Frequency - at completion of site
label | Inspection/Test method - Verification
label | Acceptance Criteria - Completed/Not completed
label | Responsibilities - Surveyor, CPM, SE
section | 8.0 Final Sign Off
checkpoint | Client Final Inspection: The signature below verifies that this ITP has been completed in conformance with the contract requirements and and other relevant specifications.
textbox | Contractor's Rep Name:
textbox | Contract Administrator:
textbox | Project Manager Name:
textbox | Quality Manager Name:
signoff | Signatures: