## struct
resource | resource | resource | resource | type | Add Step | Add Post | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Tier 7 | Tier 8 | Tier 9
Site Establishment and Safety Checklist |  |  |  | checklist |  |  | Tier 1: OHS
|  |  |  | step |  |  | Tier 1: DUCTWORK
Ductwork Checklist | Grille Fit-Off Checklist |  |  | folder-with-checklists |  |  | Tier 2: Level 5
|  |  |  | step |  |  | Tier 1: VAV
VAV Checklist |  |  |  | checklist |  |  | Tier 2: VAV-9.2
VAV Checklist |  |  |  | checklist |  |  | Tier 2: VAV-9.4
VAV Checklist |  |  |  | checklist |  |  | Tier 2: VAV-13.4
|  |  |  | step |  |  | Tier 1: FAN
Fan Checklist |  |  |  | checklist |  |  | Tier 2: GEF-5.1.1
Fan Checklist |  |  |  | checklist |  |  | Tier 2: GEF-5.1.2
Fan Checklist |  |  |  | checklist |  |  | Tier 2: GEF-5.1.3
|  |  |  | step |  |  | Tier 1: SPLIT DX
Split DX Unit Checklist | Drains Checklist | Ductwork Checklist | Grille Fit-Off Checklist | folder-with-checklists |  |  | Tier 2: AC-5.1.1
Split DX Unit Checklist | Pipework Testing Checklist |  |  | folder-with-checklists |  |  | Tier 2: CU.5.1
Split DX Unit Checklist | Drains Checklist | Ductwork Checklist | Grille Fit-Off Checklist | folder-with-checklists |  |  | Tier 2: AC-5.1.2
Split DX Unit Checklist | Pipework Testing Checklist |  |  | folder-with-checklists |  |  | Tier 2: CU.5.2
Split DX Unit Checklist | Drains Checklist | Ductwork Checklist | Grille Fit-Off Checklist | folder-with-checklists |  |  | Tier 2: AC-5.1.3
Split DX Unit Checklist | Pipework Testing Checklist |  |  | folder-with-checklists |  |  | Tier 2: CU.5.3