## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP R44 (ed6) - Earthworks QA | [5 empty] | ITP R44 (ed6) - Earthworks QA
section | Earthworks QA
checkpoint | 1 - Implement & monitor ERSED controls
label | Spec / Doc Ref. - R44.1.8, G38.3.1, G38.2.2.2
label | Inspection Requirement - Submission of an ESCP(s), Submit written advice that the ESCP controls have been implemented or the date they will be implemented.
label | Acceptance Criteria - ESCP requirements listed in G38 Cl2.2.2.
label | Frequency - ≥10 work days prior earthworks, ≥5 work days prior earthworks, each section
label | H / W - H, W
label | Inspection/ Test Type - Submission, Submission & inspection
label | Verification Ref. (Record, Test Report, HPR, NCR, etc) - HPR, ESCPs, WPR
label | Verified by - Project Mgr (PM) / Project Eng’r (PE)
date | Verification Signature - Date:
holdpoint | HOLD POINT
checkpoint | 2 - Existing utility locating & NDD potholing
label | Spec / Doc Ref. - R44.1.5.1 (n)
label | Inspection Requirement - Check service locating & marking, and NDD potholing of existing utilities is completed
label | Acceptance Criteria - Controls to protect utilities during earthworks in place
label | Frequency - Prior earthworks, each section
label | Inspection/ Test Type - Visual
label | Verified by - PM / PE / Supervisor (S)
date | Verification Signature - Date:
checkpoint | 3 - Setout earthworks extents
label | Spec / Doc Ref. - R44.1.6.2
label | Inspection Requirement - Setout by marking on the ground the earthworks limits
label | Frequency - Prior earthworks, each section
label | Inspection/ Test Type - Survey
label | Verification Ref. (Record, Test Report, HPR, NCR, etc) - Photo of marking in place
label | Verified by - PM / PE / S / Surveyor
date | Verification Signature - Date:
checkpoint | 4 - Removal of topsoil
label | Spec / Doc Ref. - R44.2.5.1
label | Inspection Requirement - Check topsoil removed & stockpiled correctly
label | Acceptance Criteria - Strip full depth of topsoil in earthworks areas. Stockpile for use in revegetation.
label | Frequency - each section
label | Inspection/ Test Type - Visual
label | Verification Ref. (Record, Test Report, HPR, NCR, etc) - Photo
label | Verified by - PM / PE / S
date | Verification Signature - Date:
checkpoint | 5 - Test pits to verify CBR10 day & PI of subgrade & insitu SMZ
label | Spec / Doc Ref. - C-0604.00 R1 Table 6 RNB-241, R44/A2.2, R44/L.1
label | Inspection Requirement - Check CBR & PI samples completed from test pits
label | Acceptance Criteria - CBR: Subgrade ≥3%, Insitu SMZlower ≥ 15%,
label | ○ Insitu SMZupper ≥ 30%
label | ○ PI≤25% (no insitu SMZ)
label | ○ PI≤15% (insitu SMZ)
label | ○ SMZ: Max particle dim: 53mm, >50% passing 19mm sieve, >30% passing 2.36mm sieve
label | Frequency - 1 / 1000m2
label | ○ 1 / 1000m2
label | ○ 1 / 1000m2
label | ○ 1 / 1000m2
label | ○ 1 / 1000m2
label | ○ Each Lot
label | ○ Each Lot
label | ○ Each Lot
label | Inspection/ Test Type - T117, T109, Inspection / T280(if req’ed), T106
label | Verification Ref. (Record, Test Report, HPR, NCR, etc) - CBR, PI, max particle, T106 test reports
label | ○ Note: Report P20009-1 (in D&N Geotechnical report C-0604.00) indicates the ex pvmnt material at BH01 has CBR10 day of 40% per T117)
label | Verified by - PM / PE
date | Verification Signature - Date:
checkpoint | 6 - Excavate to design levels and profiles
label | Spec / Doc Ref. - R44.3.2, R44/A2.2 C-0604.00 R1 Table 6 RNB-241, Pavement Design Approval - STH18 00222 Tbl R44.8
label | Inspection Requirement - Check excavated to Design Floor Level (DFL). Check CBR & PI tests completed. Present floor for inspection.
label | Acceptance Criteria - Where at Top of Formation (DSL-330mm), there is ≥300mm existing Sydney Rd pavement, SMZ comprises existing pavement left in-situ, therefore DFL is DSL-330mm.
label | ○ Where no existing pavement, DFL is DSL-630mm (& a 300mm SMZ to be provided).
label | ○ Level tolerance: +10/-40mm (no insitu SMZ), or +0/-20mm (insitu SMZ)
label | Frequency - each section
label | H / W - H
label | Inspection/ Test Type - Survey, Test & Inspection
label | Verification Ref. (Record, Test Report, HPR, NCR, etc) - HPR, DFL Level conformance report
label | Verified by - PM / PE
date | Verification Signature - Date:
holdpoint | HOLD POINT
checkpoint | 7 - Proof roll DFL
label | Spec / Doc Ref. - R44.7.5, R44/L.1
label | Inspection Requirement - Notify Council of proof roll (WP)
label | Acceptance Criteria - Not exhibit visible deformation, rutting, yielding or show signs of distress / instability
label | Frequency - ≤1 work day of proof roll
label | H / W - W
label | Inspection/ Test Type - T198
label | Verification Ref. (Record, Test Report, HPR, NCR, etc) - WPR, proof roll (T198) report
label | Verified by - PM / PE
date | Verification Signature - Date:
checkpoint | 8 - Unsuitable Material (if any)
label | Spec / Doc Ref. - R44.2.6, R44.5.2.1, R44.7.5, Tbl R44.7 R44/A5, R44/L.1
label | Inspection Requirement - Where unsuitable material indicated by:
label | – inspection in item 5,
label | – CBR / PI testing, or
label | – proof roll, excavate unsuitable to the extent directed by the Principal.
label | ○ Notify when unsuitable removed to the extent directed (Hold Point).
label | ○ Replace w/ compacted Earth Fill or (if directed) Foundation treatments
label | Acceptance Criteria - Min Rel Comp: 98%, Moisture: 60-90% of OMC
label | Frequency - each section of unsuitable material
label | H / W - H
label | Inspection/ Test Type - Inspection, Refer R44/L.1, Refer R44/L.1
label | Verification Ref. (Record, Test Report, HPR, NCR, etc) - HPR, compaction & MC (if replaced by compactible material) report, Survey reports (before & after)
label | Verified by - PM / PE
date | Verification Signature - Date:
holdpoint | HOLD POINT
checkpoint | 9 - Site won SMZ material (for placement where no insitu SMZ)
label | Spec / Doc Ref. - R44.2.8.5.1, R44.6.1.2, R44/A2.2, R44/L.1 C-0604.00 R1 Table6 RNB-241,
label | Inspection Requirement - Submit test reports verifying conformity of each site won SMZ material stockpile
label | Acceptance Criteria - CBR10 day (per RNB-241)
label | – Upper layer: ≥30%
label | – Lower layer: ≥15%
label | ○ Plasticity Index: ≤15%
label | ○ Max particle dim: 53mm
label | ○ >50% passing 19mm sieve, >30% passing 2.36mm sieve
label | Frequency - Prior SMZ placement,
label | ○ Each Lot
label | ○ Each Lot
label | ○ Each Lot
label | ○ Each Lot
label | ○ Each Lot
label | H / W - H
label | Inspection/ Test Type - T117, T109, Inspection / T280(if req’ed), T106
label | Verification Ref. (Record, Test Report, HPR, NCR, etc) - HPR, CBR, PI, PSD test reports
label | ○ Note: Report P20009-1 (in D&N Geotechnical report C-0604.00) indicates the ex pvmnt material at BH01 has CBR10 day of 40% per T117)
label | Verified by - PM / PE
date | Verification Signature - Date:
holdpoint | HOLD POINT
checkpoint | 10 - Placed site won SMZ Layer (for placement where no insitu SMZ)
label | Spec / Doc Ref. - R44.6.1.2 Tbl R44.7, R44.7.5, R44.7.7.1, R44/A5, R44/L.1 C-0604.00 R1 Table 6 RNB-241, Pavement Design Approval - STH18 00222
label | Inspection Requirement - Notify Council of proof roll (WP). Submit verification of conformity of SMZ, with test reports & survey conf reports. Check level, compaction, appearance, proof roll results conform.
label | Acceptance Criteria - Level upper: +0/-20mm
label | ○ Level lower: +10/-40mm
label | ○ Thickness upper: 150mm
label | ○ Thickness lower: 150mm
label | ○ Compaction: 102%
label | ○ MC: 60-90% of OMC
label | ○ Appearance: homogenous & free from segregated stone or excess fines.
label | ○ Proof roll: Not exhibit visible deformation, rutting, yielding or show distress/instability
label | Frequency - ≤1 work day of proof roll, Prior covering SMZ, Survey & geotech testing refer R44/L.1
label | H / W - W, H
label | Inspection/ Test Type - Survey
label | ○ Survey
label | ○ Survey
label | ○ Survey
label | ○ T166, T173
label | ○ T120/T121
label | ○ Visual
label | ○ T198
label | Verification Ref. (Record, Test Report, HPR, NCR, etc) - WPR, HPR, Comp & MC test report, proof roll report, survey thickness & level conformance report
label | Verified by - PM / PE
date | Verification Signature - Date:
holdpoint | HOLD POINT
checkpoint | 11 - Submission – Closed ITP w/ material & test reports, survey records
label | Inspection Requirement - Submit closed ITP to Council.
label | Acceptance Criteria - Complete submission to Council
label | Frequency - At completion
label | Inspection/ Test Type - Submission
label | Verification Ref. (Record, Test Report, HPR, NCR, etc) - This closed ITP & associated records
label | Verified by - PM / PE
date | Verification Signature - Date:
section | The lot verification records are complete and attached with all non-conformances and RFI’s closed out.
checkpoint | Lot Complete / Records available:
textbox | Name:
textbox | Title:
date | Date:
holdpoint | Signed:
checkpoint | Lot Approved for Closure:
textbox | Name:
textbox | Title:
date | Date:
holdpoint | Signed: