## Sheet3
Inspection and Test Plan Te Ara o Te Ata Geotechnical Equipment Installation ITP# MMA-QA-ITP-PW-GE-GE009
| This ITP has been prepared by |  |  | Reviewed by Quality Manager |  |  | Reviewed by DSR |  |  |  | Approved by Construction Manager
Rev Number | Name | Signature | Date | Name | Signature | Date | Name | Signature | Date |  | Name |  | Signature |  | Date
Rev 01 | William McCracken | WM | 2022-08-29
Rev 02 | William McCracken | WM | 2023-12-14 | Ramy Faragalla | R Faragalla | 2023-12-19 | Razel R |  | 2024-03-06 |  | Hardus Pieters |  |  |  | 2024-03-06
Rev 03
Rev 04
ITP NO: MMA-QA-ITP-PW-GE-GE009 |  | Project: Te Ara o Te Ata | [5 empty] | Method Statement Ref:
Verification Method: Hold [H] – work will not proceed past Hold Point until released by organisation imposing hold; Inspection [I] – formal inspection activity to be undertaken and recorded; ensure correct verifying records are in place; Witness [W] – an inspection that may be witnessed by organisation imposing hold; allow reasonable notification period; Review [R] – review of reports, records or other evidence of compliance. | [7 empty] | Responsibilities PE = MTM Alliance Construction TWD = Temporary Design Team
Activity/Specification: Drainage and Earthworks | [7 empty] | Area Location / Work Breakdown: Project Wide
Item | Construction Step or Material |  | Specifications and Standards |  | Acceptance criteria and testing |  |  |  | Method (H,I,W,R) |  |  |  |  | Verifying Records Checklists, Test and Supplier Certificates
Responsible [tick]
[5 empty] | Method/Description | Test frequency |  | Conformance Criteria | Installer | Contractor | Designer | Client | Lab
1.0 Pre-Construction
1.01 | Construction Environmental Management Plan |  | MMA-ENV-RMP-RPT-15631 |  | Document Review | Prior to personnel starting |  | Ensure all crew members are briefed on the CWP |  | H |  |  |  | Signed off CWP
1.02 | Construction Work Plan |  | CWP |  | Document Review | Prior to work starting |  | Ensure all crew members are briefed on the CWP |  | H |  |  |  | Signed off CWP
1.03 | IFC's specification |  | MMA-GES-GEO-E1-SPC-3859 |  | Document Review | Once prior to works commencing |  | Obtain copy of the earthworks specification and ground instrumetnation and monitoring plan |  | H | H |  |  | IFCspecifications or Written approval from PAB
1.04 | IFC drawings |  | IFC drawings including setout points of ground instrumentation |  | Document Review | Once prior to works commencing |  | Ensure all drawings are approved and of the latest revision, or written approval from PAB |  | H | H |  |  | IFC drawings or Written approval from PAB
1.05 | Approved setout locations of instrumentations |  |  |  | Designer Confirmation | Once for every fill site prior to work commencing |  | Designer to confirm and approve loation of instrumentation prior to uploading into survey equipment |  | H | H |  |  | Written Confirmation from Designeer
1.06 | Method Statements Approval |  | MMA-DES-GEO-E1-SPC-8510 |  | Document Review | Prior to installation of instrumentation |  | a) Health, Safety and Wellbeing Plan detailing hazards and mitigation for personnel involved in the installation and monitoring, as well as remaining operations staff not directly involved in the installation and monitoring. This shall be reviewed at regular intervals in consultation with the Designer and the Constructor. b) Details of the manufacturer/supplier for each type of instrument and appropriate supporting manufacturer’s literature and QA/QC documentation, including calibration certificates for all proposed instrument readout units. c) Method of installation for each instrument type, including details such as borehole construction, drilling equipment, grouting, backfilling and cover types. d) Procedures for testing the installed instrumentation to demonstrate satisfactory installation and performance, including taking and documenting of baseline readings. e) Procedures for regular monitoring of the installed instrumentation and repair / replacement options in the event of repeated failure. f) Confirm experience and competence of nominated personnel and organisations undertaking and supervising the installation and monitoring of all geotechnical instrumentation. |  | H | H |  |  | Method Statement
1.07 | Calibration of Read Out Equipment |  | Manufacturers Specification |  | Document Review | Prior to starting |  | Manufacturers Specification |  | H |  |  | I | Calibration Certificate
2.0 Material Compliance
2.01 | Vibrating Wire Piezometer manufacturer specification |  | Manufacturers Specification |  | Document Review | Once |  | Designeer to approve equipment Specifications |  |  | H |  |  | Material Certificate
2.02 | Vibrating Wire Piezometer calibration |  | Manufacturers Specification |  | Document review of manufacturer's calibration certificate of piezometer | Delivery and acceptance of piezometer material; prior to installation |  | The piezometer shall be calibrated by the manufacturer from 0 to 0.35 Mpa. A copy of the manufacturer's calibration certificate for each piezometer shall be provided to the Geotechnical Designer. |  |  | H |  |  | Bore Logs
2.03 | Extensometer manufacturer specification |  | Manufacturers Specification |  | Document Review | Once |  | Designeer to approve equipment Specifications |  |  | H |  |  | Material Certificate
2.04 | Inclinometer manufacturer specification |  | Manufacturers Specification |  | Document Review | Once |  | Designeer to approve equipment Specifications |  |  | H |  |  | Material Certificate
2.05 | Inclinometer casing material |  | MMA-DES-GEO-E1-SPC-8510 & IFC drawings |  | Inspection of Inclinometer Casing Materials | After Delivery and acceptance of Inclinometer Casing Materials; Prior to Installation. |  | The inclinometer casing shall be 70 mm ID ABS (Acrylonitrile-butadiene-styrene) plastic manufactured by Slope Indicator (or similar as approved by the Designer). It shall be self-aligning and be precisely manufactured to match the inclinometer probe. | I | W |  |  |  | Bore Logs
2.06 | Inclinometer grouting materials |  | MMA-DES-GEO-E1-SPC-8510 & IFC drawings |  | Review & approval of approved grout mix | Prior to Equipment Installation |  | Approved Grout Mix from the Designer |  |  | H
2.07 | Inclinometer materials |  | MMA-DES-GEO-E1-SPC-8510 & IFC drawings |  | Inspection of Inclinometer Measuring Equipment | After Delivery and acceptance of Inclinometer Measuring Equipment; Prior to Installation. |  | Inclinometer Measuring Equipment Materials delivered | I | W
2.08 | Rod and Plate Settlement Markers |  | MMA-DES-GEO-E1-SPC-8510 & IFC drawings |  | Inspection of Settlement Plate Materials | After Delivery and acceptance of Settlement Plate Materials; Prior to Installation. |  | Settlement plates shall consist of a 600 mm square, 12 mm thick steel plate supporting a 25 mm diameter steel upstand bar, securely bolted or welded to the steel plate. The upstand bar shall be protected by a Class D uPVC pipe separated from the steel base plate by 50mm using a compressible layer of foam or similar approved, or by lifting the first length of the uPVC prior to connecting the second length. | I |  |  |  |  | Delivery Dockets
2.09 | Surface settlement marker material |  | MMA-DES-GEO-E1-SPC-8510 & IFC drawings |  | Inspection of Surface Settlement Marker Materials | After Delivery and acceptance of Settlement Marker Materials; Prior to Installation. |  | Surface settlement marker shall consist of a steel reference pin cast into a concrete footing. A galvanised threaded rod shall be at least 12mm diameter and at least 600mm long. The footing shall be at least 400mm deep and at least 300mm square or circular. |  | W
2.1 | Surface monitoring marker material |  | MMA-DES-GEO-E1-SPC-8510 & IFC drawings |  | Inspection of Surface Monitoring Marker Materials | After Delivery and acceptance of Surface Monitoring Marker Materials; Prior to Installation. |  | Surface monitoring marker shall consist of a 12mm diameter, 300mm long steel reference pin epoxy grouted into 15mm diameter drill hole. |  | W
2.11 | Lateral deformation marker material |  | MMA-DES-GEO-E1-SPC-8510 & IFC drawings |  | Inspection of Lateral Deformation Marker Materials | After Delivery and acceptance of Surface Monitoring Marker Materials; Prior to Installation. |  | Lateral deformation markers shall comprise minimum 1500mm long 45x45 survey stakes |  | W
2.12 | Profilometer material |  | MMA-DES-GEO-E1-SPC-8510 & IFC drawings |  | Inspection of Profilometer Tubing & Backfill Materials | After Delivery and acceptance of Profilometer Tubing & Backfill Materials; Prior to Installation. |  | Tubing for profilometers shall be semi-rigid continuous MDPE pipe of nominal 63 mm ID, compatible with the probe size, and with 5 mm thick walls. The backfill surrounding the tubing shall be a compacted well graded approved sand.The draw cord within the profilometer tubing shall comprise a 2.5 mm galvanised steel cable. Probe accurate +/-10mm Vertical Operating range > 7.0m Operating Temp 0 - 40 deg | I | W |  |  |  | Material Certificate
3.0 Instrumentation Installation
3.1.0 Vibrating Wire Piezometer Installation
3.1.1 | Piezometer location per construction drawings |  | MMA-DES-GEO-E1-SPC-8510 & IFC drawings |  | Inspection of borehole location | Before borehole drilling |  | Locations will be as specified on the Construction Drawings or as directed by the Designer. | I | W
3.1.2 | Borehole Drilling |  | MMA-DES-GEO-E1-SPC-8510 |  | Inspection of borehole | After borehole drilling |  | The recovered core will be logged by a person approved by the Geotechnical Designer and who is qualified in soil logging and fully briefed on expected ground conditions. Borehole logs shall be prepared and filed, and shall form part of the as-built record. | I | W | W |  |  | Bore Logs
3.1.3 | Depth of piezometers |  | MMA-DES-GEO-E1-SPC-8510 and IFC drawings |  | Review & approval of depths of piezometer based on the results of the core logging | After borehole drilling |  | Approved depth of Piezometer as directed by the Designer |  |  | H
3.1.4 | Core materials |  | MMA-DES-GEO-E1-SPC-8510 and IFC drawings |  | Inspection of all retaining cores | After borehole installation |  | All cores shall be retained for the duration of the project construction. | I
3.1.5 | Heavy duty connecting cable placement |  | MMA-DES-GEO-E1-SPC-8510 & IFC drawings |  | Inspection of completed heavy duty connecting cable placement | After placement of heavy duty connecting cable |  | Heavy duty connecting cables shall be compatible with the piezometer and shall comply with the recommendations and requirements of the piezometer manufacturer. The cables shall be permanently and securely attached to the piezometers by a seal gland assembly. The cables shall be supplied and installed as complete lengths. | I | W
3.1.6 | Splicing of heavy duty connecting cable |  | MMA-DES-GEO-E1-SPC-8510 & IFC drawings |  | Review & approval regarding acceptance of cable splicing | Prior to splicing of heavy duty connecting cable |  | Splices will not be permitted except with the approval of the Designer. If a splice is required, the manufactures recommended splice kit shall be used. |  |  | H
3.1.7 | Readout unit/data logger placement |  | MMA-DES-GEO-E1-SPC-8510 & IFC drawings |  | Inspection of completed readout unit/data logger placement | After placement of readout unit/data logger |  | The Contractor shall provide all necessary calibration certificates and other supporting QA documentation for the readout units and/or data loggers. | I | W
3.1.8 | Ground surface finish of installed piezometer |  | MMA-DES-GEO-E1-SPC-8510 & IFC drawings |  | Inspection After completion of the installation process of Piezometer | After completion of the installation process of Piezometer |  | The piezometer shall be finished at the ground surface with a small concrete pad and a clearly visible, lockable upstand cover as detailed in the Construction Drawings | I | W
3.1.9 | Ground surface finish of installed connecting cables |  | MMA-DES-GEO-E1-SPC-8510 & IFC drawings |  | Inspection After completion of the installation process of Piezometer | After completion of the installation process of Piezometer |  | The connecting cables shall be led via a shallow trench to a clearly visible termination box as detailed in the Construction Drawings. | I | W |  |  |  | Bore Logs
3.2.0 Inclinometer Installation
3.2.1 | Inclinometer location per construction drawings |  | MMA-DES-GEO-E1-SPC-8510 & IFC drawings |  | Inspection of Inclinometer Placement | After Placement of Inclinometer |  | Inclinometer instrument levels and locations will be as specified on the Drawings or as directed by Designer | I | W | H
3.2.2 | Borehole drilling |  | MMA-DES-GEO-E1-SPC-8510 |  | Inspection of Borehole Installation | After Borehole drilling |  | The recovered core will be logged by a person approved by the Designer and who is qualified in soil logging and fully briefed on expected ground conditions. Borehole logs shall be prepared and filed, and shall form part of the as-built record. | I | W
3.2.3 | Depth of inclinometer |  | MMA-DES-GEO-E1-SPC-8510 |  | Review & Approval regarding depth of Inclinometer based on the results of the core logging | During Borehole drilling |  | Approved depth of Inclinometer as directed by the Geotechnical Designer |  |  | H
3.2.4 | Core materials |  | MMA-DES-GEO-E1-SPC-8510 |  | Inspection of all retained cores | After Borehole drilling |  | All core shall be retained for the duration of the project construction | I | W
3.2.5 | Grouting installation |  | MMA-DES-GEO-E1-SPC-8510 |  | Inspection of Grouting Installation | After Grouting Installation |  | The inclinometer tubing shall be grouted into the borehole using specialist grouting equipment, e.g. mixers and pumps. The grout shall be delivered to the base of the borehole using tremmie techniques in order to ensure that the annulus between the inclinometer casing and borehole wall is completely grouted over the full borehole length. Alternatively installation may be carried out using a grout valve in the base of the casing or a pre-grouted borehole. The inclinometer casing shall be filled with clean, potable water. Should the grout drop in level after installation, additional grout will be required to raise it flush with ground level. Additional grout shall be introduced no less than 12 hours after initial grouting. | I | W
3.2.6 | Ground surface finish of installed inclinometer |  | MMA-DES-GEO-E1-SPC-8510 |  | Inspection After completion of the installation process of Inclinometer | After completion of the installation process of Inclinometer |  | A lockable protective upstand or cover shall be installed at the top of the casing as shown on the Construction Drawings. The cover shall be large enough to allow attachment of the pulley assembly to the top of the casing, and be clearly visible to construction traffic. | I | W
3.3.0 Profilometer Installation
3.3.1 | Profilometer tubing levels and location per construction drawings |  | MMA-DES-GEO-E1-SPC-8510 & IFC drawings |  | Inspection of profilometer tubing Placement | After placement of the profilometer tubing |  | Profilometer tubing levels and locations will be as specified on the Drawings | I | W
3.3.2 | Profilometer installation |  | MMA-DES-GEO-E1-SPC-8510 |  | Inspection of profilometer tubing Placement | After placement of the profilometer tubing |  | The installation of the profilometer shall be supervised by an experienced and competent geotechnical technician. The tubing shall be installed in a trench excavated between the two end reference points, as shown on the Construction Drawings, and surrounded by well compacted sand bedding. The tubing shall be laid as horizontal and straight as possible between the two reference points specified. A sketch record shall be made of ground conditions encountered along the trench alignment. | I | W
3.3.3 | Ground surface finish of installed profilometer |  | MMA-DES-GEO-E1-SPC-8510 |  | Inspection after completion of the installation process of profilometer | After completion of the installation process of profilometer |  | Reinforced concrete monitoring pads with reference stands shall be constructed, as specified on the Construction Drawings, at each end of each profilometer tube. Where the tube exits the monitoring pad it shall be protected by a lockable protective upstand or cover. The monitoring pad shall be clearly visible and protected from construction activity with orange fencing. | I | W
3.4.0 Rod and Plate Settlement Plate Installation
3.4.1 | Settlement plate installation |  | MMA-DES-GEO-E1-SPC-8510 |  | Inspection of Settlement Plate Placement | Before placement of the Settlement Plate |  | Prior to placing the steel plate the formation shall be levelled and graded and a sand fill or similar approved placed. The steel plate shall then be carefully seated on the sand fill and fill placed. |  | W
3.4.2 | Ground surface finish of installed settlement plate |  | MMA-DES-GEO-E1-SPC-8510 |  | Inspection After completion of the installation process of Settlement Plate | After completion of the installation process of Settlement Plate |  | Ground surface finished as per Construction Drawings. The top of the rod shall be surveyed by conventional surveying techniques to achieve a level accuracy of +/-5 mm. |  | W | H
3.5.0 Surface Settlement Marker Installation
3.5.1 | Ground surface finish of installed surface settlement marker |  | MMA-DES-GEO-E1-SPC-8510 |  | Inspection After completion of the installation process of Surface Settlement Marker | After completion of the installation process of Settlement Marker |  | Ground surface finished as per Construction Drawings. The surface settlement marker shall be surveyed by conventional surveying techniques to achieve a level accuracy of +/-5 mm. |  | W
3.6.0 Surface Monitoring Marker Installation
3.6.1 | Ground surface finish of installed surface monitoring marker |  | MMA-DES-GEO-E1-SPC-8510 |  | Inspection After completion of the installation process of Surface Monitoring Marker | After completion of the installation process of Surface Monitoring Marker |  | Ground surface finished as per Construction Drawings. The surface monitoring marker shall be surveyed by conventional surveying techniques to achieve a level accuracy of +/-5 mm. |  | W
3.7.0 Lateral Deformation Marker Installation
3.7.1 | Ground surface finish of installed lateral deformation marker |  | MMA-DES-GEO-E1-SPC-8510 |  | Inspection After completion of the installation process of Lateral Deformation Marker | After completion of the installation process of Surface Monitoring Marker |  | The position of the lateral deformation markers shall be recorded to within ±100mm horizontally and ±20mm vertically. The plunge of the stake shall be recorded using either an inclinometer or similar device able to record dip/dip direction of the stake with good repeatability. Repeat surveys shall record the horizontal and vertical position to the same accuracy as the baseline survey and measure the dip/dip direction. |  | W
3.8.0 UAV Survey/Face Scan
3.8.1 | Ground surveys using unmanned aerial vehicles (UAVs) |  | MMA-DES-GEO-E1-SPC-8510 |  | Survey | 1. Prior to any ground disturbance; 2. Upon completion of vegetation and topsoil strip; 3. Regular intervals as fill embankments are raised (maximum of 5m fill placed between surveys) and cuttings are formed (maximum 10m depth increments between surveys); 4. Upon reaching final surcharge heights for preload embankments and final embankment heights where no surcharge is required, and full cut depths; 5. Monthly intervals during the earthworks operations and at the end/commencement of each earthworks season; 6. Following removal of surcharge and final embankment profiles have been formed; 7. Immediately prior to pavement construction; 8. At completion of pavement construction; 9. Practical Completion; 10. Every 3 months during Defects Liability Period; 11. End of Defects Liability Period. Face scans of rock cuttings shall be completed as each cutting is advanced in increments of 10m and at maximum three monthly intervals thereafter during the earthworks season and at commencement and end of each earthworks season. Scans shall have an accuracy of ±100mm and repeat surveys shall be able to compared to previous surveys to assess potential surface movements between surveys using 3D Reshaper software or similar. |  | Obtain copy of the survey data |  | W
3.9.0 Extensometer Installation
3.9.1 | Extensometer location per construction drawings |  | MMA-DES-GEO-E1-SPC-8510 & IFC drawings |  | Inspection of extensometer Placement | After Placement of extensometer |  | Inclinometer instrument levels and locations will be as specified on the Drawings or as directed by Designer | I | W | H
3.9.2 | Borehole Drilling |  | MMA-DES-GEO-E1-SPC-8510 & IFC drawings |  | Inspection of Borehole Installation | After Borehole drilling |  | The recovered core will be logged by a person approved by the Designer and who is qualified in soil logging and fully briefed on expected ground conditions. Borehole logs shall be prepared and filed, and shall form part of the as-built record. | I | W
3.9.3 | Extensometer tubes |  | MMA-DES-GEO-E1-SPC-8510 & IFC drawings |  | Inspection of Grouting Installation | After Grouting Installation |  | The PVC extensometer tube must be sized according to the instrumentation manufacturer’s recommendations and be fully compatible with the instrumentation and recording equipment. The tube must be able to be extended as the height of fill increases. The extensometer tube shall be grouted in place using a weak grout mix with a strength of 5 MPa to 10 MPa. |  | W
3.9.4 | Spider magnets |  | MMA-DES-GEO-E1-SPC-8510 & IFC drawings |  | Review & Approval regarding depth of based on the results of the core logging | During Borehole drilling |  | Spider magnets shall be mechanically actuated with 6 leaf springs, typically extending to a tip-to-tip diameter of 220 mm (203 mm for Geokon). It is anticipated that up to 6 no. spider magnets per installation will be installed. The base of the extensometer shall extend a minimum of 3 m into competent, slightly weathered Mt Messenger Formation Rock. A datum magnet shall be fixed at the base of the extensometer in rock . During installation, the spider magnets shall be held in place without sliding. The extensometer tubes shall be greased to allow subsequent sliding along the tube. After installation, the extensometer shall be verified by confirming that the magnets are within 200mm of their intended location and the access tube is clean of grout. |  |  | H
3.9.5 | Reading and recording settlement |  | MMA-DES-GEO-E1-SPC-8510 |  | Inspection after completion of the installation process | After completion of the installation process |  | The probe and tape shall be fully compatible with the extensometer tube. The probe must be graduated in minimum 5 mm intervals. The Constructor shall provide all necessary calibration certificates and other supporting QA documentation for the probe. |  | W
3.10.0 Reflected Survey Marker Installation
3.10.1 | Reflective survey target marker installation |  |  |  | Inspection of Reflective Survey Target Marker Placement | Before placement of the Reflective Survey Target Marker |  | Reflective survey target marker shall be firmly attached to the structure for the duration of the monitoring. Readings must be taken in all 3 directions (i.e. x, y, z) to allow assessment of any movement and/or tilt in every direction. |  | W
3.10.2 | Reflective survey target marker installation completion |  |  |  | Inspection After completion of the installationof Reflective Survey Target Marker | After completion of the installation process of Reflective Survey Target Market |  | The survey targets shall be surveyed by conventional surveying techniques to achieve a level accuracy of +/-1 mm. |  | W
4.0 Completion of Instrumentation Installation
4.01 | Vibrating Wire Piezometer completion of placement |  |  |  | Document Review submitted through Hold Point | After Piezometer Completion of Placement |  | The piezometer location and level shall be surveyed and as-built details, including borehole records, submitted to the Designer. |  |  | H
4.02 | Inclinometer Completion of Placement |  |  |  | Document Review submitted through Hold Point | After Inclinometer Completion of Placement |  | A minimum of 5 days following installation, the location of the instrument shall be accurately surveyed. The survey shall include determination of the casing groove orientations relative to True North. Testing and the determination of baseline readings shall then be carried out as per the manufacturer’s recommendations. |  |  | H
4.03 | Profilometer Completion of Placement |  |  |  | Document Review submitted through Hold Point in Aconex | After Profilometer Completion of Placement |  | Following completion of the installation a surveyed cross-section shall be measured on the ground surface along the alignment of the profilometer. Profilometer base readings shall then be taken using the following procedures: Take a minimum of two base readings with measurements at 2.5 m spacings; If the difference in levels between the two readings is greater than 10 mm, carry out a further set of readings; Survey the locations and elevations of the end datum points (reference stands); Using the above data identify the base reading for this location; The Constructor shall submit as-built details and baseline readings to the Designer, prior to commencing placement of fill materials of any kind over the profilometer tubing alignment. |  |  | H
4.04 | Instrument has been received and approved by the Designer |  |  |  | Document Review submitted through Hold Point in Aconex | After Completion of Instrumentation Installation |  | An instrument will not be accepted until the factual report for that instrument has been received and approved by the Designer |  |  | H
4.05 | If an instrument is blocked, obstructed or damaged |  | MMA-DES-GEO-E1-SPC-8510 |  | Inspection and Document Review | After completion of the remedials work on the instrument |  | Constructor shall immediately remove the obstruction, or repair or replace the damaged instrument to the satisfaction of the designer. |  |  | H
5.0 Monitoring
5.01 | Base Line Readings |  | MMA-DES-GEO-E1-SPC-8510 and ITPs for embankment/earthworks and cut slopes |  | Survey | Per individual piece of equipment refer to ITPs for embankment/earthworks and cut slopes |  | Per individual piece of equipment refer to ITPs for embankment/earthworks and cut slopes |  | H | H |  |  | To be agreed with Designer
6.0 Verification Testing
6.01 | Cone Penetration Tests with Measurement of Porewater Pressure (Piezocone) on embankments constructed on soft ground. |  | MMA-DES-GEO-E1-SPC-8510, Section 5.15.1 |  | Document Review | Following surcharge removal or as directed by the Geotechnical Designer |  | All results to be provided to the Geotechnical Designer within 24 hours of the tests being completed. |  |  | H |  |  | To be agreed with Designer
6.02 | Geonor Shear Vane Test in Borehole |  | MMA-DES-GEO-E1-SPC-8510, Section 5.15.2 |  | Document Review | Following surcharge removal or as directed by the Geotechnical Designer |  | All results to be provided to the Geotechnical Designer within 24 hours of the tests being completed. |  |  | H |  |  | To be agreed with Designer