## Sheet3
Inspection and Test Plan Te Ara o Te Ata Earthworks Fill 12 - ITP - MMA-QA-ITP-Z03-EW-FL012
| This ITP has been prepared by |  |  | Reviewed by Quality Manager |  |  | Reviewed by DSR |  |  | Approved by Construction Manager
Rev Number | Name | Signature | Date | Name | Signature | Date | Name | Signature | Date | Name |  | Signature |  | Date
Rev 01
Rev 02 | Sarah Doyle |  | 2024-04-05 | Ramy Faragalla | R Faragalla | 2024-04-05 | Danny Beasant | D.Beasant | 2024-04-09 | Hardus Pieters |  |  |  | 2024-04-10
Rev 03
Rev 04
ITP NO: XXX |  | Project: Te Ara o Te Ata | [5 empty] | Method Statement Ref: |  |  | Rev.A
Verification Method: Hold [H] – work will not proceed past Hold Point until released by organisation imposing hold; Inspection [I] – formal inspection activity to be undertaken and recorded; ensure correct verifying records are in place; Witness [W] – an inspection that may be witnessed by organisation imposing hold; allow reasonable notification period; Review [R] – review of reports, records or other evidence of compliance. | [7 empty] | Responsibilities PE = MTM Alliance Construction TWD = Temporary Design Team
Activity/Specification: Earthworks Fill | [7 empty] | Area Location / Work Breakdown: XXXX
Item | Construction Step or Material |  | Specifications and Standards |  | Acceptance criteria and testing |  |  |  | Method (H,I,W,R) |  |  |  | Verifying Records Checklists, Test and Supplier Certificates
Responsible [tick]
[5 empty] | Method/Description | Test frequency |  | Conformance Criteria | Contractor | Designer | Client | Lab
1.0 Pre-Construction
1.01 | CWP |  |  |  | Document Review | Prior to personal starting |  | Ensure all crew members are briefed on the CWP | H |  |  |  | Signed off CWP
1.02 | Design |  |  |  | Document Review | Prior to starting |  | Ensure all drawings are approved and of the latest revision, or written approval from PAB | H | H |  |  | IFC drawings or Written approval from PAB
2.0 Material Compliance
2.01 | Determination of the dry density/water content relationship (Heavy Compaction) for Structural fill Material |  | MMA-DES-GEO-E1-SPC-3859 Table 4.1, 7.1 & 7.2 |  | NZS 4402:1986, Test 4.1.2 | 1 test per 20,000m3 |  | Report Only | H | R |  | I | MDD Test Report
2.02 | Atterberg limits test for Structural fill Material |  | MMA-DES-GEO-E1-SPC-3859 Table 4.1, 7.1 & 7.2 |  | NZS 4402:1986, Test 2.2, 2.3 & 2.4 | 1 test per 20,000m3 |  | Report Only | H | H |  | I | Atterberg limits Test Report
2.03 | Determination of the dry density/water content relationship (Heavy Compaction) for Buttress Fill Material |  | MMA-DES-GEO-E1-SPC-3859 Table 4.1, 7.1 & 7.2 |  | NZS 4402:1986, Test 4.1.2 | 1 test per 20,000m3 |  | Report Only | H | R |  | I | MDD Test Report
2.04 | Atterberg limits test for Buttress Fill Material |  | MMA-DES-GEO-E1-SPC-3859 Table 4.1, 7.1 & 7.2 |  | NZS 4402:1986, Test 2.2, 2.3 & 2.4 | 1 test per 20,000m3 |  | Report Only | H | H |  | I | Atterberg limits Test Report
2.05 | Determination of the dry density/water content relationship (Heavy Compaction) GAP 65 Material |  | MMA-DES-GEO-E1-SPC-3859 Table 4.1, 7.1 & 7.2 |  | NZS 4402:1986, Test 4.1.2 | Source approval 3 no. tests |  | Report Only | H | R |  | I | MDD Test Report
2.06 | Particle size distribution (PSD) Test for GAP 65 material |  | MMA-DES-GEO-E1-SPC-3859 Table 4.1, 7.1 & 7.2 |  | NZS 4402:1986, Test 2.8 | Source approval 3 no. tests then every 2000m3. |  |  | H | H |  | I | PSD Test Report
2.07 | Permeability test for GAP 65 material |  | MMA-DES-GEO-E1-SPC-3859 Table 4.1, 7.1 & 7.2 |  | ASTM D5084 - 16a | Source approval 3 no. tests |  | > 5x10-5 m/s | H | H |  | I | Permeability Test Report
2.08 | Large Shear Box test for GAP 65 material (Minimum 3 normal stresses) |  | MMA-DES-GEO-E1-SPC-3859 Table 4.1, 7.1 & 7.2 |  | BS 1377 Part 7:1990 Test 5 Determaination of shear strength by direct shear | Source approval 3 no. tests |  | Report Only | H | H |  | I | Direct Shear Strength Test Report
3.0 During Construction
3.01 | Set out extents of fill and check against design |  |  |  | Survey/visual | Prior to Commencement |  | Consistency with Construction Drawings | W
3.02 | Ensure GPS plant have the correct model set up in machine and that a datum is available for checking |  |  |  | Survey/visual | Prior to Commencement |  | Consistency with Construction Drawings | W
3.03 | Ensure the complete removal of all organics, topsoil, Vegetation, and roots. The depth of topsoil stripping should be adequate to eliminate all organic material, turf, and significant plant roots. except for Fill 12 and 13 where the fill height is >=5m. |  | MMA-DES-GEO-E1-SPC-3859 Clause 6.3 |  | Survey/visual | Immediately prior to earthworks beginning in all Fill areas except Fill 12 & 13 |  | Construction team shall coordinate with the Designer ahead of and during clearing and stripping operations to determine the stripping depth. | H | H |  |  | Subgrade approval checksheet
3.04 | Designer witness of in-situ subgrade prior to filling |  | MMA-DES-GEO-E1-SPC-3859 Clause 7.2 |  | Inspection | Prior to Filling |  | Before fill is placed in any area, the Constructor shall notify the Designer that the fill foundation has been stripped and drained, including construction of subsoil drains and prepared as required by the Drawings and Specification, and is ready for the Designer’s inspection and approval. | H | H |  |  | Subgrade approval checksheet
3.05 | Undercuts |  | MMA-DES-GEO-E1-SPC-3859 Clauses 6.7 & 6.8 |  | Visual inspection | 100% of works area |  | • Where shown on the drawings. • The Designer will specify the depth of the undercut in materials. • The Constructor shall treat any excavated undercut material as landscape fill or unsuitable. • Backfill the undercut as per the designer's instruction. | H | H |  |  | Subgrade approval checksheet
3.06 | When required Undercuts (cut-to-fill operations) |  | MMA-DES-GEO-E1-SPC-3859 Clauses 6.7 & 6.8 |  | Visual inspection | Prior to Filling |  | Unsuitable material shall be undercut and tested as per specification or designers instruction | H | H |  | I
3.07 | Sub soil Drainage |  | MMA-DES-GEO-E1-SPC-3859 |  | Inspection | During subsoil construction |  | Ensure all additional areas that require either primary or secondary collector drains are identified | I | I |  |  | Sub soil drainage ITP,
3.08 | Monitoring Equipment |  | MMA-DES-GEO-E1-SPC-8510 |  | Survey/ data logging | As outlined in MMA-DES-GEO-E1-SKT-4077 |  | install all monitoring equipment as outline in drawings specific to area. Ensure monitoring of data is recored and supplied to designers | W | R |  |  | Drill logs
3.09 | Filling operations |  | MMA-DES-GEO-E1-SPC-3859 Clause 7.2 |  | Visual inspection | Daily |  | Filling carried out in fully drained conditions with no free water on the working surfaces. Any erosion to be repaired immediately | H |  |  |  | checksheet
3.1 | Filling operations |  | MMA-DES-GEO-E1-SPC-3859 Clause 7.2 |  | Survey/visual | Daily |  | Site Engineer to check embankment slopes for location, line and level as the fill progresses ensuring that batter faces are overfilled and trimmed back so that so that the fill is well compacted to the edge | H |  |  |  | checksheet/ Survey Report
3.11 | insitu fill testing-Plateau Test |  | MMA-DES-GEO-E1-SPC-3859 Clause 7.4.3 |  | Plateau Test | Structural Fill - 1 test per material type per earthworks zone,exepct where outlined in RFI0057 Buttress Fill - 1 test per material type per earthworks zone GAP65 - 1 test per material type per structure / location Cement Stabilised GAP65/ Structural Fill - 1 Test per material type per structure/ location |  | Reviewed by designer | W | I |  | I | Test report
3.12 | insitu fill testing-In situ moisture content and density |  | MMA-DES-GEO-E1-SPC-3859 Clause 7.4.3 |  | In situ moisture content and density | Structural Fill - 1 test per 1 m lift per 100m length, Heavy compaction and standard compaction areas outlined in RFI00057 Buttress fill - 1 test per 200m length Average GAP65 - 4 tests per lift per structure Subsoil Drainage Back fill - 1 test per 500m3 , Cement Stabilised GAP65 - 4 Tests per 0.5m lift per structure Cement Stabilised Structural fill - 1 test per 0.5m lift per 100m length |  | Structural Fill - average > 95% MDD All tests > 92%, Buttress fill - Average > 92 MDD All tests > 90%, GAP65 - Average > 98% MDD All tests > 95%, Subsoil Drainage Back fill - 1 Average > 92 MDD All tests > 90%, Cement Stabilised GAP65 - Average > 98% MDD All tests > 95%, Cement Stabilised Structural fill - average > 95% MDD All tests > 92% | W | R |  | I | Test report
3.13 | insitu fill testing- Undrained shear Strength |  | MMA-DES-GEO-E1-SPC-3859 Clause 7.4.3 |  | Undrained shear Strength | Structural fill - 1 test per layer per 1000m2 Buttress Fill - 1 Test per layer per 2000m2 Cement Stabilised Structural Fill - 1 test per layer per 500m2 | Structural fill - 1 test per layer per 1000m2 Average > 150kPa all tests > 120kPa Buttress Fill - 1 Test per layer per 2000m2 Average > 120kPa all tests > 80kPa Cement Stabilised Structural Fill - 1 test per layer per 500m2 Average > 150kPa all tests > 120kPa | Structural fill - Average > 150kPa all tests > 120kPa Buttress Fill - Average > 120kPa all tests > 80kPa Cement Stabilised Structural Fill - Average > 150kPa all tests > 120kPa | W | R |  | I | test report
3.14 | In-situ moisture content and density (and/ or air voids) testing of compacted for fill material Subgrade |  | MMA-DES-GEO-E1-SPC-3859 Clause 10.5 |  | in situ moisture content and density (and/ or air voids) testing of compacted fill material | Fill 12 & 13 - 1 test per 0.5m lift per 50m length for 1.0m subgrade depth |  | Fill 12 & 13 - 1 test per 0.5m lift per 50m length for 1.0m subgrade depth, Average > 95% mdd All tests > 92% MDD | W | R |  | I | Test report
3.15 | Carry out deflection testing (either Benkelman Beam or FWD) at the subgrade |  | MMA-DES-GEO-E1-SPC-3859 Clause 10.4 & 10.5 |  | Benkelman beam or FWD Testing | 10m interval in each wheel path at the following levels: 1) 1.0m below Subgrade Formation Level 2) 0.5m below Subgrade Formation Level 3) At Subgrade Formation Level |  | Benkelman beam, 90th percentile D0 target :1.2mm No D0 deflection exceeding 1.40mm. FWD, 90th percentile D0 target:2.0mm No D0 deflection exceeding 2.2mm | W | R |  | I | Test report
3.16 | Laboratory Soaked CBR testing for Subgrade Fill |  | MMA-DES-GEO-E1-SPC-3859 Clause 10.5 |  | Laboratory Soaked CBR | Test per 5000m2 at subgrade formation level |  | ≥ CBR 7% | W | R |  | I | Test report
4.0 Post Construction
4.01 | Monitoring Data |  | MMA-DES-GEO-E1-SPC-8510 |  | Data Recordings | During construction and at end |  | Ensure all settlement data is recorded and all post construction monitoring is programmed | H |  |  |  | monitoring Data tables
4.02 | Survey As-builts |  |  |  | Survey As-built | During construction and at end |  | Ensure all features and burried items are captured. | H |  |  |  | CAD files
4.03 | As-builts |  |  |  | Red Pen Mark up | End of Construction |  | All variances captured | H | H |  |  | Red pen mark ups
Note on K39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Inspection Point 'I' not R Reply: Done
Note on I41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Heads up only. Spec update underway and this is expected to change to scala blows. Reply: I will keep it for now and we could update the ITP once the new specification is issued,