## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-080-CIV-PSDS-Stormwater Drainage Supply & Installation | itp |  |  |  |  | ITP-080-CIV-PSDS-Stormwater Drainage Supply & Installation Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-080-CIV-PSD-Stormwater Drainage Supply & Installation
label | ITP Description: PSD-Stormwater Drainage Supply & Installation
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): 080-CIV
label | Revision Number: 0
label | Revision Date: 5/12/2023
label | ITP created by: Victor Mira
label | ITP approved for use by: Victor Mira
label | 1.1 Non Dependent
label | Reference: VicRoads Section 701 (May 2020)
label | 1.2 Non Dependent
label | Reference: VicRoads Section 705 (June 2021)
label | 1.3 Non Dependent
label | Reference: IFC Drawings
label | 1.4 Non Dependent
label | Reference: CHK-001-CIV-Stormwater Drainage Pipes Installation Rev 0
label | 1.5 Non Dependent
label | Reference: CHK-002-CIV-Stormwater Drainage Pits Installation Rev 0
section | Preliminaries-Materials
checkpoint | 2.1 Drainage Reinforced Concrete Pipes (RCP)
label | REFERENCE: Section 701.04, Section 701.05, Section 701.09
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Precast reinforced concrete pipes shall be manufactured, supplied and installed in accordance with AS/NZS 4058 and Sections 701.05 & 701.09
label | ○ Precast reinforced concrete box culverts shall comply with the requirements of Section 701.04
label | ○ Rubber ring joints shall comply with the requirements of AS 1646
text | Enter: Teambinder Material Approval number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Teambinder Material Approval
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 2.2 Drainage Flexible Pipes
label | REFERENCE: Section 701.08
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Flexible pipes shall be supplied in accordance with 701.08
text | Enter: Teambinder Material Approval number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Teambinder Material Approval
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 2.3 Precast Drainage Pit
label | REFERENCE: Section 705.07, Section 705.04, Section 705.09
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Precast steel reinforced concrete drainage pits shall be manufactured, supplied and installed in accordance with Section 705.07 & 705.09
label | ○ All concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of Section 705.04. Concrete grades shall comply with Table 705.041
text | Enter: Teambinder Material Approval number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Teambinder Material Approval
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 2.4 Cast in Place Drainage Pit
label | REFERENCE: Section 705.06 IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Cast in place drainage pits shall be constructed in accordance with the requirements of Section 705.06 and at the locations and to the dimensions shown on the drawings.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Teambinder Material Approval
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 2.5 Drainage Pit - Step Irons
label | REFERENCE: Section 705.04, Section 705.12
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Step irons shall be manufactured by 13mm steel bar covered with polypropylene plastic in accordance with 705.04
label | ○ Drainage pits greater than 1.0 m deep shall be fitted with step irons in accordance with Section 705.12
text | Enter: Teambinder Material Approval number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Teambinder Material Approval
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 2.6 Drainage Bedding Material
label | REFERENCE: Section 701.09
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Bedding Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
text | Enter: Teambinder Material Approval number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Teambinder Material Approval
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 2.7 Drainage Backfill Material
label | REFERENCE: Section 701.09, Section 701.19
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Ordinary and Selected Backfill Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
label | Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised sand in accordance with Section 701.19
text | Enter: Teambinder Material Approval number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Teambinder Material Approval
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
section | Preliminaries-Documents
checkpoint | 3.1 Subcontractor ITP (where required)
label | REFERENCE: Subcontractor ITP
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Subcontractor ITP shall conform with the IFC Drawings & Relevant Standards & Specifications.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Subcontractor ITP
date | Date Completed:
section | Pre-Construction Activities
checkpoint | 4.1 Survey Set Out - Pits & Pipes
label | REFERENCE: IFC Drawings Section 701.10
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Prior to commencement of excavation for the culverts the Contractor shall confirm the position of all culverts with the Superintendent.
label | ○ Survey activities undertaken to ensure and validate the plan location, height and line of pits and location, invert level, plan of pipes in accordance with design documentation and 701.10
label | – – – – – – – – – – – – – – – – –
label | METHOD: Survey
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation, CHK-002-CIV-Stormwater Drainage Pits Installation
date | Date Completed:
section | Construction / Installation Activities
checkpoint | 5.1 Pits - Excavation
label | REFERENCE: IFC Drawings Section 705.05
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Excavation shall be to the depth indicated on the IFC drawings or as necessary to secure a satisfactory foundation. Precast pits shall have min of 400mm clearance from all external faces of the pit to each face of the excavation.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual inspection, Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
date | Date Completed:
checkpoint | 5.2 Pits - Placement of Bedding Material
label | REFERENCE: IFC Drawings Section 705.05
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Bedding conforming to to 701.09 shall be supplied, placed and compacted to a thickness:
label | > 80mm for clay foundations
label | > 150mm for rock foundations
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual inspection, Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
date | Date Completed:
checkpoint | 5.3 Pits - Bedding Testting
label | REFERENCE: IFC Drawings Section 701.20
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding). The number of tests per lot shall be three
label | ○ Bedding shall be compacted to refusal using hand held mechanical equipment and material (Swell ≥ 2.5%) and mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
label | – – – – – – – – – – – – – – – – –
label | METHOD: Compaction Test
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
date | Date Completed:
checkpoint | 5.4 Pits - Placement of Precast Drainage Pit
label | REFERENCE: IFC Drawings Section 701.10
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Survey pick-up to verify:
label | – Plan location of pits, other than offsets to kerb line or barriers, to be +/- 100mm
label | – Offset of entry pits required to match lines of kerbs or barriers ±20 mm
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual inspection, Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
date | Date Completed:
checkpoint | 5.5 Pits - Cast in Place Drainage Pit
label | REFERENCE: IFC Drawings Section 705.06, Section 610, Section 611
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Cast in place drainage pits shall be constructed at the locations and to the dimensions shown on the drawings and in accordance with the requirements of Section 610 and 611.
label | ○ Cast in place drainage pits shall not be constructed with fibre reinforced concrete (FRC).
label | – – – – – – – – – – – – – – – – –
label | METHOD: Survey, Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
date | Date Completed:
checkpoint | 5.6 Pits - Jointing & Drainage Connections
label | REFERENCE: Section 705.11
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: All connections to drainage pits shall be neatly made in accordance with Section 705.11.
label | ○ Openings into drainage pit walls to facilitate drainage connections shall be neatly saw cut to the required size not more than 50mm greater than pipe diameter. Breaking out of holes is not permitted.
label | ○ Drainage pits shall be replaced if circumferential or longitudinal cracking occurs as a result of installing holes or if the hole exceeds the pipe diameter by more than 50 mm.
label | ○ Exposed reinforcement shall be coated with an approved epoxy treatment to prevent corrosion prior to rendering around the pipes.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual inspection, Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
date | Date Completed:
checkpoint | 5.7 Pits - Shaping of Floor
label | REFERENCE: Section 705.13
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Drainage pit floors shall be smoothly shaped from the inlets to the outlet for a height of one‑third of the diameter of the outlet pipe with cementitious mortar in accordance with Section 705.13.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual inspection, Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
date | Date Completed:
checkpoint | 5.8 Pits - Step Irons
label | REFERENCE: IFC Drawings Section 705.12
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Drainage pits greater than 1.0m deep shall be fitted with step irons in accordance with 705.12. Ladder rungs shall not opbstruct openings and that water does not discharge on them. Step rungs do not come within 50mm of the top of the riser.
label | ○ Step irons of an approved proprietary type shall be installed in accordance with the manufacturer's instructions.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual inspection, Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
date | Date Completed:
checkpoint | 5.9 Pits - Fitting of Covers
label | REFERENCE: IFC Drawings Section 705.17
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Frames for drainage pit covers shall be cast into the top of the drainage pit or bedded on fresh mortar, 5 mm thick, consisting of two parts of sand, one part of cement and sufficient water to produce a mix of suitable consistency.
label | ○ Height shall be within 10mm of the design level.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual inspection, Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
date | Date Completed:
checkpoint | 5.10 Pits - Pit Lids
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: All stormwater pits shall be provided with a locakable pit lid minimum Class D with in-fill material or fibre glass Terra Firm Enduro or similar.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual inspection
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
date | Date Completed:
checkpoint | 5.11 Pits - Backfilling Around Drainage Pits
label | REFERENCE: Section 705.18
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Backfilling around drainage pits shall be placed in layers not exceeding 300 mm loose thickness and compacted to refusal using hand held mechanical equipment.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual inspection, Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
date | Date Completed:
checkpoint | 5.12 Pipes - Trench Excavation
label | REFERENCE: IFC Drawings Section 701.15
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Excavation for pipe shall have a horizontal clearance between the pipe and the excavation wall of:
label | > 300mm, < 600mm for RCP
label | > 150mm for Flexible Pipe
label | ○ The base of the trench shall be compacted to refusal using mechanical plant.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual inspection, Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
date | Date Completed:
checkpoint | 5.13 Pipes - Bedding Placement
label | REFERENCE: IFC Drawings Section 701.16
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Bedding material shall be provided and placed in the full width of the trench to the below minimum:
label | > 100mm where D<1500mm
label | > 200mmwhwere D≥1500mm
label | ○ Bedding material shall be placed and compacted in layers <150mm loose thickness
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual inspection, Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
date | Date Completed:
checkpoint | 5.14 Pipes - Bedding Testting
label | REFERENCE: IFC Drawings Section 701.20
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding). The number of tests per lot shall be three
label | ○ Bedding shall be compacted to refusal using hand held mechanical equipment and material (Swell ≥ 2.5%) and mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
label | – – – – – – – – – – – – – – – – –
label | METHOD: Compaction Test
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
date | Date Completed:
checkpoint | 5.15 Pipes - Placement of Pipe - RCP
label | REFERENCE: IFC Drawings Section 701.17, Section 701.20
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Laying of pipes shall not commence until the Contractor has verified that culvert bedding complies with the specified lines and levels and compaction requirements, and pipes are not damaged. Laying of pipes or box culverts shall commence from the downstream end.
label | ○ Rebate and socket ends of pipe segments shall be placed facing upstream and be fully entered.
label | ○ Gaps between spigot and socket are in accordance with the manufacturers specifications
label | ○ The lower portion of the pipe shall be in contact with the bedding layer and shaped to accomodate the joint collar along its full length
label | ○ Before proceeding to install the next length of pipe, the conformity of the assembled joint shall be verified by checking that the position of the rubber ring on the spigot, and the clearance and overlap between the spigot and socket, are within the values specified by the manufacturer.
label | ○ The spacing for multiple row culverts shall be as shown in Table 701.171
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual inspection, Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
date | Date Completed:
checkpoint | 5.16 Pipes-Placement of Pipe - Flexible Pipe
label | REFERENCE: IFC Drawings Section 701.17, Section 701.22
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: All buried flexible pipe sections supplied shall be assembled in accordance with the manufacturers specifications.
label | ○ Before proceeding to install the next length of pipe, the conformity of the assembled joint shall be verified by checking that the position of the rubber ring on the spigot, and the clearance and overlap between the spigot and socket, are within the values specified by the manufacturer.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual inspection
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
date | Date Completed:
checkpoint | 5.17 Pipes - Lifting Holes
label | REFERENCE: Section 701.18
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Lifting holes shall be plugged off in accordance with the manufacturers specifications after the pipe is installed.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual inspection
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
date | Date Completed:
checkpoint | 5.18 Pipes - As-built survey pick-up
label | REFERENCE: IFC Drawings Section 710.10
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Each run of underground drainage shall be Survey verified prior to backfilling.
label | – Offset pits to kerb +/- 20mm
label | – Plan location pits not adjacent to kerb +/- 100mm
label | – Invert level of pipes at pits +/- 50mm
label | – departure from design grade +/- 10mm in 10m, provided minimum grade is not less than 1:250
label | – – – – – – – – – – – – – – – – –
label | METHOD: Survey
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
date | Date Completed:
checkpoint | 5.19 Pipes - Backfill Placement
label | REFERENCE: IFC Drawings Section 701.16
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Backfill material shall be placed the full width of the bedding material and compacted in layers <150mm loose thickness.
label | ○ Filling shall not be placed within 2.0m of the open end of the pipe where a further section is to be placed.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual inspection, Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
date | Date Completed:
checkpoint | 5.20 Pipes - Backfill Testing
label | REFERENCE: IFC Drawings Section 701.20, Section 701.29
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding or backfill)
label | ○ Backfill material shall be compacted to a density ratio > 97%. Material which has a swell equal or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual inspection
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
date | Date Completed:
section | Post-construction / Post-installation Activities
checkpoint | 6.1 Flushing & CCTV
label | REFERENCE: Section 701.28, Section 701.30
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: All culverts shall be flushed clean from end to end on completion and maintained in proper working order.
label | ○ All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed and to check for visible signs of defects.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Record Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP, CCTV Reports
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 6.2 As Built Survey
label | REFERENCE: Section 701.10
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate the drainage lines are installed within the tolerances specified in Section 701.10
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP, As Built Survey Report
date | Date Completed:
checkpoint | 6.3 Repairs to Damaged Pipes
label | REFERENCE: Section 701.31
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Where inspections after backfilling identify any of the following defects they shall be notified as a non-conformance:
label | ○ cracks wider than 0.5 mm
label | ○ spalling of concrete
label | ○ exposed reinforcement
label | ○ joints that are not fully engaged.
label | Any pipes with defects greater than the following limits shall be removed and replaced:
label | ○ longitudinal cracks greater than 2 mm
label | ○ circumferential cracks around the full circumference with width greater than 3 mm or with lateral displacement of the cracked sections exceeding 3 mm
label | ○ circumferential cracks around part of the circumference with width greater than 4 mm
label | ○ penetrations with area greater than 400 mm2
label | ○ pipe joints that are separated.
label | The Superintendent may agree to accept pipes with defects as noted above subject to demonstration that repairs will ensure that pipes will operate effectively for their design life. Consideration will only be given to products and procedures with proven performance and to the following types of treatments:
label | ○ hot sprayed epoxy coatings for cracks not wider than 4 mm with no lateral displacement
label | ○ fibre glass reinforced epoxy sleeving for cracks not wider than 4 mm with lateral displacements up to 3 mm
label | ○ spalled concrete, exposed steel reinforcement and penetrations shall be treated as patch repairs and repaired with polymer modified cementitious repair materials in accordance with the requirements of Section 689.
label | The Contractor shall submit details of proposed rectification treatments including manufacturer’s product specifications and warranties, the area and thickness of repair treatment, detailed repair procedures, and inspection and test plans.
label | No repairs shall be undertaken without the Superintendent’s approval of the repair materials and procedures.
label | All repairs shall be inspected using CCTV to verify compliance with the repair specifications.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review for Repair Procedure, CCTV Report Review, Visual Inspection
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP, Approved Repair Procedure, Post Repair CCTV Report
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 6.4 Non-conformance Report (NCR) Closure
label | REFERENCE: MRPA Quality Management Plan
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP