## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-090-CIV-PSDS-Site Clearing and Grubbing | itp |  |  |  |  | ITP-090-CIV-PSDS-Site Clearing and Grubbing Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-090-CIV-PSDS-Site Clearing and Grubbing
label | ITP Description: PSDS-Site Clearing and Grubbing
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): 090-CIV
label | Revision Number: 0
label | Revision Date: 28/02/2023
label | ITP created by: Jason Lee
label | ITP approved for use by: Jon De Castro
label | 1.1 Non Dependent
label | Reference: VicRoads Section 201 (Feb 2023)
label | 1.2 Non Dependent
label | Reference: VicRoads Section 204 (Dec 2015)
label | 1.3 Non Dependent
label | Reference: IFC Drawings
section | Preliminaries - Documentations
checkpoint | 3.1 Environmental Controls
label | REFERENCE: MRPA Environmental Management Plan
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: All environmental measures to be implemented as per current EMP and local authorities.
label | ○ Sediment control measures to be installed and protected vegetation to be clearly identified.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Where applicable, prior to starting Works
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: WP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Supervisor, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP Signed-off
date | Date Completed:
checkpoint | 3.2 Vegetation Removal Permit
label | REFERENCE: MRPA Environmental Management Plan
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Prior to removing any vegetation or habitat:
label | i. arrange an on-site inspection with the Nominated Authority and relevant authorities to confirm and clearly identify and mark trees, vegetation or habitat to be removed, consistent with the Design Documents and any relevant permits.
label | A qualified ecologist with appropriate permits/licenses shall be present on site during removal of vegetation to identify possible locations of fauna, discovery of significant flora or fauna and to examine any habitats likely to be affected by Works.
label | ii. fence and sign all sites nominated as No-Go Zones.
label | Attach: Vegetation Removal Permit
label | Attach: Ecologist's Report
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Where applicable, prior to starting Works
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Supervisor, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP Signed-off
date | Date Completed:
section | Pre-Construction Activities
checkpoint | 4.1 Survey Set-out / Limits of Work
label | REFERENCE: IFC Drawings Section 201.03
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The limits of clearing and grubbing shall be:
label | a. the limits defined on the IFC drawings
label | b. the whole width between the outside edges of any batters, including any roundings, together with a further horizontal distance of 1m beyond the outside edges of batters but not beyond the road reserve boundary or, where catch drains are required, to the outside edges of catch drains
label | c. no more than the width required for completion of the Work under the Contract.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once, prior to starting Works
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP Signed-off
date | Date Completed:
checkpoint | 4.2 Cultural Heritage and Areas of Significance
label | REFERENCE: MRPA Environmental Management Plan Section 201.10
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Areas determined to be No-Go Zones are securely fenced and clearly identified by signage installed in the fencing.
label | ○ Immediately notify the Nominated Authority if any Cultural Heritage is discovered or identified during construction and work to be suspended.
label | ○ Works may recommence with the cultural heritage approval or if works can resume without risk to the discovered Cultural Heritage.
label | Attach: Cultural Heritage Report
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Where applicable, prior to starting Works
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP Signed-off
date | Date Completed:
section | Construction Activities
checkpoint | 5.1 Stripping of Topsoil
label | REFERENCE: IFC Drawings Section 204.05
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Topsoil shall be stripped for the full width of the formation.
label | ○ Declared noxious weeds, pests and pathogens shall be treated and monitored before stripping of topsoil and after spreading, to prevent and/or minimise the spread of weeds and other pathogens throughout the site.
label | ○ Stockpiles shall be maintained in a neat, well shaped state capable of shedding water. Topsoil shall be re-spread as soon as practicable.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Site
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Supervisor, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP Signed-off
date | Date Completed:
checkpoint | 5.2 Stockpiling
label | REFERENCE: MRPA Environmental Management Plan Section 204.05
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Where soil is stock piled on Site, such stockpiles shall be located, where possible, to provide a clearance of not less than 10 metres from waterways.
label | ○ If this clearance is not possible,additional protection shall be provided.
label | ○ Stockpiles shall be maintained in a neat, well shaped state capable of shedding water.
label | ○ Topsoil shall be re-spread as soon as practicable.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Where applicable, each Site
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Supervisor, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP Signed-off
date | Date Completed:
checkpoint | 5.3 Abandoned Services
label | REFERENCE: IFC Drawings Excavation Permit Section 201.05
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Removal and disposal of abandoned services and obsolete underground drainage lines which interfere with the execution of works to be done.
label | ○ Verify service is not likely to contain a hazardous material (sewage, asbestos pipe)
label | ○ Decommissioned services to be disposed of in a suitable manner.
label | ○ Decommissioned pits have been broken back to 0.3m below subgrade level. Remaining pipe openings shall be sealed with concrete.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Where applicable, each Site
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Supervisor, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP Signed-off
date | Date Completed:
checkpoint | 5.4 Clearing of Trees and Vegetation
label | REFERENCE: IFC Drawings Section 201.04
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Clearing work shall not be undertaken outside of the specified limits of work.
label | ○ Tree branches extending over the carriageway shall be trimmed to provide a clearance of at least 6 m above the carriageway surface. Where whole branches are to be removed, the three cut method shall be used.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Where applicable, each Site
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Supervisor, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP Signed-off
date | Date Completed:
checkpoint | 5.5 Grubbing of Vegetation
label | REFERENCE: IFC Drawings Section 201.05, Section 201.06
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: In areas where excavation will be made, all vegetation, refuse and obstructions shall be totally grubbed or grubbed to a depth of not less than 0.3m below the subgrade and batters, whichever is the lesser treatment.
label | ○ In areas to be covered by embankments, grubbing to be a depth of not less than 0.3m below the stripped surface or not less than 0.6m below the finished surface of the subgrade, whichever is the lesser treatment.
label | ○ Holes resulting from grubbing shall be backfilled with material similar to the surrounding material and compacted to the same degree as the surrounding material and not less than density ratio of 95% (standard compactive effort).
label | ○ Unless otherwise shown on the drawings, trees and stumps within 10 m of any portion of a proposed bridge, or proposed culvert having a waterway area greater than 6 m2, shall be cleared and grubbed.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Where applicable, each Site
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Supervisor, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP Signed-off
date | Date Completed:
section | Post-construction Activities
checkpoint | 6.1 Disposal of Materials & Vegetation
label | REFERENCE: Section 201.07
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Salvagable material to be used wherever possible, the remainder is to be remove from site.
label | ○ Salvagable concrete and bituminous materials greater than 50 mm shall be disposed of at approved recycling establishments.
label | ○ Tree trunks and large branches shall be removed from the site.
label | ○ Small tree branches,shrubs and leaves; excluding noxious weeds, shall be disposed of by chipping and mulching to form mulch.
label | Attach: Delivery Dockets (for Items sent off Site)
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Where applicable, each Site
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Supervisor, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP Signed-off
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP